## ReadMe
Area | Guidance
Export type | Raw source extract from the legacy Compass database.
Environment | Production
Output file | /Users/andyjones/Source/code-digital-ops/FIPS/compass/exports/compass-migration-workbook-LIVE.xlsx
Legacy IDs | The `Id` column in each sheet is the source identifier to carry into the migration mapping.
Parent links | Child sheets keep their original foreign keys such as `ProjectId`, `RiskId`, `IssueId`, and `MilestoneId`.
Lookup sheets | Use lookup sheets like `BusinessAreas`, `Phases`, `RagStatuses`, `RiskTiers`, and `Users` to resolve IDs and names.
Migration hint | Use `Projects` as the parent work-item source and then attach related sheets in a second pass.
Deleted rows | This export is a full raw dump of the source tables, so soft-deleted rows are retained if they exist.

## Projects
Id | ProjectCode | Title | Aim | StrategicObjectives | MissionPillars | StartDate | TargetDeliveryDate | ActualDeliveryDate | IsFlagship | IsAiInitiative | RagStatusLookupId | RagStatus | RagJustification | PathToGreen | PhaseId | BusinessAreaId | HistoricBuRTId | PrimaryContactUserId | DeliveryPriorityId | DeliveryPriorityChangeReason | PrimaryOrganizationalGroupId | IsMultiDepartmentProject | OtherDepartments | BusinessCaseApproval | TotalPermFte | TotalMspFte | Status | StatusChangeReason | IsDeleted | CreatedAt | UpdatedAt | CreationMethod | ActivityTypeLookupId | RiskAppetiteLookupId | ServiceUsers | IsInternal | IsExternal | IsSubjectToSpendControl | DiscoveryStartDatePlanned | DiscoveryStartDateActual | DiscoveryEndDatePlanned | DiscoveryEndDateActual | AlphaStartDatePlanned | AlphaStartDateActual | AlphaEndDatePlanned | AlphaEndDateActual | PrivateBetaStartDatePlanned | PrivateBetaStartDateActual | PrivateBetaEndDatePlanned | PrivateBetaEndDateActual | PublicBetaStartDatePlanned | PublicBetaStartDateActual | PublicBetaEndDatePlanned | PublicBetaEndDateActual
1 | DEL-0001 | COMPASS | To bring together the capture, management, and reporting of compliance, outcomes, milestones, performance, assurance, standards and strategy - to give a single source of truth for delivery across DDT. |  |  | 2025-10-01 | 2026-03-31 |  | False | False | 1 | Green | Delivery on track.. |  | 5 | 13 |  | 1 | 3 |  |  | False |  | Not applicable | 5.00 |  | Active |  | False | 2025-10-30 12:53 | 2026-03-04 11:35 |  | 4 | 5 |  | True | False | False | 2025-09-01 | 2025-09-01 | 2025-10-10 | 2025-10-10 | 2025-10-19 | 2025-10-19 | 2025-11-21
2 | DEL-0002 | Cross Government Data | [6 empty] | False | False |  | Amber - Green | Pupil Premium Funding (PPF) – The Policy Lead is leaving the project at short notice with no replacement as yet, this is one of a number of unknowns which are being worked through. LEO Synthetic Data – Some unanticipated delays due to UK Data Service feedback regarding minimum metadata requirements. Working with Claire Crawford and co to provide necessary documentation | Work through emerging issues on LEO synthetic data and PPF funding. |  | 18 |  | 94 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-10-31 11:49 | 2026-03-02 12:44 |  |  |  |  | False | False | False
3 | DEL-0003 | ADA Platform | ESFA Data Science and DfE Data Directorate align their data service ambitions to offer a coherent service to end users so as to avoid duplication of governance, data, storage costs and resources. To create a joined-up service that enables users to navigate and easily access analytical data within the Department. The service to be underpinned by re-usable curated data assets that will have an appropriate service model that can ensure analytical data user journeys are met: from an, analyst, digital platforms, operational teams, policymaker and the sector perspective or facilitated by data sharing activities undertaken by the Department (e.g. statistical publications). |  |  | 2021-10-04 |  |  | False | False |  | Green |  |  | 5 | 18 |  | 94 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-10-31 11:51 | 2026-03-02 12:36 |  | 4 |  |  | True | False | False
4 | DEL-0004 | COLLECT modernisation | Ongoing collection of BAU data via multiple regular data collections. | [5 empty] | False | False | 2 | Amber - Green | RAG is amber-green. The project has just started, and we have made good progress, but we need to gather more information on the scope and problem area before determining likely outcomes of the Alpha project. | Continue to work with relevant stakeholders to clarify scope and schedule. |  | 18 |  | 94 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-10-31 11:51 | 2026-03-02 12:49 |  | 1 |  |  | True | True | False
5 | DEL-0005 | Provider Profile | [6 empty] | False | False | 2 | Amber - Green | Analysis capacity has improved following the addition of a new Business Analyst, but the backlog deficit from late last year continues to leave us with uncertainty and prevents us from downgrading the red risk associated with March deliverables. Engineering capacity also remains a concern: although a new data engineer has joined, delays in onboarding further planned resource and the confirmed departure of an existing engineer continue to impact confidence in velocity across the remaining Beta sprints. | Close managing of resource issues. Team capability and ways of working are maturing, and user research continues to develop Analyst‑focused objectives to shape the future roadmap. |  | 18 |  | 94 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-10-31 11:52 | 2026-03-02 12:40 |  |  |  |  | False | False | False
6 | DDTDEL-0006 | Find Information about Products and Services | To provide a single source of truth of the products and services DfE builds and maintains. Categorised by a range of features including user groups, phase, business areas and type. |  |  | 2025-05-12 | 2026-03-27 |  | False | False | 2 | Amber - Green | Reduced pressure on delivery as core features have been delivered. Still reliant on Andy Jones as developer. | Make more of the product configurable and work with ServiceNow team with integration into CMDB/CSDM model | 5 | 2 |  | 1 | 3 |  |  | False |  |  | 5.00 | 1.00 | Active |  | False | 2025-11-12 14:26 | 2026-03-02 13:38 |  | 4 | 5 |  | True | False | False |  |  |  |  | 2025-03-17 | 2025-05-12 | 2025-08-01 | 2025-08-01 | 2025-08-26 | 2025-08-26 | 2025-11-28 |  | 2026-01-05
7 | DDTDEL-0006 | DDT Risk Review & alignment | Review the current risk approach across DDT including all associated reporting tools and seek opertunities for rationalisation. The approach is to align with the departmental approach to ensure easy escaltion across all tiers of reporting. |  |  | 2025-11-17 | 2026-01-30 |  | False | False |  | Green | Project kicked off and scope defined. |  | 12 | 13 |  | 5 | 3 |  |  | False |  |  | 1.00 |  | Active |  | False | 2025-11-13 07:09 | 2026-03-02 07:43 |  | 2 |  |  | False | False | False
15 | DDTDEL-0006 | Service Manual | The manual will provide a cohesive, clear place for DfE colleagues and managed service providers to access the guidance and information they need to efficiently deliver high quality, consistent services, and engage with community support. |  |  | 2025-10-31 | 2026-03-31 |  | False | False | 2 | Amber - Green | Significant amount of change to merge 20 manuals, and a range of guidance. Moving to Amber-Green due to removal of "Amber" | Good planning, product and delivery management for the project with the HOPS. | 2 | 2 |  | 1 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-11-16 17:46 | 2026-03-02 13:40 |  | 4 | 4 |  | True | True | False |  |  |  |  | 2025-12-01 | 2025-12-01
16 |  | Plan Technology for Your School/ Digital Standards | The service currently has two main products: -Plan Technology for our School - a self-assessment tool gives schools a better understanding of their technology needs. It provides recommendations and actions to support technology planning. - Digital and technology Standards for Schools and Colleges- guidelines to support schools and college to use the right digital infrastructure and technology. Hosted on gov.uk The service also provides support content that to compliment the above Current agile teams are working on: - Creation and maintenance of the Digital Standards - New topics added to the Plan Technology for your School to assist schools to meet all Digital Standards - Extra support resources that might be needed by schools and colleges to meet the standards and follow recommendations - Better user journeys for MATs when using the tool - A technology financial planner https://www.gov.uk/guidance/meeting-digital-and-technology-standards-in-schools-and-colleges https://www.gov.uk/guidance/plan-technology-for-your-school. Note - The policy for this work is schools digital and the digital delivery is sector facing services portfolio | [5 empty] | False | False | 1 | Green | Fixing RAG from legacy Amber/Green to Green. We have met delivery targets in deploying new functionality that will extend our user base. We are now designing improvements that will make it easier for our growing user base to use our service. We have exceeded our targets for the year. |  | 5 | 12 | DDaT_22/23_003a | 172 |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 16:22 |  | 3 |  | Schools, Teachers, School Business Leaders, Policy Areas (Security, Commercial, Schools Group etc), Our teams of Digital professionals | False | True | True | 2022-04-06 |  |  |  | 2022-07-19 |  |  |  | 2023-03-13 |  |  |  | 2024-06-12
17 |  | CSC: Data Modernisation (daily data) | We want timely [automated], relevant CSC data to be collected and shared, including through published and private dashboards, enabling valuable insights into the policy, delivery and experiences of CSC. Our ambition is for DfE and the sector to be partners, and build trust in working together, using data to learn and improve the lives and outcomes for children and families. The service will allow Local Authorities to see their data in real time, without having to submit a return. ​ More timely data will enable the government and Local Authorities to identify and respond to arising problems quicker, making evidence-based decisions that result in better outcomes for children and families.​ The Department for Education does not have a solid, streamlined oversight of children’s social care (CSC) at national or local authority (LA) level due to the lack of frequency, consistency and quality of the data flowing in and out of the department. The department’s ability to understand, improve and support the needs of LAs and frontline workers most effectively is therefore inhibited. SoS has expressed a desire for DfE to make better use of modern data techniques (including developing dashboards and apps) to support Ministers and the department in making evidence-informed decisions around key priorities.​ | [5 empty] | False | False | 2 | Amber - Green | The API and Lakehouse are being refactored | Refactor of Silver and gold layers. | 4 | 3 | DDaT_22/23_004 | 113 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-26 12:16 |  | 4 |  | Local Authorities Public Families Group | False | True | True | 2022-06-20 |  |  |  | 2022-07-30 |  |  |  | 2022-12-01
18 |  | Configuration Management Database on ServiceNow | Understanding what services we deliver and how our existing IT estate supports these is a critical foundation to enable the delivery of DfE missions, helping to ensure that we can minimise duplication and complexity of services and supporting technology, enabling a more responsive approach to delivery demands and quickly identifying and addressing potential security threats and vulnerabilities. In the simplest terms, if we don’t know clearly what services we have and what technologies they depend on then we cannot effectively exploit, support, manage or improve our services. |  |  | 2025-01-01 |  |  | False | False |  | Green | On target with project plan for this milestone. |  |  | 20 | DDaT_22/23_005 | 63 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-05 07:49 |  | 1 |  |  | True | False | False | 2022-02-01
19 |  | Customer Experience Phase 2 | The Customer Experience team is supporting digital portfolios and wider policy teams to drive an enhanced focus on user-centred design and customer experience. The team is driving efficiency and culture change through its focus on solving complex user problems and improving user journeys across DfE products and services. This is a significant business change to the Customer Experience digital Transformation programme which was delivered in 2022. This includes substantial improvements, such as: developing an organic way of driving traffic towards our landing pages that doesn’t rely on the existence of a campaign. adding further features and tools to the landing pages, as well as new and more digestible content that links from them, such as a comparison tool for employers that will enable them to benchmark themselves against similar employers. further consolidation of content. investigating the potential for new offline resources to provide support to online developments. | [5 empty] | False | False |  | De-prioritised |  |  |  | 2 | DDaT_22/23_007 | 41 |  |  |  | False |  |  |  |  | Cancelled | This item is being removed from the Customer Experience and Design COMPASS deliverables whilst we focus on reporting against our most strategically important deliverables | False | 2025-11-20 13:56 | 2026-01-27 12:37 |  | 1 |  | Multiple internal and external users. External users include: young people, adult learners, parents, teachers, careers advisers, educational settings, local authorities, employers, OGDs Internal users include: policy teams across Skills, Families, Schools and Operations & Infrastructure Groups, comms campaign teams, data teams, DfE DDT professionals and DDT leadership. | False | True | True
20 |  | Turing Scheme Year 4 - Application phase | The overall objective of the proposal is to change how the Turing Scheme is delivered from academic year 2024/2025 onwards changing the existing delivery model and bringing the administration of the Scheme in house. There are two distinct elements to this proposal: the development of a digital service to support the administration of the Scheme; and the administration of the Scheme itself. The in-house service will be delivered in phases according to the need of users to complete a series of transactions throughout the year. Applying for funding is the first of these transactions. | [5 empty] | False | False |  | Green |  |  | 5 | 9 | DDaT_22/23_012 |  | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-06 11:56 |  | 1 |  | User in schools, colleges and universities across the UK and British Overseas Territories apply for funding on behalf of their students so that they can undertake work ans study placements across the world. | False | True | True | 2023-03-28 |  |  |  | 2023-07-10 |  |  |  | 2023-10-02 |  |  |  | 2024-02-06
21 |  | Turing Scheme Year 4 - Payments and Reporting | The overall objective of the proposal is to change how the Turing Scheme is delivered from academic year 2024/2025 onwards changing the existing delivery model and bringing the administration of the Scheme in house. The service is being developed iteratively to meet user need and delivery milestones. Following the development and launch of the application form and assessment functionality, the team is now developing processes to support the process by which funds will be allocated to and managed by organisations. We wish to re-design the existing payment process so that it is less burdensome for users while ensuring that it continues to meet DfE and HMG rules on grant payments. The first payments must be made no later than 1 September 2024 | [5 empty] | False | False | 4 | Amber - Red | Fixing RAG from legacy Amber/Red |  | 5 | 9 | DDaT_22/23_012_A |  | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-10 15:28 |  | 1 |  | User in schools, colleges and universities across the UK and British Overseas Territories apply for funding on behalf of their students so that they can undertake work ans study placements across the world. | False | True | True |  |  |  |  | 2023-07-10 |  |  |  | 2023-10-02 |  |  |  | 2024-02-06
22 |  | Skills Bootcamps Data Modernisation Project | Utilise digital technologises to fundamentally how the Skills Bootcamps can operate and deliver value to customers. It will involve a wide range of activities, including adoption of new technologies, the redisgn of business processes, and development of new organisational structures and ways of working. They are requesting assistance from the Submit Learner Data team to help build auxiliary data collection tools that produce datasets that can be merged with the dataset produced through the ILR. The Skills Bootcamps Data team has received feedback from multiple subject matter experts who have highlighted critical risks to the programme based on the lack of a &amp;quot;Single Source of the Truth&amp;quot; on programme performance. Currently, 3+ tools are used to collect data from Suppliers, resulting in duplication (even triplication) of data. This is because we have a number of data fields that existing fields in the ILR cannot accommodate. We collect these supplementary fields using excel-based collection tools with fragile validation that leads to challenges for suppliers (when submitting data) and the programme&amp;#39;s data team (when cleaning and consolidating the data). Submit Learner Data has recruited a Business Analyst and User Reearcher to deliver the work. The UR commenced work on 07/01/24 and the BA starts on 16/01/24. Scoping and other ceremonies will begin immeadiately. | [5 empty] | False | False |  | De-prioritised |  |  | 2 | 3 | DDaT_23/24_003 | 82 |  |  |  | False |  |  |  |  | Completed | PMO advised that project was completed in 2024 | False | 2025-11-20 13:56 | 2025-11-27 09:51 |  | 1 |  |  | False | True | True | 2023-06-05 |  |  |  | 2024-04-08 |  |  |  | 2024-07-04
23 |  | Eligibility Checking Service Replacement | The Eligibility Checking Service (ECS) is an application which provides local authorities (LAs) the ability to check to see if an individual (parent or carer) is in receipt of qualifying benefits, that entitles their children to a free school meal (FSM), Early Years Education for 2-year-olds (EY), Early years Pupil Premium (EYPP) or whether they are entitled to 30 Hours Free Childcare (30H). The ECS is a legacy service which is now unsupported, has not been built to GDS standards and requires retiring. As ECS is classified as legacy technology we are required by Cabinet Office to replace the system by 2025. | [5 empty] | False | False |  | Amber - Green | (1) Architecture supplier MadeTech has lost their renewal bid, meaning 2 critical resources will leave DfE. (2) FSM Expansion needs a coordinating DM role across us and the School Census teams but Board/SRO don’t seem to accept this risk. | (1) Unfortunately we lost the Principal Developer resource as they’d been reassigned. New staff coming online but it’s a big loss (2) We met with FSM Policy to explain our case but are yet to hear if the SRO is able to provide a mitigation. We believe 3m of an experienced DM would be enough to mitigate and have provided indicative costs and Key Deliverables. |  | 14 | DDaT_23/24_004 | 40 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-04 15:53 |  | 3 |  | LAs, Schools, Parents / Carers / Guardians | False | True | True | 2025-01-01 |  |  |  | 2025-01-01 |  |  |  | 2024-01-03 |  |  |  | 2025-08-01
24 |  | Social Work Practice Development Programme (SWPDP) (formerly Social Work Induction Programme (SWIP) and Early Career Framework (ECF) - Private Beta)) | To develop a strong pipeline of social workers, improved levels of retention of experienced social workers and improved quality of practice by launching a new programme of training, support and assessment for social workers: the Early Career Framework | [5 empty] | False | False |  | Amber - Red | The digital team completed its work at the end of last year following a shift in ministerial direction: the programme will now be supplier-led, and the supplier will provide the digital learning platform instead of DfE developing it in-house. The programme has also expanded to cover early career development, advanced child protection principles, and leadership, and is now called the Social Work National Professional Development Programme. Digital continues to advise and support policy with new digital requirements and procurement. | n/a | 4 | 4 | DDaT_23/24_005 | 47 | 2 |  |  | False |  |  |  |  | Completed | Completed Dec.A shift in ministerial direction means a supplier will provide the digital learning platform. Digital continues to advise and support policy with new digital requirements and procurement. | False | 2025-11-20 13:56 | 2026-03-11 06:03 |  | 1 |  | Children and Families Social Workers | False | True | True | 2023-02-06 |  |  |  | 2023-09-18 |  |  |  | 2024-04-01 |  |  |  | 2027-09-01
25 |  | Check an early years qualification and EY workforce register | The vision of the project is for an Early Years workforce that has clarity around, and confidence in their qualifications from day one of their career journey. The service aim is to be the definitive and trusted source of information about Early Years qualifications. | [5 empty] | False | False | 1 | Green | Delivery plan is on track. |  | 5 | 4 | DDaT_23/24_006 | 47 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 13:16 |  | 1 |  | Nursery managers, early years practitioners and, in the future, those looking to enter the early years sector | False | True | True |  |  |  |  | 2023-10-10 |  |  |  | 2024-02-01 |  |  |  | 2025-03-20
26 |  | Awarding Organisation Digital Portal (AODP) | Following the Government review of post-16 qualifications at level 3 and below in England, DfE needed to simplify the funding qualifications approval process. Awarding Bodies (AOs) need to be able to submit academic qualifications/submissions for 16-19 years olds/or adult offers to DfE for funding approval, 5-10 windows throughout the year that enables AOs to to submit applications. (Apprenticeship Service Deliverable) | [5 empty] | False | False | 2 | Green | All on track for agreed milestones. |  | 5 | 9 | DDaT_23/24_007 | 459 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-05 14:28 |  | 1 |  | Awarding Organisations | False | True | True | 2023-11-13 |  |  |  | 2024-04-15 |  |  |  | 2024-12-09
27 |  | Data sharing on vulnerable children between public sector bodies/Single Unique Identifier (Discovery+) | To improve the use of technology to share information between agencies working with children and families (schools, police, health and children's social care) and to explore the use of a consistent child identifier (CCI) to enable this. | [5 empty] | False | False |  | Amber - Red | No Change. | Same as last month: Escalation of concerns about NHSE engagement | 2 | 4 | DDaT_23/24_011 | 47 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 13:12 |  | 4 |  |  | False | True | True | 2024-07-01 |  |  |  | 2024-11-01
28 |  | NOT ON I&P PERF REPORT - Eligibility Checking Service (ECS) 30 hours and Early Years Pupil Premium (EYPP) eligibility expansion | By September 2025, working parents will be able to claim 30 hours of free childcare a week, over 38 weeks of the year, for children from nine months up to their child starting school. The expansion of 30 hours entitlement will also expand eligibility for EYPP. The existing ECS system will need to be updated in phases to support the expansion of entitlements | [5 empty] | False | False |  | Amber - Green |  |  | 5 | 14 | DDaT_23/24_013 | 40 |  |  |  | False |  |  |  |  | Completed | No exact date but advised that this was completed some time ago. | False | 2025-11-20 13:56 | 2026-02-05 13:10 |  | 1 |  | LAs, parents | False | True | True
29 |  | Master Education Provider System | We have a legal requirement for a register of schools and governors within the DfE, this data underpins a number of critical systems within the DfE and across wider government. The current system GIAS is currently running on a legacy database and dated code making it unsustainable moving forward. The new system will allow the retirement of several existing systems, GIAS, Provider Profile and UKRLP bringing in an estimated saving of £1.75m a year. | [5 empty] | False | False |  | ON HOLD |  |  | 2 | 8 | DDaT_23/24_016 | 39 |  |  |  | False |  |  |  |  | Paused | This work is currently on hold | False | 2025-11-20 13:56 | 2026-02-06 10:46 |  | 1 |  | Being a public service, consumers of provider data can range from private and public sector organisations or anyone who can connect via an API. The main consumer of GIAS are internal DfE users including and not limited to Schools Checking Service, ESFA and DSI. External consumers tend to be local authorities and several commercial or voluntary organisations such as software houses across the education sector and private companies with an interest in or need for official school attribute data such as Zoopla and Rightmove | False | False | True | 2023-10-09 |  |  |  | 2024-09-01
30 |  | Teaching Vacancies Service | Purpose - A free, online, national search and listing service for teaching roles in schools, for schools to list their vacancies free of any charge and for teachers to search these vacancies. Benefits - Saving schools money on recruitment costs by offering a free national job listing service | [5 empty] | False | False |  | Green |  |  | 5 | 8 | IT_TA8 | 39 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-06 12:35 |  | 4 |  |  | False | True | True | 2017-04-03 |  |  |  | 2017-07-03 |  |  |  | 2018-02-19 |  |  |  | 2018-07-13
31 |  | Live Regions Services | We make it more efficient for academies to belong to a strong trust, so that regional colleagues and schools can focus on improving education. | [5 empty] | False | False | 2 | Amber - Green | Delivery challenges & Mitigations Resource Constraints: Short‑term capacity gaps (notably Service Support and enabling roles) are being mitigated through interim cover, phased onboarding of new joiners, and prioritisation of critical BAU activity. Dependency on External Data & Policy Change: Delivery risks linked to Ofsted data availability and evolving policy are being managed through early technical preparation, mock data usage, and close engagement with policy teams. | Onboarding of required roles will assist in delivery. | 5 | 11 | IT243 | 192 |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 14:20 |  | 3 |  |  | False | True | True
32 |  | Find information about academies and trusts (FIAT) | Design and development of a tool that collates information from multiple sources about academies and trusts (replacing legacy tech - TRAMS) BETA: FIAT will be the go-to-place for DfE and ESFA colleagues to get the information they need to inform decision making and assessments about trusts and to provide better support to trusts. Brings together data from different services to give users a single source of information about trusts and academies​ | [5 empty] | False | False |  | Green |  |  | 5 | 11 | IT243a | 192 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 14:48 |  |  |  | Regions Group, Capital directorate | False | True | True | [8 empty] | 2024-03-25 |  |  |  | 2024-10-01
33 |  | Record Concerns and Support for Trusts | ReCast enables Regions Group and ESFA colleagues to record and manage concerns about schools and trusts. These include financial, governance, safeguarding and whistleblowing concerns. It enables DfE to make effective decisions about support and action that may be taken in relation to a trust. Product is currently being used by users. Allows Regions Group and SFSO (Schools Financial Support and Oversight) colleagues to record concerns and support related to trusts​ | [5 empty] | False | False |  | Green |  |  | 5 | 11 | IT243c | 192 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 14:49 |  | 3 |  | Regions Group, SFSO (ESFA) | False | True | True | 2020-03-31 |  |  |  | 2020-09-21 |  |  |  | 2022-09-30 |  |  |  | 2023-02-20
34 |  | Regional Services Division: Make changes to an Academy | Detailed understanding of school needs on significant change procedures to help schools and internal staff to manage significant changes such as school expansions and academy mergers. | [5 empty] | False | False |  | Green | On hold there is no RAG status. |  | 2 | 11 | IT243e | 192 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 14:50 |  | 3 |  |  | False | True | True | 2020-07-27 |  |  |  | 2020-11-19
35 |  | Regional Services Division: Manage free school projects | Make opening free schools easier and more efficient by capturing reliable data to manage projects, track progress and make informed decisions. | [5 empty] | False | False |  | Green |  |  | 5 | 11 | IT243f | 192 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 14:52 |  | 3 |  | Regions Group, Capital directorate | False | True | True | 2022-12-19 |  |  |  | 2023-04-10 |  |  |  | 2024-01-18 |  |  |  | 2024-07-01
36 |  | Regional Services Division: Manage Academy Projects | Enable regional colleagues to process applications from schools to become an academy and to prepare papers for approval by the Advisory Board. Improve the end-to-end process for completing academy conversions and transferring academies from one trust to another, following Advisory Board approval. | [5 empty] | False | False |  | Green |  |  | 5 | 11 | IT243g | 192 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 14:51 |  | 3 |  | Schools and academy trusts, Regions Group | False | True | True | [8 empty] | 2022-07-01 |  |  |  | 2023-01-17
37 |  | Regional Services Division: TRAMs | For staff to use one system with one version of the truth. This will reduce time taken to do their jobs and provide schools and trusts with consistent and joined up experience. To enable schools to apply to become an academy. | [5 empty] | False | False |  | Green |  |  | 5 | 11 | IT243h | 192 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 14:53 |  | 3 |  |  | False | True | True | 2017-09-04 |  |  |  | 2018-02-01 |  |  |  | 2019-02-12 |  |  |  | 2019-11-25
38 |  | Get Information About Schools | GIAS is a register of schools and colleges in England, and can be used to find and compare the performance of schools as well as the type, status and phase of each school or centre. GIAS displays information about governors, trustees and headteachers. Schools, local authorities and academy trusts can also update details by signing in to their DfE Sign-in account GIAS is the Department’s official register of state-funded and independent schools and online providers in England. It also contain vital information about and academy trusts in accordance with the Education (Supply of Information about the School Workforce) (No.2) (England) Regulations 2007). GIAS is also the national database of school governance in accordance with S538 of the Education 1996 and the Academy Trust Handbook. | [5 empty] | False | False | 2 | Amber - Green | Awaiting update. |  | 5 | 8 | IT255 | 39 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 12:59 |  | 3 |  | Schools Children's Centres Colleges Universities Local Authorities Academy trusts Dioceses Governors and Governing Bodies OGDs ALBs Rightmove UKRLP China, Ghana, Cayman Islands not for profit organisations | False | True | True | 2016-06-01 |  |  |  | 2016-07-01 |  |  |  | 2016-11-30 |  |  |  | 2017-09-18
39 |  | T Levels: Results and Certification | Design and delivery of the Manage T Level Results including digital systems and customer support, to enable T Level students receive accurate confirmation of achievement and attainment to specified deadlines. | [5 empty] | False | False | 1 | Green | The service remains stable and on track with the service in steady state and no significant development in progress or planned. |  | 5 | 9 | IT316a | 72 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-10 15:37 |  | 4 |  | Awarding organisations (currently 3 AOs, c. 40 registered users) Providers (c.250 schools and colleges for 25/26) | False | True | True | 2019-04-09 |  |  |  | 2019-09-01 |  |  |  | 2020-04-27 |  |  |  | 2024-02-01
40 |  | Get Into Teaching | The Get Into Teaching website aims to support potential candidates on their journey to becoming a teacher by offering inspiration, information and reassurance. The CRM enables support services including email journeys, events, advisers and the contact centre. Get school experience supports potential teachers to request unpaid placements so they can decide if teaching is for them and gain valuable experience for their ITT application, and enable providers to meet potential candidates. | [5 empty] | False | False |  | Green |  |  | 6 | 8 | IT322 | 39 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-06 12:16 |  | 3 |  |  | False | True | True | 2018-01-02 |  |  |  | 2018-02-01 |  |  |  | 2018-09-03 |  |  |  | 2021-04-08
41 |  | Becoming A Teacher | Our services are aiming to facilitate all postgraduate teacher training applications between candidates and training providers. With the inclusion of Find and Publish, this now includes searches for ITT courses by candidates and publishing courses by training providers. Includes; Apply For Teacher Training Find Postgraduate Teacher Training Publish Teacher Training Courses Register Trainee Teachers Manage School Placements Claim Funding For Mentor Training (was Track & Pay) | [5 empty] | False | False | 2 | Amber - Green | Fixing RAG from legacy Amber/Green |  | 5 | 8 | IT323a | 39 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-10 15:26 |  | 4 |  | Teachers, trainers, trainees | False | True | True | 2017-07-03 |  |  |  | 2017-08-19 | [7 empty] | 2020-06-01
42 |  | Claim Additional Payments for Teaching | The Claim Additional Payments for Teaching service (Claim) aims to increase teacher recruitment and retention by enabling early-career teachers to claim financial incentives. The service currently delivers the following retention policies: Teachers’ Student Loan Reimbursement (TSLR), Early-Career Payments (ECP) and Levelling Up Premium Payments (LUP). Claim will host the International Relocation Payments (IRP) service from September 2024. We are currently in the beta phase for two new services to be delivered through Claim – Further Education (FE) LUP payments and Early Years Recruitment Payments. | [5 empty] | False | False | 2 | Amber - Green | Awaiting update |  | 5 | 8 | IT453 | 39 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 12:56 |  | 4 |  |  | False | True | True | 2018-06-12 |  |  |  | 2018-10-01 |  |  |  | 2019-08-21 |  |  |  | 2019-10-31
43 |  | MYESF | The aim of the MYESF project is to deliver a modernised, resilient and user centred funding publication service to improve the full MYESF suite of services: Manage your education and skills funding, Document Exchange, and View Latest Funding, by developing a scalable pre 16 data integration pattern and strengthening the platform’s ability to integrate seamlessly with the Calculate Funding Service (CFS). This will enable MYESF to provide reliable, accessible and GOV.UK compliant digital services that operate 24/7/365 and deliver clear, accurate funding information to users. Building on ongoing service-wide transformation, MYESF will support improved end to end data flows, contribute to a unified funding service experience, and align with strategic technical upgrades across Funding Service Delivery (FSD). Key Objectives 1. Improve the user experience across all MYESF products • Deliver clearer, standardised funding statements and introduce new statement types (e.g., GAG In Year Openers). • Enhance accessibility and ensure full GOV.UK rebranding compliance across Manage your education and skills funding, Document Exchange and View Latest Funding. • Reduce complexity for providers, local authorities and internal users by improving navigation, presentation and data reliability. 2. Strengthen integration and data flows between MYESF and CFS • Develop a robust pre 16 data integration pattern that enables MYESF to consume CFS allocation data efficiently. • Support the move toward a unified, consistent data journey across funding services, including future single view funding allocations. 3. Modernise and future proof MYESF technology • Upgrade all MYESF components from .NET6 to .NET8 to mitigate end of support risks and improve service resilience. • Align MYESF with service wide technical architecture reforms, including the move to a single tenancy and improved accessibility standards. 4. Enable long term transformation across Funding Service Delivery • Support the shift toward simplified, standardised digital funding publications. • Align MYESF with the emerging single data layer and future Run state design to reduce duplication, improve governance and achieve better value for money. • Explore opportunities to streamline publication and sign off processes to reduce unnecessary bureaucracy. | [5 empty] | False | False |  | Green |  |  | 6 | 5 | IT484d | 208 |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-10 15:34 |  | 3 |  | Schools, academies & local authorities | False | True | True | 2019-04-01 | [7 empty] | 2019-08-01 |  |  |  | 2024-09-23
44 |  | Get help buying for Schools | Get Help Buying supports schools to enter better value commercial deals, saving them money Get Help Buying for Schools makes schools feel better equipped to deliver future procurements Get Help Buying meets School Business Professionals’ changing needs and they are satisfied with the service they receive | [5 empty] | False | False | 1 | Green | all major milestones achieved, currently in a BAU state and have been since October 2025 |  | 5 | 12 | IT575b | 83 |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-05 09:03 |  | 3 |  | School business buying professionals Commercial operations staff | False | True | True |  |  |  |  | 2020-07-03 |  |  |  | 2021-11-01 |  |  |  | 2023-03-20
45 |  | LDS 2.0 - AAD 2.0 | To simplify and improve the process of managing learner data | [5 empty] | False | False | 1 | Green | All key deliverables and milestones are on track for the reporting period |  | 5 | 3 | IT594 | 113 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 18:23 |  | 1 |  | Public Ofsted Ofqual STA ESFA Families Group Skills Group Schools Group | False | True | True | 2017-07-03 |  |  |  | 2017-08-19 |  |  |  | 2023-03-27 |  |  |  | 2024-10-01
46 |  | Check Your Performance Measures Data (CYPMD) | To deliver the Schools Checking Service previously provided externally by RM Education. The intial cycle delivered in house was in 2024. This was via the Oracle IA system, a tactical solution, until a strategic solution is developed. A digital service which shares school and pupil performance measures data back with schools and colleges ahead of publication of data. Users have the opportunity to requests pupils are included or removed from the performance measures calculations. They can also request amendments to their results data. These requests and any supporting evidence are scrutinised to inform a final decision. | [5 empty] | False | False | 1 | Green | All key deliverables and milestones are on track for the reporting period |  | 4 | 3 | IT594b | 113 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 10:47 |  | 3 |  | Schools LAs DfE - DISD and Policy teams | False | True | True | 2023-07-17 |  |  |  | 2023-10-02 | [7 empty] | 2024-06-24
47 |  | Teacher Continuing Professional Development | The ECF will provide teachers with high quality induction materials and support schools to set up and manage statutory induction requirements for teachers who are newly qualified and in the first two years of their profession and gain access to a funded programme of support to improve teacher retention and teaching quality. NPQ will provide high quality professional development to teachers later in their career. Includes: Continuing Professional Development Information Continuing Professional Development Service Manual Find A Teaching School Hub Manage Training For Early Career Teachers Register For A National Professional Qualification | [5 empty] | False | False | 2 | Amber - Green | Fixing RAG from legacy Amber/Green |  | 5 | 8 | IT627d | 39 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-10 15:27 |  | 4 |  |  | False | True | True |  |  |  |  | 2020-11-09 | [7 empty] | 2021-09-06
48 |  | Support for Social Workers (Public Beta) | Giving child and family social workers access to the right opportunities and encourage them to proactive manage their learning and development so that they can provide quality services while continuing to advance their careers within the profession. | [5 empty] | False | False |  | Amber - Red | The dedicated digital team for SfSW was stepped down late last year as there is no ongoing need for active development. The site remains live with static content, supported by our technical architect to ensure service continuity. Digital is working with policy on the long-term plan for the site and any interim content updates needed. | n/a | 5 | 4 | IT631 | 47 | 2 |  |  | False |  |  |  |  | Completed | The dedicated digital team for SfSW was stepped down late last year as there is no ongoing need for active development.Site remains live with static content, supported by our technical architect to ensure service continuity. Digital is working with policy on the long-term plan for the site and any interim content updates needed. | False | 2025-11-20 13:56 | 2026-03-11 06:07 |  | 1 |  | Children and Families Social Workers | False | True | True | 2021-05-04 |  |  |  | 2022-05-05 |  |  |  | 2022-08-15 |  |  |  | 2023-09-22
49 |  | Teaching Records Service | Creating the modern and reliable services, data and infrastructure needed to enable DfE to meet the needs of teachers, and confidently inform future strategy and policy decisions Data: - The data that Teacher Services stores is high quality, safe, secure and relevant - Removal of duplicate data flows; increase of data automation via secure APIs - Removal of legacy technology, components and implement full continuous integration and continuous deployment Digital services: - We understand how we can add more value to our users through the teaching record services - We understand how the teaching record services can better serve other Teacher Services Includes: Access Your Teaching Qualifications Check A Teacher's Record Find a lost Teacher Record Number Teacher Services Portals (part of DQT) Teaching Identity Teaching Record System (replacement for legacy database - DQT) | [5 empty] | False | False | 2 | Amber - Green | Fixing RAG from legacy Amber/Green |  | 5 | 8 | IT636 | 39 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-10 15:27 |  | 4 |  |  | True | False | True | 2021-04-26 |  |  |  | 2021-09-06
50 |  | Children's Barred List | The service allows authorised users to conduct checks in the following circumstances, in line with Keeping Children Safe in Education: ** newly appointed staff who are engaging in regulated activity, pending the receipt of an Enhanced Certificate with Barred List information from the Disclosure and Barring Service (DBS) ** where an individual has worked in a post in a school or college that brought them into regular contact with children or young persons which ended not more than three months prior to that person’s appointment to the organisation | [5 empty] | False | False |  | Green |  |  | 5 | 8 | IT636e | 39 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-06 11:58 |  | 4 |  |  | False | True | True | 2021-11-30 |  |  |  | 2023-06-21 |  |  |  | 2024-01-25 |  |  |  | 2024-08-01
51 |  | Apply for Qualified Teacher Status (QTS) | Purpose - Development and delivery of a new service for the award of QTS to overseas qualified teachers, including a new policy approach and underpinning legistlation Benefits - Opportunity to increase the number of international teachers being awarded QTS and working in English schools ​ Opportunity to improve the user journey for applicants | [5 empty] | False | False | 2 | Amber - Green | Fixing RAG from legacy Amber/Green |  | 5 | 8 | IT638b | 39 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-10 15:26 |  | 4 |  |  | False | True | True | 2021-11-01 |  |  |  | 2022-01-31 |  |  |  | 2022-05-23 |  |  |  | 2023-06-01
52 |  | Daily Attendance Data | Accelerating improvements in attendance data benchmarking functionality for schools, trusts and LAs, and explore matching with other data sets to support improvements in attendance through targeted interventions Background The project aims to enhance attendance data benchmarking and self-review in schools and local authorities, helping identify areas for improvement and assess intervention effectiveness. Reducing student absences could significantly boost lifetime earnings, with a 1% reduction potentially adding £282 million. Integrating attendance data with Children’s Social Care data will inform better interventions for vulnerable children. | [5 empty] | False | False |  | Green |  |  |  | 3 | IT642 | 491 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-11 15:09 |  | 3 |  | External reporting via View Your Education Data (VYED) to the Sector: Schools, SATs, MATs, and LAs. Internal use of the data by the Analytical Function Fortnightly publications via gov.uk | False | True | False | 2021-10-21 |  |  |  | 2022-04-01 |  |  |  | 2022-07-01 |  |  |  | 2023-11-01
53 |  | Early years child development training & Help for early years providers | Provide information and guidance needed to successfully implement the EYFS in an early years setting, and upskill the early years workforce on child development, empowering them to enable each child in their care to thrive. Early years child development training- A universally accessible, trusted training service for the early years workforce to provide skills and tools in child development so that they can improve outcomes for every child in their care. . Help for early years providers- Providing the trusted information and guidance you need to successfully implement the EYFS in your Early Years setting. | [5 empty] | False | False | 2 | Amber - Green | Its actually Amber but that option has gone? | We continue to provide policy with a clear, prioritised list of requests to support progress on the most urgent items. We have reviewed returned video scripts and SME draft content, but these remain dependent on policy review and the required clearance stages | 6 | 4 | IT650 | 47 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 14:13 |  |  |  | Early Years Practitioners and managers. Reception school staff. | False | True | True | 2021-10-04 |  |  |  | 2021-11-24 |  |  |  | 2022-06-30 |  |  |  | 2022-11-24
54 |  | Project Titan: Education Record | Develop a decentralised student ID system for citizens, build data automation tools and build a single post-14 education data store that this student data feeds into . | [5 empty] | False | False |  | Green |  |  | 4 | 17 | IT652 | 82 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 09:06 |  | 4 |  |  | False | True | True | 2022-04-01 |  |  |  | 2022-08-01 |  |  |  | 2024-06-04 |  |  |  | 2025-07-01
55 |  | Project Titan: Enter Learning Data | To develop a new MI System for training providers to record their learner data and support Individual Learner Record (ILR) data generation, also to provide real time BI reporting through links to View Your Education Data (VYED) | [5 empty] | False | False |  | Green |  |  | 4 | 17 | IT652a | 82 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 09:06 |  | 4 |  |  | False | True | True | 2021-06-09 |  |  |  | 2022-12-18 |  |  |  | 2024-08-01 |  |  |  | 2025-04-01
56 |  | DfE Connect (School Account) | To improve discoverability, findability, and navigation of DfE services. To provide better personalisation of content and experience for users and consider how data join up might be progressed between different services. This is a user facing service. | [5 empty] | False | False | 4 | Amber - Red | We know the current digital product does not meet users needs. By shifting effort to ensuring the product is scalable, future‑proof design and architecture, we expect smoother delivery and the ability to move at greater scale. | ​Our path to green relies on completing and agreeing feasibility against the agreed proposition. Once that’s done, we can move into scalable design with confidence in the approach. | 5 | 5 | IT663 | 168 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 15:15 |  |  |  | Current users: School Business Managers /School Leaders for all Pre-16 Academies. | False | True | True | 2022-01-01 |  |  |  | 2022-08-01 |  |  |  | 2023-09-28
57 |  | Identity Strategy | The Department has made a commitment to the Cabinet Office to ensure all relevant services are using GOV.UK One Login by 2025, and also to not build or buy any new authentication solutions for relevant services. The Department also has an Identity Management Strategy that this work enables us to meet. Migrate all existing citizen-facing digital services that require identity management to GOV.UK One Login by 2025 and migrate wallet credentials to Gov.uk Wallet by end of 2027. Ensure that any new digital services that require identity management abide by the Department’s identity management standard and therefore use the appropriate authentication solution. Create an Enterprise Identity Management strategy and standards. To improve user experience around identity management and authentication, and reduce the burden of fragmentation of identity management solutions for the sector and department. To reduce security risk around identity and access management for the department. | [5 empty] | False | False | 1 | Green | Implementation of strategy delayed due capacity of key stakeholders and potential appetite for slow adoption. |  | 5 | 14 | IT663b | 40 |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-04 15:56 |  | 2 |  |  | False | True | True | 2022-01-01 |  |  |  | 2022-09-01 |  |  |  | 2023-04-03 |  |  |  | 2023-10-02
58 |  | Standards Testing Agency (STA) Transformation Programme | STA will be a modern, diverse, inclusive world leader in developing and delivering accessible, valid and reliable digital assessments that support the delivery of excellent standards for education. Our services will be user centred to support schools effectively and efficiently to carry out these assessments. | [5 empty] | False | False | 2 | Amber - Green | Fixing RAG from legacy Amber/Green |  | 1 | 8 | DDaT_22/23_013 | 39 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-10 15:29 |  | 1 |  |  | False | True | True | 2025-09-01
59 |  | EUC: Core Service run and improvements | Improving the colleague experience and delivering exceptional workplace technology by maintaining, assuring and upgrading core technology services including: Videoconferencing refresh; headset refresh; mobile refresh, print refresh (aligned to the DfE Technology Strategy themes). Incl Unified Comms (Fixed and Mobile Telephony, Teams, AV/VC, Contact Centres); Desktop; Productivity (O365); Digital Tools, Accounts & Access, headset refresh, mobile refresh, CCTS). | [5 empty] | False | False |  | Green |  |  | 6 | 20 | BuRT006 | 37 |  |  |  | False |  |  |  |  | Completed | Project completed | False | 2025-11-20 13:56 | 2026-01-20 15:17 |  | 2 |  | Department | True | False | False | 2024-04-01 | [14 empty] | 2025-11-28
60 |  | Desktop Improvement | Delivering high performing secure end user compute through technical upgrades (Win 10 – Win 11), EUC service review assessing org wide strategy needs and reshaping the core device and virtual service. Multiple projects incl. print estate refresh and device refresh. | [5 empty] | False | False |  | Green |  |  | 6 | 20 | BuRT007 | 37 |  |  |  | False |  |  |  |  | Completed | Project completed. | False | 2025-11-20 13:56 | 2026-01-20 15:15 |  | 2 |  | Department | True | False | False | 2024-04-01 | [14 empty] | 2025-12-01
61 |  | Productivity Improvement and Enhancements | Development of a Power Platform Centre of Excellence, consideration and deployment of products across corporate tools (e.g. O365 Copilot) . Multiple projects incl. powerplatform expansion | [5 empty] | False | False |  | Green |  |  | 6 | 20 | BuRT008 | 37 |  |  |  | False |  |  |  |  | Completed | Project completed | False | 2025-11-20 13:56 | 2026-01-20 15:18 |  | 1 |  | Department | True | False | False | 2024-04-01 | [14 empty] | 2025-12-15
62 |  | GPA Technology Partnership | Developing and implementing the Shared Service Tech Offer in GPA buildings to deliver economies of scale whilst ensuring autonomy of DfE services. Phase 1 Coventry North, Phase 2 Sanctuary Buildings). | [5 empty] | False | False |  | Green | Still on track to deliver against GPA project timelines across all three phases. The biggest issue, is the ever changing, plan, timelines, baselines requirements, impact of DWP MoG. |  |  | 20 | BuRT009 | 52 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 09:16 |  | 3 |  | Department | True | False | False | 2024-09-30
63 |  | Improving the Colleague Experience | Developing and integrating strategic tools to improve the colleague experience (E.g. Teams integration with Service Now) |  |  | 2025-03-24 | 2025-11-28 |  | False | False |  | Green |  |  |  | 20 | BuRT010 | 37 |  |  |  | False |  |  |  |  | Completed | Work completed on time | False | 2025-11-20 13:56 | 2026-01-20 15:25 |  | 1 |  | Department | True | False | False | 2024-04-01
64 |  | Education Estates | Provide BAU support to ensure sector facing services are maintained and live for users | [5 empty] | False | False | 1 | Green | The service of Manage your education estate has now launched successfully. Previously recorded risks around unavailability of data, unavailability of MYEE to all potential users, and service assessment and/or accessibility audit outcomes delaying release date were not realised. An onboarding approach, including clear step-by-step DSI provisioning guidance and communications to reduce friction has been deployed. Adoption metrics are being actively monitored throughout Public Beta to inform further interventions. Post- accessibility audit triage completed. Remediation plan agreed with prioritised actions aligned to impact and feasibility. Progress tracked through to ensure timely resolution. ITHC scheduling and scope under review (managed centrally via the programme). Public Beta phase will be used to strengthen operational controls, security posture, and documentation of formal processes. |  | 5 | 12 | BuRT011 | 169 |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-05 07:46 |  | 3 |  |  | False | True | True | [8 empty] | 2025-09-05 | 2025-09-05 | 2026-02-25 |  | 2026-02-25
65 |  | DfE PAS (DfE Platform Architechture Standards) | To provide standards and reusable artefacts for infrastructure deployment. | [5 empty] | False | False | 2 | Amber - Green | There is a risk that standards will not be adopted if we are unable to gain consensus via governance and IE Community. Issue: unable to upload drafted standards to Find & Use Standards for approval as parts of the template do not copy over correctly. A call has been arranged to see if this can be resolved. | Continue to socialise and review standards with IE community. |  | 14 | BuRT022 | 40 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-04 15:52 |  | 4 |  | Department | True | False | False | 2023-03-01
66 |  | FinOps Services | Making every pound count by improving financial and commercial accountability and planning for cloud computing services; implement devolved budgeting and cost avoidance. | [5 empty] | False | False | 2 | Amber - Green | Service Lines have been slow to engage with the Cost Avoidance Advisory service. Significant number of Reserved Instances due to expire in February/March 2026 impacting on several service lines. | The team is working hard to identify cost savings for Service Lines, but some have not been very responsive in agreeing to a workshop, either delaying in agreeing to a meeting or just not responding to e-mails, despite it clearly identifying the potential savings. The team will be considering how to mitigate this at the next Azure Governance board. Reaching out to services lines affected to determine if their future plans are likely to affect the decision to renew the expiring Reserved Instances. |  | 14 | BuRT023 | 40 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-04 15:54 |  | 4 |  | Department | True | False | False | 2023-03-01
67 |  | Find and use APIs | To drive improvements to the FaUAPI platform in order to ensure it is the central tool that all development teams use for API management. To ensure all DfE APIs are in one place, discoverable and easy to interact with. | [5 empty] | False | False | 2 | Amber - Green | In beta testing: (1) Per-workspace feature flags , allows us to opt-in individual workspaces to new features so teams can test new functionality and provide feedback (2) Custom fields - Collect more data from users when they subscribe to your API (3) Webhooks - Send subscription events (create/update/delete) to external systems to allowing tracking/authorisation of API users In alpha testing: API import consolidation – Will allow users to import any kind of API using the same consistent JSON definition file format as the API export feature. API analytics phase 1 (senior managers) - building working prototypes UX for home page + onboarding & service design Migrations and onboarding ongoing | Status: Decom has been delayed to April 2026. FaUAPI team is already supporting API team in establishing a clear timeline to ensure potential impacts are minimised. This is still on track. Mitigation: handover plans in place, option to utilise BA if needed Mitigation: handover plans in place, expect poss delivery slowdown |  | 14 | BuRT024 | 40 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-04 15:54 |  | 1 |  | Department | True | False | False | 2023-03-01
68 |  | Eligibility Checking Service (ECS) Replacement | Replacement of ECS legacy system in 2025. The Replacement project has reviewed the end-to-end process for eligibility checking and determined what the overall process and technology should look like in the post-ECS environment. Now in Beta we are building two products as an MVP: a hub – the Entitlements Checking Engine (ECE), and replacement spokes for both School Meals and Childcare. | [5 empty] | False | False |  | Amber - Green |  |  |  | 4 | BuRT025 | 47 |  |  |  | False |  |  |  |  | Cancelled | Removed as this is a duplicate of Eligibility Checking Engine. | True | 2025-11-20 13:56 | 2025-12-04 15:35 |  | 3 |  | LAs, department | True | False | False | 2023-03-01
69 |  | CRM - Delivery Team | Programme of work to deliver standardised products across the business using the Dynamics 365 CRM platform. The CRM applications used across DfE include: Provider; Employer; Capital; ICA; EDD; IEBT and SISL. | [5 empty] | False | False | 2 | Amber - Green | No capacity for any additional work or incident resolution from SDT team resource – if urgent development/resolution of incidents is required for EDD, ICA, IEBT, SISL or SDT supported EDD services we will be unable to do this due to team being at capacity and no additional resource available. | Current team is stretched and at risk of burnout, no capacity for incident resolution, high priority work or illness cover if required. Paused work for improvements that aren't essential. CBP now in place although still awaiting CRM developer recruitment |  | 14 | BuRT026 | 40 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-04 15:51 |  | 3 |  |  | True | False | False | 2023-03-01
70 |  | Infrastructure Services BAU | BAU activity | [5 empty] | False | False |  | Green | ServiceNow Tickets Closed in Month and Open at Month End |  |  | 14 | BuRT028 | 40 | 4 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-12 16:57 |  | 2 |  |  | True | False | False | 2021-04-01
71 |  | Architecture | BAU activity To drive AI technology innovation, create sustainable AI capabilities and enable the successful integration of AI into operational delivery. To facilitate the adoption of AI across the DfE through an AI centre of excellence (CoE). The objectives of the CoE are to: Lead AI adoption across the Department and engage with all business areas ensuring central oversight. Develop and maintain the core technologies and platforms for AI. Guide and support teams to develop and optimise new AI solutions and integrate them with service delivery. Directly deliver new AI projects and lead discovery of new tools. Build skills and capability for the effective development and use of AI technologies. | [5 empty] | False | False |  | Amber - Green | The lack of a joined-up operating model in DDT means Enterprise Architecture is unable to drive strategic decision-making in DfE, leading to sub-optimal / inconsistent delivery and operations, where efficiency opportunities are lost and cost/risk increases for DfE. | Influence DDT operating model development with target architecture / model, grow EA / Business Architecture capability in both the architecture team and across portfolios, drive alignment with the target architecture in all portfolios and domains, and with Service Delivery Revolution. |  | 14 | BuRT030 | 40 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-04 15:49 |  | 2 |  |  | True | False | False | 2023-04-01
72 |  | AI Adoption | To drive AI technology innovation, create sustainable AI capabilities and enable the successful integration of AI into operational delivery. To facilitate the adoption of AI across the DfE through an AI centre of excellence (CoE). The objectives of the CoE are to: Lead AI adoption across the Department and engage with all business areas ensuring central oversight. Develop and maintain the core technologies and platforms for AI. Guide and support teams to develop and optimise new AI solutions and integrate them with service delivery. Directly deliver new AI projects and lead discovery of new tools. Build skills and capability for the effective development and use of AI technologies. |  |  | 2023-04-01 | 2026-03-31 |  | False | False | 2 | Amber - Green | Risks around readiness of AI tools for internal delivery which could lead to portfolios pursing AI based solutions which do not align with expects standards and impact security. Some blockers in ED Chat and Records management poc impacting schedule. | Increase Governance. Implement comms plan. |  | 14 | BuRT031 | 40 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-04 15:48 |  | 2 |  |  | True | False | False | 2023-04-01 | 2023-04-01
73 |  | Criticality Classification | Harmonisation of criticality classifications to ensure a consistent taxonomy so that services apply the appropriate criteria relevant to their service – to ensure appropriate support and assurance is in place. | [5 empty] | False | False | 1 | Green | The project is now closed ahead of the original timeline. |  |  | 20 | BuRT032 | 37 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 09:10 |  | 4 |  | Department | True | False | False | 2024-10-07
74 |  | DDT Finance | Oversight and planning of DDT finances providing insight to DDT directors and governance forums. Includes spending review work and other finance business planning. | [5 empty] | False | False |  | Green |  |  |  | 13 | BuRT037 |  |  |  |  | False |  |  |  |  | Completed | This work no longer requires reporting on as no longer in development. | False | 2025-11-20 13:56 | 2026-01-27 13:07 |  | 2 |  | All divisions in Tech and CXD Directorates, plus Data, CXD and Tech directors for information and insight on DDT workforce as a whole and related reporting to Cabinet Office, DDT Committee and others. | True | False | False | 2024-04-01
75 |  | Contract Management | Management of contracts and suppliers through which CXD (participating divisions), Tech and other part of DfE budgets. Provide insights to support decision making. Contract management is an essential activity to ensure public money is spent compliantly and achieved vfm. This is a shared service for Tech and most of CXD which achieves economies of scale and continuity of service and expertise for the areas supported. | [5 empty] | False | False |  | Amber - Green |  |  |  | 13 | BuRT042 |  |  |  |  | False |  |  |  |  | Cancelled | This work no longer requires reporting on as no longer in development. | False | 2025-11-20 13:56 | 2026-01-27 13:06 |  | 3 |  | All divisions in Tech Directorate plus six Divisions in CXD. Five divisions in CXD who partner with: - Families Group - Regions Group (primarily academies service lines) - Commercial (e.g. Get Help Buying for Schools) - Ops &amp; Infra Group (e.g. Schools Technology). - Skills Group (e.g. Turing Scheme). Plus other users who have nowhere to go or need support in a hurry - e.g. Data Directorate to support management of a critical risk to DfE, we have only User Research participant contract in DfE. | True | False | False
76 |  | Workforce management | Managing the workforce in two large Directorates (MI, analysis, reward and recognition) plus insight on DDT workforce as a whole and related reporting to Cabinet Office, DDT Committee and others. | [5 empty] | False | False |  | Green |  |  |  | 13 | BuRT043 |  |  |  |  | False |  |  |  |  | Completed | This work no longer requires reporting on as no longer in development. | False | 2025-11-20 13:56 | 2026-01-27 13:08 |  | 3 |  | All divisions in Tech and CXD Directorates, plus Data, CXD and Tech directors for information and insight on DDT workforce as a whole and related reporting to Cabinet Office, DDT Committee and others. | True | False | False
77 |  | Learning & Development / Early Talent | Leading on key aspects of DDT capability across DfE - early talent schemes, L&D budget and capability-based pay. These are critical to solving recruitment and retention issues that have been longstanding. Driving up Apprenticeship numbers within our Directorates (6%), delivery of £335,000 L&D budget and increasing access to L&D through internal enhancements, implement capability based pay across DDT. | [5 empty] | False | False |  | Amber - Green |  |  |  | 13 | BuRT044 |  |  |  |  | False |  |  |  |  | Completed | This work no longer requires reporting on as no longer in development. | False | 2025-11-20 13:56 | 2026-01-27 13:08 |  | 1 |  | DfE LT, DDT committee, Design and Delivery Board, Cabinet Office, DDT Directors and DDs, Finance colleagues, Commercial colleagues. HR colleagues, all DDT professionals. | True | False | False
78 |  | Governance, Performance & Insight | Effective and proporiate governance and assurance including board secretariat, planning, performance, risk and audit. Underpinned by tools and automation to support efficiencies and maintain one version of the truth across the Directorate(s). Shared service across CXDT &amp; DDT for Governance, Performance &amp; Insight. Automation service (PowerPlatform tools Apps and BI) to support effiencies across other SSO teams and provide effective live, self serve tools to DDT customer and leadership. Governance (DDT wide SLT, Design and Delivery Board &amp; DDT Committee) Planning, Performance &amp; Insight - PAD (CXDT &amp; DDT) Insights &amp; associated PowerApps to collect and manage data RMT, Contracts App, BuRT, IYA and IR Apps &amp; DDT Portfolio App Risk management, Audit Management, Performance/KPI and Objective tracking and monitoring &amp; DDT Correspondence | [5 empty] | False | False |  | Amber - Green |  |  |  | 13 | BuRT045 |  |  |  |  | False |  |  |  |  | Completed | This work no longer requires reporting on as no longer in development. | False | 2025-11-20 13:56 | 2026-01-27 13:07 |  | 3 |  | DfE LT, DDT committee, Design and Delivery Board, Cabinet Office, DDT Directors and DDs, Finance colleagues, all DDT professionals. | True | False | False | 2024-04-01
79 |  | DDT Spend Controls & Service Assessments | Ensure compliance with GDS/CDDO service standards and spend controls. | [5 empty] | False | False |  | Amber - Green |  |  |  | 13 | BuRT046 |  |  |  |  | False |  |  |  |  | Completed | This work no longer requires reporting on as no longer in development. | False | 2025-11-20 13:56 | 2026-01-27 13:07 |  | 3 |  | DfE, GDS, HMT, CDDO | True | False | False
80 |  | DDT Capability based pay | Implement DDT Capability Based Pay for Group 1 professions in DfE within three years of business case approval (which was January 2024). We have DfE LT and Baroness Barran's approval for the overall proposition, which is to save significant taxpayers' money by paying certain DDT professionals more and reducing reliance on managed services. DfE has approval from the Government Chief People Offier for its business case to implement CBP for Group 1 professions. | [5 empty] | False | False | 2 | Amber - Green | Issues: 1) Lack of clarity on financial processes in-year and in business planning. There is a risk that we do not secure enough in business planning to continue the rollout to new professions and to accommodate allowance changes as people develop. Close working with finance colleagues on this and paper going to Jane Cunliffe first week of March. 2) Capacity of DDs and teams to provide information and participate in recruitment and assessment. 3) Capacity of CBP team - two people – is limited. | This is a BAU activity which us unlikely to ever be completely green as there will always be blockers and risks but it continues to provide strong vfm so no major cause for concern. |  | 2 | BuRT047 | 209 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 14:40 |  | 2 |  | DDT Directors, DDs plus HoPs and SEO to Grade 6 staff in Group 1 professions. Recruiting Line Managers for eligible posts. Strategic Finance will collect the savings in a single cost centre and allocate as needed across DfE. Will work in conjunction with HR pay team on approving payments. | True | False | False
81 |  | Care leavers information / support | Create a service that aims to ensure that young people know all the options and support that are available to them across the journey of leaving care (approaching leaving and having left care) | [5 empty] | False | False |  | Green |  |  | 5 | 4 | BuRT050 | 251 | 2 |  |  | False |  |  |  |  | Cancelled | This has been superseded by Care Leavers DFE-DDT-193 | False | 2025-11-20 13:56 | 2026-03-04 09:56 |  | 4 |  | Children approaching leaving care, care leavers and those who support them | False | True | False
82 |  | FE Performance Dashboard - Provider & MCA | The FE Performance Dashboard project aims to deliver a dashboard tracking high level outcomes for FE providers and seperately for MCAs. Both products will initially go live on VYED in 2024. By July 25 both products are expected to be launched as public versions on GOV.UK. They are two measure in the FE provider dashboard which we currently have no method of collecting the data to populate the dashboard. We are currently looking at short term solution and longer term options to address this. Expect any longer term version will be a major project. | [5 empty] | False | False | [5 empty] | 9 | BuRT066 |  | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-06 12:11 |  | 4 |  |  | True | False | False
83 |  | Lifelong Loan Entitlement | The Lifelong Learning Entitlement (LLE) is a transformation of the student finance system that will replace the current HE Student Finance system from 2025. | [5 empty] | False | False | [5 empty] | 9 | BuRT067 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-01-26 08:01 |  | 4 |  | Higher Education/Students | True | False | False
84 |  | Contact Centre Procurement | The re-procurement activity of a business as usual Contact Centre Service provision for the operational areas of Apply to Pay (A2P) and Repayment Customer Services (RCS) within SLC | [5 empty] | False | False | [5 empty] | 9 | BuRT068 |  | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-06 12:00 |  | 1 |  | Higher Education/Students | True | False | False
85 |  | iFATE CRM | IFATE is an ALB hosted on DfE’s IT infrastructure. As part if its wider IT transformation programme, IfATE will be introduce a CRM system to support its front line delivery to stakeholder who include Employers and other organisations. | [5 empty] | False | False | [5 empty] | 9 | BuRT069 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-23 14:44 |  | 4 |  |  | True | False | True
86 |  | Interventions to harness generative AI in our sectors | Ambitious interventions to harness the opportunities for generative AI in our sectors, on critical path for SoS priorities in 24/25 (unlocking the potential of tech in education). 1) improve evidence base; 2) hackathons and 3) sandbox NOTE INFORMED BY RDS PMO THAT THIS SERVICE DOES NOT SIT IN BRIDIES AREA. CURRENTLY CONFIRMING WHICH DIVISION. | [5 empty] | False | False | 2 | Amber - Green | Awaiting Update. |  |  |  | BuRT070 | 192 |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-05 08:16 |  | 1 |  | Schools, colleges, edtech providers | False | True | False | 2023-01-03
87 |  | School Account Programme | Developing an external website that targets personalised support to School Leaders and School Business Professionals; Implementing an internal change programme inc setting out tasks and support to ensure the right services in place (Task and Service Index); Developing a Digital Services Strategy for Schools to co-ordinate service improvement. The programme seeks to improve the way that school leaders and school business professionals intetract with the department and seeks to be a single version of the truth. By standardising the creation & publishing of content, products & services and providing a digital platform that aims to eliminate the fragmentation in both the user’s journey and the underlying digital infrastructure, the DfE can give schools what they need in one place whilst reducing cost, increasing speed of delivery, and transforming and improving our current digital estate. Work in 25/26 will focus on: - developing the underlying source/database of DfE products, services and content that drives the school account experience - developing an onboarding strategy &amp; plan to expand the number and type of DfE products and services that are part of the School Account - developing &amp; scaling the School Account platform and programme delivery approach to deliver the service to a larger group of settings and users at scale, including the internal user experience - transforming the collective approach that the department takes to prioritising, funding, delivering and evaluating the delivery of services to schools. | [5 empty] | False | False |  | Green | N/A This is a duplicate entry |  |  | 5 | BuRT072 | 168 | 2 |  |  | False |  |  |  |  | Cancelled | This entry is cancelled as it is a duplicate of DFE-DDT-56 DfE Connect (School Account Programme) | False | 2025-11-20 13:56 | 2026-03-10 20:11 |  | 4 |  | School leaders, School business professionals, internal users from service teams and teams who publish and/or share information & comms with the sector | False | True | False | 2022-01-03
88 |  | Service Support & Performance Analysis | Provision of frontline support to schools and trusts and to users within Regions Group and SFSO (ESFA). Maintaining legacy systems and services in public beta, including bug fixes. Continously improving the services, based on user feedback and programme priorities. | [5 empty] | False | False |  | Green |  |  |  | 11 | BuRT073 | 192 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 14:56 |  | 2 |  | Schools and academy trusts, Regions Group, SFSO (ESFA) | False | True | False
89 |  | Funding Data Service (FDS) | Funding operations are heavily data dependant. FDS enables operators to make sure that the provider and funding data used in the Funding Service is correct. Work underway to enhance aspects of funding data managed out of CFS into FDS. Future work to integrate into the wider service to centrally serve data. | [5 empty] | False | False | 1 | Green |  |  |  | 5 | BuRT074 | 198 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-10 09:11 |  | 3 |  | Department | False | True | False
90 |  | Calculation Funding Service (CFS) | CFS enables users in business teams to create and manage funding models to calculate funding allocations for education providers to be used to create funding statements, contracts and payment requests. For PI 14 (17/12/2025 to 17/03/2026) the CFS objectives are 1 BAU- Support live funding in CFS (Jan to Mar allocations period). 2 Complete Adult onboarding- Support ALL and ASF 25/26 PMP updates and corresponding contract updates. 3 Refinements for Adults funding in 26/27- Explore refinements to profiling for Adults 26/27. Support comms funding towards delivery of digital Adult statements for 26/27. 4 Fix the big batch release problem - Enable CFS users to release whole batches of provider allocations without having to create smaller batches. 5 Continue the CFS containers transition from Cosmos to SQL - Deploy solutions for calcs container and data aggregations container. Implement solution for calculation results container. Start implementation for the users container. 6 Update the CFS UI for the refined user permissions journey- Implement the design from the refinement team for the CFS permissions journey that has been revised to meet GDS standards. 7 Support tenancy project towards migrating CFS - Support the tenancy team to migrate CFS environments to the single tenant. 8 Support comms funding project - Support with next phase beyond Adult 26/27 statements 9 Support the Data journey project - Support data team to understand CFS and how it may link into the single data layer. 10 Tech debt: Complete the upgrade of the ServiceBus package to use the ServiceBusReceivedMessage. Fix remaining failing integration tests. | [5 empty] | False | False |  | Green | Delivery on track. |  | 5 | 5 | BuRT075 | 194 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 09:48 |  | 3 |  | Department | False | True | True
91 |  | Digital Forms Builder (DFB) | Product being moved to SQL to allow for more complex forms and integration. Allows the user to quickly stand up professional, GDS compliant micro-services to make small collections and transactions better and more efficient. There is an opportunity to improve the efficiency and effectiveness of data collection. The team can then focus on the wider process around the forms to make sure accurate data is collected and that users are aware of what they can apply for, when and how. | [5 empty] | False | False | 1 | Green | No issues and progressing smoothly. |  |  | 5 | BuRT076 | 198 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-18 10:29 |  | 1 |  | Department | False | True | False
92 |  | Funding and Contracting Service (FCS) | Automates the generation of hundreds of further education funding agreements and controls the FE payments from data supplied by the provider.​ | [5 empty] | False | False |  | Green |  |  |  | 5 | BuRT078 | 200 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-16 08:14 |  | 3 |  |  | False | True | False
93 |  | Attendance mentoring | This intervention seeks to support better attendance for persistently or severely absent pupils (those who miss 10% or 50% or more of their education). | [5 empty] | False | False | [5 empty] | 4 | BuRT079 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmed that this was grant funded in 2023 and could be removed. | False | 2025-11-20 13:56 | 2026-01-07 10:42 |  | 4 |  |  | True | False | False
94 |  | DCS (Director Childrens Services) Leadership Program (UPON FutureLeaders Programme) | The Upon programme is an important part of the Children’s Social Care (CSC) workforce strategy. The programme has two strands: one for newly recruited Directors of Children’s Services (DCS) and a second strand focussing on those aspiring to the role. | [5 empty] | False | False | [5 empty] | 4 | BuRT081 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation from families group that DDT involvement was limited sot self service functions such as information and security and advice was given. | False | 2025-11-20 13:56 | 2026-01-12 10:20 |  | 4 |  | DCS/ADCS | True | False | False
95 |  | Child Minder Grants | launching a grant scheme for childminders, which is likely to be run externally. Expecting the contractor to build a website / portal to receive applications and with information about the scheme, and commercial have informed us that we need to let you know about any govt business not hosted on gov.uk | [5 empty] | False | False | [5 empty] | 4 | BuRT082 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation that this was grant funded and can be removed from COMPASS reporting. | False | 2025-11-20 13:56 | 2026-01-07 10:48 |  | 4 |  | EY Workforce | True | False | False
96 |  | Always Heard Helpline | Provision of a national advocacy advice and ‘safety net’ service (currently known as the “Always Heard” service). The service ensures looked-after children are aware of and understand their rights and entitlements to advocacy; signposts them to local advocacy services; and provides direct ‘safety net’ advocacy for those who have been denied or cannot access local services. | [5 empty] | False | False | [5 empty] | 4 | BuRT083 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation from families group that DDT involvement was limited sot self service functions such as information and security and advice was given. Several helplines were also candidates for back end unification hosting by DDT, but this did not happen and managed services were procured. | False | 2025-11-20 13:56 | 2026-01-12 10:13 |  | 4 |  | looked-after children | True | False | False
97 |  | Assessed & Supported Year in Employment | funds employers to provide bespoke support to their newly qualified social workers (NQSWs) which is fundamental to raising the quality of frontline practice and improving social worker retention. The funding enables further professional development to take place and requires employers to meet expectations around induction and support for newly qualified staff. | [5 empty] | False | False | [5 empty] | 4 | BuRT084 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation received that this was completed in 2024. | False | 2025-11-20 13:56 | 2026-01-07 10:40 |  | 4 |  | NQSWs | True | False | False
98 |  | LA Early Implementers | Sub programme of Early Years Childcare reforms Programme - plan to extend rollout to LAs ahead of the national rollout to understand the labour market impacts and to understand the barriers/impacts of the extension to the EY entitlements. | [5 empty] | False | False | [5 empty] | 4 | BuRT085 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation from families group that DDT involvement was limited sot self service functions such as information and security and advice was given. | False | 2025-11-20 13:56 | 2026-01-12 10:22 |  | 4 |  | LAs | True | False | False
99 |  | National School Breakfast Programme | The National School Breakfast Programme (NSBP) is funded by the Department for Education and delivered by Family Action to support schools in England to provide children with a healthy breakfast at the start of the school day. +1 - final year of contract. NOTE: WAS ORIGINALLY IN FAMILIES DELIVERABLES BUT WE HAVE BEEN ADVISED THAT THEY ARE NOT DELIVERING. BELIEVE IT IS SCHOOLS BUT AWAITING CONFIRMATION. THERE IS A DELIVERY IN EDS - BREAKFAST CLUBS. UNSUERE IF THIS DELIVERALBE IS A DUPLICATE OR PROGRAMME TO BE MONITORED SEPERATELY. EMAILED TRYSTAN TO TRY TO CONFIRM. | [5 empty] | False | False | [5 empty] | 8 | BuRT086 | 39 |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-02 08:53 |  | 4 |  | Schools, pupils | True | False | False
100 |  | NELI (Nuffield Early Language Intervention) | to improve language outcomes for disadvantage children in Reception Class. Training being delivered to TAs to implement with children. This was to reduce the progress impact as a result of Covid. | [5 empty] | False | False | [5 empty] | 4 | BuRT087 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation from families group that DDT involvement was limited sot self service functions such as information and security and advice was given. | False | 2025-11-20 13:56 | 2026-01-12 10:23 |  | 4 |  | Settings, reception learners | True | False | False
101 |  | Loving Relationships Programme | Funding of £30.1m in the next two years (£11.7m in 2023-24 and £18.4m in 2024-25) to significantly increase the number of LAs with family finding, mentoring and befriending programmes, including Lifelong Links. | [5 empty] | False | False | [5 empty] | 4 | BuRT088 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation from families group that DDT involvement was limited sot self service functions such as information and security and advice was given. | False | 2025-11-20 13:56 | 2026-01-12 10:23 |  | 4 |  | LAs | True | False | False
102 |  | SEND Supported Internships | SIs are a type of study programme aimed at 16-24 year olds who have an Education Health and Care (EHC) plan, who want to move into employment and who need extra support to do so. | [5 empty] | False | False | [5 empty] | 4 | BuRT089 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation from families group that DDT involvement was limited sot self service functions such as information and security and advice was given. | False | 2025-11-20 13:56 | 2026-01-12 10:24 |  | 4 |  | LAs (learners) | True | False | False
103 |  | Fostering recruitment and retention | Working with local authorities across the North East region to introduce a new regional hub to support individuals interested in applying to foster, facilitate regional targeted communications and improve retention. | [5 empty] | False | False | [5 empty] | 4 | BuRT090 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation that the work ended and can be removed from COMPASS reporting. | False | 2025-11-20 13:56 | 2026-01-07 10:46 |  | 4 |  | LAs | True | False | False
104 |  | New data solution for tracking and analysing Serious Incident Notifications (SINs), Rapid Reviews and Local Child Safeguarding Practice Reviews (LCSPRs) | Summary – what the project is aiming to achieve: A sustainable data solution will: Improve the quality, collection and analysis of serious incident data, addressing SoS concerns around data quality and underreporting and supporting better policy development that in turn helps to prevent future death or harm to children Minimise duplication of processes and manual efforts promoting a VfM approach that reduces errors and improves efficiency Streamline the process across the statutory stages, supporting users to meet their responsibilities Reduce reliance on and cost from outsourcing data analysis with an aim to bring data analysis in-house Provide a digital infrastructure that gives a foundation to support the Child Safeguarding Practice Review Panel’s priority to improve their analytical capabilities and dissemination of learning to the sector Benefit local authorities and safeguarding partners by improving their experience for data input and supporting them to meet quality and accuracy expectations | [5 empty] | False | False | 2 | Amber - Green | Path to Green: Alpha outputs delivered: minimum day‑5 SIN dataset, feasibility assessment, CSIN/reporting prototypes, and internal case‑tracking concept to reduce manual reconciliation. Clear decision gate: SRO decision on whether to proceed to Beta once Alpha defines scope, timeline and cost for Phase 1b. Parallel tactical fixes (Laura Bailey): strengthen live dashboard/briefing processes and reduce duplication. Alignment across system: integrate Panel Secretariat and CSIRT processes and case‑management lifecycle into design to eliminate duplication and clarify data flows. Continuity secured: progress extension of NCVPP/CoP cooperation agreement to maintain analytical capacity until end of FY26-27 whilst SIDD team’s work progresses. | As per RAG justification | 1 | 4 | BuRT091 | 47 |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 16:51 |  | 4 |  | DfE, | True | False | False
105 |  | Care Leavers Covenant | CLC is designed to enable national and local private, public and voluntary sector organisations across wider society to make a public commitment to support care leavers by providing specific practical things that help them to live independently | [5 empty] | False | False | [5 empty] | 4 | BuRT092 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation that this was grant funded in 2023 and can be removed from COMPASS reporting. | False | 2025-11-20 13:56 | 2026-01-07 10:47 |  | 4 |  | national and local private, public and voluntary sector organisations | True | False | False
106 |  | Fosterlink | To support local authorities (LAs) to increase the numbers of foster carers they successfully recruit, increase placement stability, and deliver cost savings for the LA | [5 empty] | False | False | [5 empty] | 4 | BuRT093 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation from families group that DDT involvement was limited sot self service functions such as information and security and advice was given. Several helplines were also candidates for back end unification hosting by DDT, but this did not happen and managed services were procured. | False | 2025-11-20 13:56 | 2026-01-12 10:21 |  | 4 |  | LAs | True | False | False
107 |  | Designated Family Judge - Trailblazer Pilot | Trailblazer pilot aims to tackle the drivers of delay across the FJ system therefore reducing costs across the FJ system and improving children’s outcomes. | [5 empty] | False | False | [5 empty] | 4 | BuRT094 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation that the pilot ended and can be removed from COMPASS reporting. | False | 2025-11-20 13:56 | 2026-01-07 10:44 |  | 4 |  | LAs | True | False | False
108 |  | Fosterline | Reprocurement of a free, confidential, impartial advice/support service | [5 empty] | False | False | [5 empty] | 4 | BuRT095 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation from families group that DDT involvement was limited sot self service functions such as information and security and advice was given. Several helplines were also candidates for back end unification hosting by DDT, but this did not happen and managed services were procured. | False | 2025-11-20 13:56 | 2026-01-12 10:21 |  | 4 |  | Existing and potential foster carers | True | False | False
109 |  | Wraparound Childcare - Start-up Programme | pump prime pilot, help test and further understand what support and funding is needed at a national level to support all schools to ensure availability of wraparound childcare for all families who need it, so we can support parents to work/get into work. | [5 empty] | False | False | [5 empty] | 4 | BuRT096 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation from demand team and Business Partner that this was advice only which has been provided. | False | 2025-11-20 13:56 | 2026-01-12 11:13 |  | 4 |  | schools | True | False | False
110 |  | CYP Advisory Board | The team are setting up a Children and Young Person’s Board. They want to set up a website to provide updates on the activities of this CYP Board. Also looking to procure secretariat function (contract). | [5 empty] | False | False | [5 empty] | 4 | BuRT097 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation from families group that DDT involvement was limited sot self service functions such as information and security and advice was given. | False | 2025-11-20 13:56 | 2026-01-12 10:19 |  | 4 |  | DfE, Board members | True | False | False
111 |  | Always Heard (Advocacy) helpline | Provision of a national advocacy advice and ‘safety net’ service (currently known as the “Always Heard” service). | [5 empty] | False | False | [5 empty] | 4 | BuRT098 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation from families group that DDT involvement was limited sot self service functions such as information and security and advice was given. Several helplines were also candidates for back end unification hosting by DDT, but this did not happen and managed services were procured. | False | 2025-11-20 13:56 | 2026-01-12 10:12 |  | 4 |  | CYP | True | False | False
112 |  | Educational Psychology Training | Programme aims to continue the supply of Educational Psychologists (EPs) into the local authority (LA) workforce, by seeking approval to continue part -funding the three-year EP Doctorate training course. | [5 empty] | False | False | [5 empty] | 4 | BuRT099 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation that this work ended and can be removed from COMPASS reporting. | False | 2025-11-20 13:56 | 2026-01-07 10:44 |  | 4 |  | Universities | True | False | False
113 |  | What Works Centre Foundations | Learning and evaluation from the IP and PIP is currently available on different websites and is not well utilised by the sector. This programme would see the body of work hosted in one place and communicated to the sector as part of WWCSC’s impact strategy, therefore increasing the use and impact of the learning in practice settings. | [5 empty] | False | False | [5 empty] | 4 | BuRT101 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation from families group that DDT involvement was limited sot self service functions such as information and security and advice was given. | False | 2025-11-20 13:56 | 2026-01-12 10:24 |  | 4 |  | CSC and SEND worksforces | True | False | False
114 |  | Complete end-to-end grant management system | MAPs initial overall aim is to be a complete end-to-end grant management system from data to payment approval for all funding. | [5 empty] | False | False | [5 empty] | 5 | BuRT104 | 166 |  |  |  | False |  |  |  |  | Cancelled | Was cancelled in 2025. | False | 2025-11-20 13:56 | 2026-02-05 11:42 |  | 4 |  |  | True | False | False
115 |  | Schools Tech Policy (Strategy for schools to gain digital maturity) | Policy interventions to make sure all schools have secure, effective and efficient techology infrastructure, meet basic technology standards, have the capability and capacity to use tech effectively and set a sustainable digital strategy for the future, including use of emerging technologies and assistive technology. Responsible for dept relationship with the edtech market including new activity on kitemarking products for safety and outcomes. Aims of programme: to improve outcomes, reduce workload and make efficiencies in schools. Set the strategy and policy interventions so that all schools can achieve a good level of digital maturity and use technology effectively. This is on the critical path for SoS priorities (digital/AI - ensure broadband and basic infrastructure in sectors). Aims of programme: to improve pupil outcomes, reduce staff workload and make efficiencies in schools. NOTE INFORMED BY RDS PMO THAT THIS SERVICE DOES NOT SIT IN BRIDIES AREA. CURRENTLY CONFIRMING WHICH DIVISION. | [5 empty] | False | False | 2 | Amber - Green | Fixing RAG from legacy Amber/Green |  |  |  | BuRT107 | 192 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-05 08:19 |  | 3 |  | Schools, colleges, edtech providers | False | True | False
116 |  | Live Apprenticeship Service | Build/test/run an end to end Digital Service for Apprentices, Employers, Providers and End Point Assessment Organisations. The Apprenticeship Service is an end-to-end Digital service that builds, tests and runs Digital systems for Apprentices, Employers, Providers and End Point Assessment Organisations. It comprises of 11 transactions (0.7bn transactions a year) that drives efficiencies through a Digital first approach of self-serve. Apprentices are inspired to apply for an Apprenticeship through Apprenticeships.gov. Find an apprenticeship has 2.8million accounts. 30,000 vacancies are added by employers and providers a month. Employers manage apprentices and their Levy funds online through 253,000 employer accounts, and providers apply through the Register of Training Providers to qualify for Government Funding. We pay £2.4bn yearly to providers and employers through digital payments systems. The functionality is supported by a Service Support desk which gets 500 calls per week and through user research and testing (3,000 face to face UR sessions, 4,500 surveys). (Apprenticeship Service Deliverable) | [5 empty] | False | False |  | Green | N/A |  | 6 | 9 | Z00ERF0012/13 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-24 14:13 |  | 3 |  | Apprentices (and Potential Apprentices), Employers (Levy Payers) and SMEs, Approved Training Providers, End Point Assessment Organisations | False | True | True
117 |  | ALB cyber resilience - Benchmark our ALBs level of cyber maturity | Establishing Governance and Oversight over the department’s ALBs. The aim of our first project is to Benchmark cyber maturity of our 12 DFE ALB across five CAF critical domains.​ | [5 empty] | False | False | 2 | Amber - Green | Lack of dedicated SME resource to support required activities to articulate cyber risk baseline position and expectations on us and ALBs of the government cyber action plan and security strategies | A better understanding of the expectations and accountabilities on the department of the new government cyber action plan in relation to our ALBs. Cyber SMEs resource to support the work. Short term resource due to be onboarded at the start of March. |  | 16 | BuRT132 | 61 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 22:48 |  | 1 |  |  | False | True | False | 2024-09-01
118 |  | Compare School and College Performance | A digital service provided by DfE to help the public access and compare school or college performance. CSCP is mainly used by school and college staff, leaders and governing bodies, parents and other stakeholders interested in educational outcomes. It is a Public facing service that provides information on school and college performance to parents, schools, Ofsted, LA’s, researchers and governors. The service is designed to support parental choice, increase school accountability and support improvement. | [5 empty] | False | False |  | Green |  |  |  | 8 | BuRT136 | 39 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-06 11:59 |  | 4 |  | Parents; Schools; Ofsted; Local Authoriteis; Researchers; Governors. | False | True | True | 2021-03-01
119 |  | Analyse School Performance | A web-based interactive that allows schools to review their performance data to support self-evaluation, and is the main source of data for School Improvement Advisers and OFSTED Inspectors. ASP is accessed through DfE Sign in that gives school leaders, governors, LAs, MATs, dioceses, DfE and Ofsted access to official detailed pupil level performance data. The service is designed to support accountability policy and helps schools improve by providing accurate attainment data. | [5 empty] | False | False | 2 | Green | Service is in BAU. All intended service operations and data publications successfully implemented as planned. |  | 5 | 8 | BuRT137 | 39 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-19 13:45 |  | 3 |  | Schools; Local Autorities; MATs; Dioceses; Ofsted; Traning Providers; DfE regional & policy teams. | False | True | True | [12 empty] | 2022-03-04
120 |  | Metadata & Data Quality - Education and Awareness | [6 empty] | False | False | 1 | Green | Not currently active |  |  | 16 | BuRT138 |  |  |  |  | False |  |  |  |  | Paused | Project not currently active | False | 2025-11-20 13:56 | 2026-03-11 14:18 |  | 5 |  |  | True | False | False | 2023-04-03
121 |  | NOT ON I&P PERF REPORT - Critical Data / ESDA (Data Quality Capability Development) | An Essential Shared Data Asset (ESDA) is data provided or acquired by a government department or agency to provide an essential process or purpose. To provide CDDO with information required to support their Roadmap 2022-2025, xpecifically "better data to power decision making", of which 2 specifically relate to critical data assets. | [5 empty] | False | False |  | Green |  |  |  | 14 | BuRT140 | 40 |  |  |  | False |  |  |  |  | Cancelled | This is no longer under EDS with Matt Evans. This is now under Mike Bennett in Cyber Security. | False | 2025-11-20 13:56 | 2026-02-05 15:29 |  | 5 |  |  | True | False | False | 2023-04-03
122 |  | AI - Driving effectiveness of AI tools for education (Programme) | To develop the departments AI capability we are bringing together a store of education content which has been optimised for AI use. This content is a vital ingredient for high quality AI education tools which are tailored to our system and curriculum. Working with DSIT, no10 colleagues and an external contractor, we will run hackathons where edtech developers can access this content to develop new AI education tools. | [5 empty] | False | False | 2 | Amber - Green | 1 project (AI tools) slightly delayed but supporting supplier - assured that delivery is on track with appropriate prioritisation. | monitoring delays and milestones | 5 | 8 | BuRT143 | 108 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-05 14:12 |  | 4 |  | For the content store: Schools, colleges, providers for uploading content to the content store. Developers/edtech providers accessing content store content via API. | False | True | False | 2024-09-09
123 |  | Advice and guidance - Get Help with Data Protection in Schools | Providing advice and guidance on the use of personal data to DfE and ESFA staff, ensuring policies and practices meet with data protection legislation and codes of practice. | [5 empty] | False | False |  | Green |  |  | 6 | 20 | BuRT147 | 37 |  |  |  | False |  |  |  |  | Completed | This project was reported on progress while being embedded into the Data Protection Team. This is fully embedded now and on a cycle of priorities being determined through user research. This remains a priority to support schools, but is no longer classed as a project. This is BAU | False | 2025-11-20 13:56 | 2026-01-20 09:53 |  |  |  |  | True | True | False
124 |  | AI Tools for Appraisal | To develop an AI tool to assist with the review of digital records. To reduce the digital heap through identifying records for destruction, review and preservation (National Archives) |  |  |  | 2026-06-30 |  | False | False | 2 | Amber - Green | This project is subject to test and learn, business rules need to be reviewed each time testing is carried out on new data sets. The initial data set iterated to accuracy over 90%. Accuracy on record for destruction is currently 16% for the extended data set. The records management team are reviewing the results and updating business rules to be tested. | Continue to work on business rules. |  | 20 | BuRT149 | 36 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 15:41 |  | 1 |  |  | True | False | False | 2024-09-01
125 |  | Individualised Learner Record (ILR) | We will collect, assure, analyse, manage and share key data on learners and the sector for processing as part of the end-to-end funding service. | [5 empty] | False | False |  | Green |  |  |  | 17 | BuRT151 | 82 | 4 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 09:06 |  | 3 |  |  | False | True | False
126 |  | Approvals Simplification and Earnings Calc | The Service are implementing a new payments system that pays providers using primarily Service data, reducing reliance on ILR data. This work will provide more flexibility for the programme to adapt payment models, improve the management of change of circumstances through provider accounts, and release funding more readily to providers as a result of reduced data locks. (Apprenticeship Service Deliverable) |  |  |  | 2026-09-30 |  | False | False | 4 | Amber - Red | Funding rules publication and announcements are now due much later than planned, anything unexpected from these will impact on delivery timeliness. The change of circumstance part of the April delivery has been delayed due to other commitments. There is also nervousness about new requirements arising that will derail delivery. | Working across teams to resolve. We are triaging any conflicting requests as they come in. | 13 | 9 | BuRT155 |  | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 12:57 |  | 4 |  |  | False | True | False | 2024-12-02 | [7 empty] | 2024-10-04 |  |  |  | 2025-09-01
127 |  | Run and maintain live service National Careers Service and Skills for Careers | To support the triage (1st line) Service Management Services and provide 2nd line resolution (where relevant), using the Buyer’s Tooling, including: Incident Management; Problem Management; Change Management; Release Management; Risks and Issues and Knowledge Management. Provide support during the development lifecycle to include the development and testing of environment configuration, including Technical Spikes; assist with debugging and troubleshooting of platform level problems. (National Careers Service Deliverable) | [5 empty] | False | False |  | Green |  |  |  | 9 | BuRT156 | 182 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-11 13:02 |  | 3 |  |  | False | True | False
128 |  | Interactive Careers and Skills | The Beta phase was approved at the Portfolio Review Meeting on 2 July 2024 with the following agreed recommendations: The high-level recommendations that were presented for Beta are: Understanding Skills User needs, this includes a continuing with User Research and the retirement of Skills Health check, Improving the Signposting of service features and Navigation of the product Improvements to the Triage Tool – including personalisation of content to mindsets, 2 stage selection of articles and filtering. Improvements to DYSAC – includes changes to content to improve on users understanding of the intent of using DYSAC, improvement of users understanding of the summary and the results shown. (National Careers Service Deliverable) | [5 empty] | False | False |  | Green |  |  | 6 | 9 | BuRT157 |  |  |  |  | False |  |  |  |  | Cancelled | Confirmation from Piers Dunstall that , Interactive Careers and Skills needs removing as there is no longer any work in that space. | True | 2025-11-20 13:56 | 2026-03-06 08:25 |  | 3 |  |  | False | True | True | 2024-02-01
129 |  | Data Insights | Design, develop, and maintain the technical infrastructure, data models, and visualisations that enable the Digital scorecard and Power Bi to deliver insights Supporting the identifying of additional KPI’s and data points which work to demonstrate performance of the digital service in line with user, policy and business needs.Developing additional visualisations within PowerBi or improving existing ones. Development or support with any Digital Scorecard and data insights team backlog items (National Careers Service Deliverable) | [5 empty] | False | False |  | Green |  |  |  | 9 | BuRT160 |  | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-11 13:00 |  | 3 |  |  | False | True | False | 2023-07-03
130 |  | Access Your Teaching Qualifications | [6 empty] | False | False |  | NOT STARTED |  |  |  | 8 | IT636b | 39 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-06 11:51 |  |  |  |  | False | False | True
131 |  | Find a lost Teacher Record Number | [6 empty] | False | False |  | NOT STARTED |  |  |  | 8 | IT636a | 39 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-06 12:12 |  | 4 |  |  | False | False | True
132 |  | SLD - FE workforce collection roll forward for 24/25 | Roll forward the FE Workforce collection for 24/25 and delivery any required policy updates. Will open in Oct 25 and close in Jan 26. | [5 empty] | False | False |  | Green |  |  |  | 17 | BuRT164 | 82 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 09:07 |  | 4 |  |  | False | True | False
133 |  | LDS - Matched Data Production | To deliver accurate, timely, and well matched data that supports the needs of our stakeholders (AAD/NPD/YPMAD). | [5 empty] | False | False | 1 | Green | All key deliverables and milestones are on track for the reporting period |  |  | 3 | BuRT166 | 113 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 13:31 |  | 3 |  | End users - The key users are the National Funding Formula, Pupil Premium and Accountability & Skills Policy and Statistics Teams. However, the data under NPDAAT is used across the department, sector and public citizen to inform research, analysis and decision making. | False | True | True
134 |  | LDS - KS2 | To enable the department to provide KS2 data to fulfil education and department needs. | [5 empty] | False | False | 1 | Green | All key deliverables and milestones are on track for the reporting period |  |  | 3 | BuRT168 | 113 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 10:16 |  | 3 |  | Public Ofsted Ofqual STA | False | True | True
135 |  | LDS - KS4 | To enable the department to provide KS4 data to fulfil education and department needs. | [5 empty] | False | False | 1 | Green | All key deliverables and milestones are on track for the reporting period |  |  | 3 | BuRT167 | 113 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 10:31 |  | 3 |  | Public Ofsted Ofqual STA | False | True | True
136 |  | LDS - 16-18 | To enable the department to provide 16-18 data to fulfil education and department needs. | [5 empty] | False | False | 1 | Green | All key deliverables and milestones are on track for the reporting period |  | 6 | 3 | BuRT169 | 113 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 10:03 |  | 3 |  | Public Ofsted Ofqual STA | False | True | True
137 |  | Find education and training | Creation of a single search tool that:​​ empowers young people to explore all their education and training options in their area; helps those facing additional barriers; assists parents, teachers and careers advisors to support these decisions; maintains relevance regardless of the direction of future policy and organisational delivery |  |  |  | 2026-03-27 |  | False | False | 1 | Green | All green assessment with one amber for NCS to take forward. |  | 4 | 2 | BuRT177 | 24 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-25 13:04 |  | 4 |  |  | False | True | True | 2024-04-01
138 |  | Heads of Profession Framework | Embed the Heads of Profession Framework including weekly profession time | [5 empty] | False | False |  | Amber - Green |  |  | 6 | 2 | BuRT186 | 41 |  |  |  | False |  |  |  |  | Cancelled | This item is being removed from the Customer Experience and Design COMPASS deliverables whilst we focus on reporting against our most strategically important deliverables | False | 2025-11-20 13:56 | 2026-01-27 12:38 |  | 1 |  |  | True | False | False | 2024-04-01
139 |  | Culture & behaviours (wave 2) | [6 empty] | False | False |  | Green |  |  |  | 4 | BuRT190 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation received that this was completed in 2024. | False | 2025-11-20 13:56 | 2026-01-07 10:41 |  | 1 |  |  | True | False | False | 2024-06-03
140 |  | Service and delivery lifecycle (wave 2) | [6 empty] | False | False |  | ON HOLD |  |  |  | 9 | BuRT193 |  |  |  |  | False |  |  |  |  | Cancelled | Work on this has been superceeded by Service Delivery Revolution which will be reported on via the Strategy & Transformation area. Workstream closed. | False | 2025-11-20 13:56 | 2025-12-02 13:32 |  | 1 |  |  | True | False | False
141 |  | AI - Driving safety of AI tools for education (Programme) | Lay the groundwork to ensure the safe and compliant use and monitoring of generative AI in education. Background The program aims to optimise generative AI tools to benefit the English education system, reducing teacher workload and closing the attainment gap. It ensures safe governance of UK education data for AI training, improving tool quality and benefits. It enhances the DfE’s ability to develop AI/ML tools and insights, informing better interventions, support, and policy. These are the projects: Content Store and Catalyst Fund: Make funding and pre-processed education content/data available to AI developers to drive creation of high-quality, evidence-based AI educational products (£3m DSIT funding, £1m DfE funding). Safety expectations and safety interface piloting: Setting expectations for the safety of AI products used in education; small scale testing of safety mechanisms in school | [5 empty] | False | False |  | Green | on track |  |  | 8 | BuRT197 | 108 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-05 14:13 |  | 4 |  |  | False | True | False | 2025-04-30
142 |  | To provide a digital service to collect organisation level data from the sector to support Funding and Oversight | To collect and process that data to inform funding, assurance and provide business intelligence to the organisation. | [5 empty] | False | False |  | Green |  |  |  | 17 | BuRT199 | 82 | 4 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 09:07 |  | 2 |  |  | False | False | False
143 |  | To provide data collections and modelling services within EDFO for funding and assurance purposes | To provide collections, data management, business intelligence and visualisation services across ESFA and DfE where we are required. | [5 empty] | False | False |  | Amber - Green | Currently we have a number of high profile and competing commissions which is stretching our resource and capacity, this has been exacerbated by a priority tech forms commission which is causing delays. | We expect the TEC forms commission to be completed in the next few weeks which will alleviate pressure and move us closer to returning to green. |  | 17 | BuRT200 | 82 | 4 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 09:07 |  | 3 |  |  | False | False | False
144 |  | Operational Data Science Service | Deliver the analysis and modeling requests from the ESFA Directorates, prioritised and agreed upon for the financial year, within the specified timeframe and quality standards. | [5 empty] | False | False |  | Amber - Green | Limited resources due to staff leave and significant risks around talent retention | Limitations with staff leave/retention |  | 17 | BuRT201 | 82 | 4 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 09:06 |  | 3 |  |  | False | False | False
145 |  | Get Information about Pupils (GIAP) | GIAP allows schools, Local Authorities and Further Education establishments to search for and download pupils’ end-of-Key Stage results data and their contextual indicators, including Pupil Premium information, from a DfE National Database The service allows users to access selected pupil level census and attainment data from the national pupil database, to create and monitor the progress of virtual cohorts of pupils and access pupil premium information It is used by schools, further education colleges and Local Authorities to access matched National Pupil Database (NPD) datasets for their pupils and download important Pupil Premium data. | [5 empty] | False | False |  | Green |  |  | 5 | 8 | BuRT202 | 39 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-19 14:10 |  | 3 |  | Schools (c20,000)​ Local authorities (c150) Academy trusts (c5,000) Further Education colleges (c300) | False | True | True
146 |  | Growth & Skills Offer (phase 2) | (Apprenticeship Service Deliverable) |  |  |  | 2026-04-30 |  | False | False | 1 | Green | We're feeling confident based on what we know now and how close to delivery we are. |  | 13 | 9 | BuRT206 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-24 11:57 |  | 1 |  |  | False | True | False | 2025-04-01
147 |  | HMRC validation | Automated checking of whether an apprentice is employed. Reduce fraud. (Apprenticeship Service Deliverable) | [5 empty] | False | False | 1 | Green | Back on track to deliver for end of March |  |  | 9 | BuRT207 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-24 14:13 |  | 1 |  |  | False | True | False | 2024-06-03
148 |  | School Accountability and Performance Discovery | By providing parents with comprehensive, accessible and transparent data/info on school performance, schools will be motivated to maintain or improve their standards to remain competitive and attract pupils to secure revenue. | [5 empty] | False | False |  | Green |  |  |  | 8 | BuRT209 | 39 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-06 14:41 |  | 4 |  | Discovery: Policy team; parents, school leaders | True | False | False | 2025-01-20
149 |  | Find a Course / Publish to the Course Directory | TBC (National Careers Service Deliverable) | [5 empty] | False | False |  | Green |  |  | 6 | 9 | BuRT210 | 182 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-06 08:30 |  | 1 |  |  | False | True | False | 2025-01-14
150 |  | Define Team (Paused) | [6 empty] | False | False |  | Green |  |  |  | 11 | BuRT211 |  |  |  |  | False |  |  |  |  | Cancelled | Paused for over 12 months. Will re-add if necessary. | False | 2025-11-20 13:56 | 2026-01-26 16:52 |  | 4 |  |  | False | False | False
151 |  | External Applications | [6 empty] | False | False |  | Green |  |  |  | 11 | BuRT212 | 192 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 14:47 |  | 4 |  |  | False | False | False
152 |  | CAT/CI | [6 empty] | False | False | 2 | Amber - Green | Mail check replacements – Awaiting Cyber decision on strategy. LSRP – Supporting the VCU work. Awaiting clearer requirements to aide sizing. | Strategy defined |  | 11 | BuRT214 | 192 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 14:34 |  | 2 |  |  | True | False | False
153 |  | LDS 2.0 - Matched Data Production | Re-platform the Central Learner Data Store (CLDS) from Informatica to Databricks by 26/27 so that datasets runs are faster, more reliable, and scalable. Re-platforming work in advanced stage and first datasets will begin switching over to Databricks in March 2026 for completion by end of the calendar year. | [5 empty] | False | False | 1 | Green | All key deliverables and milestones are on track for the reporting period |  |  | 3 | BuRT216 | 113 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 13:33 |  | 1 |  | The key users are the National Funding Formula, Pupil Premium and Accountability & Skills Policy and Statistics Teams. However, the data under NPDAAT is used across the department, sector and public citizen to inform research, analysis and decision making. | False | False | False | 2024-11-01
154 |  | Digital Certification | Switch apprenticeship certificates to digital by default. This project is essential for gaining efficiencies and programme value for money. (Apprenticeship Service Deliverable) |  |  |  | 2026-05-20 |  | False | False | 1 | Green | on track |  | 13 | 9 | BuRT218 |  | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-24 14:12 |  | 1 |  |  | False | True | False | 2024-08-01
155 |  | Ministerial Commission - Online Safety (Discovery) | 12-week research project to conduct one-to-one interviews with parents from a range of backgrounds, to understand their views around online safety and extreme misogyny in more depth, along with ideas for the role of DfE in supporting them. The project will also link with DfE policy colleagues and other Government Departments. | [5 empty] | False | False | 2 | Amber - Green | Require funding to be identified for 26/27 UCD support given rapidly changing policy in this area and new campaigns. Seeking joint DSIT / DFE funding. | As per RAG justification. | 2 | 4 | BuRt220 | 47 |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 13:19 |  | 1 |  |  | False | False | False
156 |  | Early Years Census: termly collection | Move to collect the EYC data termly rather than annually. | [5 empty] | False | False |  | Green |  |  |  | 18 | BuRT221 | 94 |  |  |  | False |  |  |  |  | Cancelled | Removed from COMPASS as EDAS confirmed this would not be reported on. | False | 2025-11-20 13:56 | 2026-02-02 14:32 |  | 3 |  |  | False | False | False
157 |  | Existing data collection | Ongoing collection of BAU data used by Families Group including School Census | [5 empty] | False | False |  | Green |  |  |  | 4 | BuRT222 | 47 |  |  |  | False |  |  |  |  | Cancelled | Duplicate entry of DFE-DDT-4 - Data Collections ran in the EDAS division. | False | 2025-11-20 13:56 | 2026-01-07 10:58 |  | 3 |  |  | False | False | False
158 |  | Breakfast Clubs | There are four data elements required to support the introduction of breakfast clubs: 1. Expression of Interest form for schools to sign-up to the pilot [now live] 2. Sharing of the blueprint toolkit with pilot schools 3. Medium term data required for funding and analysis of the pilot starting in April 2025. 4. Longer term data needed for live running. NOTE: WAS ORIGINALLY IN FAMILIES DELIVERABLES BUT WE HAVE BEEN ADVISED THAT THEY ARE NOT DELIVERING. BELIEVE IT IS EDS BUT AWAITING CONFIRMATION. | [5 empty] | False | False | 1 | Green | Currently reported under CRM Delivery |  |  | 14 | BuRT223 | 40 |  |  |  | False |  |  |  |  | Paused | Currently reported under CRM Delivery. However CRM is to be reviewed and split out in the near future. | False | 2025-11-20 13:56 | 2026-03-11 08:34 |  | 4 |  |  | False | False | False
159 |  | CS Technology: Digital Strategy | Addressing this gap is essential. A coherent Customer Service Digital Strategy will ensure digital services are designed around user needs, reduce avoidable contact, and free up capacity for staff to support those with the most complex or critical needs. By embedding consistent design principles, strengthening integration between policy, digital, and operational teams, and proactively using customer insight, the Department can modernise its service offer—driving up standards, improving efficiency, and delivering clearer, simpler, and more accessible experiences for all users. | [5 empty] | False | False | 2 | Amber - Green | Work has been paused whilst other business priorities (Machinery Of Government with DWP) and decisions (Future design of DDT and underpinning divisions) are concluded. | Work for transition of skills work is progressing as planned and awaiting agreement with DWP for next steps. Clear accountability internally has supported this work. Awaiting decision as to future shape of DDT (Through appointment of new Director) expect this to conclude in March 2026. Work will re-commence from here. |  | 15 | BuRT224 | 51 | 3 |  |  | False |  |  |  |  | Paused | Due to dependencies on other work / decisions, this is on hold. | False | 2025-11-20 13:56 | 2026-03-02 09:17 |  | 4 |  |  | False | False | False | 2025-06-02
160 |  | CS Centralisation and Transition | Create an Enterprise level Customer Service function for the Department - Centralise external customer facing and complaints teams into the CSEO division. - Effective contract management of the relevant service and service technology partners centrally in the CSEO division Reduce need for commercial procurements and multiple service partnerships. - Aim to source strategic partners across the service specialisms, (technology / service delivery etc) and bring other service work into these contracts. Improve Service resilience, efficiency, scalability & flexibility - Decrease the burden on the taxpayer and reinvest savings into core Ministerial priorities - Insight for future service improvement Improve simplicity and convenience of customer facing services - Standard published SLA's for consistency - Human 'hand to hold' in times of need (Vulnerability/Complexity/Emotion) | [5 empty] | False | False | 1 | Green | This was GREEN in Burts last entry, so not sure why its Amber Green here. Project on track |  |  | 15 | BuRT225 | 136 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-27 09:29 |  | 1 |  |  | False | False | False | 2025-01-02
161 |  | CS Technology: Portal | [6 empty] | False | False | 1 | Green |  |  |  | 15 | BuRT226 | 219 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-27 10:17 |  | 3 |  |  | False | False | False | 2025-04-01
162 |  | CS Service: Customer Engagement | [6 empty] | False | False |  | Amber - Green |  |  |  | 15 | BuRT227 |  |  |  |  | False |  |  |  |  | Cancelled | duplicate | True | 2025-11-20 13:56 | 2026-02-27 09:31 |  | 3 |  |  | False | False | False | 2025-04-01
163 |  | CS Service recovery / Complaints | Complaint improvement delivery program and complaint policy review. (Includes process and policy review customer concerns about whistleblowing and safeguarding.) Options / recommendations on opportunity to create central team, governed by one policy and using one CRM to enhance insight and reporting. | [5 empty] | False | False | 2 | Amber - Green | We still have the ambition to deliver within the original timeline (31/3/2026) however, this work may still extend to July 2026 given previous complications and delays. We will have a better understanding of the timeline once the approved option paper is delivered to IT. Keeping the rating as Amber due to this. | We still have the ambition to deliver within the original timeline (31/3/2026) however, this work may still extend to July 2026 given previous complications and delays. We will have a better understanding of the timeline once the approved option paper is delivered to IT. Keeping the rating as Amber due to this. |  | 15 | BuRT228 | 136 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-27 09:07 |  | 3 |  |  | False | False | False | 2024-11-01
164 |  | CS Data: Service Insight | Insight into why customers are behaving (making contact) in the way they do and identify policy, process and communication failures and reduce / automate future contact. Providing insight across the Department will stabilise demand, improve operational efficiency, and improve the end‑to‑end customer journey. It will also improve how customer insight feeds into decision‑making will enable the organisation to prevent avoidable contact, drive service quality, and strengthen customer satisfaction over time. | [5 empty] | False | False |  | Green | This was Green in Burts last input, dont know its been caried over as Amber green. project is on track. |  |  | 15 | BuRT229 | 188 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-27 10:04 |  | 3 |  |  | False | False | False | 2025-04-01
165 |  | AI Statement of Work Assessment: Part 2 | To investigate uncover user experiences and needs relating to SOW To identify business requirements for SOW within DfE To establish and align with external workflow for using external SOW tool | [5 empty] | False | False |  | Green |  |  |  | 10 | DDTi-17 | 41 |  |  |  | False |  |  |  |  | Completed | Confirmation from DDT Strategy and Transformation PMO that project is completed and does not require reporting on COMPASS. | False | 2025-11-20 13:56 | 2026-01-15 17:00 |  | 1 |  |  | False | False | False | 2025-06-16
166 |  | Data Insights project | Short Term: Deliver an interim tactical solution which enables sharing of mapped information and drawing of insights. Long Term: Deliver a solution which enables maps to be shared, insights to be created, and maps to be maintained as live. | [5 empty] | False | False |  | Amber - Green |  |  |  | 10 | DDTi-18 |  |  |  |  | False |  |  |  |  | Cancelled | Project confirmed as closed. | False | 2025-11-20 13:56 | 2025-12-15 13:55 |  |  |  |  | True | False | False | 2025-03-16
167 |  | Find User Insights (FUI) | Private Beta Mission Find User Insights will validate that the service reliably supports real insight discovery workflows, across a defined set of portfolios and users, while maintaining trust, security and governance. |  |  | 2025-10-28 | 2026-06-30 |  | False | False | 2 | Amber - Green | Some challenges are being experienced in accessing computer vision (Computer vision is a field of AI that teaches computers to “see” and understand visual information — a bit like giving them eyesight.) but exploring options with the AI centre of excellence and Microsoft. Some issues getting access to live sharepoint. Portfolios are slow at giving us data for our demo. | Work with the AI CofE and IT team on access to share point. Engage more with pilot portfolios for test information | 13 | 2 | DDTi-24 | 97 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 17:16 |  | 4 |  |  | True | False | False | 2025-06-16
168 |  | Keeping children safe online (responsible adults) digital information project | "Comissioned by Minister Morgan Project goal is: To understand issues around online safety and extreme misogyny among a range of parents and experts alongside mapping out the policy interventions by DfE and other government departments. This will enable a gap analysis and assessment of potential for further interventions by DfE or government to better support parents to understand and educate their children, alongside interventions through schools." | [5 empty] | False | False |  | Amber - Green |  |  |  | 2 | BuRT230 | 41 |  |  |  | False |  |  |  |  | Cancelled | This item is being removed from the Customer Experience and Design COMPASS deliverables - double entry | False | 2025-11-20 13:56 | 2026-01-27 13:48 |  | 4 |  |  | False | True | False | 2025-07-09
169 |  | Internal services for DDT staff | Includes: FIPs, Design Histories, Service Assessment Service, Megamanual, FUI, COMPASS etc | [5 empty] | False | False |  | Amber - Green |  |  |  | 2 | BuRT231 | 24 |  |  |  | False |  | Not applicable |  |  | Cancelled | Removed as a reporting line on CMPASS as the majority of services listed in the aim are reported as individual projects. | False | 2025-11-20 13:56 | 2026-02-09 16:10 |  | 2 |  |  | True | False | False | 2025-04-25
170 |  | DDT Skills and Expertise Objective (Obj 8) | [6 empty] | False | False |  | Green |  |  |  | 2 |  | 41 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 14:40 |  | 2 |  |  | False | False | False
171 |  | Helping parents keep children safe online | Create a landing page for the DSIT digital literacy campaign, which unifies information about online safety for parents into one single location. This will be aimed primarily at parents and carers, and secondarily at other responsible adults. |  |  | 2026-10-02 | 2026-04-24 |  | False | False |  | Green |  |  |  | 2 | BuRT233 | 24 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-04 10:49 |  | 4 |  |  | False | True | False | 2025-05-25
172 |  | AI Comms Hub | Ensures that all employees have access to the most current updates, policies, and details in the I space. This hub helps maintain consistency in messaging and ensures that everyone is on the same page. |  |  | 2025-05-25 | 2026-04-26 |  | False | False |  | Green |  |  |  | 2 | BuRT324 | 10 |  |  |  | False |  |  |  |  | Cancelled | This item is being removed from the Customer Experience and Design COMPASS deliverables whilst we focus on reporting against our most strategically important deliverables | False | 2025-11-20 13:56 | 2026-01-27 12:37 |  | 2 |  |  | True | False | False | 2025-05-25
173 |  | Gen AI Champions Network | The Champions network enhances communication, engagement, and the successful implementation of AI initiatives. It will help foster a positive mindset within the organisation. Champions have been setup to engage early and continuously with stakeholders, facilitating understanding and trust, and mitigating challenges. | [5 empty] | False | False |  | Green |  |  |  | 2 | BuRT235 | 41 |  |  |  | False |  |  |  |  | Cancelled | This item is being removed from the Customer Experience and Design COMPASS deliverables whilst we focus on reporting against our most strategically important deliverables | False | 2025-11-20 13:56 | 2026-01-27 12:38 |  |  |  |  | True | False | False | 2025-05-25
174 |  | DfE Ethics for Gen AI | The Ethics policy is being set up to enhance the work in the AI space, protect our organisational reputation, and ensure effectiveness. It will ensure consistency, understanding and governance within DfE and provide clear guidance to staff on when and how to implement ethical considerations. | [5 empty] | False | False |  | Green |  |  |  | 2 | BuRT326 | 41 |  |  |  | False |  |  |  |  | Cancelled | This item is being removed from the Customer Experience and Design COMPASS deliverables whilst we focus on reporting against our most strategically important deliverables | False | 2025-11-20 13:56 | 2026-01-27 12:38 |  | 1 |  |  | True | False | False | 2025-05-25
175 |  | User research manual guidance improvements | Redesign and rewrite the content in the Guidance and User Insights to make it more usable, findable and specific to DfE user research contexts, enabling better efficiency and lower risk user research across DfE. Delivered in two phases: 1. design content strategy and patterns, and redesign information architecture, and 2. rewrite all existing content into the new design. | [5 empty] | False | False |  | Green |  |  |  | 2 | BuRT327 | 30 |  |  |  | False |  |  |  |  | Cancelled | This item is being removed from the Customer Experience and Design COMPASS deliverables whilst we focus on reporting against our most strategically important deliverables | False | 2025-11-20 13:56 | 2026-01-27 12:39 |  | 2 |  |  | True | False | False | 2024-12-24
176 |  | Schools users research participant panel | Creation of a CRM of opted-in research participants from school leadership and school business professional user groups, plus processes for URs across DfE to access it, and comms strategy to drive sign-ups into it. Technical build of the platform (into DfE Microsoft CRM) is being delivered by the Solution Delivery Team in Infrastructure and Platforms. | [5 empty] | False | False |  | Red |  |  |  | 2 | BuRT328 |  |  |  |  | False |  |  |  |  | Cancelled | This item is being removed from the Customer Experience and Design COMPASS deliverables whilst we focus on reporting against our most strategically important deliverables | False | 2025-11-20 13:56 | 2026-01-27 12:39 |  | 1 |  |  | True | False | False | 2025-06-24
177 |  | User research incentives service and policy | Procurement of specialist supplier of user research incentives, to enable teams to access incentives in an efficient, cost effective way. Also an incentives policy to ensure proper, ethical and value for money use of incentives (policy being developed in collaboration with DfE Social Research) | [5 empty] | False | False |  | Amber - Green |  |  |  | 2 | BuRT329 | 30 |  |  |  | False |  |  |  |  | Cancelled | This item is being removed from the Customer Experience and Design COMPASS deliverables whilst we focus on reporting against our most strategically important deliverables | False | 2025-11-20 13:56 | 2026-01-27 12:39 |  | 1 |  |  | True | False | False | 2025-06-25
178 |  | User research participant supplier re-procurement | Procurement to replace incumbent supplier at end of contract, to ensure all teams across DfE have access to a high quality commercial recruitment capability (nb, this re-procurement will happen earlier than initially planned, due to burn rate in current contract) | [5 empty] | False | False |  | Amber - Green |  |  |  | 2 | BuRT330 | 30 |  |  |  | False |  |  |  |  | Cancelled | This item is being removed from the Customer Experience and Design COMPASS deliverables whilst we focus on reporting against our most strategically important deliverables | False | 2025-11-20 13:56 | 2026-01-27 12:40 |  | 2 |  |  | True | False | False | 2025-06-25
179 |  | Accessibility audit process improvement | [6 empty] | False | False |  | Amber - Green | Internal auditing team has been disbanded and now audits are coming to Jake which is not his role to do audits. | Either recruit an auditor role, or ensure all audits are procured externally. | 6 | 2 | BuRT331 | 7 | 2 |  |  | False |  |  |  |  | Cancelled | This item is being removed from the Customer Experience and Design COMPASS deliverables whilst we focus on reporting against our most strategically important deliverables | False | 2025-11-20 13:56 | 2026-01-27 12:36 |  | 1 |  |  | True | False | False
180 |  | Interaction design and ux training programme development for people looking to move into, or develop their technical design skills | [6 empty] | False | False |  | NOT STARTED |  |  |  | 2 | BuRT332 | 41 |  |  |  | False |  |  |  |  | Cancelled | Not something to be reported through compass | False | 2025-11-20 13:56 | 2026-01-13 10:29 |  | 1 |  |  | False | False | False
181 |  | Improving user journeys in early education and childcare | [6 empty] | False | False |  | Green |  |  | 2 | 4 | BuRT333 | 47 |  |  |  | False |  |  |  |  | Completed | Confirmation from families group that DDT involvement was limited sot self service functions such as information and security and advice was given. | False | 2025-11-20 13:56 | 2026-01-12 10:22 |  | 4 |  | Parents and carers accessing government funded childcare. | False | True | True |  |  |  |  | 2025-10-13
182 |  | School Cyber Resilience - Launch Operational Hub for Schools | Development of an education.gov.uk hosted information service, targeted at Head Teachers, Governors and Digital Leaders, will enable DFE to proactively support them in improving awareness of and the response to Cyber Security incidents and threats | [5 empty] | False | False | 2 | Amber - Green | Iterating service based on user feedback during private BETA, including condensing playbooks. DAC audit is underway, awaiting outcome. | Final iterations to the service based on feedback from private BETA and DAC audit outcome. | 4 | 16 | BuRT334 | 61 | 1 |  |  | False |  | Yes |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 15:00 |  | 4 |  |  | False | True | False
183 |  | Development of Secure Software Development Lifecycle Framework | Embed Security in DFEs delivery lifecycle | [5 empty] | False | False | 2 | Amber - Green | Resource identification and onboarding has impacted delivery as has the need to address GitHub Advanced Security as part of our recent GitHub Enterprise purchase | Have Resource in place and tooling |  | 16 | BuRT335 | 57 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-16 10:42 |  | 1 |  |  | True | False | False
184 |  | Harden DfE's core systems to meet a baseline security posture | DFEs foundation systems are significantly hardened against cyber-attacks and remain resilient to emerging threats | [5 empty] | False | False | 2 | Amber - Green | Some work still required to address ownership and measurement on a minority of controls in the foundation systems space | Create a governance mechanism to be able to address controls where ownership is not aligned with area of responsibility which could fix the issue - GRC - By end of March Address measurement issues with regard to Group memberships and / or naming of policies causing a red measurement when control is in place (Dev time constraint) - By end March |  | 16 | BuRT336 | 57 |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-02 08:58 |  | 1 |  |  | True | False | False | 2025-07-01
185 |  | Risk visibility and governance - single view of departmental cyber risks | A clearly understood cyber security risk management processes is in place to enable security risk decisions to be taken at the most appropriate level. Ensure central visibility of strategic risks to inform leadership. | [5 empty] | False | False | 2 | Amber - Green | Governance mechanism to escalate risk is struggling to operate with low levels of risk input from the assurance process. This is being addressed with an iteration to the assurance mechanism but will take time to show whether this addresses the issue and allows the governance escalations to work effectively | By mid March Iteration of the CIS Risk assessment mechanism to address issues with risk thresholds. Creation of a rollout plan for the CIS assessment for lower criticality services in line with the SCA By end of March Monitor input to the governance mechanism to evaluate success of CIS update |  | 16 | BuRT337 | 121 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-27 14:46 |  | 1 |  |  | True | False | False
186 |  | Effective Data Governance - Establish DFE'S Data Governance Function | To ensure that data is managed responsibly, securely, and effectively to support decision-making, service delivery, and policy development. | [5 empty] | False | False | 1 | Green | Deliverables are progressing against milestone |  |  | 16 | BuRT338 | 229 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-04 10:30 |  | 2 |  |  | True | False | False
187 |  | FE Cyber Resilience - Further Education Network Connectivity, Cyber Security Services | [6 empty] | False | False | 1 | Green | Contact and governance is now in place and this has transitioned to business as usual |  |  | 16 | BuRT339 | 57 |  |  |  | False |  |  |  |  | Completed | Contract is now in place and this project is now defined as Business As Usual | False | 2025-11-20 13:56 | 2026-02-04 15:04 |  | 1 |  |  | False | False | False
188 |  | Meeting our statutory assurance obligations - GOVASSURE Yr3 assessments enable targeted hardening of essential services | Apply GovAssure framework to agreed year 3 in scope systems (Business Central and TMS), so that DFE can accurately assess the level of cyber security and resilience of our critical systems and highlight priority areas for improvement | [5 empty] | False | False | 1 | Green |  |  |  | 16 | BuRT340 | 121 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-02-27 14:51 |  | 1 |  |  | True | False | False
189 |  | Best Start Digital Service | Exploring how we can maximise the impact of the BSIL website through improving parent/carer cross-government user journeys and developing new products to support parents. In the discovery phase, we will explore what support around parenting and the home learning environment parents/carers need for their children to get the outcomes they need and the opportunities to deliver the biggest impact. | [5 empty] | False | False |  | Green | on track |  | 1 | 4 | BuRT341 | 47 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 12:38 |  | 4 |  | Parents/carers of 0-5 year old children | False | True | True | 2025-10-06 |  |  |  | 2026-01-05
190 |  | Best Start in Life Campaign Site (Live) | Use user centred design (UCD to design a Government Communications Service (GCS) campaign landing page for the Best Start in Life comms campaign to parents of 0 - 5-year-olds ready for the campaign launch in September. The campaign needs to strongly signpost to both the NHS "Start in Life" campaign and the Childcare Choices as well any other priority government information needed by parents of 0 - 5-year-olds. | [5 empty] | False | False | 2 | Amber - Green | Campaign site is currently running successfully and as intended so far to support the new BSiL campaign between DHSC and DfE. However, the recent steer to pause the wider BSiL digital parenting hub project creates significant uncertainty around the future of the website, its broader digital strategic positioning, resourcing and ability to deliver on commitments outlined in the BSiL strategy. Communications are currently working to define next steps and how this is reported to Cabinet Office and No10 (both of whom have an interest in the project). | DfE and DHSC are in the process of agreeing next steps for mitigating the risks from the pause in the BSIL parenting hub and the role of the current website in meeting the broader digital parenting hub commitments outlined in the BSiL strategy. | 6 | 4 | BuRT342 | 47 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 17:19 |  | 3 |  |  | False | False | False
191 |  | Early Years – Childcare Access | Alpha Vision: We are here to improve how parents and carers understand what early education and childcare funding is available to them, and apply that understanding to their own circumstances. | [5 empty] | False | False |  | Green | See update text. |  | 2 | 4 | BuRT343 | 47 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 13:13 |  | 1 |  |  | False | False | False
192 |  | Early Years – Workforce Register (Discovery) | To introduce a professional register of EY practitioners to gain a better view of those who work in EY including the qualifications they hold. This is called out in the BSIL publication. The register will support DfE to make targeted interventions, improve workforce management and sufficiency, and reduce safeguarding risks. The belief is that it would also lead to the workforce feeling more valued through providing them professionalisation and recognition, with a hope that any future workforce register might improve relationships with the sector. | [5 empty] | False | False |  | Green | Discovery completed successfully. |  | 1 | 4 | BuRT346 | 47 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 13:14 |  | 1 |  |  | False | False | False
193 |  | Care Leavers | To bring together and simplify relevant information for young people leaving care and their intermediaries to make them aware of, and help them understand, the services and support available to them so they can navigate independent life to meet their diverse needs. Support for care leavers | [5 empty] | False | False | 2 | Amber - Green | Metrics: analysis of performance metrics presents some areas where data hasn’t enabled comparability of insights over time. Analysis underway to address this and enable the team to give a full view of performance. Translation: high-level testing of sample translations with first-language speakers highlighted some issues with accuracy, clarity and appropriateness of automatic translation. A banner is being implemented to ensure users know that translations are AI-driven on every page where the translator is used. | Same as RAG Justification. | 5 | 4 | BuRT347 | 47 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-04 09:45 |  | 4 |  |  | False | False | False
194 |  | Eligibility Checking Service (ECS) – Eligibility Expansion (Change Project) | By September 2025, working parents will be able to claim 30 hours of free childcare a week, over 38 weeks of the year, for children from nine months up to their child starting school. The ECS needs to be updated and changes made to ensure the entitlement expansion is built in. | [5 empty] | False | False |  | Green |  |  |  | 4 | BuRT348 | 47 |  |  |  | False |  |  |  |  | Completed | Completed September | True | 2025-11-20 13:56 | 2025-12-04 15:39 |  | 3 |  |  | False | False | False
195 |  | Eligibility Checking Engine (Private Beta) | Replacement of ECS legacy system in 2025. The Replacement project has reviewed the end-to-end process for eligibility checking and determined what the overall process and technology should look like in the post-ECS environment. Now in Beta we are building two products as an MVP: a hub – the Entitlements Checking Engine (ECE), and replacement spokes for both School Meals and Childcare. | [5 empty] | False | False |  | Amber - Green | No change | Agree non project team owner for accreditation process issues. Continue to work with 3rd parties to ensure all can adopt solution. | 13 | 14 | BuRT349 | 40 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-04 16:00 |  | 4 |  |  | False | False | False
196 |  | In house UKRLP and incorporate PIMS into a single Provider Management service | In housing UKRLP and incorporating PIMS into a single service. The solution will be a fit-for-purpose, DfE design that fulfils all of the operational and technical requirements through one service. | [5 empty] | False | False |  | Green | See update |  |  | 17 | BuRT355 | 82 | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 13:56 | 2026-03-03 09:06 |  | 4 |  |  | False | False | False | 2025-04-30
197 | DDTDEL-0006 | DDT Heads of Profession | The work of the Heads of Profession across DDT to develop and grow professions, capability, skills, and better service delivery. |  |  | 2025-01-01 |  |  | False | False |  | Green | Initial status |  | 16 | 6 | [5 empty] | False |  |  |  |  | Completed | Whilst work to develop an grow the profession continues, this is not required to be reported on at this point. | False | 2025-11-25 17:11 | 2026-01-14 14:42 | Manual | 2 | 5 |  | True | True | False
198 | DDTDEL-0006 | Service assessment service | A product to support the booking, management, assessment, and reporting of assurance against the Service Standard. |  |  | 2023-05-01 |  |  | False | False |  | Green | Service is operational with minimal issues and ongoing iterative development. |  |  | 13 |  | 78 | 3 |  |  | False |  |  |  |  | Completed | This work no longer requires reporting on as no longer in development. | False | 2025-11-25 21:58 | 2026-01-27 13:08 | Manual | 1 | 4 | Delivery teams in DfE Service assessment + team | True | True
199 | DDTDEL-0006 | Design Operations | Supporting design professions with advice, guidance, standards and accessibility support. |  |  | 2023-09-01 |  |  | False | False |  | Amber - Green | We are picking up accessibility audits for DDT teams which is not in the remit of our team due to the abandonment of the internal accessibility function in technology. This is putting additional pressure on the team to support a growing requirement for audits and 1:1 accessibility support. | Test | 16 | 2 |  | 1 | 2 |  |  | False |  |  |  |  | Cancelled | This item is being removed from the Customer Experience and Design COMPASS deliverables whilst we focus on reporting against our most strategically important deliverables | False | 2025-11-27 08:50 | 2026-01-27 12:38 | Manual | 2 | 5 | Anyone who is involved in the design of digital products and services in, or for, DfE. | True | False
200 | DDTDEL-0006 | DDT 2030 Programme OFFSEN | TBC |  |  | 2025-10-16 |  |  | False | False | 2 | Amber - Green | The programme is delivering sensitive change, some of which is waiting on senior permissions to enable us to mobilise the programme under the defined scope. | We are planning communications materials to mitigate key risks as the top priority. | 12 | 10 |  | 42 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-12-15 13:47 | 2026-02-22 20:58 | Manual | 1 |  |  | False | False
201 | DDTDEL-0006 | Find User Insights Project | As a project within the Service Delivery Revolution programme, the project aims are - TBC |  |  | 2025-12-01 |  |  | False | False |  | Amber - Green | [9 empty] | False |  |  |  |  | Cancelled | Entered in error - duplicate entry. | False | 2025-12-15 13:49 | 2025-12-15 13:50 | Manual |  |  |  | False | False
202 | DDTDEL-0006 | Skills - Real Time data | The Department for Education (DfE) faces ongoing challenges in effectively responding to key Post-16 Skills issues—such as forecasting, FE attendance, NEET rates, and more—due to a lack of timely, actionable data. To address this, the DfE will undertake a proof of concept (PoC) for real-time data collection from FE colleges in FY26/27. The PoC must be supported by a clear narrative and evidence base to gain buy in from the FE sector. The core challenge is to demonstrate how real-time data can enhance decision-making, policy responsiveness, and programme outcomes to help solve these challenges as well as identify gaps and overlap across the Post 16 landscape e.g. fixing the same problem.. |  |  | 2025-10-01 |  |  | False | False |  | Green |  |  | 12 | 10 |  | 42 |  |  |  | False |  |  |  |  | Completed | Project has been successfully delivered | False | 2025-12-15 15:11 | 2026-01-05 16:09 | Manual | 1 |  |  | True | False
203 | DDTDEL-0006 | Early Years and Wraparound Childcare Website | The contract ends in March 2026. Currently through the contract, Childcare Works hosts a website with resources for providers, schools and local authorities (https://childcareworks.org.uk/). Childcare Works also operates a dashboard using PowerBi and Microsoft Lists which enables us to monitor emerging themes and data from discussions with LAs. We are considering options for what we do with these products as part of exit planning and would appreciate assistance from DDAT in exploring the options available to us, including the routes to bringing this in-house. ​ Consist of two different elements – LAB and HUB – one for LAs and one for providers and schools. Contains over 245 resources for providers, schools and local authorities​ It would be good to know any research which informed this split, and whether usage reflects that this split is the best way of meeting the needs that the site is intended to meet. |  |  | 2025-12-04 | 2025-12-24 |  | False | False |  | Green |  |  |  | 2 |  | 41 |  |  |  | False |  |  |  |  | Cancelled | This is an active demand DDT-202572 | False | 2025-12-15 15:30 | 2026-01-27 14:37 | Manual | 1 |  |  | False | False
204 | DDTDEL-0006 | PAS - STA Capability Review Pilot | Part of the Productive and Agile State Programme (PAS). W1 - high level problem definition + analysis W2 - low level problem analysis, architecture review W3 - high level capability, service, tech, data, op model mapping W4 - op model options / recommendations |  |  | 2025-12-15 |  |  | False | False | 1 | Green | Progressing to plan |  | 12 | 10 |  | 42 | 3 |  |  | False |  | Not applicable |  |  | Active |  | False | 2025-12-15 15:37 | 2026-03-02 17:04 | Manual | 1 |  |  | True | False
205 | DDTDEL-0006 | Data Spine Programme | The long term vision is that DfE can access and leverage commercial learning system providers data for the analytical purposes of DfE and the sector. There is a short term aim to assess if a new collection process is feasible and is it worthwhile in terms of delivering data which DfE analysts and policy community find useful, as well as to the sector. |  |  | 2025-11-07 |  |  | False | False | 4 | Amber - Red | The programme status has decreased to Amber/Red. Confidence in delivering the strategic objectives remains high; however, the current risk position is expected to affect the Proof of Concept timeline, with post‑March slippage anticipated but no impact on key outcomes. | • DPIA and all data sharing agreements are approved for Wonde, MIS suppliers, and EdTech partners. • Commercial approach for engagement with MIS suppliers who have registered an interest in the pilot is agreed. • Terms and Conditions are formally agreed and signed with MIS suppliers and the aggregator (Wonde). • Increased uptake of EdTech providers registering their interest. And an understand of the quality of data any financial implications • Understanding whether there will be any financial implications associated with the ingestion of the data | 1 | 3 |  | 114 | 2 |  |  | True | [566] |  |  |  | Active |  | False | 2025-12-15 15:53 | 2026-02-27 13:39 | Manual | 4 | 3 |  | True | True
206 | DDTDEL-0006 | Data Spine WS1 - Data Architecture & Strategic Model project | A project within the Data Spine Programme, WS1 aims to Agree on target architecture and data model, designed around schools, with a strategic roadmap finalised by end of March |  |  | 2025-10-06 | 2026-03-31 |  | False | False | 2 | Amber - Green | Overall delivery confidence continues to be Amber/Green, scope on track, no significant risks or issues identified. We remain on track for the March deadline, with workstream re-alignment planning in progress. | Complete refinement of the detailed workstream plan and conclude re‑alignment planning to confirm all March‑critical deliverables | 1 | 3 |  | 114 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-12-16 11:24 | 2026-02-27 13:40 | Manual | 1 | 3 |  | False | False
207 | DDTDEL-0006 | Data Spine WS2 - Data Domain (MIS & Wonde) Discovery/PoC project | As part of the Data Spine Programme, this project will connect with MIS providers to obtain the data they hold so that DfE can use this to improve reporting and decision making |  |  | 2025-11-26 | 2026-03-31 |  | False | False | 4 | Amber - Red | Delivery timescales are at significant risk : Wonde - Although the T&L- DPIA has finally been signed off Wonde are looking at a variation of the current DfE agreement to include the DS PoC (this is a recent development). Wonde are also drafting T&Cs for the PoC, that will need to be agreed in conjunction with the revised DfE agreement, before any live data can be ingested. MIS- further engagement with Arbor is blocked pending conversations about the right commercial approach, discussion with Commercial colleagues is ongoing , to determine the best way forward | Work with colleagues from DfE Commercials to define an approach, that addresses PoC T&Cs between MIS Providers Arbor & Compass that can be applied to other MIS Providers who might express an interest in participating in the PoC. Wonde contract variation approved and signed off by the Commercial team. | 1 | 3 |  | 114 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-12-17 14:30 | 2026-02-27 13:41 | Manual | 4 | 4 |  | False | False
208 | DDTDEL-0006 | Data Spine WS3 - Data Domain (EdTech) Discovery/PoC project | As part of the Data Spine programme, this project will establish data pull through from the many EdTech providers that our education establishments work with enabling a richer data picture and more informed decision making. |  |  | 2025-12-03 | 2026-03-31 |  | False | False | 4 | Amber - Red | Insufficient engagement from EdTech providers following the invitation to participate resulting in a small sample of test data, alongside unknown data quality and unclear timelines for data sharing. In addition, the financial impact of supplier agreements remains uncertain, and there is a risk of delays linked to the late start and ongoing commercial challenges.​ The lack of DPIA approval has blocked the team from obtaining live data, and it remains unclear whether a DSA will be needed for every data controller. | To secure more data, the team will continue to explore engaging with MATs for direct data access, assess the responses from the engagement notice once Commercial publish it, and liaise with DfE project teams who work with EdTech providers in case they have data to share or contacts to explore. DPIA lack of approval has been escalated and a meeting scheduled for 25/02/2025 hopes to unblock this. Decision around the need for a DSA per data controller needs to be reached and communicated to project teams | 1 | 3 |  | 114 | 2 |  |  | False |  |  |  |  | Active |  | False | 2025-12-17 14:34 | 2026-02-27 13:42 | Manual | 4 | 3 |  | True | False
209 | DDTDEL-0006 | Project Hampton (OFFSEN) | OFFICIAL-SENSITIVE Following the Discovery phase run by the Innovation Team, we are progressing with Alpha phase with the aim of delivering an MVP solution. This project looks to create efficiencies in the current process for sharing data with CTP. |  |  | 2025-07-22 | 2026-03-31 |  | False | False | 1 | Green | Proceeding to plan |  | 2 | 10 |  | 42 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-12-18 12:22 | 2026-03-02 17:20 | Manual | 1 | 1 | Key Stakeholders: - CENSED Team - Information Rights Team - Data Sharing Team - CTP | True | False
210 | DDTDEL-0006 | PAS - Productive & Agile State Transformation Programme | To align with the government productivity objective using AI and digital products to expedite DfE work both efficiently and effectively |  |  | 2026-01-05 |  |  | False | True | 2 | Amber - Green | Programme has hit a key milestone in launching the board and given a positive trajectory for work going forward. Delivery plan is in place and we have confirmed objectives for the programme. Still some alignment needed. | Delivery plan in place to progress programme | 12 | 10 |  | 42 | 3 |  |  | False |  |  |  |  | Active |  | False | 2025-12-18 12:59 | 2026-03-02 17:09 | Manual | 1 | 4 | Internal colleagues | True | False
211 | DDTDEL-0006 | AI - AI Content Store In-Housing | The content store aims to explore how we can curate and provide the high-quality education data and content that developers need to create high-quality AI tools. The content store is not a tool; it is the enabling infrastructure for better AI tools used in education​. |  |  | 2025-05-31 |  |  | False | False |  | Green | Project is paused whilst procurement options are explored |  | 2 | 8 |  | 108 |  |  |  | False |  |  |  |  | Paused | Commercial re-procurement being explored | False | 2026-01-05 15:44 | 2026-03-05 13:40 | Manual |  |  | EdTech Companies - Companies developing AI tooling will be granted access to interact with the content store view via an API, filter content and download as required. EdTech Consumers - End users of AI EdTech products will benefit from AI tools which have been trained to produce safer, more aligned and more accurate outputs. | True | True
212 | DDTDEL-0006 | Investment Management Transformation | Objective 1 — Faster, clearer workflow • Implement a single, secure end-to-end investment workflow and document hub for Investment Committee (and Joint Assurance Committee, and Group Assurance Committee). • Targets (within 3 months of go-live): create a workflow which supports the IM team to reach an average ‘handling time’ of no more than an hour per case; 95% of cases progress via standardised stage-gates with live status visibility. Objective 2 — Better business cases, first time • Provide AI-assisted authoring (templates, prompts, live checks) to raise quality and consistency. • Targets (within 6 months): 90% template and Five Case Model compliance on first submission; substantially fewer amber/red assurance findings attributable to drafting defects. Objective 3 — Stronger, earlier scrutiny • Deploy AI “first-pass” assurance (human-in-the-loop) to flag issues early; orchestrate who reviews what, when. • Targets: AI checks achieve ≥75% agreement with human reviewers in pilot and ≥70% at scale; senior IC members receive concise packs ≥5 working days pre-meeting for 95% of cases; 100% of review comments, advice, and decisions captured in an auditable trail. Objective 4 — Institutional memory & auditability • Create a searchable knowledge base of past cases, decisions, benefits, and PIRs with proper records management. • Targets (within 12 months): median retrieval time <60 seconds; 95% of IC decisions have a complete linked evidence file; 90% of FOI/Internal Audit queries answered within SLA; insights reused in ≥30% of new cases. |  |  | 2025-12-02 |  |  | False | False |  | Green | Katharine Beer join us as a senior interaction designer. Katharine has been working closely with the developers and Oli on the user journey mapping to further determine pain points and opportunities to improve the process, as well as detailing the journey users of the service will go to when submitting their InvestCo business cases. |  | 12 | 14 |  | 40 |  |  |  | False |  |  |  |  | Active |  | False | 2026-01-08 11:56 | 2026-03-04 16:01 | Manual | 4 | 2 |  | True | False
213 | DDTDEL-0006 | Tenancy Project | This project aims to move all products onto one single Tenant |  |  | 2025-07-01 | 2026-07-31 |  | False | False |  | Green | Project delivery remains on track |  | 13 | 5 |  | 199 | 1 |  |  | False |  |  |  |  | Active |  | False | 2026-01-20 13:33 | 2026-03-10 08:43 | Manual | 1 | 4 | The users impacted by this work are mainly Service Delivery (Digital) colleagues | True | False
214 | DDTDEL-0006 | Communicating Funding Project | The Funding Service calculates, allocates, and instructs payment of funding to education providers. In line with the 2024–25 business plan, a key outcome is that “those we fund have certainty in their funding, enabling them to plan effectively.” However, current processes for communicating this funding information are fragmented, complex, time-consuming for users to navigate, and expensive for the Department to deliver. This work looks to improve how funding information is presented and accessed, helping users find what they need quickly, and in one place. Being mindful of the objective to make 'digital statements driven by data, removing as much effort as possible and funding streams transferred to this solution. |  |  | 2025-07-01 | 2026-06-30 |  | False | False |  | Amber - Green | Delivery remains on track, however there is a lot still left to build and deliver to achieve success. |  | 4 | 5 |  | 196 | 1 |  |  | False |  |  |  |  | Active |  | False | 2026-01-20 13:37 | 2026-03-10 08:38 | Manual | 1 | 3 | Internal and external users (operation colleagues and education providers). | True | True
215 | DDTDEL-0006 | Operational Data Layer Project | A shared operational data layer for managing funding data, A service capability and set of operational patterns​ (not a single platform or tool)​, used to support day-to-day operational service delivery​ and supports updates, validation, and auditability |  |  | 2025-07-01 | 2027-03-31 |  | False | False | 1 | Green | Delivery has been reset, MVP approach agreed and new scope in definition, all deliverables are tracking green currently and the team are working to schedule |  | 2 | 5 |  | 203 |  |  |  | False |  |  |  |  | Active |  | False | 2026-01-20 13:42 | 2026-03-10 10:04 | Manual | 1 | 3 | Internal users (operational colleagues), digital users | True | False
216 | DDTDEL-0006 | The Future of FCS | A discovery piece to look at the FCS product, it's capabilities and possibilities for the future design of the Service. |  |  | 2025-12-01 | 2026-02-27 |  | False | False |  | Green | Delivery on track |  | 12 | 5 |  | 208 | 2 |  |  | False |  |  |  |  | Completed | Discovery completed. Outcomes are being reviewed. | False | 2026-01-20 13:44 | 2026-03-10 08:44 | Manual | 1 | 4 | Internal users including Operational colleagues, Business Central and digital teams | True | False
217 | DDTDEL-0006 | Youth Guarantee NEET | TBC (National Careers Service Deliverable) |  |  | 2025-10-05 |  |  | False | False | 1 | Green | Delivery on track |  |  | 9 | BuRT358 | 182 | 1 |  |  | False |  |  |  |  | Active |  | False | 2026-01-26 07:43 | 2026-02-24 09:38 | Manual | 1 |  |  | False | False
218 | DDTDEL-0006 | School twinning programme user research | Triaged to CX&D from Devolved Union team Research aims and objectives: Identify the needs, motivations, and barriers faced by schools participating in twinning programmes and those not yet participating. Explore what would make a school twinning programme genuinely user-driven to inform the design to be scalable, inclusive and impactful. Assess the perceived value of twinning and mobility initiatives Understand the role of twinning in teacher professional development |  |  | 2025-09-15 | 2026-02-13 |  | False | False |  | Green |  |  | 1 | 2 |  | 24 | 3 |  |  | False |  |  |  |  | Completed | Short term work, providing insights to the Devolved union team are now complete | False | 2026-01-27 13:30 | 2026-02-25 13:01 | Manual | 1 |  |  | False | True
219 | DDTDEL-0006 | DDT Prioritisation to support demand | To design and implement a robust prioritisation tool that enables DDT to assess new and emerging demands consistently and transparently by testing their alignment to portfolio roadmaps and DDT’s strategic outcomes. This tool will strengthen the central triage process by providing a structured, evidence‑based framework for deciding which requests should progress, be reshaped, or be deprioritised—improving strategic focus, resource optimisation, and confidence in decision‑making |  |  | 2025-12-01 | 2026-06-01 |  | False | False | 1 | Green | Decision making tool was finalised at the beginning of February and taken to Triage on 04.02. This will be used to support scoping conversations pre-Triage and ensure more consistent conversations at Triage meetings. |  | 13 | 13 |  | 4 | 3 |  |  | False |  |  |  |  | Active |  | False | 2026-01-28 12:01 | 2026-03-02 07:41 | Manual | 1 | 2 | Central operations and the wider demand triage would use the outputs | True | False | False
220 | DDTDEL-0006 | PAS - FEO Capability Review Pilot | To review processes and digital services used in FEO to identify opportunities for automation and efficiencies to support the Productive and Agile State agenda and/or future organisational design. |  |  | 2026-01-01 |  |  | False | False | 2 | Amber - Green | Project is awaiting resource (action in progress). Once resource in place, status can be changed to green. | Awaiting resource | 12 | 10 |  | 42 | 3 |  |  | False |  |  |  |  | Active |  | False | 2026-01-30 10:52 | 2026-03-02 17:05 | Manual | 1 | 4 |  | True | False
221 | DDTDEL-0006 | PAS - Post 16 Qualifications Capability Review Pilot | Review the content development process for Post 16 qualifications and identify areas for improvement, productivity gains, and ways to maintain or enhance the quality of service.​ |  |  | 2026-01-01 |  |  | False | False | 1 | Green | Progressing as planned |  | 12 | 10 |  | 42 | 3 |  |  | False |  |  |  |  | Active |  | False | 2026-01-30 11:16 | 2026-03-02 17:07 | Manual | 1 | 4 |  | True | False
222 | DDTDEL-0006 | Strategy - Strategy Implementation Plan | To align DDT delivery with DDT strategic plan |  |  | 2025-04-01 |  |  | False | False |  | Amber - Green | This has been paused whilst we are focusing on strategy work with the pillars, but work should be commencing again in a couple of months | To be agreed when project resumes. |  | 10 |  | 42 |  |  |  | False |  |  |  |  | On Hold |  | False | 2026-01-30 15:42 | 2026-03-05 09:48 | Manual | 1 |  |  | True | False
223 | DDTDEL-0006 | Strategy - Data Strategy | To be added |  |  | 2025-04-01 |  |  | False | False | 4 | Amber - Red | "Data spine is reporting Amber on several workstreams due to issues engaging the sector. Strategically not a problem at this stage, just moves timelines to the right which could cause issues justifying the spend on the programme. More widely, long term work on data strategy hasn't progressed - partially due to other priorities, partially as without a CDO in place, there are some outstanding questions around the future of this work." | Data spine have been setting expectations around delivery dates so if one workstream does move to the right it won't come as a shock. |  | 10 |  | 42 | 3 |  |  | False |  |  |  |  | Paused | Agreed at DDT Delivery Board on 11/03 to pause this work until new Data Director starts in May. | False | 2026-01-30 15:50 | 2026-03-11 14:19 | Manual | 1 |  |  | True | False
224 | DDTDEL-0006 | Strategy - AI Strategic Function Proposal | To create a central strategic function that provides leadership, coherence and assurance for AI activity across DfE and its sector‑facing role. |  |  | 2025-04-01 |  |  | False | False | 1 | Green | on track |  |  | 10 |  | 42 | 3 |  |  | False |  |  |  |  | Active |  | False | 2026-01-30 15:53 | 2026-03-09 16:45 | Manual | 4 |  |  | True | False
225 | DDTDEL-0006 | Strategy - Mission Pillars Digital & Data Priority Outcomes | to be added |  |  | 2025-04-01 |  |  | False | False | 2 | Amber - Green | Next step on how to use the framework to support prioritisation is going to be tricky, hence Amber/Green rather than Green | agree strategic prioritisation milestones |  | 10 |  | 42 | 3 |  |  | False |  |  |  |  | Active |  | False | 2026-01-30 16:00 | 2026-03-11 14:17 | Manual | 1 |  |  | True | False
226 | DDTDEL-0006 | Strategy - Strategy & Transformation Workplace Refresh | To update the previous DDTi workplace to reflect the revised objectives of the division and to provide a clear route for those outside the division to access the strategic and transformative work we accomplish. Particular emphasis will be given to making routes for DDT PAS demand clear and straightforward. |  |  | 2025-12-01 | 2026-03-31 |  | False | False |  | Amber - Green | Just started | planning milestones and technical redesign in progress | 13 | 10 |  | 42 | 3 |  |  | False |  |  |  |  | Cancelled | Will now report under DDT Comms Strategy DFE-DDT-230 | False | 2026-01-30 16:08 | 2026-03-02 17:21 | Manual | 1 |  |  | True | False
227 | DDTDEL-0006 | Strategy - Data Spine | to be added |  |  | 2025-08-01 |  |  | False | False |  | Green | Programme is currently progressing well towards interim goals to deliver a POC within the FY. Startegy work next FY will focus on use cases, and cross governemnt link up. |  |  | 10 |  | 42 | 3 |  |  | False |  |  |  |  | Cancelled | Data Spine strategy will now report as part of the overall Data Strategy project DDT-DFE-223 | False | 2026-01-30 17:26 | 2026-03-02 17:18 | Manual | 4 |  |  | True | True
228 | DDTDEL-0006 | Strategy - AI Principles | The aim of the AI Principles work is to establish a clear, consistent and practical set of principles that guide the responsible, ethical and effective use of artificial intelligence across the Department for Education and its sector‑facing activities. |  |  | 2025-04-01 |  |  | False | False | 1 | Green | on track |  |  | 10 |  | 42 | 3 |  |  | False |  |  |  |  | Active |  | False | 2026-01-30 17:30 | 2026-03-09 16:41 | Manual | 1 |  |  | True | False
229 | DDTDEL-0006 | Strategy - AI GIAA Review | The aim of this review is to provide independent assurance on whether the Department for Education has appropriate and effective arrangements in place to support the responsible and effective use of artificial intelligence, in its role of setting direction, providing guidance and governance, and managing risks associated with AI across the education sector |  |  | 2026-01-01 |  |  | False | True | 1 | Green | on track |  |  | 10 |  | 42 | 2 |  |  | True | [697] |  |  |  | Active |  | False | 2026-01-30 17:32 | 2026-03-09 16:35 | Manual | 3 |  |  | True | False
230 | DDTDEL-0006 | Strategy - DDT Comms Strategy | There is currently a communications gap in raising the profile of the DDT Strategy across DfE. Work has started to develop a 12‑month communications plan that will set out the key activities required to build awareness and improve understanding across the department. |  | The comms workstream improves knowledge of DDaT across the Department and therefore facilitates effective delivery of the Opportunity Missions without directly contributing to a single pillar. | 2026-01-01 |  |  | False | False | 2 | Amber - Green | This workstream is in the early stages. There is currently a communications gap in raising the profile of the DDT Strategy across DfE. Work has started to develop a 12‑month communications plan that will set out the key activities required to build awareness and improve understanding across the department. RAG remains AmberGreen until the plan is agreed and implementation begins. | "• Finalise the draft 12‑month comms plan • Secure sign‑off from G6 and DD • Develop a clear delivery schedule for the comms activities • Begin rollout and monitor engagement • Adjust approach based on feedback and analytics" |  | 10 |  | 42 | 3 |  |  | False |  |  |  |  | Active |  | False | 2026-01-30 17:35 | 2026-03-11 12:10 | Manual | 4 | 4 |  | True | False | False
231 | DDTDEL-0006 | Test | Test |  |  | 2026-01-01 |  |  | False | False | 1 | Green | [9 empty] | False |  |  |  |  | Cancelled | testing | False | 2026-02-04 15:45 | 2026-02-04 15:45 | Manual |  |  |  | False | False
232 | DDTDEL-0006 | portfolio security assessment snapshot to identify good security practices and high levels of risk across ddt | Enable us to identify and address critical risks before they are exploited. Support consistent, high-quality security practices across all portfolios. Inform strategic decision-making on where to focus resources and effort. Strengthen our overall resilience and public trust in government digital services. |  |  | 2025-12-01 | 2026-03-31 |  | False | False | 2 | Amber - Green | Code review work has been more challenging than anticipated due to higher volumes of Git Hub findings than originally expected, which is taking time to triage. Expectation is similar challenge as the testing continues with ADO. Automation being used to accelerate capture and analysis. Targeted penetration testing lead time has taken longer than anticipated, with the external resource availability limitations. | Finalise code based reviews and undertake penetration tests to feed into overall reporting. |  | 16 |  | 61 | 2 |  |  | False |  |  |  |  | Active |  | False | 2026-02-04 21:19 | 2026-03-05 12:04 | Manual | 1 |  |  | True | False
233 | DDTDEL-0006 | Improving NEET Data and Insights | To complete three strands of work to improve the availability and flow of NEET data and create useful insights to support strategy. The three strands are: NEETs NCCIS - In-housing and modernisation; Risk of NEET Indicator AI developments and FE timeliness of data improvements. |  |  | 2026-03-02 |  |  | False | False | 2 | Amber - Green | Project has only just started and there are too many unknowns at this point to rate as Green - as we move through the coming months and complete our initial phases we will have greater clarity over delivery. | Project has only just started and there are too many unknowns at this point to rate as Green - as we move through the coming months and complete our initial phases we will have greater clarity over delivery. | 12 | 17 |  | 82 | 1 |  |  | False |  |  |  |  | Active |  | False | 2026-02-09 10:55 | 2026-03-04 15:26 | Manual |  |  |  | False | False
234 | DDTDEL-0006 | SEND Recording and Monitoring of need | To help SENCOs and other practitioners record needs, provision and progress of children and young people with potential and identified SEND more effectively, so that they can provide more consistent and timely support, and ultimately improve the educational outcomes of children and young people. We aim to do this by exploring whether a new digital service would help with this whilst reducing administrative burden, and if so, what the best delivery method would be. |  |  | 2026-01-05 | 2026-05-29 |  | False | False | 2 | Amber - Green | The service was mentioned in the White Paper, SEND consultation document and annexes, with conflicting descriptions. The work is extremely high profile and is subject to ministerial interest and pressures. There are commercial sensitivities to consider as there are already suppliers operating in the SEND recording of need space (MIS and EdTech suppliers). There are also other areas of work in the department that overlap or which have interdependencies, such as MIS procurement framework, data spine and other SEND policy areas, and these will require careful co-ordination and collaboration. | Now that the White Paper and SEND consultation document has been published, we are able to progress key conversations and research. We're reaching out to colleagues across the department where we have identified key links/dependences and have also been supporting the DDT mapping of the SEND reform activity. | 2 | 8 |  | 413 |  |  |  | False |  | Yes |  |  | Active |  | False | 2026-02-13 12:36 | 2026-02-26 17:03 | Manual | 4 | 3 | School professionals, with a focus on SENCOs But also exploring other users such as Specialists e.g. speech and language and parents | False | True |  | 2025-06-16 | 2025-06-16 | 2025-11-28 | 2025-11-28 | 2026-01-05 | 2026-01-05 | 2026-05-29
235 | DDTDEL-0006 | SEND recording and monitoring need - Early Years | To understand how the needs, provision and progress of children and young people with special educational needs and disabilities are currently recorded, monitored and shared across Early Years education settings. Identify areas where the process might be improved. |  |  | 2026-01-12 | 2026-05-22 |  | False | False | 1 | Green | Extends learning from original Disco (now in Alpha). Also builds on past research by Early Years teams. |  | 1 | 8 |  | 391 |  |  |  | False |  |  |  |  | Cancelled | This item was entered by mistake DFE-DDT-236 covers both Post16 and Early Years as part of the same discovery | True | 2026-02-13 16:15 | 2026-02-23 17:13 | Manual | 4 | 3 | Early years professionals ("maintained" settings) | False | True
236 | DDTDEL-0006 | SEND recording and monitoring need - Post-16 and Early Years | To understand how the needs, provision and progress of children and young people with special educational needs and disabilities are currently recorded, monitored and shared across Early Years and Post-16 mainstream education settings. Identify areas where the process might be improved. |  |  | 2026-01-12 | 2026-04-22 |  | False | False | 1 | Green | Extends learning from original Disco (now in Alpha). Also builds on past research. |  | 1 | 8 |  | 391 |  |  |  | False |  | Yes |  |  | Active |  | False | 2026-02-13 16:20 | 2026-03-02 13:19 | Manual | 4 | 3 | Post-16 professionals / SENCOs | False | True
237 | DDTDEL-0006 | SEND Identification and support | By the end of this discovery, we will:​ 1. understand how special educational needs and disabilities (SEND) are currently identified in mainstream primary and secondary settings​ 2. understand how support is selected to meet those needs​ 3. have identified where these processes might be improved ​ Awaiting approval with team and policy |  |  | 2026-02-17 | 2026-05-29 |  | False | False | 4 | Amber - Red | Due to the scope for the discovery being unclear and seemingly large, there is a risk that we may not be able to complete the discovery in the previously set out timescales of mid May. | Specific actions: - Desk research starting to understand the landscape further to narrow down the scope to focus on specific areas required - Agreement on scope required - Potential to review end timescale for the discovery dependent on scope Responsible parties: Sally Casey, Ayaz Akram, Emily Sadler, Ana Alencar Target dates: Agreement on scope and timescales by end of March | 1 | 8 |  | 175 |  |  |  | False |  |  |  |  | Active |  | False | 2026-02-13 16:25 | 2026-03-03 09:09 | Manual | 4 | 3 | Expected users are SENCOs and educational professional involved in identifying special educational needs and finding suitable support/interventions. | False | True |  | 2026-02-18 |  | 2026-05-15
238 | DDTDEL-0006 | LDS Programme | To deliver timely and accurate learner data to our customers and stakeholders. |  |  | 2026-01-05 |  |  | False | False | 1 | Green | All key deliverables and milestones are on track for the reporting period |  | 6 | 3 |  | 113 | 1 |  |  | False |  |  |  |  | Active |  | False | 2026-02-18 13:55 | 2026-03-02 11:43 | Manual |  |  |  | False | False
239 | DDTDEL-0006 | Get School Improvement Insights - GSII (School Profiles- Sector) | Team responsible for the delivery of a digital service to enable school and trust leaders to identify their strengths and weaknesses and find the right schools to work with to improve their school's performance |  |  | 2025-09-10 |  |  | False | False | 2 | Amber - Green |  |  | 4 | 8 |  | 445 |  |  |  | False |  |  |  |  | Active |  | False | 2026-02-19 11:52 | 2026-02-19 12:12 | Manual | 4 |  | Schools and Trusts leaders Local Authorities | False | True
240 | DDTDEL-0006 | School Profiles - Public | To empower parents with clear, balanced, and trustworthy insights into school performance and suitability - helping families make confident decisions about their child’s education while ensuring schools are held accountable through public performance measures. |  |  | 2025-09-10 |  |  | False | False | 2 | Amber - Green |  |  | 4 | 8 |  | 446 |  |  |  | False |  |  |  |  | Active |  | False | 2026-02-19 11:55 | 2026-02-19 16:09 | Manual | 4 |  |  | False | True
241 | DDTDEL-0006 | CS Technology: Provider CRM / DCASS | To upgrade our primary Customer Service CRM system to expand digital opportunities and improvements whilst replacing multiple other CRMs across DfE, and customer service systems eg Zendesk |  |  | 2026-03-02 | 2027-03-31 |  | True | False | 1 | Green | Work progressing as planned. |  | 12 | 15 |  | 219 |  |  |  | False |  |  |  |  | Active |  | False | 2026-02-19 15:28 | 2026-02-27 10:08 | Manual | 1 | 2 |  | True | True
242 | DDTDEL-0006 | CS Technology: Chatbot / AI . | Upgrade chat bot to a fully fledged generative AI chatbot which will have significantly more MI and Insight and analytics. |  |  | 2026-03-02 |  |  | False | True | 1 | Green |  |  | 12 | 15 |  | 219 |  |  |  | False |  |  |  |  | Active |  | False | 2026-02-19 16:37 | 2026-03-17 10:46 | Manual | 1 | 3 |  | False | True
243 | DDTDEL-0006 | CS Technology: AI Digital Concierge | Upgrade chat bot to a fully fledged generative AI chatbot which will have significantly more MI and Insight and analytics. |  |  | 2026-03-02 |  |  | False | True | 1 | Green |  |  |  | 15 |  | 219 |  |  |  | False |  |  |  |  | Active |  | False | 2026-02-19 16:40 | 2026-02-27 10:27 | Manual |  |  |  | False | True
244 | DDTDEL-0006 | CS Helpdesk / Community | Provide ability to track customer journeys across the rest of our tech stack. By moving everything to dynamics we should be able to better link articles from Help Portal (inc Davina 2.0) and monitor whether the customer is then able to self-serve. This will give us an accurate deflection rating. |  |  | 2026-03-02 |  |  | False | True | 1 | Green |  |  | 12 | 15 |  | 450 |  |  |  | False |  |  |  |  | Cancelled | duplicate of others created in error | True | 2026-02-19 16:52 | 2026-02-26 09:47 | Manual | 1 | 1 |  | False | True
245 | DDTDEL-0006 | CS Technology: Outbound Comms | Provide ability to track customer journeys across the rest of our tech stack. By moving everything to dynamics we should be able to better link articles from Help Portal (inc Davina 2.0) and monitor whether the customer is then able to self-serve. This will give us an accurate deflection rating. |  |  | 2026-03-02 |  |  | False | True | 1 | Green |  |  |  | 15 |  | 450 |  |  |  | False |  |  |  |  | Active |  | False | 2026-02-19 16:52 | 2026-02-27 09:20 | Manual | 1 | 4 | Internal teams use bulk mailouts to provide efficient external updates. One to many contact system. | False | True
246 | DDTDEL-0006 | CS Technology: AI Service Productivity | Improving efficiencies by automating or augmenting non value manual tasks. |  |  | 2025-09-01 |  |  | False | True | 1 | Green |  |  |  | 15 |  | 188 |  |  |  | False |  |  |  |  | Active |  | False | 2026-02-23 13:41 | 2026-03-02 14:58 | Manual | 1 | 3 |  | False | False
247 | DDTDEL-0006 | CS Technology: AI Service Productivity | Improving efficiencies by automating or augmenting non value manual tasks. |  |  | 2025-09-01 |  |  | False | True | 1 | Green | [5 empty] | 188 |  |  |  | False |  |  |  |  | Cancelled | duplicate | True | 2026-02-23 13:42 | 2026-03-02 10:36 | Manual |  |  |  | False | False
248 | DDTDEL-0006 | CS Technology: CXOne Telephony | In Discovery phase - Understand how full functionality of the platform can deliver greater efficiency and effectiveness in handling customer contact. |  |  | 2025-12-01 |  |  | False | False | 1 | Green |  |  |  | 15 |  | 137 |  |  |  | False |  |  |  |  | Active |  | False | 2026-02-23 13:55 | 2026-03-02 14:43 | Manual | 1 | 3 |  | False | False
249 | DDTDEL-0006 | CS Technology: CXOne Telephony | In Discovery phase - Understand how full functionality of the platform can deliver greater efficiency and effectiveness in handling customer contact. |  |  | 2025-12-01 |  |  | False | False | 1 | Green | [5 empty] | 137 |  |  |  | False |  |  |  |  | Cancelled | duplicate | True | 2026-02-23 13:55 | 2026-03-02 10:34 | Manual |  |  |  | False | False
250 | DDTDEL-0006 | CS Technology: Video creation and curation | Create videos and content that helps colleagues and customer do something |  |  | 2026-01-01 |  |  | False | False | 1 | Green |  |  | 12 | 15 |  | 137 |  |  |  | False |  |  |  |  | Active |  | False | 2026-02-23 14:06 | 2026-03-02 14:45 | Manual | 4 | 3 |  | False | False
251 | DDTDEL-0006 | CS Technology: Video creation and curation | Create videos and content that helps colleagues and customer do something |  |  | 2026-01-01 |  |  | False | False | 1 | Green |  |  | 12 |  |  | 137 |  |  |  | False |  |  |  |  | Cancelled | duplicate | True | 2026-02-23 14:06 | 2026-03-02 10:33 | Manual |  |  |  | False | False
252 | DDTDEL-0006 | CS Service: Outsource Partnership | Ongoing contract management and opportunities. |  |  | 2026-01-01 |  |  | False | False | 1 | Green |  |  |  | 15 |  | 137 |  |  |  | False |  |  |  |  | Active |  | False | 2026-02-23 14:13 | 2026-03-02 14:41 | Manual | 2 | 3 |  | False | False
253 | DDTDEL-0006 | CS Service: Outsource Partnership | Ongoing contract management and opportunities. |  |  | 2026-01-01 |  |  | False | False | 1 | Green | [5 empty] | 137 |  |  |  | False |  |  |  |  | Cancelled | duplicate | True | 2026-02-23 14:13 | 2026-03-02 10:35 | Manual |  |  |  | False | False
254 | DDTDEL-0006 | CS Technology: Communities and Social | In Discovery - |  |  | 2026-01-01 |  |  | False | False | 1 | Green |  |  |  | 15 |  | 450 |  |  |  | False |  |  |  |  | Active |  | False | 2026-02-23 14:27 | 2026-02-27 09:14 | Manual |  |  |  | False | False
255 | DDTDEL-0006 | CS Service: Knowledge | Blurb |  |  | 2026-01-01 |  |  | False | False | 1 | Green |  |  |  | 15 |  | 450 |  |  |  | False |  |  |  |  | Active |  | False | 2026-02-23 14:29 | 2026-02-27 09:11 | Manual |  |  |  | False | False
256 | DDTDEL-0006 | Find Education and Training | x |  |  | 2026-01-05 | 2026-09-30 |  | False | False | 2 | Amber - Green | Completing handover from CXandD team | Complete handover from CxD | 6 | 9 |  | 182 |  |  |  | True | [569] |  |  |  | Active |  | False | 2026-02-24 11:34 | 2026-03-06 08:29 | Manual | 1 | 3 |  | False | True
257 | DDTDEL-0006 | PAS - Improving Schools Guidance | tbc |  |  | 2026-01-01 |  |  | False | False | 1 | Green | Progressing to plan |  |  | 10 |  | 42 | 3 |  |  | False |  |  |  |  | Active |  | False | 2026-03-02 17:33 | 2026-03-16 13:18 | Manual |  |  | Schools sector | False | False
258 | DDTDEL-0006 | Fostering (end-to-end digital solution) – Scoping for Scale | The Scoping for Scale phase is a short, focused piece of work to test the feasibility of a national fostering digital platform. It provides a ‘minimum viable discovery’ to reduce uncertainties, refine our requirements, and give assurance that a scalable sector-ready solution exists before we go to tender. |  |  | 2026-02-02 |  |  | False | False | 2 | Amber - Green | The team are moving at pace and progressing well with scoping for scale activities to and while market engagement is progressing well, we are Amber due to ongoing work with Commercial to ensure 1-2-1 supplier sessions provide sufficient technical depth whilst ensuring parity of discussion. | Following initial pushback about detailed technical supplier questions, we have now received commercial sign-off on higher-level survey questions that will allow us to ask more granular questions during 1-2-1 conversations. Commercial have agreed to help shape the framing of the questions we intend to ask to fulfil our commitments to the minister to ensure parity of discussion. | 1 | 4 |  | 47 | 2 |  |  | False |  |  |  |  | Active |  | False | 2026-03-03 13:33 | 2026-03-16 13:29 | Manual | 4 | 4 | Foster carers | False | True
259 | DDTDEL-0006 | Early years provider experience of navigating childcare entitlements | The discovery is building on a deep dive carried out by policy colleagues and our existing insights to explore the experience of early years providers in administering entitlements to understand how their experience could be improved through system improvements. |  |  | 2026-02-02 |  |  | False | False | 1 | Green | Project has just started and is on track. |  | 1 | 4 |  | 47 | 2 |  |  | False |  |  |  |  | Active |  | False | 2026-03-03 13:42 | 2026-03-16 13:27 | Manual | 1 | 4 | Early Years Providers | False | True
260 | DDTDEL-0006 | Explore Careers | improve sectors search filters in explore careers tool |  |  | 2025-12-15 |  |  | False | False | 2 | Amber - Green | some delays in continuous improvement |  |  | 9 |  | 182 |  |  |  | True | [569] |  |  |  | Active |  | False | 2026-03-11 13:11 | 2026-03-11 13:11 | Manual | 1 | 2 | Users of the National Careers Service, seeking careers information, advice and guidance | False | True

## Users
Id | AzureObjectId | Email | Name | FirstName | LastName | UserPrincipalName | JobTitle | PhotoUpdatedAt | Role | CreatedAt | UpdatedAt
1 | 02f70415-5d66-4b88-af44-e21d0879808a | Andy.JONES@education.gov.uk | JONES, Andy | Andy | JONES | Andy.JONES@education.gov.uk |  | 2026-02-18 11:57 | SuperAdmin | 2025-10-17 21:30 | 2026-02-18 11:57
2 | 014b2155-8a03-43a9-b59e-38b83949ce37 | Kerry.LYONS@education.gov.uk | LYONS, Kerry | Kerry | LYONS | Kerry.LYONS@education.gov.uk |  | 2026-02-03 16:10 | Visitor | 2025-10-27 12:59 | 2026-02-03 16:10
3 | faaca2ab-4904-4f18-8228-4a011f6e4faf | Louise.CLARK@education.gov.uk | CLARK, Louise | Louise | CLARK | Louise.CLARK@EDUCATION.GOV.UK |  | 2026-02-11 17:51 | SuperAdmin | 2025-10-31 13:25 | 2026-02-11 17:51
4 | c010c450-1cef-4ad2-8ac2-96870b5b3dd8 | Jo.WRIGHT@education.gov.uk | WRIGHT, Jo | Jo | WRIGHT | Jo.WRIGHT@EDUCATION.GOV.UK |  | 2026-02-11 17:51 | SuperAdmin | 2025-10-31 13:25 | 2026-02-11 17:51
5 | ef58175c-38bb-4aa4-b081-c5f0e49b2e10 | Prina.PATEL@education.gov.uk | PATEL, Prina | Prina | PATEL | Prina.PATEL@EDUCATION.GOV.UK |  | 2026-03-02 07:42 | SuperAdmin | 2025-10-31 13:25 | 2026-03-02 07:42
6 | e57d3845-6188-48e7-963e-d46363500207 | Tracey.DALE@education.gov.uk | DALE, Tracey | Tracey | DALE | Tracey.DALE@EDUCATION.GOV.UK |  | 2026-03-05 09:22 | SuperAdmin | 2025-10-31 13:25 | 2026-03-05 09:22
7 | b020bca5-2ec2-4c23-bcb2-804630eb2f14 | Jake.LLOYD@education.gov.uk | LLOYD, Jake | Jake | LLOYD | Jake.LLOYD@EDUCATION.GOV.UK |  | 2025-11-27 09:31 | SuperAdmin | 2025-10-31 13:26 | 2025-11-27 09:31
8 | 652744d9-9a6b-401b-a970-64e3073e2ee0 | Rachel.SHOOTER@education.gov.uk | SHOOTER, Rachel | Rachel | SHOOTER | Rachel.SHOOTER@EDUCATION.GOV.UK |  | 2026-03-16 13:29 | Visitor | 2025-11-16 16:53 | 2026-03-16 13:29
9 | 8a7709e4-773f-4036-b61d-8fe67755dd0c | Gary.TUCKER@education.gov.uk | TUCKER, Gary | Gary | TUCKER | Gary.TUCKER@EDUCATION.GOV.UK |  | 2026-03-11 13:09 | Visitor | 2025-11-16 16:53 | 2026-03-11 13:09
10 | 7e454097-80fb-4470-959a-3eb9a2ea0e37 | Sam.BARTON@education.gov.uk | BARTON, Sam | Sam | BARTON | Sam.BARTON@education.gov.uk |  | 2026-03-03 17:11 | Visitor | 2025-11-16 16:54 | 2026-03-03 17:11
11 | 1c2acf9b-3ab5-4ad4-af8c-5b124a7232ab | Robert.RODNEY@education.gov.uk | RODNEY, Robert | Robert | RODNEY | Robert.RODNEY@EDUCATION.GOV.UK |  | 2026-02-19 11:56 | Visitor | 2025-11-16 16:54 | 2026-02-19 11:56
12 | 7bbd6f1f-2577-4c40-910b-bd8ac9be1475 | Bridie.TOOHER@education.gov.uk | TOOHER, Bridie | Bridie | TOOHER | Bridie.TOOHER@EDUCATION.GOV.UK |  | 2026-02-11 17:52 | Visitor | 2025-11-16 16:55 | 2026-02-11 17:52
13 | ab9ba1e5-379d-4b88-b3e9-64ed07019806 | Gemma.DONNELLY@education.gov.uk | DONNELLY, Gemma | Gemma | DONNELLY | Gemma.DONNELLY@EDUCATION.GOV.UK |  | 2026-02-11 17:54 | Visitor | 2025-11-16 16:55 | 2026-02-11 17:54
14 | 49068521-d1df-460a-a4b4-65c7ae53d6b5 | Cathy.DUTTON@EDUCATION.GOV.UK | DUTTON, Cathy | Cathy | DUTTON | Cathy.DUTTON@EDUCATION.GOV.UK |  | 2026-02-19 19:37 | Visitor | 2025-11-16 16:56 | 2026-02-19 19:37
15 | 8aff9f19-cbfa-40d9-a3e2-5097a7a86928 | Matthew.EVANS@EDUCATION.GOV.UK | EVANS, Matthew | Matthew | EVANS | Matthew.EVANS@EDUCATION.GOV.UK |  | 2026-02-02 08:35 | Visitor | 2025-11-16 16:56 | 2026-02-02 08:35
16 | fbcf800a-b91a-48bb-93d1-d4d27e67e97b | Shafiqa.DAWOOD@education.gov.uk | DAWOOD, Shafiqa | Shafiqa | DAWOOD | Shafiqa.DAWOOD@EDUCATION.GOV.UK |  | 2026-02-11 17:46 | Visitor | 2025-11-16 16:58 | 2026-02-11 17:46
17 | d9e108d8-0f36-4c86-877d-c9250cbd7685 | Daniel.KEELEY@education.gov.uk | KEELEY, Daniel | Daniel | KEELEY | Daniel.KEELEY@EDUCATION.GOV.UK |  | 2026-03-02 17:31 | Visitor | 2025-11-16 16:58 | 2026-03-02 17:31
18 | b66dc82f-abc5-44d9-9bf8-085af1bfa3f2 | Jane.CUNLIFFE@education.gov.uk | CUNLIFFE, Jane | Jane | CUNLIFFE | Jane.CUNLIFFE@EDUCATION.GOV.UK |  | 2025-11-16 16:59 | Visitor | 2025-11-16 16:59 | 2025-11-16 16:59
19 | 6c2cc316-78c1-45ad-a686-f1fffe2d1f21 | Susan.ACLAND-HOOD-PRIVATE@education.gov.uk | ACLAND-HOOD-PRIVATE, Susan | Susan | ACLAND-HOOD-PRIVATE | Susan.ACLAND-HOOD-PRIVATE@EDUCATION.GOV.UK |  | 2025-11-16 16:59 | Visitor | 2025-11-16 16:59 | 2025-11-16 16:59
20 | 87f440df-c322-496a-8075-0b25a0eac4f7 | Susan.ACLAND-HOOD@education.gov.uk | ACLAND-HOOD, Susan | Susan | ACLAND-HOOD | Susan.ACLAND-HOOD@EDUCATION.GOV.UK |  | 2025-11-16 16:59 | Visitor | 2025-11-16 16:59 | 2025-11-16 16:59
21 | a2330846-1fe5-49c2-8931-c72db41db0df | Juliet.KAMPASI@education.gov.uk | KAMPASI, Juliet | Juliet | KAMPASI | Juliet.KAMPASI@EDUCATION.GOV.UK |  | 2026-01-28 12:04 | Visitor | 2025-11-16 17:17 | 2026-01-28 12:04
22 | f042d586-c1d9-462a-bc0f-89ad9b1ecff7 | Louisa.CLARK@education.gov.uk | CLARK, Louisa | Louisa | CLARK | Louisa.CLARK@EDUCATION.GOV.UK |  | 2025-11-16 17:40 | Visitor | 2025-11-16 17:40 | 2025-11-16 17:40
23 | b3bd6455-ffa1-4ec9-92e6-e1bee91efcf7 | Paul.KELMAN@education.gov.uk | KELMAN, Paul | Paul | KELMAN | Paul.KELMAN@EDUCATION.GOV.UK |  | 2026-02-25 10:13 | Visitor | 2025-11-16 21:08 | 2026-02-25 10:13
24 | ae9d166e-7a5b-44a2-acfa-ee02c3c2ea24 | Kuldip.OSBORNE@education.gov.uk | OSBORNE, Kuldip | Kuldip | OSBORNE | Kuldip.OSBORNE@EDUCATION.GOV.UK |  | 2026-02-03 10:53 | Visitor | 2025-11-17 08:03 | 2026-02-03 10:53
25 | 5d29ea54-aacd-4209-b91f-afb191e97cd8 | Adam.DUMBELL@education.gov.uk | DUMBELL, Adam | Adam | DUMBELL | Adam.DUMBELL@EDUCATION.GOV.UK |  | 2026-02-21 15:50 | Visitor | 2025-11-17 08:03 | 2026-02-21 15:50
26 | 2d8cb4a5-98e4-4adb-847c-b3b9a4ea3639 | Sammi.CLARKE@EDUCATION.GOV.UK | CLARKE, Sammi | Sammi | CLARKE | Sammi.CLARKE@EDUCATION.GOV.UK |  | 2026-02-18 16:17 | Visitor | 2025-11-17 08:03 | 2026-02-18 16:17
27 | 9556c339-cdf8-4b2a-ad3f-00fed5f97ec1 | Sherene.MORRIS@education.gov.uk | MORRIS, Sherene | Sherene | MORRIS | Sherene.MORRIS@EDUCATION.GOV.UK |  |  | Visitor | 2025-11-17 08:03 | 2026-02-24 10:02
28 | a36751bc-6ab3-4924-92c9-cf611d457eea | Shalini.SHIWANI@education.gov.uk | SHIWANI, Shalini | Shalini | SHIWANI | Shalini.SHIWANI@EDUCATION.GOV.UK |  | 2025-11-17 08:04 | Visitor | 2025-11-17 08:04 | 2025-11-17 08:04
29 | 9dbac0db-d531-4943-bad2-9ab98b9a1e7a | Emily.SAUNDERSON@education.gov.uk | SAUNDERSON, Emily | Emily | SAUNDERSON | Emily.SAUNDERSON@EDUCATION.GOV.UK |  | 2026-02-24 10:03 | Visitor | 2025-11-17 08:04 | 2026-02-24 10:03
30 | 31f19578-3331-41f2-8f30-ed951033930d | Tom.ADAMS@education.gov.uk | ADAMS, Tom | Tom | ADAMS | Tom.ADAMS@EDUCATION.GOV.UK |  | 2026-02-17 19:40 | Visitor | 2025-11-17 08:05 | 2026-02-17 19:40
31 | c5c11481-a388-46de-a15a-19903787c2c5 | Debbie.BLANCHARD@education.gov.uk | BLANCHARD, Debbie | Debbie | BLANCHARD | Debbie.BLANCHARD@EDUCATION.GOV.UK |  | 2026-02-17 19:41 | Visitor | 2025-11-17 08:05 | 2026-02-17 19:41
32 | fa01b414-9e39-4740-ab85-0ef228e3f7e7 | Luke.SLOWEN@education.gov.uk | SLOWEN, Luke | Luke | SLOWEN | Luke.SLOWEN@EDUCATION.GOV.UK |  | 2026-02-17 19:41 | Visitor | 2025-11-17 08:06 | 2026-02-17 19:41
33 | b338f5b9-f876-4d12-8585-639a93f56ebc | Gila.SACKS@education.gov.uk | SACKS, Gila | Gila | SACKS | Gila.SACKS@EDUCATION.GOV.UK |  |  | Visitor | 2025-11-20 07:59 | 2025-11-20 07:59
34 | 9b512b48-b3bf-4903-8fb5-0b5fe97d919b | Juliet.CHUA@education.gov.uk | CHUA, Juliet | Juliet | CHUA | Juliet.CHUA@EDUCATION.GOV.UK |  | 2025-11-20 08:00 | Visitor | 2025-11-20 08:00 | 2025-11-20 08:00
35 | 9cd05bfa-af51-4744-aaef-aed9f9b8eed8 | Julia.Kinniburgh@education.gov.uk | KINNIBURGH, Julia | Julia | KINNIBURGH | Julia.KINNIBURGH@EDUCATION.GOV.UK |  | 2025-11-20 08:01 | Visitor | 2025-11-20 08:01 | 2025-11-20 08:01
36 | be9b390a-94b5-47c2-aa27-c503c315a3d0 | Sue.WHARAM@education.gov.uk | WHARAM, Sue | Sue | WHARAM | Sue.WHARAM@education.gov.uk |  | 2026-02-05 11:16 | Visitor | 2025-11-22 11:15 | 2026-02-05 11:16
37 | 6b4046d9-efb4-470d-aa43-be0f9470d142 | Amanda.WARNOCK@education.gov.uk | WARNOCK, Amanda | Amanda | WARNOCK | Amanda.WARNOCK@EDUCATION.GOV.UK |  | 2026-03-05 07:49 | Visitor | 2025-11-22 11:16 | 2026-03-05 07:49
38 | a03e6c14-0239-4344-97a7-ed0ab721bb57 | Rodney.LEE@education.gov.uk | LEE, Rodney | Rodney | LEE | Rodney.LEE@EDUCATION.GOV.UK |  | 2025-11-22 11:18 | Visitor | 2025-11-22 11:18 | 2025-11-22 11:18
39 | a9c0980f-267c-44b6-b3ac-645b0b807af9 | Tristan.MYNARD@education.gov.uk | MYNARD, Tristan | Tristan | MYNARD | Tristan.MYNARD@EDUCATION.GOV.UK |  | 2026-02-02 08:53 | Visitor | 2025-11-22 11:20 | 2026-02-02 08:53
40 | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | Louise.HAGUE@education.gov.uk | HAGUE, Louise | Louise | HAGUE | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-02-25 14:32 | Visitor | 2025-11-22 11:24 | 2026-02-25 14:32
41 | 32908ea6-3e40-4e69-9cff-3fa3c6aab41f | Samantha.RYE@education.gov.uk | RYE, Samantha | Samantha | RYE | Samantha.RYE@EDUCATION.GOV.UK |  | 2026-02-27 09:28 | Visitor | 2025-11-22 11:35 | 2026-02-27 09:28
42 | d4968443-887a-4dcb-a13e-475357639ee2 | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | Sharon | THOMPSON | Sharon.THOMPSON@education.gov.uk |  | 2026-03-05 09:44 | Visitor | 2025-11-22 11:38 | 2026-03-05 09:44
43 | 01633895-5ba6-4ac6-be83-0a3c88d4a8c5 | Sabina.RATTAN@education.gov.uk | RATTAN, Sabina | Sabina | RATTAN | Sabina.RATTAN@EDUCATION.GOV.UK |  | 2026-02-20 15:32 | Visitor | 2025-11-22 19:23 | 2026-02-20 15:32
44 | 136a0cf2-fe98-48cd-a033-cc29256b9088 | Chris.DAVIES@education.gov.uk | DAVIES, Chris | Chris | DAVIES | Chris.DAVIES@EDUCATION.GOV.UK |  | 2025-11-22 19:26 | Visitor | 2025-11-22 19:26 | 2025-11-22 19:26
45 | 7a96c238-6ce4-4c54-9531-bf093cf44724 | Kiera.HARPER@education.gov.uk | HARPER, Kiera | Kiera | HARPER | Kiera.HARPER@EDUCATION.GOV.UK |  | 2025-11-22 19:27 | Visitor | 2025-11-22 19:27 | 2025-11-22 19:27
46 | 8a26af68-a316-4db8-9844-061ce05072c3 | Riikka.LUNDAHL@education.gov.uk | LUNDAHL, Riikka | Riikka | LUNDAHL | Riikka.LUNDAHL@EDUCATION.GOV.UK |  | 2026-02-11 14:07 | Visitor | 2025-11-22 19:28 | 2026-02-11 14:07
47 | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | Sue.MOLYNEUX@education.gov.uk | MOLYNEUX, Sue | Sue | MOLYNEUX | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-03-03 13:40 | Visitor | 2025-11-22 19:33 | 2026-03-03 13:40
48 | 5c36a4ce-4e6c-4b53-b656-603a93b20a68 | Michael.DAVIES@education.gov.uk | DAVIES, Michael | Michael | DAVIES | Michael.DAVIES@EDUCATION.GOV.UK |  | 2026-02-11 11:26 | Visitor | 2025-11-22 19:42 | 2026-02-11 11:26
49 | 1f7a9eaa-7963-45c8-b051-3c5fa7adf722 | Corinne.RICHARDSON@education.gov.uk | RICHARDSON, Corinne | Corinne | RICHARDSON | Corinne.RICHARDSON@EDUCATION.GOV.UK |  | 2026-02-20 15:51 | Visitor | 2025-11-22 19:43 | 2026-02-20 15:51
50 | 14afb2df-bba4-4bc1-8e04-39f2c0afdade | Jennifer.O'CONNOR@education.gov.uk | O'CONNOR, Jennifer | Jennifer | O'CONNOR | Jennifer.OCONNOR@EDUCATION.GOV.UK |  | 2025-11-22 19:46 | Visitor | 2025-11-22 19:46 | 2025-11-22 19:46
51 | 3189190b-a1ce-45e5-8a4f-3610efa00201 | Stuart.BALNAVES@education.gov.uk | BALNAVES, Stuart | Stuart | BALNAVES | Stuart.BALNAVES@EDUCATION.GOV.UK |  | 2026-03-05 11:48 | Visitor | 2025-11-22 19:46 | 2026-03-05 11:48
52 | 976f27df-5486-4d6a-8afd-b46f95453e70 | Ushma.GILL@education.gov.uk | GILL, Ushma | Ushma | GILL | Ushma.GILL@EDUCATION.GOV.UK |  | 2026-01-20 14:49 | Visitor | 2025-11-22 19:47 | 2026-01-20 14:49
53 | 1eba1221-0e77-4768-afdb-fb7d6dd51000 | Iain.BRADLEY@education.gov.uk | BRADLEY, Iain | Iain | BRADLEY | Iain.BRADLEY@EDUCATION.GOV.UK |  | 2025-11-22 20:06 | Visitor | 2025-11-22 20:06 | 2025-11-22 20:06
54 | 968d2dff-5175-49ad-964d-a1c3cedf28ab | Mark.HUBBARD@education.gov.uk | HUBBARD, Mark | Mark | HUBBARD | Mark.HUBBARD@EDUCATION.GOV.UK |  | 2025-11-22 21:37 | Visitor | 2025-11-22 20:08 | 2025-11-22 21:37
55 | e242b05a-d958-4be1-9a71-b70ddee680a6 | Saheel.SANKRIWALA@education.gov.uk | SANKRIWALA, Saheel | Saheel | SANKRIWALA | Saheel.SANKRIWALA@EDUCATION.GOV.UK |  | 2025-11-22 20:10 | Visitor | 2025-11-22 20:10 | 2025-11-22 20:10
56 | 98f17053-38e6-40fb-9e51-346bab8df1c5 | Harjit.ATHWAL@education.gov.uk | ATHWAL, Harjit | Harjit | ATHWAL | Harjit.ATHWAL@EDUCATION.GOV.UK |  | 2026-02-11 12:53 | Visitor | 2025-11-22 20:12 | 2026-02-11 12:53
57 | 03f57944-a573-4abb-b765-28ecc11d00df | Angela.SCALE@education.gov.uk | SCALE, Angela | Angela | SCALE | Angela.SCALE@EDUCATION.GOV.UK |  | 2026-03-02 16:04 | Visitor | 2025-11-22 20:13 | 2026-03-02 16:04
58 | 0bb218f8-c939-46de-88c5-dbc67ceabb01 | Martin.SIVORN@education.gov.uk | SIVORN, Martin | Martin | SIVORN | Martin.SIVORN@EDUCATION.GOV.UK |  | 2026-03-11 14:16 | Visitor | 2025-11-22 20:14 | 2026-03-11 14:16
59 | 8b4c3f45-a49e-43b7-a5ff-978e2e264d65 | Susan.Dawson@education.gov.uk | DAWSON, Susan | Susan | Dawson | Susan.Dawson@EDUCATION.GOV.UK |  | 2025-11-22 20:33 | Visitor | 2025-11-22 20:33 | 2025-11-22 20:33
60 | 026d2c7b-9f3a-46be-9c15-a3292190ba40 | Clare.MATTHEWS@education.gov.uk | MATTHEWS, Clare | Clare | MATTHEWS | Clare.MATTHEWS@EDUCATION.GOV.UK |  | 2025-11-22 20:33 | Visitor | 2025-11-22 20:33 | 2025-11-22 20:33
61 | 53b409ec-10a3-4b05-ad6d-d7ff8d9946f1 | Alison.Dunne@education.gov.uk | DUNNE, Alison | Alison | Dunne | Alison.Dunne@EDUCATION.GOV.UK |  | 2026-03-02 15:00 | Visitor | 2025-11-22 20:35 | 2026-03-02 15:00
62 | 2610dc90-af64-4ebf-8a45-f32f71d74265 | Paul.DOWSE@education.gov.uk | DOWSE, Paul | Paul | DOWSE | Paul.DOWSE@EDUCATION.GOV.UK |  | 2026-02-11 11:42 | Visitor | 2025-11-22 20:36 | 2026-02-11 11:42
63 | 73fa79c3-5d67-4a7a-bf30-12fa7da710d2 | Angus.RAE@education.gov.uk | RAE, Angus | Angus | RAE | Angus.RAE@EDUCATION.GOV.UK |  | 2026-03-05 07:49 | Visitor | 2025-11-22 20:38 | 2026-03-05 07:49
64 | e29b855a-722b-4f00-9508-719afc4ee065 | Joanna.MACKIE@education.gov.uk | MACKIE, Joanna | Joanna | MACKIE | Joanna.MACKIE@EDUCATION.GOV.UK |  | 2025-11-22 20:39 | Visitor | 2025-11-22 20:39 | 2025-11-22 20:39
65 | 3cec6833-aba6-4751-929f-6269536070d3 | Tom.BERESFORD@education.gov.uk | BERESFORD, Tom | Tom | BERESFORD | Tom.BERESFORD@EDUCATION.GOV.UK |  | 2025-11-22 21:45 | Visitor | 2025-11-22 20:39 | 2025-11-22 21:45
66 | 8ac2dcc2-a4bf-4592-983c-654523358a53 | Sophie.Taylor@education.gov.uk | TAYLOR, Sophie | Sophie | Taylor | Sophie.Taylor@EDUCATION.GOV.UK |  | 2025-11-22 20:47 | Visitor | 2025-11-22 20:47 | 2025-11-22 20:47
67 | a73e04bc-2b37-4ac0-9e91-eabb44a44501 | Sam.RICHARDSON@education.gov.uk | RICHARDSON, Sam | Sam | RICHARDSON | Sam.RICHARDSON@EDUCATION.GOV.UK |  | 2026-02-11 13:58 | Visitor | 2025-11-22 20:48 | 2026-02-11 13:58
68 | 15f43d12-7298-474e-bdf8-04a219253416 | Katherine.MOULDS@education.gov.uk | MOULDS, Katherine | Katherine | MOULDS | Katherine.MOULDS@EDUCATION.GOV.UK |  | 2025-11-22 21:42 | Visitor | 2025-11-22 20:48 | 2025-11-22 21:42
69 | 748e40b9-e04f-47a4-bdad-ef83f5f07f5c | Lorna.HOWARTH@education.gov.uk | HOWARTH, Lorna | Lorna | HOWARTH | Lorna.HOWARTH@EDUCATION.GOV.UK |  | 2025-11-22 21:41 | Visitor | 2025-11-22 21:41 | 2025-11-22 21:41
70 | 172048d2-415f-4c13-b49c-d033f057cc90 | James.ODONOGHUE@education.gov.uk | O'DONOGHUE, James | James | ODONOGHUE | James.ODONOGHUE@EDUCATION.GOV.UK |  | 2025-11-22 21:46 | Visitor | 2025-11-22 21:45 | 2025-11-22 21:46
71 | 887f7521-f1f0-46a0-bd55-007f8ea4df06 | Kevin.CHEUNG@EDUCATION.GOV.UK | CHEUNG, Kevin | Kevin | CHEUNG | Kevin.CHEUNG@EDUCATION.GOV.UK |  | 2025-11-22 21:46 | Visitor | 2025-11-22 21:46 | 2025-11-22 21:46
72 | f7f31ca6-8502-4d63-93e2-bac025095fa3 | David.SCOTT@education.gov.uk | SCOTT, David | David | SCOTT | David.SCOTT@EDUCATION.GOV.UK |  | 2026-03-05 14:05 | Visitor | 2025-11-22 21:46 | 2026-03-05 14:05
73 | fe2968dd-f578-406e-bb26-e687a63ea88e | Nabil.ALI@education.gov.uk | ALI, Nabil | Nabil | ALI | Nabil.ALI@EDUCATION.GOV.UK |  | 2025-11-26 17:43 | Visitor | 2025-11-22 21:48 | 2025-11-26 17:43
74 | 28943d77-fbbc-4d5c-a185-2399ad107c44 | Lya.NOON@education.gov.uk | NOON, Lya | Lya | NOON | Lya.NOON@EDUCATION.GOV.UK |  | 2025-11-22 21:49 | Visitor | 2025-11-22 21:48 | 2025-11-22 21:49
75 | a38c230e-1559-4b86-9325-8d86bf6068c9 | Tayler.FINNEGAN@education.gov.uk | FINNEGAN, Tayler | Tayler | FINNEGAN | Tayler.FINNEGAN@EDUCATION.GOV.UK |  | 2025-11-25 10:51 | Visitor | 2025-11-25 10:51 | 2025-11-25 10:51
76 | 29796b3a-f940-4690-bd8b-b7f8401f6d3d | Lucy.SUTTON@education.gov.uk | SUTTON, Lucy | Lucy | SUTTON | Lucy.SUTTON@EDUCATION.GOV.UK |  | 2025-11-25 20:45 | Visitor | 2025-11-25 20:45 | 2025-11-25 20:45
77 | 26a64294-e228-47da-b07a-50626b44c9ff | Gary.PERKINS@education.gov.uk | PERKINS, Gary | Gary | PERKINS | Gary.PERKINS@EDUCATION.GOV.UK |  | 2026-02-21 17:06 | Visitor | 2025-11-25 21:57 | 2026-02-21 17:06
78 | 9467031a-2add-45fa-af18-1de3470a7aa1 | Michael.DUNN@education.gov.uk | DUNN, Michael | Michael | DUNN | Michael.DUNN@EDUCATION.GOV.UK |  | 2025-11-27 09:02 | Visitor | 2025-11-25 21:57 | 2025-11-27 09:02
79 | a30f9a1a-6bc2-45e4-a63a-70ecf8bf2e80 | David.STUMBRA@EDUCATION.GOV.UK | STUMBRA, David | David | STUMBRA | David.STUMBRA@EDUCATION.GOV.UK |  | 2025-11-26 13:13 | Visitor | 2025-11-26 13:13 | 2025-11-26 13:13
80 | 5035d8c0-26e1-4eeb-a018-12252451ca26 | Tracey.COX@education.gov.uk | COX, Tracey | Tracey | COX | Tracey.COX@EDUCATION.GOV.UK |  | 2025-11-26 17:43 | Visitor | 2025-11-26 17:43 | 2025-11-26 17:43
81 | f607106c-ecd4-4fbc-a002-6ce93dec2189 | Nabeel.RAUF@education.gov.uk | RAUF, Nabeel | Nabeel | RAUF | Nabeel.RAUF@EDUCATION.GOV.UK |  | 2026-02-09 10:51 | Visitor | 2025-11-26 17:43 | 2026-02-09 10:51
82 | da21d04a-4be8-4094-8021-ae677cce629b | Anne-Marie.BLUNT@education.gov.uk | BLUNT, Anne-Marie | Anne-Marie | BLUNT | Anne-Marie.BLUNT@EDUCATION.GOV.UK |  | 2026-03-04 15:26 | Visitor | 2025-11-27 09:28 | 2026-03-04 15:26
83 | 9e149494-1e97-40db-af68-22913287a3ef | Chris.KIRBY@education.gov.uk | KIRBY, Chris | Chris | KIRBY | Chris.KIRBY@EDUCATION.GOV.UK |  | 2026-03-02 16:19 | Visitor | 2025-11-27 09:34 | 2026-03-02 16:19
84 | 817ce0dd-c08b-435c-8a1e-8f592028eade | Ruth.MEDLOCK@education.gov.uk | MEDLOCK, Ruth | Ruth | MEDLOCK | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-02-10 14:05 | Visitor | 2025-11-27 10:16 | 2026-02-10 14:05
85 | 50bd0de7-7783-4433-9316-361333211ec2 | Richie.BURKE@education.gov.uk | BURKE, Richie | Richie | BURKE | Richie.BURKE@EDUCATION.GOV.UK |  | 2025-12-01 08:22 | Visitor | 2025-12-01 08:22 | 2025-12-01 08:22
86 | b8a74466-e1c8-4d33-9b6d-13714c49dcf3 | Jonathan.DALTON@education.gov.uk | DALTON, Jonathan | Jonathan | DALTON | Jonathan.DALTON@EDUCATION.GOV.UK |  | 2025-12-03 14:13 | Visitor | 2025-12-03 14:13 | 2025-12-03 14:13
87 | 4a61827f-2b7b-426c-bad8-e007d5ff25f7 | David.BURTON@education.gov.uk | BURTON, David | David | BURTON | David.BURTON@education.gov.uk |  | 2025-12-03 14:56 | Visitor | 2025-12-03 14:56 | 2025-12-03 14:56
88 | b7680d65-eb71-4c1c-a68e-b95fa6248026 | Iain.McINTOSH@education.gov.uk | McINTOSH, Iain | Iain | McINTOSH | Iain.McINTOSH@EDUCATION.GOV.UK |  | 2026-02-11 12:31 | Visitor | 2025-12-03 15:51 | 2026-02-11 12:31
89 | d56c029a-f148-459c-8707-b95e54d7e98b | Emily.SEVERN@education.gov.uk | SEVERN, Emily | Emily | SEVERN | Emily.SEVERN@education.gov.uk |  | 2025-12-08 11:13 | Visitor | 2025-12-08 11:13 | 2025-12-08 11:13
90 | e7c78c86-0af2-4d32-930f-9af6605ad1bf | JohnH.CARTER@education.gov.uk | CARTER, JohnH | JohnH | Carter | JohnH.Carter@EDUCATION.GOV.UK |  | 2025-12-12 12:34 | Visitor | 2025-12-12 12:34 | 2025-12-12 12:34
91 | a811c844-0f6d-4ded-a5c1-e852c2c23bdb | Jonathan.LOWTHER@education.gov.uk | LOWTHER, Jonathan | Jonathan | LOWTHER | Jonathan.LOWTHER@education.gov.uk |  | 2026-01-30 10:53 | Visitor | 2025-12-18 12:19 | 2026-01-30 10:53
92 | 60925ff4-7bd6-4e96-a18e-12260134f451 | Louise.SHUTT@education.gov.uk | SHUTT, Louise | Louise | SHUTT | Louise.SHUTT@EDUCATION.GOV.UK |  |  | Visitor | 2025-12-18 15:26 | 2026-01-26 13:46
93 | 8d6d4ba5-65bb-4179-a775-e6cf8879b4a3 | Rachel.MOUNTCASTLE@education.gov.uk | MOUNTCASTLE, Rachel | Rachel | MOUNTCASTLE | Rachel.MOUNTCASTLE@EDUCATION.GOV.UK |  |  | Visitor | 2025-12-18 15:30 | 2026-01-26 13:46
94 | eda6f8c4-5b2d-488f-8c3f-a7bcae98b027 | PMO.EDAS@education.gov.uk | EDAS, PMO | PMO | EDAS | PMO.EDAS@EDUCATION.GOV.UK |  |  | Visitor | 2025-12-18 15:31 | 2026-01-26 13:44
95 | 984332b9-688d-4db4-8275-75e1fcdfbdb4 | Annaliese.LAMB@EDUCATION.GOV.UK | LAMB, Annaliese | Annaliese | LAMB | Annaliese.LAMB@EDUCATION.GOV.UK |  | 2026-02-11 12:32 | Visitor | 2026-01-05 10:32 | 2026-02-11 12:32
96 | a1adc3bc-56fa-45fb-9392-b443cbef7adf | John.WATERFIELD@education.gov.uk | WATERFIELD, John | John | WATERFIELD | John.WATERFIELD@EDUCATION.GOV.UK |  | 2026-01-05 12:46 | Visitor | 2026-01-05 12:46 | 2026-01-05 12:46
97 | b6548968-6432-4b31-92a4-1a14b2521b44 | Julie.JENKINS@education.gov.uk | JENKINS, Julie | Julie | JENKINS | Julie.JENKINS@EDUCATION.GOV.UK |  | 2026-01-14 16:04 | Visitor | 2026-01-05 12:46 | 2026-01-14 16:04
98 | d748bf84-6000-44ec-adae-5e679275e358 | George.CHACHOU@education.gov.uk | CHACHOU, George | George | CHACHOU | George.CHACHOU@EDUCATION.GOV.UK |  | 2026-02-02 19:25 | Visitor | 2026-01-05 12:48 | 2026-02-02 19:25
99 | e2b36bcd-9451-48bf-bf41-a16ba35a48ee | Jenny.KLAASSEN@education.gov.uk | KLAASSEN, Jenny | Jenny | KLAASSEN | Jenny.KLAASSEN@EDUCATION.GOV.UK |  | 2026-01-05 12:52 | Visitor | 2026-01-05 12:52 | 2026-01-05 12:52
100 | 6f61ab6a-9483-415e-8d47-f393df5e82f7 | Mick.ROTHWELL@education.gov.uk | ROTHWELL, Mick | Mick | ROTHWELL | Mick.ROTHWELL@EDUCATION.GOV.UK |  | 2026-01-05 12:52 | Visitor | 2026-01-05 12:52 | 2026-01-05 12:52
101 | ff69ce3c-e2fb-4108-8b0b-21bf5227e54a | Mark.HAMMOND@education.gov.uk | HAMMOND, Mark | Mark | HAMMOND | Mark.HAMMOND@EDUCATION.GOV.UK |  | 2026-01-15 16:14 | Visitor | 2026-01-05 12:53 | 2026-01-15 16:14
102 | e84b15d4-473a-4365-bf92-8eb4323a1937 | Angela.BAINS@education.gov.uk | BAINS, Angela | Angela | BAINS | Angela.BAINS@EDUCATION.GOV.UK |  | 2026-01-07 15:38 | Visitor | 2026-01-05 12:54 | 2026-01-07 15:38
103 | 1ae27a3d-58b3-4dc4-8220-598f1cd61d31 | Katherine.BEHESHTI-SHIRAZI@education.gov.uk | BEHESHTI-SHIRAZI, Katherine | Katherine | BEHESHTI-SHIRAZI | Katherine.BEHESHTI-SHIRAZI@EDUCATION.GOV.UK |  | 2026-01-05 12:55 | Visitor | 2026-01-05 12:55 | 2026-01-05 12:55
104 | 7952eace-1d12-4468-b9dc-7259f26a6320 | Joanna.WIERZEWSKA@education.gov.uk | WIERZEWSKA, Joanna | Joanna | WIERZEWSKA | Joanna.WIERZEWSKA@EDUCATION.GOV.UK |  | 2026-01-07 15:56 | Visitor | 2026-01-05 12:56 | 2026-01-07 15:56
105 | ba8b05a7-c512-4b9c-b13c-c808550a5b4c | Lisa.KING@education.gov.uk | KING, Lisa | Lisa | KING | Lisa.KING@EDUCATION.GOV.UK |  | 2026-01-07 16:03 | Visitor | 2026-01-05 12:56 | 2026-01-07 16:03
106 | 9f0cbaa0-39b9-4049-9b8b-d6efc3648bb4 | Sam.SMITH@education.gov.uk | SMITH, Sam | Sam | SMITH | Sam.SMITH@EDUCATION.GOV.UK |  | 2026-01-05 14:06 | Visitor | 2026-01-05 14:06 | 2026-01-05 14:06
107 | 5962e07d-9e53-4dd7-a43d-efeb6928693d | Faye.SKELTON@education.gov.uk | SKELTON, Faye | Faye | SKELTON | Faye.SKELTON@EDUCATION.GOV.UK |  | 2026-01-05 15:11 | Visitor | 2026-01-05 15:11 | 2026-01-05 15:11
108 | 0f9f7777-e6eb-4bd9-99af-fa0b883c2a83 | Georgina.LANGLEY@education.gov.uk | LANGLEY, Georgina | Georgina | LANGLEY | Georgina.LANGLEY@education.gov.uk |  | 2026-03-05 13:39 | Visitor | 2026-01-05 15:12 | 2026-03-05 13:39
109 | c0c41c5c-3600-4b46-ae1c-4e9ad94a91ff | Fay.SKEVINGTON@education.gov.uk | SKEVINGTON, Fay | Fay | SKEVINGTON | Fay.SKEVINGTON@EDUCATION.GOV.UK |  | 2026-01-20 15:56 | Visitor | 2026-01-05 15:20 | 2026-01-20 15:56
110 | 74acf6d9-062c-4d7e-9c4f-e07ea9bb6fbe | Paul.MCWHIRTER@EDUCATION.GOV.UK | MCWHIRTER, Paul | Paul | MCWHIRTER | Paul.MCWHIRTER@EDUCATION.GOV.UK |  | 2026-02-02 17:07 | Visitor | 2026-01-05 16:02 | 2026-02-02 17:07
111 | fbbcb071-17e5-4966-a3fe-79d838966c47 | Hardeep.PADAM@education.gov.uk | PADAM, Hardeep | Hardeep | PADAM | Hardeep.PADAM@EDUCATION.GOV.UK |  | 2026-01-05 16:10 | Visitor | 2026-01-05 16:10 | 2026-01-05 16:10
112 | 38aedc59-1b7a-4a12-b427-7b083b3064f5 | Tejinder.MANIK@education.gov.uk | MANIK, Tejinder | Tejinder | MANIK | Tejinder.MANIK@EDUCATION.GOV.UK |  | 2026-02-03 20:22 | Visitor | 2026-01-05 16:11 | 2026-02-03 20:22
113 | 92796edb-6474-493d-a0a1-a61fe83fccca | Amanda.STRINE@education.gov.uk | STRINE, Amanda | Amanda | STRINE | Amanda.STRINE@EDUCATION.GOV.UK |  | 2026-03-11 15:09 | Visitor | 2026-01-06 13:18 | 2026-03-11 15:09
114 | 99e5d621-5a73-4f0a-bfe5-7f379240f3d8 | Lorraine.COLEY@education.gov.uk | COLEY, Lorraine | Lorraine | COLEY | Lorraine.COLEY@EDUCATION.GOV.UK |  | 2026-02-17 13:19 | Visitor | 2026-01-06 13:19 | 2026-02-17 13:19
115 | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | Daniel | KUMAR | Daniel.KUMAR@EDUCATION.GOV.UK |  | 2026-02-18 13:56 | Visitor | 2026-01-06 13:19 | 2026-02-18 13:56
116 | 357d5790-e952-439e-885a-a91e5328defd | Derek.HALSTEAD@education.gov.uk | HALSTEAD, Derek | Derek | HALSTEAD | Derek.HALSTEAD@EDUCATION.GOV.UK |  |  | Visitor | 2026-01-06 13:19 | 2026-01-06 13:19
117 | 5d57042a-7ef3-466b-a9c0-a8e194f7baef | Natalie.MASTERS@education.gov.uk | MASTERS, Natalie | Natalie | MASTERS | Natalie.MASTERS@EDUCATION.GOV.UK |  | 2026-02-11 13:02 | Visitor | 2026-01-06 14:23 | 2026-02-11 13:02
118 | d79caaa3-0072-4731-8913-ac5e04b2ef6c | Richard.O'HARA@education.gov.uk | O'HARA, Richard | Richard | O'HARA | Richard.O'HARA@EDUCATION.GOV.UK |  | 2026-01-15 16:42 | Visitor | 2026-01-06 16:25 | 2026-01-15 16:42
119 | 57411a93-c74b-4acd-b146-cc6d6b98ff9d | Nikki.MURFITT@education.gov.uk | MURFITT, Nikki | Nikki | MURFITT | Nikki.MURFITT@EDUCATION.GOV.UK |  | 2026-01-26 16:37 | Visitor | 2026-01-07 11:49 | 2026-01-26 16:37
120 | cd7aeb2e-404e-45fb-8e32-0b42409cbe80 | Salomy.MAROMANI@education.gov.uk | MAROMANI, Salomy | Salomy | MAROMANI | Salomy.MAROMANI@EDUCATION.GOV.UK |  | 2026-01-07 14:08 | Visitor | 2026-01-07 14:08 | 2026-01-07 14:08
121 | ebc20421-40e4-4b9c-96ce-982eacb84002 | Mark2.PHILLIPS@EDUCATION.GOV.UK | PHILLIPS, Mark2 | Mark | PHILLIPS | Mark2.PHILLIPS@EDUCATION.GOV.UK |  | 2026-02-04 11:25 | Visitor | 2026-01-07 15:35 | 2026-02-04 11:25
122 | 6c3db910-9333-4729-a9be-9143619cc5ed | Clare.STANLEY@education.gov.uk | STANLEY, Clare | Clare | STANLEY | Clare.STANLEY@EDUCATION.GOV.UK |  | 2026-01-07 15:35 | Visitor | 2026-01-07 15:35 | 2026-01-07 15:35
123 | 33366a5e-8bd6-4939-a80d-4adee8bb01f8 | Blanche.SPATARO@education.gov.uk | SPATARO, Blanche | Blanche | SPATARO | Blanche.SPATARO@EDUCATION.GOV.UK |  | 2026-01-07 16:59 | Visitor | 2026-01-07 16:59 | 2026-01-07 16:59
124 | 3f5bfa64-1878-450d-90bc-3c43de4432cf | Judith.RUSSELL@EDUCATION.GOV.UK | RUSSELL, Judith | Judith | RUSSELL | Judith.RUSSELL@EDUCATION.GOV.UK |  | 2026-01-07 17:00 | Visitor | 2026-01-07 17:00 | 2026-01-07 17:00
125 | 69b970ca-eb59-49a0-b11d-67d5e1c9a816 | Alison.GALE@education.gov.uk | GALE, Alison | Alison | GALE | Alison.GALE@EDUCATION.GOV.UK |  | 2026-01-08 13:32 | Visitor | 2026-01-08 12:56 | 2026-01-08 13:32
126 | 31dbfdb3-3ffc-4f6d-8dc1-ac63beb993f8 | Samantha1.RYE@education.gov.uk | RYE, Samantha1 | Samantha1 | RYE | Samantha1.RYE@EDUCATION.GOV.UK |  |  | Visitor | 2026-01-08 13:32 | 2026-01-08 13:32
127 | 9859f5fa-2aec-449a-a2df-61f623313558 | Erhan.TAHIR@education.gov.uk | TAHIR, Erhan | Erhan | TAHIR | Erhan.TAHIR@EDUCATION.GOV.UK |  | 2026-01-08 14:12 | Visitor | 2026-01-08 14:12 | 2026-01-08 14:12
128 | 63d465ce-ec01-4b50-88b1-e7748c8df354 | Andrew.CARPENTER@education.gov.uk | CARPENTER, Andrew | Andrew | CARPENTER | Andrew.CARPENTER@EDUCATION.GOV.UK |  | 2026-01-08 14:12 | Visitor | 2026-01-08 14:12 | 2026-01-08 14:12
129 | cb8f27f3-57ff-447e-a412-4301552e8965 | Becky.LOFTUS@education.gov.uk | LOFTUS, Becky | Becky | LOFTUS | Becky.LOFTUS@education.gov.uk |  | 2026-02-11 12:32 | Visitor | 2026-01-13 10:11 | 2026-02-11 12:32
130 | 41ce24c0-5082-4dcd-845e-3eef8e7cb14a | Deepak.SHARMA@education.gov.uk | SHARMA, Deepak | Deepak | SHARMA | Deepak.SHARMA@EDUCATION.GOV.UK |  | 2026-01-13 10:19 | Visitor | 2026-01-13 10:19 | 2026-01-13 10:19
131 | 82fac966-7213-4683-8267-c2f803ff8923 | Clare.AROLKER@education.gov.uk | AROLKER, Clare | Clare | AROLKER | Clare.AROLKER@EDUCATION.GOV.UK |  | 2026-02-11 10:00 | Visitor | 2026-01-13 10:21 | 2026-02-11 10:00
132 | 5db485b1-b742-4916-9ec6-6beb6c5bf0e1 | Laura.CHILCOTT@EDUCATION.GOV.UK | CHILCOTT, Laura | Laura | CHILCOTT | Laura.CHILCOTT@EDUCATION.GOV.UK |  | 2026-02-17 19:40 | Visitor | 2026-01-13 10:22 | 2026-02-17 19:40
133 | 2a50c286-8ba7-46d8-97fa-58b52d25a370 | Mark10.EDWARDS@education.gov.uk | EDWARDS, Mark10 | Mark10 | EDWARDS | Mark10.EDWARDS@EDUCATION.GOV.UK |  | 2026-01-13 10:47 | Visitor | 2026-01-13 10:47 | 2026-01-13 10:47
134 | b72dad8f-5fe7-4823-af91-f73e849cdff6 | Helen.TAVERNER@education.gov.uk | TAVERNER, Helen | Helen | TAVERNER | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | Visitor | 2026-01-13 14:48 | 2026-03-02 14:44
135 | 49a3cbad-3ed3-4ad4-b748-67484d4f0866 | Jennifer8.WRIGHT@education.gov.uk | WRIGHT, Jennifer8 | Jennifer8 | WRIGHT | Jennifer8.WRIGHT@EDUCATION.GOV.UK |  | 2026-02-11 11:37 | Visitor | 2026-01-13 15:47 | 2026-02-11 11:37
136 | ba5d42f1-db0f-4d03-9ae5-117fda981dd6 | Luke.CUNNINGHAM@education.gov.uk | CUNNINGHAM, Luke | Luke | CUNNINGHAM | Luke.CUNNINGHAM@EDUCATION.GOV.UK |  | 2026-02-19 16:59 | Visitor | 2026-01-13 15:48 | 2026-02-19 16:59
137 | 6b9ea2de-8864-4e6b-95a7-7c7feaebe329 | Andrew.SCOTT@education.gov.uk | SCOTT, Andrew | Andrew | SCOTT | Andrew.SCOTT@EDUCATION.GOV.UK |  | 2026-02-23 14:12 | Visitor | 2026-01-13 15:49 | 2026-02-23 14:12
138 | 51885484-02b8-4a54-8a44-e7adcead0757 | Joel.DICKENS@education.gov.uk | DICKENS, Joel | Joel | DICKENS | Joel.DICKENS@EDUCATION.GOV.UK |  | 2026-01-15 16:38 | Visitor | 2026-01-13 17:03 | 2026-01-15 16:38
139 | 8a93f19f-db4a-4144-b841-3ddf1c196368 | Michelle.BALNAVES@EDUCATION.GOV.UK | BALNAVES, Michelle | Michelle | BALNAVES | Michelle.BALNAVES@EDUCATION.GOV.UK |  |  | Visitor | 2026-01-15 14:44 | 2026-03-02 14:44
140 | c744c8ea-a3ed-44a3-9093-e2cdd4d2480c | Clare.CHARLESWORTH@education.gov.uk | CHARLESWORTH, Clare | Clare | CHARLESWORTH | Clare.CHARLESWORTH@EDUCATION.GOV.UK |  | 2026-02-26 08:54 | Visitor | 2026-01-15 14:45 | 2026-02-26 08:54
141 | 221bac2d-1147-4a10-9abb-8e7fd17f8700 | Patrick.HEALY@education.gov.uk | HEALY, Patrick | Patrick | HEALY | Patrick.HEALY@EDUCATION.GOV.UK |  | 2026-02-11 13:57 | Visitor | 2026-01-15 16:02 | 2026-02-11 13:57
142 | 6dd4f7c7-0eb9-423b-bfb7-7a3db0ba141c | Robin.APPLETON-POWER@education.gov.uk | APPLETON-POWER, Robin | Robin | APPLETON-POWER | Robin.APPLETON-POWER@EDUCATION.GOV.UK |  | 2026-01-15 16:23 | Visitor | 2026-01-15 16:23 | 2026-01-15 16:23
143 | 0f92dd9e-4620-49c7-85da-64ea796a98d0 | Margaret.HARDIE@education.gov.uk | HARDIE, Margaret | Margaret | HARDIE | Margaret.HARDIE@EDUCATION.GOV.UK |  |  | Visitor | 2026-01-15 16:25 | 2026-01-15 16:25
144 | b1be8acd-6d6f-46c7-9fe5-c98c615a5cad | Sankalp.JAIN@education.gov.uk | JAIN, Sankalp | Sankalp | JAIN | Sankalp.JAIN@EDUCATION.GOV.UK |  |  | Visitor | 2026-01-15 16:25 | 2026-01-15 16:25
145 | 36d40ccd-8459-4297-90b2-747bb6345158 | Venkata.PODILI@education.gov.uk | PODILI, Venkata | Venkata | PODILI | Venkata.PODILI@EDUCATION.GOV.UK |  |  | Visitor | 2026-01-15 16:26 | 2026-01-15 16:26
146 | 4af8f3c7-d01c-4089-b525-801aee92d7a6 | Chris7.JONES@education.gov.uk | JONES, Chris7 | Chris7 | JONES | Chris7.JONES@EDUCATION.GOV.UK |  | 2026-01-15 16:27 | Visitor | 2026-01-15 16:27 | 2026-01-15 16:27
147 | 3350f4f0-fe45-49f2-83a1-0af9384e7cf3 | Kumar.AMITESH@education.gov.uk | AMITESH, Kumar | Kumar | AMITESH | Kumar.AMITESH@EDUCATION.GOV.UK |  | 2026-01-15 16:28 | Visitor | 2026-01-15 16:28 | 2026-01-15 16:28
148 | feaf2875-3373-47d8-b540-dc507e055db5 | Prasanta.SAHU@education.gov.uk | SAHU, Prasanta | Prasanta | SAHU | Prasanta.SAHU@EDUCATION.GOV.UK |  | 2026-01-15 16:29 | Visitor | 2026-01-15 16:29 | 2026-01-15 16:29
149 | a9639a31-9400-431b-ac9d-0f1f6b823ba0 | Jayasree.CHOWDHURY@education.gov.uk | CHOWDHURY, Jayasree | Jayasree | CHOWDHURY | Jayasree.CHOWDHURY@EDUCATION.GOV.UK |  |  | Visitor | 2026-01-15 16:30 | 2026-01-15 16:30
150 | 5c35ffe8-9e04-4ee8-8ff9-0460c25f04fd | Matthew.KIRTON@education.gov.uk | KIRTON, Matthew | Matthew | KIRTON | Matthew.KIRTON@EDUCATION.GOV.UK |  | 2026-01-15 16:31 | Visitor | 2026-01-15 16:31 | 2026-01-15 16:31
151 | 68b0d47f-182a-4f9b-8df7-7e4166c9748e | Simon.WHALLEY@education.gov.uk | WHALLEY, Simon | Simon | WHALLEY | Simon.WHALLEY@education.gov.uk |  | 2026-01-15 16:32 | Visitor | 2026-01-15 16:32 | 2026-01-15 16:32
152 | dd9ebf5c-3b8a-4312-97b5-9414a2549688 | Victoria.SERIKI@education.gov.uk | SERIKI, Victoria | Victoria | SERIKI | Victoria.SERIKI@EDUCATION.GOV.UK |  |  | Visitor | 2026-01-15 16:35 | 2026-01-15 16:35
153 | 19bd7573-9239-482d-8494-5a57246eb7b4 | Wayne.RABIN@education.gov.uk | RABIN, Wayne | Wayne | RABIN | Wayne.RABIN@EDUCATION.GOV.UK |  | 2026-01-15 16:36 | Visitor | 2026-01-15 16:36 | 2026-01-15 16:36
154 | 684104c4-9e2b-4967-a0be-29e7f2a34eb2 | Paul.HODGSON@education.gov.uk | HODGSON, Paul | Paul | HODGSON | Paul.HODGSON@EDUCATION.GOV.UK |  |  | Visitor | 2026-01-15 16:43 | 2026-01-15 16:43
155 | 55fadac9-8bd2-441c-8ed7-78cc4d627b5a | Craig.ATTWELL@education.gov.uk | ATTWELL, Craig | Craig | ATTWELL | Craig.ATTWELL@EDUCATION.GOV.UK |  | 2026-01-15 16:43 | Visitor | 2026-01-15 16:43 | 2026-01-15 16:43
156 | 54a1ef13-b433-4f2a-ad2a-b2c70de69636 | Srinivas.LINGAMPALLY@education.gov.uk | LINGAMPALLY, Srinivas | Srinivas | LINGAMPALLY | Srinivas.LINGAMPALLY@EDUCATION.GOV.UK |  |  | Visitor | 2026-01-15 16:44 | 2026-01-15 16:44
157 | 6aef3312-8c40-49b2-a254-7add1f776024 | Myla.OLORODE@education.gov.uk | OLORODE, MOLORODE | Myla | OLORODE | Myla.OLORODE@EDUCATION.GOV.UK |  |  | Visitor | 2026-01-15 16:44 | 2026-01-15 16:44
158 | 38543f97-fc62-45fd-be23-83a9534fd35e | Emily.WARNER@education.gov.uk | WARNER, Emily | Emily | WARNER | Emily.WARNER@EDUCATION.GOV.UK |  | 2026-01-15 16:45 | Visitor | 2026-01-15 16:45 | 2026-01-15 16:45
159 | dea371fe-e43c-4ddb-9962-91c0db133bd5 | Reni.SONDE@education.gov.uk | SONDE, Reni | Reni | SONDE | Reni.SONDE@EDUCATION.GOV.UK |  |  | Visitor | 2026-01-15 16:46 | 2026-01-15 16:46
160 | eaa11efe-81b0-4ad5-b476-483400dc40b6 | Daniel.LUGOPINO@education.gov.uk | LUGOPINO, Daniel | Daniel | LUGOPINO | Daniel.LUGOPINO@EDUCATION.GOV.UK |  | 2026-01-15 16:46 | Visitor | 2026-01-15 16:46 | 2026-01-15 16:46
161 | d6058305-4b69-4d58-b866-5b183fc29615 | Niharika.GELLA@education.gov.uk | GELLA, Niharika | Niharika | GELLA | Niharika.GELLA@EDUCATION.GOV.UK |  | 2026-01-15 16:47 | Visitor | 2026-01-15 16:47 | 2026-01-15 16:47
162 | 54c769a3-fdc9-4684-ae44-2687af4f8b89 | Russell.CLARKE@education.gov.uk | CLARKE, Russell | Russell | CLARKE | Russell.CLARKE@education.gov.uk |  | 2026-01-15 16:48 | Visitor | 2026-01-15 16:48 | 2026-01-15 16:48
163 | cc9f5862-40ae-4933-a63b-21f44eba0154 | Oliver.TOWNSEND@EDUCATION.GOV.UK | TOWNSEND, Oliver | Oliver | TOWNSEND | Oliver.TOWNSEND@EDUCATION.GOV.UK |  | 2026-01-30 17:26 | Visitor | 2026-01-15 16:50 | 2026-01-30 17:26
164 | 067d5616-2c4b-4293-a08c-baa238a938bc | Rose.DUNSTALL@education.gov.uk | DUNSTALL, Rose | Rose | DUNSTALL | Rose.DUNSTALL@EDUCATION.GOV.UK |  | 2026-01-26 07:15 | Visitor | 2026-01-19 15:00 | 2026-01-26 07:15
165 | d6411a8f-8121-4a04-87fc-9233d2693595 | John.PHILLIPS@education.gov.uk | PHILLIPS, John | John | PHILLIPS | John.PHILLIPS@EDUCATION.GOV.UK |  | 2026-01-20 09:45 | Visitor | 2026-01-20 09:45 | 2026-01-20 09:45
166 | aac475f0-b93e-4beb-941f-df80219d434c | Mel.HUME@EDUCATION.GOV.UK | HUME, Mel | Mel | HUME | Mel.HUME@EDUCATION.GOV.UK |  | 2026-03-10 08:41 | Visitor | 2026-01-20 12:55 | 2026-03-10 08:41
167 | cf6ce0e5-5f56-4381-a4b2-a6bbcf911d99 | Priya.LALLY@education.gov.uk | LALLY, Priya | Priya | LALLY | Priya.LALLY@education.gov.uk |  | 2026-02-05 11:41 | Visitor | 2026-01-20 12:58 | 2026-02-05 11:41
168 | 847721d6-8a9e-4a7a-8170-76096b429a8d | Shelley.BRIGGS@education.gov.uk | BRIGGS, Shelley | Shelley | BRIGGS | Shelley.BRIGGS@EDUCATION.GOV.UK |  | 2026-01-27 15:32 | Visitor | 2026-01-20 13:44 | 2026-01-27 15:32
169 | a23b8aca-1c7f-4ee6-8670-a5a2b8e790cb | Paul.RAINE@education.gov.uk | RAINE, Paul | Paul | RAINE | Paul.RAINE@EDUCATION.GOV.UK |  | 2026-02-11 14:08 | Visitor | 2026-01-21 13:32 | 2026-02-11 14:08
170 | d46c78e6-9f62-4213-8cc2-489763a4b444 | Kathryn.KING@education.gov.uk | KING, Kathryn | Kathryn | KING | Kathryn.KING@EDUCATION.GOV.UK |  | 2026-01-21 13:36 | Visitor | 2026-01-21 13:36 | 2026-01-21 13:36
171 | cb741519-cd94-4769-bc35-460da8496726 | Adam.RAISTRICK@education.gov.uk | RAISTRICK, Adam | Adam | RAISTRICK | Adam.RAISTRICK@EDUCATION.GOV.UK |  | 2026-02-11 13:13 | Visitor | 2026-01-21 13:39 | 2026-02-11 13:13
172 | f7abf0c1-9598-41e9-957a-3d7638a74856 | Carmel.MURPHY@Education.gov.uk | MURPHY, Carmel | Carmel | MURPHY | Carmel.MURPHY@EDUCATION.GOV.UK |  | 2026-03-02 16:17 | Visitor | 2026-01-21 13:40 | 2026-03-02 16:17
173 | f8b57d05-fb6a-40a9-a371-106395565cfc | Phil.KENNAUGH@education.gov.uk | KENNAUGH, Phil | Phil | KENNAUGH | Phil.KENNAUGH@EDUCATION.GOV.UK |  | 2026-01-21 14:45 | Visitor | 2026-01-21 14:45 | 2026-01-21 14:45
174 | 378efe98-ac92-4ac7-94db-184238651a43 | Rose.CATT@education.gov.uk | CATT, Rose | Rose | CATT | Rose.CATT@education.gov.uk |  |  | Visitor | 2026-01-21 15:04 | 2026-02-11 14:04
175 | 54364aac-c110-4452-817e-340427ac1f35 | Sally.CASEY@education.gov.uk | CASEY, Sally | Sally | CASEY | Sally.CASEY@EDUCATION.GOV.UK |  | 2026-02-13 16:23 | Visitor | 2026-01-21 15:04 | 2026-02-13 16:23
176 | f87d8e2d-db33-4379-a6cf-9f2e5254633a | Fisal.YUSUF@education.gov.uk | YUSUF, Fisal | Fisal | YUSUF | Fisal.YUSUF@EDUCATION.GOV.UK |  | 2026-01-21 15:10 | Visitor | 2026-01-21 15:10 | 2026-01-21 15:10
177 | 84d1af90-3a84-458f-893f-aa533b0571c0 | Emily.SADLER@education.gov.uk | SADLER, Emily | Emily | SADLER | Emily.SADLER@EDUCATION.GOV.UK |  | 2026-02-24 14:35 | Visitor | 2026-01-21 16:46 | 2026-02-24 14:35
178 | d38ccf32-7b2f-42b5-a1fc-b7b2e7b9a71d | Caroline.KEMPNER@education.gov.uk | KEMPNER, Caroline | Caroline | KEMPNER | Caroline.KEMPNER@EDUCATION.GOV.UK |  | 2026-02-24 14:57 | Visitor | 2026-01-21 16:49 | 2026-02-24 14:57
179 | 131e528a-e44b-4d7a-af79-6819d247a709 | Alison.COLQUHOUN@education.gov.uk | COLQUHOUN, Alison | Alison | COLQUHOUN | Alison.COLQUHOUN@EDUCATION.GOV.UK |  | 2026-01-21 16:50 | Visitor | 2026-01-21 16:50 | 2026-01-21 16:50
180 | d55d48a3-565f-4109-a5f6-63a8fbe9cb59 | Kristi.BEAK@education.gov.uk | BEAK, Kristi | Kristi | BEAK | Kristi.BEAK@EDUCATION.GOV.UK |  | 2026-01-22 18:31 | Visitor | 2026-01-22 18:31 | 2026-01-22 18:31
181 | b14c838d-d1d7-4c4d-951c-0beeef1bef6f | Alan.BARKER@education.gov.uk | BARKER, Alan | Alan | BARKER | Alan.BARKER@EDUCATION.GOV.UK |  | 2026-01-26 07:15 | Visitor | 2026-01-26 07:12 | 2026-01-26 07:15
182 | dc63b4e6-7088-459b-86cb-ddfab57b804a | Piers.DUNSTALL@education.gov.uk | DUNSTALL, Piers | Piers | DUNSTALL | Piers.DUNSTALL@EDUCATION.GOV.UK |  | 2026-03-11 13:09 | Visitor | 2026-01-26 07:17 | 2026-03-11 13:09
183 | 292d5e6e-f900-4cf3-b60c-13b7a2fb7041 | Jackie.CAWTHORNE@education.gov.uk | CAWTHORNE, Jackie | Jackie | CAWTHORNE | Jackie.CAWTHORNE@EDUCATION.GOV.UK |  | 2026-03-11 13:09 | Visitor | 2026-01-26 07:17 | 2026-03-11 13:09
184 | f4514559-cacf-41f5-89e8-8940898dfafd | Stephen.MARR@education.gov.uk | MARR, Stephen | Stephen | MARR | Stephen.MARR@EDUCATION.GOV.UK |  | 2026-01-26 07:56 | Visitor | 2026-01-26 07:56 | 2026-01-26 07:56
185 | 4e4e5979-61d8-4340-ae4f-ece0645998c6 | Elinor.HARMAN@education.gov.uk | HARMAN, Elinor | Elinor | HARMAN | Elinor.HARMAN@EDUCATION.GOV.UK |  | 2026-01-26 07:58 | Visitor | 2026-01-26 07:58 | 2026-01-26 07:58
186 | 96a6d70c-0e74-4053-b177-466d3d375303 | Jemma.MORGAN@education.gov.uk | MORGAN, Jemma | Jemma | MORGAN | Jemma.MORGAN@EDUCATION.GOV.UK |  | 2026-01-26 08:00 | Visitor | 2026-01-26 08:00 | 2026-01-26 08:00
187 | efbc0c34-269d-4881-91f0-56f9ebd97805 | Emanuele.BORMIDA@education.gov.uk | BORMIDA, Emanuele | Emanuele | BORMIDA | Emanuele.BORMIDA@EDUCATION.GOV.UK |  | 2026-01-26 08:01 | Visitor | 2026-01-26 08:01 | 2026-01-26 08:01
188 | b2ab1965-d6fd-4a16-ba74-ccaa7c75de17 | Mohammad.ALI@education.gov.uk | ALI, Mohammad | Mohammad | ALI | Mohammad.ALI@EDUCATION.GOV.UK |  | 2026-02-25 09:56 | Visitor | 2026-01-26 10:41 | 2026-02-25 09:56
189 | 86965299-5b71-4045-94ac-da162f6d2ba7 | Mayura.ANNADATE@education.gov.uk | ANNADATE, Mayura | Mayura | ANNADATE | Mayura.ANNADATE@EDUCATION.GOV.UK |  | 2026-01-26 13:38 | Visitor | 2026-01-26 13:38 | 2026-01-26 13:38
190 | 4ca494c8-495b-401f-bbcb-29006fbcb650 | Laura.PAINE@education.gov.uk | PAINE, Laura | Laura | PAINE | Laura.PAINE@EDUCATION.GOV.UK |  | 2026-01-26 16:07 | Visitor | 2026-01-26 16:07 | 2026-01-26 16:07
191 | 3a9398b2-2ab8-43c0-9676-92f304dc238e | Monty.LIDHER@education.gov.uk | LIDHER, Monty | Monty | LIDHER | Monty.LIDHER@EDUCATION.GOV.UK |  | 2026-01-26 16:13 | Visitor | 2026-01-26 16:13 | 2026-01-26 16:13
192 | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | Rhiannon.BARNES@education.gov.uk | BARNES, Rhiannon | Rhiannon | BARNES | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-01-26 16:59 | Visitor | 2026-01-26 16:50 | 2026-01-26 16:59
193 | c0b9c3a8-be4a-4969-8e14-f0843adcef64 | Sofia.SOUSA@education.gov.uk | SOUSA, Sofia | Sofia | SOUSA | Sofia.SOUSA@EDUCATION.GOV.UK |  | 2026-01-26 16:59 | Visitor | 2026-01-26 16:51 | 2026-01-26 16:59
194 | 53e52a08-4639-44ad-b2b3-2811de877217 | Robert.SPARKS@education.gov.uk | SPARKS, Robert | Robert | SPARKS | Robert.SPARKS@EDUCATION.GOV.UK |  | 2026-02-16 08:12 | Visitor | 2026-01-27 07:20 | 2026-02-16 08:12
195 | 54e445e1-790f-41b3-a95f-763d7892bfc5 | Abhishek.SINGH@education.gov.uk | SINGH, Abhishek | Abhishek | SINGH | Abhishek.SINGH@EDUCATION.GOV.UK |  | 2026-01-27 07:26 | Visitor | 2026-01-27 07:20 | 2026-01-27 07:26
196 | 412c1ddb-bc30-4774-8a54-e41a561acbc4 | Ami.HILLS@education.gov.uk | HILLS, Ami | Ami | HILLS | Ami.HILLS@EDUCATION.GOV.UK |  |  | Visitor | 2026-01-27 07:23 | 2026-03-10 08:38
197 | 7409fffa-69ce-40b5-9d36-2c1307e937c9 | Chris.KEMM@education.gov.uk | KEMM, Chris | Chris | KEMM | Chris.KEMM@EDUCATION.GOV.UK |  | 2026-01-27 07:23 | Visitor | 2026-01-27 07:23 | 2026-01-27 07:23
198 | e83f7a5b-59b4-4ac0-bf4a-a87587a40d7d | Joe.YOUNG@education.gov.uk | YOUNG, Joe | Joe | YOUNG | Joe.YOUNG@EDUCATION.GOV.UK |  | 2026-03-10 08:39 | Visitor | 2026-01-27 07:25 | 2026-03-10 08:39
199 | 3e4e3bc6-7c4d-4ae2-9d98-64e0342db772 | Lavanya.GANESULA@education.gov.uk | GANESULA, Lavanya | Lavanya | GANESULA | Lavanya.GANESULA@EDUCATION.GOV.UK |  | 2026-03-10 08:43 | Visitor | 2026-01-27 07:25 | 2026-03-10 08:43
200 | 97b26ecf-01d6-4641-b70e-6558c3c45646 | Ravi.THIPPESWAMY@education.gov.uk | THIPPESWAMY, Ravi | Ravi | THIPPESWAMY | Ravi.THIPPESWAMY@EDUCATION.GOV.UK |  | 2026-02-16 08:14 | Visitor | 2026-01-27 07:26 | 2026-02-16 08:14
201 | c5f424e9-3cd0-4876-9bfa-04e66a2fc25d | Amina.ABDULLAHI@education.gov.uk | ABDULLAHI, Amina | Amina | ABDULLAHI | Amina.ABDULLAHI@EDUCATION.GOV.UK |  | 2026-01-27 07:27 | Visitor | 2026-01-27 07:27 | 2026-01-27 07:27
202 | 03c18cf1-f359-48ea-9f23-8ccf168a149e | Rupinder.LOTAY@education.gov.uk | LOTAY, Rupinder | Rupinder | LOTAY | Rupinder.LOTAY@EDUCATION.GOV.UK |  | 2026-01-27 07:27 | Visitor | 2026-01-27 07:27 | 2026-01-27 07:27
203 | f16be3e8-8523-460d-af95-7d6290fbf32b | Amna.HALIM@education.gov.uk | HALIM, Amna | Amna | HALIM | Amna.HALIM@EDUCATION.GOV.UK |  | 2026-03-10 08:42 | Visitor | 2026-01-27 07:28 | 2026-03-10 08:42
204 | 7c3fdd56-23f2-49e0-8211-5a26df2f21f6 | Beth6.DAVIES@education.gov.uk | DAVIES, Beth6 | Beth6 | DAVIES | Beth6.DAVIES@EDUCATION.GOV.UK |  |  | Visitor | 2026-01-27 07:28 | 2026-01-27 07:28
205 | 6c06e32e-2aa7-42e1-af2b-2e315ced3302 | Robin.DARBY@education.gov.uk | DARBY, Robin | Robin | DARBY | Robin.DARBY@EDUCATION.GOV.UK |  | 2026-01-27 07:29 | Visitor | 2026-01-27 07:29 | 2026-01-27 07:29
206 | aa3a3c5d-7417-4f66-abdb-448e707230e9 | Tor.LEAR@education.gov.uk | LEAR, Tor | Tor | LEAR | Tor.LEAR@EDUCATION.GOV.UK |  | 2026-01-27 07:29 | Visitor | 2026-01-27 07:29 | 2026-01-27 07:29
207 | 66387692-fa0c-443d-a196-2b4014d65f1e | Samantha.SHARPE@education.gov.uk | SHARPE, Samantha | Samantha | SHARPE | Samantha.SHARPE@EDUCATION.GOV.UK |  | 2026-01-27 07:30 | Visitor | 2026-01-27 07:30 | 2026-01-27 07:30
208 | 9cdea143-507b-4b33-831b-9e2ddeae99c5 | Jennifer.MYERSCOUGH@education.gov.uk | MYERSCOUGH, Jennifer | Jennifer | MYERSCOUGH | Jennifer.MYERSCOUGH@EDUCATION.GOV.UK |  | 2026-03-10 08:43 | Visitor | 2026-01-27 08:55 | 2026-03-10 08:43
209 | aba43bb4-6f1f-401b-959d-d4ecf70bf792 | Catherine.WILSON@education.gov.uk | WILSON, Catherine | Catherine | WILSON | Catherine.WILSON@EDUCATION.GOV.UK |  | 2026-01-29 14:50 | Visitor | 2026-01-27 14:38 | 2026-01-29 14:50
210 | 32d43dbb-a64e-4608-9184-ca451ebf0bf7 | Alexandra.KARATHODOROU@education.gov.uk | KARATHODOROU, Alexandra | Alexandra | KARATHODOROU | Alexandra.KARATHODOROU@EDUCATION.GOV.UK |  | 2026-01-30 16:01 | Visitor | 2026-01-27 15:31 | 2026-01-30 16:01
211 | 6c743d54-a44d-490e-a27a-ca7453095ae9 | Kathryn.GANDY@education.gov.uk | GANDY, Kathryn | Kathryn | GANDY | Kathryn.GANDY@EDUCATION.GOV.UK |  | 2026-01-27 15:32 | Visitor | 2026-01-27 15:32 | 2026-01-27 15:32
212 | 20008085-f3b9-4c5e-9dc5-4baa35c46f21 | Dawn.GAGA@education.gov.uk | GAGA, Dawn | Dawn | GAGA | Dawn.GAGA@EDUCATION.GOV.UK |  | 2026-01-29 13:19 | Visitor | 2026-01-27 16:33 | 2026-01-29 13:19
213 | fcc20cf6-8841-477b-b290-b8519c8e1b14 | Matthew.HUMPHRIES@education.gov.uk | HUMPHRIES, Matthew | Matthew | HUMPHRIES | Matthew.HUMPHRIES@EDUCATION.GOV.UK |  | 2026-01-28 14:41 | Visitor | 2026-01-28 14:41 | 2026-01-28 14:41
214 | cd0b87d7-6cb8-4640-99f2-6266c26f6a18 | Pravinkumar.KARTHIKEYAN@education.gov.uk | KARTHIKEYAN, Pravinkumar | Pravinkumar | KARTHIKEYAN | Pravinkumar.KARTHIKEYAN@EDUCATION.GOV.UK |  | 2026-01-28 16:53 | Visitor | 2026-01-28 16:53 | 2026-01-28 16:53
215 | 4b88e13d-cc89-4e5c-9bbd-e9dc93e2ddb4 | Mark.JAMES@education.gov.uk | JAMES, Mark | Mark | JAMES | Mark.JAMES@EDUCATION.GOV.UK |  | 2026-01-29 07:33 | Visitor | 2026-01-29 07:33 | 2026-01-29 07:33
216 | a06112f8-ffbf-459e-b694-dfc95fd858c7 | Sanjiv.Jhalla@education.gov.uk | JHALLA, Sanjiv | Sanjiv | Jhalla | Sanjiv.Jhalla@EDUCATION.GOV.UK |  | 2026-01-29 13:19 | Visitor | 2026-01-29 13:17 | 2026-01-29 13:19
217 | 6d7d0c37-1103-48a4-9f2f-034ecdb5e1b4 | Jordine.STEWART@education.gov.uk | STEWART, Jordine | Jordine | STEWART | Jordine.STEWART@EDUCATION.GOV.UK |  | 2026-01-29 14:23 | Visitor | 2026-01-29 14:23 | 2026-01-29 14:23
218 | 6ecf483d-4d9d-41e9-9552-051f143da73e | Rachel.MORLEY@education.gov.uk | MORLEY, Rachel | Rachel | MORLEY | Rachel.MORLEY@EDUCATION.GOV.UK |  | 2026-01-29 16:33 | Visitor | 2026-01-29 16:33 | 2026-01-29 16:33
219 | 8619af26-5d96-435b-9b94-378c99d86c5e | Paul.PHILIPSON@education.gov.uk | PHILIPSON, Paul | Paul | PHILIPSON | Paul.PHILIPSON@EDUCATION.GOV.UK |  | 2026-02-20 09:00 | Visitor | 2026-01-30 11:00 | 2026-02-20 09:00
220 | 3b03a4f0-9a23-4530-a4c9-33699fa16131 | Arti.BHANDERI@education.gov.uk | BHANDERI, Arti | Arti | BHANDERI | Arti.BHANDERI@EDUCATION.GOV.UK |  | 2026-01-30 17:32 | Visitor | 2026-01-30 15:54 | 2026-01-30 17:32
221 | ea7ca947-9b25-4e39-8bec-2b333b4afeec | Stuart.Dominguez@education.gov.uk | DOMINGUEZ, Stuart | Stuart | Dominguez | Stuart.Dominguez@EDUCATION.GOV.UK |  | 2026-01-30 16:09 | Visitor | 2026-01-30 16:09 | 2026-01-30 16:09
222 | 49484499-e464-40e5-ac0d-05e998a8b24a | Kiranjit.GILL@education.gov.uk | GILL, Kiranjit | Kiranjit | GILL | Kiranjit.GILL@EDUCATION.GOV.UK |  | 2026-01-30 17:36 | Visitor | 2026-01-30 17:36 | 2026-01-30 17:36
223 | b73bce0f-1847-4ce0-ae85-ae93a840e2f3 | C-ADM-HEVANS@education.gov.uk | C-ADM-HEVANS | HUW | EVANS | C-ADM-HEVANS@education.gov.uk |  |  | Visitor | 2026-02-02 08:35 | 2026-02-02 08:35
224 | 13aa3d58-58c3-4599-bdd0-1ca18f966597 | Giverny.BROMLEY@education.gov.uk | BROMLEY, Giverny | Giverny | BROMLEY | Giverny.BROMLEY@EDUCATION.GOV.UK |  | 2026-02-09 11:38 | Visitor | 2026-02-02 08:37 | 2026-02-09 11:38
225 | 9fb72e3a-afdd-4b75-a489-21648c2d9110 | Claire.FOLAN@education.gov.uk | FOLAN, Claire | Claire | FOLAN | Claire.FOLAN@EDUCATION.GOV.UK |  | 2026-02-02 11:37 | Visitor | 2026-02-02 11:37 | 2026-02-02 11:37
226 | 2d538f8a-a226-4e7d-b4fc-63320c8c4736 | Claudia.HERNANDEZIRIGOYEN@EDUCATION.GOV.UK | HERNANDEZIRIGOYEN, Claudia | Claudia | HERNANDEZ IRIGOYEN | Claudia.HERNANDEZIRIGOYEN@EDUCATION.GOV.UK |  | 2026-02-02 12:31 | Visitor | 2026-02-02 12:31 | 2026-02-02 12:31
227 | d276cc73-caa7-4a49-8e2e-81db9220c5ca | Kevin.DRAISEY@education.gov.uk | DRAISEY, Kevin | Kevin | DRAISEY | Kevin.DRAISEY@EDUCATION.GOV.UK |  | 2026-02-11 12:45 | Visitor | 2026-02-02 13:55 | 2026-02-11 12:45
228 | ffdc15d8-6bc6-4acb-96ff-668d25fe7510 | Greta.SMALLEY@education.gov.uk | SMALLEY, Greta | Greta | SMALLEY | Greta.SMALLEY@EDUCATION.GOV.UK |  | 2026-02-04 11:10 | Visitor | 2026-02-02 14:13 | 2026-02-04 11:10
229 | 9f1278e8-7670-4e9a-8a6b-861a04e7a4e6 | Mike.BENNETT@education.gov.uk | BENNETT, Mike | Mike | BENNETT | Mike.BENNETT@EDUCATION.GOV.UK |  | 2026-02-04 21:11 | Visitor | 2026-02-02 15:24 | 2026-02-04 21:11
230 | 8303295f-1591-4488-8d8f-ccda3e2af51e | Amandeep.KHERA@education.gov.uk | KHERA, Amandeep | Amandeep | KHERA | Amandeep.KHERA@EDUCATION.GOV.UK |  | 2026-02-03 09:36 | Visitor | 2026-02-03 09:36 | 2026-02-03 09:36
231 | bfeaf6c9-4cae-4dca-a944-527e2f6545c5 | Claire8.HUGHES@education.gov.uk | HUGHES, Claire8 | Claire | HUGHES | Claire8.HUGHES@education.gov.uk |  | 2026-02-03 09:52 | Visitor | 2026-02-03 09:52 | 2026-02-03 09:52
232 | 97f4d881-1d28-41f4-b9a6-fbf4c59aa9ac | Tirath.BAL@education.gov.uk | BAL, Tirath | Tirath | BAL | Tirath.BAL@EDUCATION.GOV.UK |  | 2026-02-03 14:38 | Visitor | 2026-02-03 14:02 | 2026-02-03 14:38
233 | bb7258b7-7a7f-48cf-9d0c-ce837f473db3 | Rizwana.NISA@education.gov.uk | NISA, Rizwana | Rizwana | NISA | Rizwana.NISA@EDUCATION.GOV.UK |  | 2026-02-04 11:13 | Visitor | 2026-02-03 14:03 | 2026-02-04 11:13
234 | 2a3751db-8ba1-4d9c-9c7e-f3fd4da676ba | Anthony.MCCREA@education.gov.uk | MCCREA, Anthony | Anthony | MCCREA | Anthony.MCCREA@EDUCATION.GOV.UK |  | 2026-02-04 11:07 | Visitor | 2026-02-03 14:21 | 2026-02-04 11:07
235 | 9d286650-5ffc-4c99-bada-31bcb22cbc10 | Huw.EVANS@education.gov.uk | EVANS, Huw | Huw | EVANS | Huw.EVANS@EDUCATION.GOV.UK |  | 2026-02-04 11:09 | Visitor | 2026-02-03 14:57 | 2026-02-04 11:09
236 | c116fd59-61f8-48da-a698-55c5bd23858e | Mark.WILSON@education.gov.uk | WILSON, Mark | Mark | WILSON | Mark.WILSON@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-03 15:04 | 2026-02-03 15:04
237 | 4695380e-4c10-45bb-bb58-b8d9828e48fd | Mark10.WILSON@education.gov.uk | WILSON, Mark10 - Digital & Technology | Mark10 | WILSON | Mark10.WILSON@EDUCATION.GOV.UK |  | 2026-02-04 11:13 | Visitor | 2026-02-03 15:04 | 2026-02-04 11:13
238 | 1092ae1c-2e53-4699-9485-42b65b028cc6 | Joe.JARVIS@education.gov.uk | JARVIS, Joe | Joe | JARVIS | Joe.JARVIS@EDUCATION.GOV.UK |  | 2026-02-11 11:42 | Visitor | 2026-02-03 15:11 | 2026-02-11 11:42
239 | 1066112f-a798-44c0-bd8e-f0809088a18c | Faith.TOMBS@education.gov.uk | TOMBS, Faith | Faith | TOMBS | Faith.TOMBS@EDUCATION.GOV.UK |  | 2026-02-17 19:45 | Visitor | 2026-02-04 09:50 | 2026-02-17 19:45
240 | b8f37bae-2272-43f9-ab16-9a36393675f1 | Gemma.JONES@education.gov.uk | JONES, Gemma | Gemma | JONES | Gemma.JONES@EDUCATION.GOV.UK |  | 2026-02-04 11:08 | Visitor | 2026-02-04 11:08 | 2026-02-04 11:08
241 | 8c71788d-b37d-4b06-944e-49d68a9ab25a | Theresa.MERCER@education.gov.uk | MERCER, Theresa | Theresa | MERCER | Theresa.MERCER@EDUCATION.GOV.UK |  | 2026-02-04 11:09 | Visitor | 2026-02-04 11:09 | 2026-02-04 11:09
242 | 44778f6e-db17-4f2b-a32a-4b3e03f55e16 | Anantha.ANILKUMAR@education.gov.uk | ANILKUMAR, Anantha | Anantha | ANILKUMAR | Anantha.ANILKUMAR@EDUCATION.GOV.UK |  | 2026-02-04 11:10 | Visitor | 2026-02-04 11:10 | 2026-02-04 11:10
243 | 1c9d44c5-0bde-4812-aca2-d4c5353c608d | Katherine.MURRELL@education.gov.uk | MURRELL, Katherine | Katherine | MURRELL | Katherine.MURRELL@EDUCATION.GOV.UK |  | 2026-02-04 11:11 | Visitor | 2026-02-04 11:11 | 2026-02-04 11:11
244 | 7e831e96-5ff2-4f34-8679-aeb58dbbf011 | Angie.PAYLOR@education.gov.uk | PAYLOR, Angie | Angie | PAYLOR | Angie.PAYLOR@EDUCATION.GOV.UK |  | 2026-02-11 12:45 | Visitor | 2026-02-04 11:11 | 2026-02-11 12:45
245 | 4fd81c1d-9e92-461c-907a-3a1d7574246a | Zoe.DREW@education.gov.uk | DREW, Zoe | Zoe | DREW | Zoe.DREW@EDUCATION.GOV.UK |  | 2026-02-04 11:11 | Visitor | 2026-02-04 11:11 | 2026-02-04 11:11
246 | cd40f156-db9e-4fa2-8051-f5dd360ed91b | Dominic.HARLEY@education.gov.uk | HARLEY, Dominic | Dominic | HARLEY | Dominic.HARLEY@EDUCATION.GOV.UK |  | 2026-02-04 11:12 | Visitor | 2026-02-04 11:12 | 2026-02-04 11:12
247 | 48541cd0-9f89-4c21-8112-c2ea361bf0e8 | Matt.BURROWS@education.gov.uk | BURROWS, Matt | Matt | BURROWS | Matt.BURROWS@education.gov.uk |  | 2026-02-04 11:13 | Visitor | 2026-02-04 11:13 | 2026-02-04 11:13
248 | 7143dc79-fda0-4d6c-9b7f-f6e486e2690b | Joanne.BROWNBRIDGE@education.gov.uk | BROWNBRIDGE, Joanne | Joanne | BROWNBRIDGE | Joanne.BROWNBRIDGE@EDUCATION.GOV.UK |  | 2026-02-18 20:12 | Visitor | 2026-02-04 11:57 | 2026-02-18 20:12
249 | 9a764859-e9d3-4439-9ac3-92f3eb9f8c75 | Ana.ALENCAR@education.gov.uk | ALENCAR, Ana | Ana | ALENCAR | Ana.ALENCAR@education.gov.uk |  | 2026-02-24 14:38 | Visitor | 2026-02-04 13:29 | 2026-02-24 14:38
250 | bbb373bd-1aa5-4dfa-b42f-082c842d0a8e | Emily.MASON@education.gov.uk | MASON, Emily | Emily | MASON | Emily.MASON@EDUCATION.GOV.UK |  | 2026-02-04 13:41 | Visitor | 2026-02-04 13:41 | 2026-02-04 13:41
251 | 1233bfae-9349-42b0-afeb-f8fab0522384 | Olivia.GREENAN@education.gov.uk | GREENAN, Olivia | Olivia | GREENAN | Olivia.GREENAN@EDUCATION.GOV.UK |  | 2026-02-11 14:08 | Visitor | 2026-02-05 10:24 | 2026-02-11 14:08
252 | f148585c-3fe2-4d26-b6e2-e8e94b76c694 | Ian.HOWARD@education.gov.uk | HOWARD, Ian | Ian | HOWARD | Ian.HOWARD@EDUCATION.GOV.UK |  | 2026-02-25 14:33 | Visitor | 2026-02-05 12:21 | 2026-02-25 14:33
253 | 4b1bf59f-2919-45e3-a366-7542e131a0cc | Julian.HARTLEY@education.gov.uk | HARTLEY, Julian | Julian | HARTLEY | Julian.HARTLEY@EDUCATION.GOV.UK |  | 2026-02-05 15:44 | Visitor | 2026-02-05 15:44 | 2026-02-05 15:44
254 | 441d9292-6d42-45ff-bf99-2f241c040c57 | Lisa.ATTENBORROW@education.gov.uk | ATTENBORROW, Lisa | Lisa | ATTENBORROW | Lisa.ATTENBORROW@EDUCATION.GOV.UK |  | 2026-02-06 08:51 | Visitor | 2026-02-06 08:51 | 2026-02-06 08:51
255 | a07bc346-f194-4f6d-bc3b-76545301a27c | Aneesah.KHALIL@education.gov.uk | KHALIL, Aneesah | Aneesah | KHALIL | Aneesah.KHALIL@EDUCATION.GOV.UK |  | 2026-02-09 09:05 | Visitor | 2026-02-09 09:05 | 2026-02-09 09:05
256 | 6b6d7ee3-5804-4c13-9c3a-5df9940613d1 | Craig.TOULSON@education.gov.uk | TOULSON, Craig | Craig | TOULSON | Craig.TOULSON@EDUCATION.GOV.UK |  | 2026-02-09 10:51 | Visitor | 2026-02-09 10:51 | 2026-02-09 10:51
257 | bd50aaf5-286e-49d4-97b2-2e86663897bc | Matt.FOULDS@education.gov.uk | FOULDS, Matt | Matt | FOULDS | Matt.FOULDS@EDUCATION.GOV.UK |  | 2026-02-09 11:23 | Visitor | 2026-02-09 11:23 | 2026-02-09 11:23
258 | 0e42cd6e-b688-4678-831b-80d134ede7c9 | Chloe-Jane.DEFTY@education.gov.uk | DEFTY, Chloe-Jane | Chloe-Jane | DEFTY | Chloe-Jane.DEFTY@EDUCATION.GOV.UK |  | 2026-02-09 11:35 | Visitor | 2026-02-09 11:35 | 2026-02-09 11:35
259 | d9628514-b627-417e-a733-e55ef95b36fb | Loren.MOMODU-GORDON@EDUCATION.GOV.UK | MOMODU-GORDON, Loren | Loren | MOMODU-GORDON | Loren.MOMODU-GORDON@EDUCATION.GOV.UK |  | 2026-02-09 16:57 | Visitor | 2026-02-09 16:57 | 2026-02-09 16:57
260 | ed02e862-fae5-4216-8473-3cbaf6e3764e | Susanne.DEVLIN@EDUCATION.GOV.UK | DEVLIN, Susanne | Susanne | DEVLIN | Susanne.DEVLIN@EDUCATION.GOV.UK |  | 2026-02-09 17:07 | Visitor | 2026-02-09 17:07 | 2026-02-09 17:07
261 | 0e7aa37a-9ed9-44ce-8377-61923a4c12e7 | Sandy.DYSON@education.gov.uk | DYSON, Sandy | Sandy | DYSON | Sandy.DYSON@education.gov.uk |  |  | Visitor | 2026-02-09 17:12 | 2026-02-09 17:12
262 | 1e728403-e525-44df-bc24-6e0742032726 | Austin.DALBY@education.gov.uk | DALBY, Austin | Austin | DALBY | Austin.DALBY@EDUCATION.GOV.UK |  | 2026-02-11 12:57 | Visitor | 2026-02-10 10:30 | 2026-02-11 12:57
263 | 82c88d8e-1c4b-4db9-825c-2aa3a51f6d20 | Steve.BEALS@education.gov.uk | BEALS, Steve | Steve | BEALS | Steve.BEALS@EDUCATION.GOV.UK |  | 2026-02-10 11:01 | Visitor | 2026-02-10 11:01 | 2026-02-10 11:01
264 | 88479d08-9583-42f8-a957-8f6da573b174 | Marios.HORNSBY-EVLAMBIOU@education.gov.uk | HORNSBY-EVLAMBIOU, Marios | Marios | HORNSBY-EVLAMBIOU | Marios.HORNSBY-EVLAMBIOU@EDUCATION.GOV.UK |  | 2026-02-10 13:05 | Visitor | 2026-02-10 13:05 | 2026-02-10 13:05
265 | 27fb6d40-5fdc-4fdf-a7a3-b57b6384a771 | Daniel.TOVEY@education.gov.uk | TOVEY, Daniel | Daniel | TOVEY | Daniel.TOVEY@EDUCATION.GOV.UK |  | 2026-02-10 13:16 | Visitor | 2026-02-10 13:16 | 2026-02-10 13:16
266 | 5a55de78-d303-4a96-ae46-379a37ab01b2 | Oliver.OLDFIELD@education.gov.uk | OLDFIELD, Oliver | Oliver | OLDFIELD | Oliver.OLDFIELD@education.gov.uk |  |  | Visitor | 2026-02-10 13:17 | 2026-02-11 11:45
267 | d4057aea-6e65-46b6-b2c0-d3c807a90aa9 | Colin.GROVER@education.gov.uk | GROVER, Colin | Colin | GROVER | Colin.GROVER@EDUCATION.GOV.UK |  | 2026-02-10 13:19 | Visitor | 2026-02-10 13:19 | 2026-02-10 13:19
268 | 5386df3b-9ee3-4b39-bd1d-3314e4fa05e1 | Nicholas.HARLOW@education.gov.uk | HARLOW, Nicholas | Nicholas | HARLOW | Nicholas.HARLOW@EDUCATION.GOV.UK |  | 2026-02-11 12:55 | Visitor | 2026-02-10 13:29 | 2026-02-11 12:55
269 | 5fc9cf09-eac0-45b8-8319-7d3cede8fea2 | Gavin.MONUMENT@education.gov.uk | MONUMENT, Gavin | Gavin | MONUMENT | Gavin.MONUMENT@EDUCATION.GOV.UK |  | 2026-02-10 13:30 | Visitor | 2026-02-10 13:30 | 2026-02-10 13:30
270 | 0ade8852-538a-4828-81f2-fd7a47afa45a | Chris.Collins@education.gov.uk | COLLINS, Chris | Chris | Collins | Chris.Collins@EDUCATION.GOV.UK |  | 2026-02-10 13:34 | Visitor | 2026-02-10 13:34 | 2026-02-10 13:34
271 | 0dd29a76-a27c-4f1b-88d6-b97561d236f5 | Andrew.JONES@education.gov.uk | JONES, Andrew | Andrew | JONES | Andrew.JONES@EDUCATION.GOV.UK |  | 2026-02-10 13:36 | Visitor | 2026-02-10 13:36 | 2026-02-10 13:36
272 | f090a9e5-0260-483c-97e2-8b51439ccc92 | Ritesh.PATEL@education.gov.uk | PATEL, Ritesh | Ritesh | PATEL | Ritesh.PATEL@EDUCATION.GOV.UK |  | 2026-02-10 13:39 | Visitor | 2026-02-10 13:39 | 2026-02-10 13:39
273 | f71e0a2f-c306-4bd4-948a-75c0b38ca768 | Amy.MATTHEWS@education.gov.uk | MATTHEWS, Amy | Amy | MATTHEWS | Amy.MATTHEWS@EDUCATION.GOV.UK |  | 2026-02-10 13:42 | Visitor | 2026-02-10 13:41 | 2026-02-10 13:42
274 | 7e7953e5-bfa8-4f87-9e96-759cdb7fde6f | Ivan.SIMMS@education.gov.uk | SIMMS, Ivan | Ivan | SIMMS | Ivan.SIMMS@EDUCATION.GOV.UK |  | 2026-02-11 11:36 | Visitor | 2026-02-10 13:55 | 2026-02-11 11:36
275 | c6a94ba0-f7fc-49a2-8df7-c53fcd20e090 | Rob.GILLESPIE@education.gov.uk | GILLESPIE, Rob | Rob | GILLESPIE | Rob.GILLESPIE@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-10 14:02 | 2026-02-10 14:02
276 | 9d01a44a-0fe8-487e-b118-fe4da5688880 | Niall.GERAGHTY@education.gov.uk | GERAGHTY, Niall | Niall | GERAGHTY | Niall.GERAGHTY@EDUCATION.GOV.UK |  | 2026-02-10 14:07 | Visitor | 2026-02-10 14:07 | 2026-02-10 14:07
277 | f1dd03ce-3dcb-4fcc-a961-04e3a8dbd335 | Bryan.WATERSON@education.gov.uk | WATERSON, Bryan | Bryan | WATERSON | Bryan.WATERSON@EDUCATION.GOV.UK |  | 2026-02-11 11:41 | Visitor | 2026-02-10 14:12 | 2026-02-11 11:41
278 | 6cd20975-a99f-40e7-9209-a01b7be05bbc | Paul.MIDDLEMAS@education.gov.uk | MIDDLEMAS, Paul | Paul | MIDDLEMAS | Paul.MIDDLEMAS@EDUCATION.GOV.UK |  | 2026-02-10 14:16 | Visitor | 2026-02-10 14:16 | 2026-02-10 14:16
279 | 16276de0-9379-47df-b07e-d7d51dc5e41c | Maia.WILLIAMS@education.gov.uk | WILLIAMS, Maia | Maia | WILLIAMS | Maia.WILLIAMS@EDUCATION.GOV.UK |  | 2026-02-11 13:59 | Visitor | 2026-02-10 14:51 | 2026-02-11 13:59
280 | 3547b306-4b3e-418b-a5ff-510612e3c589 | Nathan.EASEY@education.gov.uk | EASEY, Nathan | Nathan | EASEY | Nathan.EASEY@education.gov.uk |  | 2026-02-10 15:00 | Visitor | 2026-02-10 15:00 | 2026-02-10 15:00
281 | 3961cf28-0334-41a3-b24a-6bf62996e28e | Rani.PINDER@education.gov.uk | PINDER, Rani | Rani | PINDER | Rani.PINDER@EDUCATION.GOV.UK |  | 2026-02-10 15:31 | Visitor | 2026-02-10 15:31 | 2026-02-10 15:31
282 | 02203291-4f4d-4582-915a-37b50d08e575 | Paul.RUSHTON@education.gov.uk | RUSHTON, Paul | Paul | RUSHTON | Paul.RUSHTON@EDUCATION.GOV.UK |  | 2026-02-11 13:14 | Visitor | 2026-02-10 15:31 | 2026-02-11 13:14
283 | 47c1a26a-bcc9-4ee8-9c1e-80e0bed66115 | Sophie.COY@EDUCATION.GOV.UK | COY, Sophie | Sophie | COY | Sophie.COY@EDUCATION.GOV.UK |  | 2026-02-10 15:44 | Visitor | 2026-02-10 15:44 | 2026-02-10 15:44
284 | 722fd3e8-4fab-43c6-9e71-fef5dc1b027c | Simon.COOK@education.gov.uk | COOK, Simon | Simon | COOK | Simon.COOK@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-10 15:48 | 2026-02-10 15:48
285 | aaddf702-1a38-4f66-a5d3-53d6527082ab | Lynne.BURDON@education.gov.uk | BURDON, Lynne | Lynne | BURDON | Lynne.BURDON@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-10 15:51 | 2026-02-11 12:59
286 | 441a66f2-f02c-4cfb-9622-8839517dc1c9 | David.BEDFORD@education.gov.uk | BEDFORD, David | David | BEDFORD | David.BEDFORD@EDUCATION.GOV.UK |  | 2026-02-10 16:00 | Visitor | 2026-02-10 16:00 | 2026-02-10 16:00
287 | 31001b45-a619-4a98-9716-caf422415756 | Ann.STRICKLAND@education.gov.uk | STRICKLAND, Ann | Ann | STRICKLAND | Ann.STRICKLAND@EDUCATION.GOV.UK |  | 2026-02-11 13:11 | Visitor | 2026-02-10 16:29 | 2026-02-11 13:11
288 | 5ebf37c2-9174-4a3c-b362-04504d6290be | Gary.Mead@education.gov.uk | MEAD, Gary | Gary | Mead | Gary.Mead@EDUCATION.GOV.UK |  | 2026-02-10 17:23 | Visitor | 2026-02-10 17:23 | 2026-02-10 17:23
289 | 76a9b9ec-f43e-40a6-9f5b-2ead7d04e2b2 | Alex.ADAMS@education.gov.uk | ADAMS, Alex | Alex | ADAMS | Alex.ADAMS@EDUCATION.GOV.UK |  | 2026-02-11 13:07 | Visitor | 2026-02-11 07:48 | 2026-02-11 13:07
290 | 505eebb7-5395-4e08-9a97-0fc51eb3c5dd | Catrin.BURROWS@education.gov.uk | BURROWS, Catrin | Catrin | BURROWS | Catrin.BURROWS@EDUCATION.GOV.UK |  | 2026-02-11 08:29 | Visitor | 2026-02-11 08:29 | 2026-02-11 08:29
291 | 6ebbc23c-a6f4-4674-83c1-db3b908426b1 | Helen.SOUTH@education.gov.uk | SOUTH, Helen | Helen | SOUTH | Helen.SOUTH@EDUCATION.GOV.UK |  | 2026-02-11 08:33 | Visitor | 2026-02-11 08:33 | 2026-02-11 08:33
292 | f3b7dd50-cf1b-467d-80af-5ec84f24c72a | Chris.WOODRUFF@education.gov.uk | WOODRUFF, Chris | Chris | WOODRUFF | Chris.WOODRUFF@EDUCATION.GOV.UK |  | 2026-02-11 08:45 | Visitor | 2026-02-11 08:45 | 2026-02-11 08:45
293 | 568ed61b-fef8-4d9a-9de2-367636395afa | Steven2.LEGG@education.gov.uk | LEGG, Steven2 | Steven2 | LEGG | Steven2.LEGG@EDUCATION.GOV.UK |  | 2026-02-11 09:20 | Visitor | 2026-02-11 09:20 | 2026-02-11 09:20
294 | 56ef4f0c-e1f6-474f-8303-1b2eb18a8255 | Andy.MCBEATH@EDUCATION.GOV.UK | MCBEATH, Andy | Andy | MCBEATH | Andy.MCBEATH@EDUCATION.GOV.UK |  | 2026-02-11 09:20 | Visitor | 2026-02-11 09:20 | 2026-02-11 09:20
295 | 7a69fd6f-8d99-4016-89f4-4dd8098e963d | Liz.HILLYARD@EDUCATION.GOV.UK | HILLYARD, Liz | Liz | HILLYARD | Liz.HILLYARD@EDUCATION.GOV.UK |  | 2026-02-11 09:25 | Visitor | 2026-02-11 09:25 | 2026-02-11 09:25
296 | 2884c79d-de52-4508-a326-5a4d6ab60f11 | Sam.REYNOLDS@education.gov.uk | REYNOLDS, Sam | Sam | REYNOLDS | Sam.REYNOLDS@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-11 10:33 | 2026-02-11 10:33
297 | bc14e393-d05b-47e6-9e13-f97ec62608b6 | John.Myers@education.gov.uk | MYERS, John | John | Myers | John.Myers@EDUCATION.GOV.UK |  | 2026-02-11 10:59 | Visitor | 2026-02-11 10:59 | 2026-02-11 10:59
298 | b26ede63-a1e9-4ba6-8ac7-4eb8f28b6cb8 | Laura.PULLIN@education.gov.uk | PULLIN, Laura | Laura | PULLIN | Laura.PULLIN@EDUCATION.GOV.UK |  | 2026-02-11 11:00 | Visitor | 2026-02-11 11:00 | 2026-02-11 11:00
299 | a54daccf-1a2d-468b-915e-da79592e26a8 | David.BURNETT@education.gov.uk | BURNETT, David | David | BURNETT | David.BURNETT@EDUCATION.GOV.UK |  | 2026-02-11 12:00 | Visitor | 2026-02-11 11:00 | 2026-02-11 12:00
300 | a73ca46e-fb50-4478-8993-eead64a9bfe0 | Peter.WARD@education.gov.uk | WARD, Peter | Peter | WARD | Peter.WARD@education.gov.uk |  | 2026-02-11 11:01 | Visitor | 2026-02-11 11:01 | 2026-02-11 11:01
301 | c0b3596e-7c7e-4bf8-8b5c-af24054fdf3f | Chris3.DAVIS@education.gov.uk | DAVIS, Chris3 | Chris3 | DAVIS | Chris3.DAVIS@EDUCATION.GOV.UK |  | 2026-02-11 11:01 | Visitor | 2026-02-11 11:01 | 2026-02-11 11:01
302 | 9e9f37ba-dd31-4d87-9b6a-deb61242421e | Paul.SIMMONS@education.gov.uk | SIMMONS, Paul | Paul | SIMMONS | Paul.SIMMONS@EDUCATION.GOV.UK |  | 2026-02-11 14:09 | Visitor | 2026-02-11 11:02 | 2026-02-11 14:09
303 | 04310ec5-df20-453e-a86c-c644e2b228d5 | Andrew.KING@education.gov.uk | KING, Andrew | Andrew | KING | Andrew.KING@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-11 11:16 | 2026-02-11 11:16
304 | 50b874ce-1fc1-4564-9cc1-bd9f9772f6e9 | Richard.HINDMARCH@education.gov.uk | HINDMARCH, Richard | Richard | HINDMARCH | Richard.HINDMARCH@EDUCATION.GOV.UK |  | 2026-02-11 11:43 | Visitor | 2026-02-11 11:21 | 2026-02-11 11:43
305 | d4d8d8c9-03c2-42f3-913e-7298d69e0fee | Matt.CLEGG@education.gov.uk | CLEGG, Matt | Matt | CLEGG | Matt.CLEGG@EDUCATION.GOV.UK |  | 2026-02-11 11:23 | Visitor | 2026-02-11 11:23 | 2026-02-11 11:23
306 | c0ce52ec-ae11-4f73-a5dc-37ef5edf0b3f | Tim.MOSES@education.gov.uk | MOSES, Tim | Tim | MOSES | Tim.MOSES@EDUCATION.GOV.UK |  | 2026-02-11 11:24 | Visitor | 2026-02-11 11:24 | 2026-02-11 11:24
307 | 3cb0399e-05de-4d63-91e1-b6824b94162b | Charlie.HUGHES@education.gov.uk | HUGHES, Charlie | Charlie | HUGHES | Charlie.HUGHES@EDUCATION.GOV.UK |  | 2026-02-11 11:25 | Visitor | 2026-02-11 11:25 | 2026-02-11 11:25
308 | d98a1316-3df5-40a1-8d1d-74a8c9906fa9 | Neil.TAYLOR@education.gov.uk | TAYLOR, Neil | Neil | TAYLOR | Neil.TAYLOR@EDUCATION.GOV.UK |  | 2026-02-11 14:00 | Visitor | 2026-02-11 11:25 | 2026-02-11 14:00
309 | 73441d9e-36b3-404b-8611-a9ca0ce2e81f | Andy.GODFREY@education.gov.uk | GODFREY, Andy | Andy | GODFREY | Andy.GODFREY@EDUCATION.GOV.UK |  | 2026-02-11 13:04 | Visitor | 2026-02-11 11:25 | 2026-02-11 13:04
310 | 71c13d79-db0c-400b-be99-0138d45df859 | Harinder.SAHOTA@education.gov.uk | SAHOTA, Harinder | Harinder | SAHOTA | Harinder.SAHOTA@EDUCATION.GOV.UK |  | 2026-02-11 11:28 | Visitor | 2026-02-11 11:28 | 2026-02-11 11:28
311 | 007c4b80-a1d8-4e40-b117-901d925196b8 | Jon.TROTT@education.gov.uk | TROTT, Jon | Jon | TROTT | Jon.TROTT@EDUCATION.GOV.UK |  | 2026-02-11 14:03 | Visitor | 2026-02-11 11:28 | 2026-02-11 14:03
312 | 3f46c1dd-fe42-48f2-9dee-b63c687f38b7 | Andrew.COTTRELL@childrenscommissioner.gov.uk | COTTRELL, Andrew - Children's Commissioner | Andrew | COTTRELL | Andrew.COTTRELL@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-11 11:29 | 2026-02-11 11:29
313 | aa42ef75-8439-41e2-86ff-3325852f6db1 | Oliver.DAVIES@openinnovation.gov.uk | DAVIES, Oliver | Oliver | DAVIES | Oliver.DAVIES@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-11 11:30 | 2026-02-11 11:30
314 | 36d88781-b12c-46ed-a9f4-38d29348f1bf | Michelle.BRANKIN@education.gov.uk | BRANKIN, Michelle | Michelle | BRANKIN | Michelle.BRANKIN@EDUCATION.GOV.UK |  | 2026-02-11 13:50 | Visitor | 2026-02-11 11:32 | 2026-02-11 13:50
315 | ca1f1ffc-bf37-4d70-9050-5ace79d3e265 | Laurence.JONES@education.gov.uk | JONES, Laurence | Laurence | JONES | Laurence.JONES@EDUCATION.GOV.UK |  | 2026-02-11 11:34 | Visitor | 2026-02-11 11:34 | 2026-02-11 11:34
316 | d99857f1-b95b-4593-9f09-f35abef67f00 | Freddie.CRANE@education.gov.uk | CRANE, Freddie | Freddie | CRANE | Freddie.CRANE@EDUCATION.GOV.UK |  | 2026-02-11 13:47 | Visitor | 2026-02-11 11:35 | 2026-02-11 13:47
317 | 51a926c2-b998-4f1e-aa17-d32af7ee2b77 | Tom.WHITE@education.gov.uk | WHITE, Tom | Tom | WHITE | Tom.WHITE@EDUCATION.GOV.UK |  | 2026-02-11 11:36 | Visitor | 2026-02-11 11:36 | 2026-02-11 11:36
318 | 4a651a0b-3fc1-4f45-9b39-ac6a2d37a352 | Joanna.TAYLOR@education.gov.uk | TAYLOR, Joanna | Joanna | TAYLOR | Joanna.TAYLOR@EDUCATION.GOV.UK |  | 2026-02-11 11:37 | Visitor | 2026-02-11 11:37 | 2026-02-11 11:37
319 | 3753f45d-d00f-4212-8378-34bc59f5bf0e | Susan.WHITEHOUSE@education.gov.uk | WHITEHOUSE, Susan | Susan | WHITEHOUSE | Susan.WHITEHOUSE@EDUCATION.GOV.UK |  | 2026-02-11 11:38 | Visitor | 2026-02-11 11:38 | 2026-02-11 11:38
320 | f2223b24-d1a9-4cb2-bcd8-7cd6de50f7e3 | Hannah.SPEED1@education.gov.uk | SPEED, Hannah1 | Hannah | SPEED | Hannah.SPEED1@EDUCATION.GOV.UK |  | 2026-02-11 11:38 | Visitor | 2026-02-11 11:38 | 2026-02-11 11:38
321 | 11914ffb-385f-4101-8418-ab0cfbf7e77f | Hans.CAYLEY@education.gov.uk | CAYLEY, Hans | Hans | CAYLEY | Hans.CAYLEY@EDUCATION.GOV.UK |  | 2026-02-11 13:51 | Visitor | 2026-02-11 11:41 | 2026-02-11 13:51
322 | c0306f2e-96f1-4eff-9c0f-a3e3b49e6d56 | Andrew.BLOWER@education.gov.uk | BLOWER, Andrew | Andrew | BLOWER | Andrew.BLOWER@EDUCATION.GOV.UK |  | 2026-02-11 13:54 | Visitor | 2026-02-11 11:43 | 2026-02-11 13:54
323 | c8356644-75b3-4bea-a5aa-35e8a990cadd | Mark.SHIELD@education.gov.uk | SHIELD, Mark | Mark | SHIELD | Mark.SHIELD@EDUCATION.GOV.UK |  | 2026-02-11 12:29 | Visitor | 2026-02-11 11:46 | 2026-02-11 12:29
324 | 85a75988-faec-48bf-bcb5-3215c6fbaeb2 | David1.CRAIG@education.gov.uk | CRAIG, David1 | David1 | CRAIG | David1.CRAIG@EDUCATION.GOV.UK |  | 2026-02-11 13:06 | Visitor | 2026-02-11 11:57 | 2026-02-11 13:06
325 | b069b219-8e62-4040-abb1-b72bda4a69b0 | Seymour.PEARMAN@education.gov.uk | PEARMAN, Seymour | Seymour | PEARMAN | Seymour.PEARMAN@EDUCATION.GOV.UK |  | 2026-02-11 11:58 | Visitor | 2026-02-11 11:58 | 2026-02-11 11:58
326 | 56d4e979-ce80-4e96-908b-275886bce32c | Richard.CLARKE@education.gov.uk | CLARKE, Richard | Richard | CLARKE | Richard.CLARKE@EDUCATION.GOV.UK |  | 2026-02-11 14:02 | Visitor | 2026-02-11 11:58 | 2026-02-11 14:02
327 | a04f3f2d-6639-458d-a3a0-cc5cb6119e3f | Dave.BURNETT@education.gov.uk | BURNETT, Dave | Dave | BURNETT | Dave.BURNETT@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-11 11:59 | 2026-02-11 11:59
328 | 7da79b5e-5f62-4f03-9dcb-a30523a35284 | Sam.BRENNAN@education.gov.uk | BRENNAN, Sam | Sam | BRENNAN | Sam.BRENNAN@EDUCATION.GOV.UK |  | 2026-02-11 14:00 | Visitor | 2026-02-11 12:00 | 2026-02-11 14:00
329 | 725cb802-0cf7-4c67-aa88-a892c76da1f9 | Jesal.MAVADIYA@education.gov.uk | MAVADIYA, Jesal | Jesal | MAVADIYA | Jesal.MAVADIYA@EDUCATION.GOV.UK |  | 2026-02-11 12:02 | Visitor | 2026-02-11 12:01 | 2026-02-11 12:02
330 | 70e83954-281f-41ba-ac6d-0bc5b7f16d57 | Laura.SELBY@education.gov.uk | SELBY, Laura | Laura | SELBY | Laura.SELBY@EDUCATION.GOV.UK |  | 2026-02-11 12:27 | Visitor | 2026-02-11 12:25 | 2026-02-11 12:27
331 | f78853b0-6ca3-4f3c-84f7-a4948d110b49 | Bethan.WATERHOUSE@education.gov.uk | WATERHOUSE, Bethan | Bethan | WATERHOUSE | Bethan.WATERHOUSE@EDUCATION.GOV.UK |  | 2026-02-11 14:01 | Visitor | 2026-02-11 12:27 | 2026-02-11 14:01
332 | a703a964-a7ad-4d33-af3a-e11e44244946 | Joe.BILLINGTON@education.gov.uk | BILLINGTON, Joe | Joe | BILLINGTON | Joe.BILLINGTON@EDUCATION.GOV.UK |  | 2026-02-11 12:28 | Visitor | 2026-02-11 12:28 | 2026-02-11 12:28
333 | d00296a1-862c-4f75-ad57-eb112c94fd48 | Jo.HODKINSON@education.gov.uk | HODKINSON, Jo | Jo | HODKINSON | Jo.HODKINSON@EDUCATION.GOV.UK |  | 2026-02-11 12:29 | Visitor | 2026-02-11 12:29 | 2026-02-11 12:29
334 | 1ce1895d-9f91-4d1b-9265-2241e233ab90 | Jane.DAVIES@education.gov.uk | DAVIES, Jane | Jane | DAVIES | Jane.DAVIES@EDUCATION.GOV.UK |  | 2026-02-11 12:30 | Visitor | 2026-02-11 12:30 | 2026-02-11 12:30
335 | bb9aa616-0107-4b44-856c-ebb92b2c15c4 | Gary.CONNELL@education.gov.uk | CONNELL, Gary | Gary | CONNELL | Gary.CONNELL@EDUCATION.GOV.UK |  | 2026-02-11 12:31 | Visitor | 2026-02-11 12:31 | 2026-02-11 12:31
336 | 71ed8bc9-69e8-4f32-a430-81b379975525 | Rachel.HOPE@education.gov.uk | HOPE, Rachel | Rachel | HOPE | Rachel.HOPE@EDUCATION.GOV.UK |  | 2026-02-11 12:57 | Visitor | 2026-02-11 12:32 | 2026-02-11 12:57
337 | ee3bddee-78bd-4ab9-8b9f-55afa3ab2bf1 | Simon.MATTHEWS@education.gov.uk | MATTHEWS, Simon | Simon | MATTHEWS | Simon.MATTHEWS@EDUCATION.GOV.UK |  | 2026-02-11 12:40 | Visitor | 2026-02-11 12:40 | 2026-02-11 12:40
338 | bf8b979d-e13c-4148-b8be-e5769b4966a5 | Richard.STEWART@education.gov.uk | STEWART, Richard | Richard | STEWART | Richard.STEWART@EDUCATION.GOV.UK |  | 2026-02-11 12:44 | Visitor | 2026-02-11 12:44 | 2026-02-11 12:44
339 | a90f8263-8559-4cbd-b0c6-d09f11e2dcd5 | Emily.VICKERS@education.gov.uk | VICKERS, Emily | Emily | VICKERS | Emily.VICKERS@EDUCATION.GOV.UK |  | 2026-02-11 12:47 | Visitor | 2026-02-11 12:47 | 2026-02-11 12:47
340 | e5e33253-d6f4-4693-a52b-bb306fa62f03 | Sarah.SANTIAPILLAI@EDUCATION.GOV.UK | SANTIAPILLAI, Sarah | Sarah | SANTIAPILLAI | Sarah.SANTIAPILLAI@EDUCATION.GOV.UK |  | 2026-02-11 12:47 | Visitor | 2026-02-11 12:47 | 2026-02-11 12:47
341 | eea0a273-fb71-4fc5-9335-29869ed5052d | Jonathan.BRYAN@education.gov.uk | BRYAN, Jonathan | Jonathan | BRYAN | Jonathan.BRYAN@EDUCATION.GOV.UK |  | 2026-02-11 12:48 | Visitor | 2026-02-11 12:48 | 2026-02-11 12:48
342 | 06f3538c-29fc-4478-8138-31085882cff8 | Beatrice.LONGMORE@childrenscommissioner.gov.uk | LONGMORE, Beatrice - Children's Commissioner | Beatrice | LONGMORE | Beatrice.LONGMORE@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-11 12:53 | 2026-02-11 12:53
343 | 8f029bce-a4c2-4bd0-90e9-c81b510b7781 | Nick.MANTON@education.gov.uk | MANTON, Nick | Nick | MANTON | Nick.MANTON@EDUCATION.GOV.UK |  | 2026-02-11 12:54 | Visitor | 2026-02-11 12:54 | 2026-02-11 12:54
344 | d216405e-f698-40e4-bfdd-17686b496adc | Robin.HALL@education.gov.uk | HALL, Robin | Robin | HALL | Robin.HALL@EDUCATION.GOV.UK |  | 2026-02-11 12:55 | Visitor | 2026-02-11 12:55 | 2026-02-11 12:55
345 | d084a71b-0648-43d4-bf32-008ff00c712e | Helene.BRECHIN@education.gov.uk | BRECHIN, Helene | Helene | BRECHIN | Helene.BRECHIN@EDUCATION.GOV.UK |  | 2026-02-11 12:57 | Visitor | 2026-02-11 12:57 | 2026-02-11 12:57
346 | d013d746-38d3-426e-8c53-68b23e004a5a | Stacy.SINGLETON@education.gov.uk | SINGLETON, Stacy | Stacy | SINGLETON | Stacy.SINGLETON@EDUCATION.GOV.UK |  | 2026-02-11 12:58 | Visitor | 2026-02-11 12:58 | 2026-02-11 12:58
347 | 99931ea5-53dd-4ee6-b11c-f4ddb833573f | Anne.DENNIS@education.gov.uk | DENNIS, Anne | Anne | DENNIS | Anne.DENNIS@EDUCATION.GOV.UK |  | 2026-02-11 12:58 | Visitor | 2026-02-11 12:58 | 2026-02-11 12:58
348 | 58408f76-4456-4c3a-a382-0b2769db95fe | Debbie.HUGHES@education.gov.uk | HUGHES, Debbie | Debbie | HUGHES | Debbie.HUGHES@EDUCATION.GOV.UK |  | 2026-02-11 12:59 | Visitor | 2026-02-11 12:59 | 2026-02-11 12:59
349 | dd0454e9-bb2c-40c3-8ea0-d23202af1629 | Julie.BERNDT@education.gov.uk | BERNDT, Julie | Julie | BERNDT | Julie.BERNDT@EDUCATION.GOV.UK |  | 2026-02-11 13:00 | Visitor | 2026-02-11 13:00 | 2026-02-11 13:00
350 | 1c21465e-fc52-4a3e-8c63-55acc7081044 | Louise.Feebrey@education.gov.uk | FEEBREY, Louise | Louise | Feebrey | Louise.Feebrey@EDUCATION.GOV.UK |  | 2026-02-11 13:01 | Visitor | 2026-02-11 13:00 | 2026-02-11 13:01
351 | 65638b18-59a4-4026-b813-c657f531cbc1 | John.KNOWLES@education.gov.uk | KNOWLES, John | John | KNOWLES | John.KNOWLES@EDUCATION.GOV.UK |  | 2026-02-11 13:03 | Visitor | 2026-02-11 13:03 | 2026-02-11 13:03
352 | d091b942-ff96-41aa-a676-e28f5dd353bb | John.DONELAN@education.gov.uk | DONELAN, John | John | DONELAN | John.DONELAN@EDUCATION.GOV.UK |  | 2026-02-11 13:03 | Visitor | 2026-02-11 13:03 | 2026-02-11 13:03
353 | b6772b50-4fa7-4b20-875a-d89d4741dd9a | Kathryn.WARRILLOW@education.gov.uk | WARRILLOW, Kathryn | Kathryn | WARRILLOW | Kathryn.WARRILLOW@EDUCATION.GOV.UK |  | 2026-02-11 13:07 | Visitor | 2026-02-11 13:07 | 2026-02-11 13:07
354 | 789c4763-0527-43a8-aa0c-23d48097bf85 | Philip.MANNERING@education.gov.uk | MANNERING, Philip | Philip | MANNERING | Philip.MANNERING@EDUCATION.GOV.UK |  | 2026-02-11 13:52 | Visitor | 2026-02-11 13:09 | 2026-02-11 13:52
355 | 1ce5dbba-25ae-48e7-8895-dca40603afbd | Katie.WILCOCK@education.gov.uk | WILCOCK, Katie | Katie | WILCOCK | Katie.WILCOCK@EDUCATION.GOV.UK |  | 2026-02-11 13:10 | Visitor | 2026-02-11 13:10 | 2026-02-11 13:10
356 | d481915d-b600-4bdd-bdb9-04afbe515cc7 | Jake.WOOD@education.gov.uk | WOOD, Jake | Jake | WOOD | Jake.WOOD@EDUCATION.GOV.UK |  | 2026-02-11 13:10 | Visitor | 2026-02-11 13:10 | 2026-02-11 13:10
357 | 5985b7dd-75c1-4b7e-bf8f-b9e0816e7308 | Clifford.SMITH@education.gov.uk | SMITH, Clifford | Clifford | SMITH | Clifford.SMITH@EDUCATION.GOV.UK |  | 2026-02-11 13:11 | Visitor | 2026-02-11 13:11 | 2026-02-11 13:11
358 | 123676a4-d62a-4f14-956f-74f2960c2cf1 | Kate.MOORE@education.gov.uk | MOORE, Kate | Kate | MOORE | Kate.MOORE@EDUCATION.GOV.UK |  | 2026-02-11 13:14 | Visitor | 2026-02-11 13:14 | 2026-02-11 13:14
359 | 1321b10b-462e-401e-a701-d0e8708c881d | Majid.HAMID@education.gov.uk | HAMID, Majid | Majid | HAMID | Majid.HAMID@EDUCATION.GOV.UK |  | 2026-02-11 14:05 | Visitor | 2026-02-11 13:47 | 2026-02-11 14:05
360 | 2d27f6d9-8edf-42a8-b67b-4f0198408c1c | Elliot.FOX@education.gov.uk | FOX, Elliot | Elliot | FOX | Elliot.FOX@EDUCATION.GOV.UK |  | 2026-02-11 13:49 | Visitor | 2026-02-11 13:49 | 2026-02-11 13:49
361 | f421f854-d048-464d-838e-2be470614e07 | Chloe.SAKLOW@education.gov.uk | SAKLOW, Chloe | Chloe | SAKLOW | Chloe.SAKLOW@EDUCATION.GOV.UK |  | 2026-02-11 13:51 | Visitor | 2026-02-11 13:51 | 2026-02-11 13:51
362 | cedb47c7-9e48-4606-a242-3d809c22bac8 | Michelle.TOPPING@education.gov.uk | TOPPING, Michelle | Michelle | TOPPING | Michelle.TOPPING@EDUCATION.GOV.UK |  | 2026-02-11 13:51 | Visitor | 2026-02-11 13:51 | 2026-02-11 13:51
363 | 84071899-4327-475d-a448-dff401222b14 | Alix.Crabtree@education.gov.uk | CRABTREE, Alix | Alix | Crabtree | Alix.CRABTREE@EDUCATION.GOV.UK |  | 2026-02-11 13:52 | Visitor | 2026-02-11 13:52 | 2026-02-11 13:52
364 | 5c3e618a-0173-4f55-b639-97cd634f12d0 | Philip.GALLAGHER@education.gov.uk | GALLAGHER, Philip | Philip | GALLAGHER | Philip.GALLAGHER@EDUCATION.GOV.UK |  | 2026-02-11 14:03 | Visitor | 2026-02-11 13:54 | 2026-02-11 14:03
365 | abedd7b3-6acc-4409-b043-59606967f308 | Adaobi.IFEACHOR@education.gov.uk | IFEACHOR, Adaobi | Adaobi | IFEACHOR | Adaobi.IFEACHOR@education.gov.uk |  | 2026-02-11 13:56 | Visitor | 2026-02-11 13:56 | 2026-02-11 13:56
366 | 1bf01aeb-575f-4553-b15d-95ea60000969 | Heather.MARTIN@education.gov.uk | MARTIN, Heather | Heather | MARTIN | Heather.MARTIN@EDUCATION.GOV.UK |  | 2026-02-11 14:01 | Visitor | 2026-02-11 14:01 | 2026-02-11 14:01
367 | c3f65520-7fce-4ed9-a0ab-b1a566fc6acb | Darryl.LESTER@education.gov.uk | LESTER, Darryl | Darryl | LESTER | Darryl.LESTER@EDUCATION.GOV.UK |  | 2026-02-11 14:02 | Visitor | 2026-02-11 14:02 | 2026-02-11 14:02
368 | 41d511d1-d970-4e14-b0cc-3ffbb857965d | Jenny.OLDROYD@education.gov.uk | OLDROYD, Jenny | Jenny | OLDROYD | Jenny.OLDROYD@EDUCATION.GOV.UK |  | 2026-02-11 14:02 | Visitor | 2026-02-11 14:02 | 2026-02-11 14:02
369 | 3255e909-8162-4dc4-ae2d-c49958d55065 | Charlotte.STRAKER@education.gov.uk | STRAKER, Charlotte | Charlotte | STRAKER | Charlotte.STRAKER@EDUCATION.GOV.UK |  | 2026-02-11 14:03 | Visitor | 2026-02-11 14:03 | 2026-02-11 14:03
370 | 6858804a-880b-414f-956b-a45c688be1d4 | Nicola.KEANE@education.gov.uk | KEANE, Nicola | Nicola | KEANE | Nicola.KEANE@EDUCATION.GOV.UK |  | 2026-02-11 14:04 | Visitor | 2026-02-11 14:04 | 2026-02-11 14:04
371 | 2a7351f4-cee4-46a6-adeb-433922ce541f | Andrew.EMLEY@education.gov.uk | EMLEY, Andrew | Andrew | EMLEY | Andrew.EMLEY@EDUCATION.GOV.UK |  | 2026-02-11 14:05 | Visitor | 2026-02-11 14:05 | 2026-02-11 14:05
372 | 1accd27c-b784-4c4f-9a9d-ad9ea9e9333c | Ravi.SACHDEV@education.gov.uk | SACHDEV, Ravi | Ravi | SACHDEV | Ravi.SACHDEV@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-11 14:05 | 2026-02-11 14:05
373 | ff729ce8-1960-4b4d-abbf-a1ceae536d22 | Jordan.RUSSELL@education.gov.uk | RUSSELL, Jordan | Jordan | RUSSELL | Jordan.RUSSELL@EDUCATION.GOV.UK |  | 2026-02-11 14:06 | Visitor | 2026-02-11 14:06 | 2026-02-11 14:06
374 | 1a54d1e8-9685-43af-9b0b-cb5fa191d29c | David.LAYTON-SCOTT@education.gov.uk | LAYTON-SCOTT, David | David | LAYTON-SCOTT | David.LAYTON-SCOTT@EDUCATION.GOV.UK |  | 2026-02-11 14:06 | Visitor | 2026-02-11 14:06 | 2026-02-11 14:06
375 | 672c3237-9116-402e-8b20-bac7c9c27a3b | Helen.LALOR@education.gov.uk | LALOR, Helen | Helen | LALOR | Helen.LALOR@EDUCATION.GOV.UK |  | 2026-02-11 14:07 | Visitor | 2026-02-11 14:07 | 2026-02-11 14:07
376 | 0b773d0e-3e79-492c-b8e7-48a7ac0bcfa5 | Stuart.BAILLIE@education.gov.uk | BAILLIE, Stuart | Stuart | BAILLIE | Stuart.BAILLIE@EDUCATION.GOV.UK |  | 2026-02-11 14:08 | Visitor | 2026-02-11 14:08 | 2026-02-11 14:08
377 | 451d6c3e-49d1-45ac-bdc4-a35c9da8dc63 | Adam.MAXFIELD@education.gov.uk | MAXFIELD, Adam | Adam | MAXFIELD | Adam.MAXFIELD@education.gov.uk |  | 2026-02-11 16:14 | Visitor | 2026-02-11 16:14 | 2026-02-11 16:14
378 | c19dafa8-8065-4aa4-962a-e8d3588076a4 | Jayne.FARRINGTON@education.gov.uk | FARRINGTON, Jayne | Jayne | FARRINGTON | Jayne.FARRINGTON@EDUCATION.GOV.UK |  | 2026-02-12 07:58 | Visitor | 2026-02-12 07:58 | 2026-02-12 07:58
379 | b5c373d4-52e0-492d-9cec-53091debdea4 | Christopher.LAZENBY@education.gov.uk | LAZENBY, Christopher | Christopher | LAZENBY | Christopher.LAZENBY@EDUCATION.GOV.UK |  | 2026-02-12 12:23 | Visitor | 2026-02-12 12:23 | 2026-02-12 12:23
380 | df4048d1-65a6-424f-bf3c-3ccedfe02a73 | Jennifer.CAWSON-WILLIAMS@education.gov.uk | CAWSON-WILLIAMS, Jennifer | Jennifer | CAWSON-WILLIAMS | Jennifer.CAWSON-WILLIAMS@EDUCATION.GOV.UK |  | 2026-02-12 14:53 | Visitor | 2026-02-12 14:53 | 2026-02-12 14:53
381 | c534140d-c775-41f9-bd41-8d98518a790c | Andy.FENNER@education.gov.uk | FENNER, Andy | Andy | FENNER | Andy.FENNER@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-12 14:59 | 2026-02-26 11:59
382 | 3a91dab1-85f7-485c-a399-8897da7580f9 | Arati.PATEL-MISTRY@education.gov.uk | PATEL-MISTRY, Arati | Arati | PATEL-MISTRY | Arati.PATEL-MISTRY@EDUCATION.GOV.UK |  | 2026-03-02 13:52 | Visitor | 2026-02-12 15:25 | 2026-03-02 13:52
383 | 8ff8c4f3-45b2-404d-8717-220d950e47c4 | Ben.BELWARD@education.gov.uk | BELWARD, Ben | Ben | BELWARD | Ben.BELWARD@education.gov.uk |  | 2026-02-13 10:28 | Visitor | 2026-02-13 10:28 | 2026-02-13 10:28
384 | d25c949e-e80d-456b-88c5-ebea7f12e883 | Gillian.DONOVAN@education.gov.uk | DONOVAN, Gillian | Gillian | DONOVAN | Gillian.DONOVAN@EDUCATION.GOV.UK |  | 2026-02-13 10:40 | Visitor | 2026-02-13 10:40 | 2026-02-13 10:40
385 | 956637e6-c32d-4b0c-bdcb-4b2f21f97ade | David.LYNN@education.gov.uk | LYNN, David | David | LYNN | David.LYNN@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-13 11:57 | 2026-02-13 11:57
386 | 337489ad-8849-40b8-8c1d-044502d64f84 | Gaye.CORDINGLEY@education.gov.uk | CORDINGLEY, Gaye | Gaye | CORDINGLEY | Gaye.CORDINGLEY@EDUCATION.GOV.UK |  | 2026-02-13 12:30 | Visitor | 2026-02-13 12:30 | 2026-02-13 12:30
387 | b6022446-f684-45e7-b607-c7a070fcc0ca | Matthew.GOOCH@education.gov.uk | GOOCH, Matthew | Matthew | GOOCH | Matthew.GOOCH@EDUCATION.GOV.UK |  | 2026-02-13 13:42 | Visitor | 2026-02-13 13:42 | 2026-02-13 13:42
388 | 40d11434-b18a-4158-96eb-7ee00c09ba8e | Sarah.ARDIN@education.gov.uk | ARDIN, Sarah | Sarah | ARDIN | Sarah.ARDIN@EDUCATION.GOV.UK |  | 2026-02-13 14:42 | Visitor | 2026-02-13 14:42 | 2026-02-13 14:42
389 | 17cd77e6-269a-4942-b19a-a912028f7c58 | Ria.GODDARD@education.gov.uk | GODDARD, Ria | Ria | GODDARD | Ria.GODDARD@EDUCATION.GOV.UK |  | 2026-02-13 15:31 | Visitor | 2026-02-13 15:31 | 2026-02-13 15:31
390 | f3ab4d7f-fd31-4710-b658-65ada00f1894 | Savannah.ALLEN@education.gov.uk | ALLEN, Savannah | Savannah | ALLEN | Savannah.ALLEN@EDUCATION.GOV.UK |  | 2026-02-24 14:36 | Visitor | 2026-02-13 16:12 | 2026-02-24 14:36
391 | 0b3ddd1b-cbab-49b0-ab3f-1cf4f757191a | Tejas.JINARAL@education.gov.uk | JINARAL, Tejas | Tejas | JINARAL | Tejas.JINARAL@EDUCATION.GOV.UK |  | 2026-02-13 16:18 | Visitor | 2026-02-13 16:12 | 2026-02-13 16:18
392 | 1af71c9e-6bfc-42ad-b362-2b9114c9f25b | Ayaz.AKRAM@education.gov.uk | AKRAM, Ayaz | Ayaz | AKRAM | Ayaz.AKRAM@EDUCATION.GOV.UK |  | 2026-02-25 10:20 | Visitor | 2026-02-13 16:24 | 2026-02-25 10:20
393 | 9b97b77c-8437-4c50-b03e-523f15381d35 | Nic.CHAUHAN@education.gov.uk | CHAUHAN, Nic | Nic | CHAUHAN | Nic.CHAUHAN@education.gov.uk |  | 2026-02-16 10:37 | Visitor | 2026-02-16 10:37 | 2026-02-16 10:37
394 | 67ae4a22-fc1b-4e11-9763-33c0e200e73d | Claire.French@education.gov.uk | FRENCH, Claire1 | Claire | French | Claire.French@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-16 10:38 | 2026-02-16 10:38
395 | aae50ed2-69e1-41e2-923f-d50fbb5d5cba | David.PEARSON@education.gov.uk | PEARSON, David | David | PEARSON | David.PEARSON@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-16 10:38 | 2026-02-16 10:38
396 | 7e8c919c-5c4c-44f6-98e5-745b8c340c35 | Richard.BIELBY@education.gov.uk | BIELBY, Richard | Richard | BIELBY | Richard.BIELBY@education.gov.uk |  | 2026-02-16 10:40 | Visitor | 2026-02-16 10:40 | 2026-02-16 10:40
397 | 48e5c028-0787-42d8-baaa-caffdcf3edac | Sangita.PAUL@education.gov.uk | PAUL, Sangita | Sangita | PAUL | Sangita.PAUL@EDUCATION.GOV.UK |  | 2026-02-16 10:43 | Visitor | 2026-02-16 10:43 | 2026-02-16 10:43
398 | b9146eec-b7bf-4a06-9bfb-f93b4fb9b7e5 | Hal.ANGSEESING@education.gov.uk | ANGSEESING, Hal | Hal | ANGSEESING | Hal.ANGSEESING@EDUCATION.GOV.UK |  | 2026-02-16 10:44 | Visitor | 2026-02-16 10:44 | 2026-02-16 10:44
399 | e6cb94da-76eb-4e7e-9394-2aebd20253e1 | Richard.BRYANT@education.gov.uk | BRYANT, Richard | Richard | BRYANT | Richard.BRYANT@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-16 10:50 | 2026-02-16 10:50
400 | 9ff024ec-e6fa-4c6c-ab4c-ded64713707c | Jenny.ALEXANDER@education.gov.uk | ALEXANDER, Jenny | Jenny | ALEXANDER | Jenny.ALEXANDER@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-16 10:51 | 2026-02-16 10:51
401 | 6c360d49-cd55-497f-8b49-a7d07041fd02 | Hassan.MIR@education.gov.uk | MIR, Hassan | Hassan | MIR | Hassan.MIR@EDUCATION.GOV.UK |  | 2026-02-16 10:51 | Visitor | 2026-02-16 10:51 | 2026-02-16 10:51
402 | 7c0d04e1-8491-42f1-bf2d-27abb65034d4 | Sanjay.SOOD@education.gov.uk | SOOD, Sanjay | Sanjay | SOOD | Sanjay.SOOD@EDUCATION.GOV.UK |  | 2026-02-16 11:47 | Visitor | 2026-02-16 11:47 | 2026-02-16 11:47
403 | 44a031aa-73ea-46de-a063-b3ac719a115d | Megan.ARCHER@education.gov.uk | ARCHER, Megan | Megan | ARCHER | Megan.ARCHER@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-16 11:52 | 2026-02-16 11:52
404 | 05f12707-cf64-4928-a6da-d5b4d96c5870 | James.CHEETHAM@education.gov.uk | CHEETHAM, James | James | CHEETHAM | James.CHEETHAM@EDUCATION.GOV.UK |  | 2026-02-16 12:56 | Visitor | 2026-02-16 12:56 | 2026-02-16 12:56
405 | 67b0fff1-2081-4888-afc5-7d3ecbcb45d9 | Mark.KIDDER@EDUCATION.GOV.UK | KIDDER, Mark | Mark | KIDDER | Mark.KIDDER@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-16 13:19 | 2026-02-16 13:19
406 | 11d4f2f6-f1a7-42c9-93bc-80db538eb7f4 | Lenarts.KEOMEGI@education.gov.uk | KEOMEGI, Lenarts | Lenarts | KEOMEGI | Lenarts.KEOMEGI@EDUCATION.GOV.UK |  | 2026-02-16 15:58 | Visitor | 2026-02-16 15:58 | 2026-02-16 15:58
407 | 610b3e1a-9fe7-4791-b851-14fd22895f93 | Andrew.PROCTOR@education.gov.uk | PROCTOR, Andrew | Andrew | PROCTOR | Andrew.PROCTOR@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-16 17:29 | 2026-02-16 17:29
408 | 82ea9343-ec38-4837-b584-4df689af7aa2 | James.HEATHCOTE@education.gov.uk | HEATHCOTE, James | James | HEATHCOTE | James.HEATHCOTE@EDUCATION.GOV.UK |  | 2026-02-17 10:04 | Visitor | 2026-02-17 10:04 | 2026-02-17 10:04
409 | 6c0dd332-819a-4ddb-b7cb-2e983f03c64d | Ahanzati.AMBITUUNI@EDUCATION.GOV.UK | AMBITUUNI, Ahanzati | Ahanzati | AMBITUUNI | Ahanzati.AMBITUUNI@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-17 10:04 | 2026-02-17 10:05
410 | 03613506-e184-4f0a-9abb-3b11ffcf9f45 | Hannah.GREEN@education.gov.uk | GREEN, Hannah | Hannah | GREEN | Hannah.GREEN@EDUCATION.GOV.UK |  | 2026-02-17 10:08 | Visitor | 2026-02-17 10:08 | 2026-02-17 10:08
411 | 6e617be8-cd8d-49a1-8a3d-de964b9cea3e | Gwen.McGill@education.gov.uk | McGILL, Gwen | Gwen | McGill | Gwen.McGill@EDUCATION.GOV.UK |  | 2026-02-17 10:30 | Visitor | 2026-02-17 10:30 | 2026-02-17 10:30
412 | 24431825-8cab-4f37-b789-39d1a7de0002 | Laura.WALKLETT-LYNCH@education.gov.uk | WALKLETT-LYNCH, Laura | Laura | WALKLETT-LYNCH | Laura.WALKLETT-LYNCH@EDUCATION.GOV.UK |  | 2026-02-17 10:48 | Visitor | 2026-02-17 10:48 | 2026-02-17 10:48
413 | e027ce85-43c0-4f81-ba60-1a972ff37626 | Gemma.DALLMAN@education.gov.uk | DALLMAN, Gemma | Gemma | DALLMAN | Gemma.DALLMAN@EDUCATION.GOV.UK |  | 2026-02-17 12:57 | Visitor | 2026-02-17 11:14 | 2026-02-17 12:57
414 | b4f4c611-81d5-4aa2-926e-a741b5dcf7ab | Peter.YATES@education.gov.uk | YATES-DIGI, Peter | Peter | YATES | Peter.YATES@education.gov.uk |  | 2026-02-17 11:41 | Visitor | 2026-02-17 11:41 | 2026-02-17 11:41
415 | 81d4a12d-4c70-47c9-b96f-a85e71556ac2 | Nithya.JAIGANESH@education.gov.uk | JAIGANESH, Nithya | Nithya | JAIGANESH | Nithya.JAIGANESH@education.gov.uk |  | 2026-02-17 11:42 | Visitor | 2026-02-17 11:42 | 2026-02-17 11:42
416 | d09d684c-85fb-40f6-9cbf-de658409921d | Laura.KING@education.gov.uk | KING, Laura | Laura | KING | Laura.KING@EDUCATION.GOV.UK |  | 2026-02-17 16:22 | Visitor | 2026-02-17 16:22 | 2026-02-17 16:22
417 | 36f0b3e6-e6c7-495b-8ad5-265fe56a66f3 | Tara.WAREHAM@education.gov.uk | WAREHAM, Tara | Tara | WAREHAM | Tara.WAREHAM@EDUCATION.GOV.UK |  | 2026-02-18 09:24 | Visitor | 2026-02-18 09:24 | 2026-02-18 09:24
418 | 3b1f6c2b-a478-4ca8-ae67-10b6d13466f0 | Dean.ELLIOTT@education.gov.uk | ELLIOTT, Dean | Dean | ELLIOTT | Dean.ELLIOTT@EDUCATION.GOV.UK |  | 2026-02-18 10:11 | Visitor | 2026-02-18 10:11 | 2026-02-18 10:11
419 | 217974ae-ef9b-4af1-8883-19245e9a6a8c | Amy.BUSH@education.gov.uk | BUSH, Amy | Amy | BUSH | Amy.BUSH@EDUCATION.GOV.UK |  | 2026-02-18 10:51 | Visitor | 2026-02-18 10:51 | 2026-02-18 10:51
420 | 60359cca-9a13-4955-80bd-006fc0fff47e | Benjamin.DANCE@education.gov.uk | DANCE, Benjamin | Benjamin | DANCE | Benjamin.DANCE@EDUCATION.GOV.UK |  | 2026-02-18 11:07 | Visitor | 2026-02-18 11:07 | 2026-02-18 11:07
421 | ae9caf25-355c-42fb-9331-d9e491f1457d | Nicholas.BURNESS@education.gov.uk | BURNESS, Nicholas | Nicholas | BURNESS | Nicholas.BURNESS@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-18 11:45 | 2026-02-18 11:45
422 | 954bb430-c4d6-4201-8de6-91773b9ac1b9 | Jim.GREGORY@education.gov.uk | GREGORY, Jim | Jim | GREGORY | Jim.GREGORY@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-18 11:46 | 2026-02-18 11:46
423 | 78ae8f4e-92fa-4955-88d8-e40db816e19b | Victoria.WINLOW@education.gov.uk | WINLOW, Victoria | Victoria | WINLOW | Victoria.WINLOW@EDUCATION.GOV.UK |  | 2026-02-18 11:48 | Visitor | 2026-02-18 11:48 | 2026-02-18 11:48
424 | 9ab8a75f-4c40-4f21-982a-9823a1e7b38d | John.ABLETT@education.gov.uk | ABLETT, John | John | ABLETT | John.ABLETT@EDUCATION.GOV.UK |  | 2026-02-18 11:58 | Visitor | 2026-02-18 11:58 | 2026-02-18 11:58
425 | ed709167-ca26-44ee-86f3-4df1b27f8267 | John.WALL@EDUCATION.GOV.UK | WALL, John | John | WALL | John.WALL@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-18 13:41 | 2026-02-18 20:09
426 | 13aaf3f0-8574-4cbf-9a73-69320e7421e0 | James.PEEL@education.gov.uk | PEEL, James | James | PEEL | James.PEEL@EDUCATION.GOV.UK |  | 2026-02-18 14:07 | Visitor | 2026-02-18 14:07 | 2026-02-18 14:07
427 | a0322e0f-496e-40c4-b34e-221c35ba3dca | Marc.BREESE@education.gov.uk | BREESE, Marc | Marc | BREESE | Marc.BREESE@EDUCATION.GOV.UK |  | 2026-02-18 14:09 | Visitor | 2026-02-18 14:09 | 2026-02-18 14:09
428 | 10e1e929-691d-474c-bd14-bb3e15193851 | Grace.VERGHIS@education.gov.uk | VERGHIS, Grace | Grace | VERGHIS | Grace.VERGHIS@EDUCATION.GOV.UK |  | 2026-02-18 14:11 | Visitor | 2026-02-18 14:11 | 2026-02-18 14:11
429 | 76561ade-2278-4491-a583-ac522af1006b | Anita.HOLCROFT@education.gov.uk | HOLCROFT, Anita | Anita | HOLCROFT | Anita.HOLCROFT@EDUCATION.GOV.UK |  | 2026-02-18 14:12 | Visitor | 2026-02-18 14:12 | 2026-02-18 14:12
430 | d26ef77b-1be7-4559-8c4a-3206c0544e68 | Jake.BAXTER@education.gov.uk | BAXTER, Jake | Jake | BAXTER | Jake.BAXTER@EDUCATION.GOV.UK |  | 2026-02-18 14:59 | Visitor | 2026-02-18 14:59 | 2026-02-18 14:59
431 | 5b72706e-b199-4628-9756-0f2f9bf6dd2b | Jon-Pierre.THOMAS@education.gov.uk | THOMAS, Jon-Pierre | Jon-Pierre | THOMAS | Jon-Pierre.THOMAS@EDUCATION.GOV.UK |  | 2026-02-18 20:10 | Visitor | 2026-02-18 20:10 | 2026-02-18 20:10
432 | cc4335c2-3f63-458e-b946-e6b4125c6c12 | Khilat.KHAN@education.gov.uk | KHAN, Khilat | Khilat | KHAN | Khilat.KHAN@EDUCATION.GOV.UK |  | 2026-02-18 20:11 | Visitor | 2026-02-18 20:11 | 2026-02-18 20:11
433 | 712f3b12-9ff9-4804-a54a-325b05b42af5 | Claire-Louise.PATRICK@education.gov.uk | PATRICK, Claire-Louise | Claire-Louise | PATRICK | Claire-Louise.PATRICK@EDUCATION.GOV.UK |  | 2026-02-18 20:11 | Visitor | 2026-02-18 20:11 | 2026-02-18 20:11
434 | 0b92a648-145b-4d6d-b936-4e3ffb115c61 | Niall1.BOOTH@education.gov.uk | BOOTH, Niall1 | Niall1 | BOOTH | Niall1.BOOTH@EDUCATION.GOV.UK |  | 2026-02-18 20:12 | Visitor | 2026-02-18 20:12 | 2026-02-18 20:12
435 | 0cd5a19e-79b8-470d-9d45-0ddcc56afa6b | Mark.CHANDLER@education.gov.uk | CHANDLER, Mark | Mark | CHANDLER | Mark.CHANDLER@education.gov.uk |  | 2026-02-19 11:36 | Visitor | 2026-02-18 20:13 | 2026-02-19 11:36
436 | 3cdcb342-8a03-449a-8463-0f9d07792168 | Joanne.CROOK@education.gov.uk | CROOK, Joanne | Joanne | CROOK | Joanne.CROOK@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-18 21:53 | 2026-02-18 21:53
437 | 85785848-e4bf-4c26-bcc6-585d40151d8e | Paul.TIDMAN@education.gov.uk | TIDMAN, Paul | Paul | TIDMAN | Paul.TIDMAN@EDUCATION.GOV.UK |  | 2026-02-19 09:02 | Visitor | 2026-02-19 09:02 | 2026-02-19 09:02
438 | c880e986-6c5b-4844-a3ab-ac39168ef3c5 | Jodie.LAFFAR@education.gov.uk | LAFFAR, Jodie | Jodie | LAFFAR | Jodie.LAFFAR@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-19 09:39 | 2026-02-19 09:39
439 | 4a707d5f-c00d-4e08-8961-6c3b2be143be | Jake.COHEN@education.gov.uk | COHEN, Jake | Jake | COHEN | Jake.COHEN@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-19 10:05 | 2026-02-19 10:05
440 | b5f01968-21a7-4e97-8aa3-467bd21db0a4 | Daniel.MCCORMACK@education.gov.uk | MCCORMACK, Daniel | Daniel | MCCORMACK | Daniel.MCCORMACK@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-19 10:07 | 2026-02-19 10:07
441 | ad20ab3d-cd9c-42af-b4aa-9682e9adb212 | Sherida.KIRBY@education.gov.uk | KIRBY, Sherida | Sherida | KIRBY | Sherida.KIRBY@EDUCATION.GOV.UK |  | 2026-02-19 10:31 | Visitor | 2026-02-19 10:31 | 2026-02-19 10:31
442 | b9f7f814-0151-4206-8784-0fbfe5ec43ef | Mel.MCGURK@education.gov.uk | MCGURK, Mel | Mel | MCGURK | Mel.MCGURK@EDUCATION.GOV.UK |  | 2026-02-19 11:21 | Visitor | 2026-02-19 11:21 | 2026-02-19 11:21
443 | dab44e29-60c1-46fa-8a0e-904e79de1cf4 | Will.FINN@education.gov.uk | FINN, Will | Will | FINN | Will.FINN@EDUCATION.GOV.UK |  | 2026-02-19 11:54 | Visitor | 2026-02-19 11:50 | 2026-02-19 11:54
444 | c6dd55d5-124c-4d22-a1cb-379ab5f97398 | Ehsan.UDDIN@education.gov.uk | UDDIN, Ehsan | Ehsan | UDDIN | Ehsan.UDDIN@EDUCATION.GOV.UK |  | 2026-02-19 11:50 | Visitor | 2026-02-19 11:50 | 2026-02-19 11:50
445 | 4f2d5a27-fe15-40e5-8447-c396cfba2a77 | Lea.ALIPERTA@education.gov.uk | ALIPERTA, Lea | Lea | ALIPERTA | Lea.ALIPERTA@EDUCATION.GOV.UK |  | 2026-02-19 11:50 | Visitor | 2026-02-19 11:50 | 2026-02-19 11:50
446 | aacc88e8-0ace-4d0d-9b53-66b7bb88509a | Luke.ANSLOW@education.gov.uk | ANSLOW, Luke | Luke | ANSLOW | Luke.ANSLOW@EDUCATION.GOV.UK |  | 2026-02-19 11:54 | Visitor | 2026-02-19 11:54 | 2026-02-19 11:54
447 | 7a571d45-ab32-4398-8c39-40b42dd734a6 | Godwin.OLORUNTOLA@education.gov.uk | OLORUNTOLA, Godwin | Godwin | OLORUNTOLA | Godwin.OLORUNTOLA@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-19 11:54 | 2026-02-19 11:54
448 | 2a1f457c-17d7-4549-abec-8979cf50e36c | Alex6.HARRIS@education.gov.uk | HARRIS, Alex6 | Alex6 | HARRIS | Alex6.HARRIS@EDUCATION.GOV.UK |  | 2026-02-19 12:13 | Visitor | 2026-02-19 12:13 | 2026-02-19 12:13
449 | 40757922-2ddc-4491-ab69-043106176d65 | Ilona.POSLUSZNY@education.gov.uk | POSLUSZNY, Ilona | Ilona | POSLUSZNY | Ilona.POSLUSZNY@EDUCATION.GOV.UK |  | 2026-02-19 13:47 | Visitor | 2026-02-19 13:47 | 2026-02-19 13:47
450 | 56d7f285-26a6-4120-84b5-850e41b59b68 | James.LUMLEY@EDUCATION.GOV.UK | LUMLEY, James | James | LUMLEY | James.LUMLEY@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-19 16:51 | 2026-02-25 15:38
451 | 28a9de61-65a4-440b-910c-4a9d42ea7f57 | Paul.ALLEN@education.gov.uk | ALLEN, Paul | Paul | ALLEN | Paul.ALLEN@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-19 16:55 | 2026-02-19 16:55
452 | 9b8ba1f7-8dbd-49e9-8b98-ff0a62cd4ec6 | Paul2.ALLEN@education.gov.uk | ALLEN, Paul2 | Paul | ALLEN | Paul2.ALLEN@education.gov.uk |  | 2026-03-02 14:44 | Visitor | 2026-02-19 16:55 | 2026-03-02 14:44
453 | 7d34209c-5b92-4703-813f-f56c15f5e11e | Abimbola.ILORI@education.gov.uk | ILORI, Abimbola | Abimbola | ILORI | Abimbola.ILORI@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-19 17:22 | 2026-02-19 17:22
454 | 36c52aab-2752-4fd2-9b81-2590857a62c7 | Munpreet.JHANGRA@education.gov.uk | JHANGRA, Munpreet | Munpreet | JHANGRA | Munpreet.JHANGRA@EDUCATION.GOV.UK |  | 2026-02-19 22:34 | Visitor | 2026-02-19 22:34 | 2026-02-19 22:34
455 | 43eec986-96bd-45d5-9651-3fea8d5f5164 | Harmandip.CHEEMA@education.gov.uk | CHEEMA, Harmandip | Harmandip | CHEEMA | Harmandip.CHEEMA@EDUCATION.GOV.UK |  | 2026-02-20 08:25 | Visitor | 2026-02-20 08:25 | 2026-02-20 08:25
456 | e29d4096-9a88-41e1-9a57-82db880d0474 | Joy.ROBINSON@education.gov.uk | ROBINSON, Joy | Joy | ROBINSON | Joy.ROBINSON@EDUCATION.GOV.UK |  | 2026-02-20 10:13 | Visitor | 2026-02-20 10:13 | 2026-02-20 10:13
457 | 9e53c392-00ba-48b2-a26f-32defe823850 | Howard.STAPLE@education.gov.uk | STAPLE, Howard | Howard | STAPLE | Howard.STAPLE@EDUCATION.GOV.UK |  | 2026-02-20 14:11 | Visitor | 2026-02-20 14:11 | 2026-02-20 14:11
458 | e0572600-13b6-4503-97f4-ed7d2be7fd89 | David.HARTLEY@education.gov.uk | HARTLEY, David | David | HARTLEY | David.HARTLEY@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-20 14:13 | 2026-02-20 14:13
459 | f3e1f612-d430-4f14-b918-df815d949249 | Daniel.MARSDEN@education.gov.uk | MARSDEN, Daniel | Daniel | MARSDEN | Daniel.MARSDEN@EDUCATION.GOV.UK |  | 2026-02-23 07:33 | Visitor | 2026-02-23 07:33 | 2026-02-23 07:33
460 | 02f13b3a-938e-41a3-93df-008d4a8c0ba1 | Tingting.SHU@education.gov.uk | SHU, Tingting | Tingting | SHU | Tingting.SHU@EDUCATION.GOV.UK |  | 2026-02-23 09:19 | Visitor | 2026-02-23 09:19 | 2026-02-23 09:19
461 | 10aa5e5d-3ed9-4878-b4f4-4d4d4aadb16f | Pallavi.KUMAR@education.gov.uk | KUMAR, Pallavi | Pallavi | KUMAR | Pallavi.KUMAR@EDUCATION.GOV.UK |  | 2026-02-23 10:34 | Visitor | 2026-02-23 10:34 | 2026-02-23 10:34
462 | 2ac6c7f9-3df0-4219-9eae-e32ced70f579 | Naomi.LOCKHART@education.gov.uk | LOCKHART, Naomi | Naomi | LOCKHART | Naomi.LOCKHART@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-23 11:44 | 2026-02-23 11:44
463 | edafc6ac-c50f-4187-b97c-06612dd4bc85 | James.WAGEMAKER@education.gov.uk | WAGEMAKER, James | James | WAGEMAKER | James.WAGEMAKER@EDUCATION.GOV.UK |  | 2026-02-23 16:24 | Visitor | 2026-02-23 16:24 | 2026-02-23 16:24
464 | 955adcba-0ae9-4339-9f0a-cdcbc3dc2619 | Robert.GAMMON@education.gov.uk | GAMMON, Robert | Robert | GAMMON | Robert.GAMMON@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-24 12:06 | 2026-02-24 12:06
465 | 686edb48-672d-403f-bc8d-d0a6d672f7df | Jonathan.DORSEY@EDUCATION.GOV.UK | DORSEY, Jonathan | Jonathan | DORSEY | Jonathan.DORSEY@EDUCATION.GOV.UK |  | 2026-02-24 12:29 | Visitor | 2026-02-24 12:29 | 2026-02-24 12:29
466 | 726f66db-1fb2-44e0-bbe3-1f8185fa1696 | Patrick.COOTES@EDUCATION.GOV.UK | COOTES, Patrick | Patrick | COOTES | Patrick.COOTES@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-25 09:09 | 2026-02-25 09:09
467 | ab57d115-730b-48af-8b4e-0425961289cb | Tayyaba.RIAZ-JAMIL@education.gov.uk | RIAZ-JAMIL, Tayyaba | Tayyaba | RIAZ-JAMIL | Tayyaba.RIAZ-JAMIL@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-25 11:37 | 2026-02-25 11:37
468 | 21175a72-ecd1-4a6c-9902-754364e6cc13 | Keisha.HERBERT@education.gov.uk | HERBERT, Keisha | Keisha | HERBERT | Keisha.HERBERT@EDUCATION.GOV.UK |  | 2026-02-25 12:34 | Visitor | 2026-02-25 12:34 | 2026-02-25 12:34
469 | 5eac385b-2282-437a-a9a1-889af562d3ae | Kate.NICOLSON@education.gov.uk | NICOLSON, Kate | Kate | NICOLSON | Kate.NICOLSON@EDUCATION.GOV.UK |  | 2026-02-25 15:15 | Visitor | 2026-02-25 15:15 | 2026-02-25 15:15
470 | e2c04fe8-95f1-4de2-b69c-526709727d9a | Josh.SWALES-DAWSON@education.gov.uk | SWALES-DAWSON, Josh | Josh | SWALES-DAWSON | Josh.SWALES-DAWSON@EDUCATION.GOV.UK |  |  | Visitor | 2026-02-25 16:24 | 2026-02-25 16:24
471 | 7dacda00-2a7b-43da-b500-3529d93ca3d2 | Rachel14.SMITH@education.gov.uk | SMITH, Rachel14 | Rachel | SMITH | Rachel14.SMITH@education.gov.uk |  | 2026-02-26 09:23 | Visitor | 2026-02-26 09:23 | 2026-02-26 09:23
472 | fc69ac7b-024d-42e1-a9f3-f35641fdcbf8 | Pragya.SINGH@education.gov.uk | SINGH, Pragya | Pragya | SINGH | Pragya.SINGH@EDUCATION.GOV.UK |  | 2026-02-26 12:16 | Visitor | 2026-02-26 11:27 | 2026-02-26 12:16
473 | 6de303ab-e6eb-4b22-8fe9-50384aec0955 | Giulio.FOLINO@education.gov.uk | FOLINO, Giulio | Giulio | FOLINO | Giulio.FOLINO@EDUCATION.GOV.UK |  | 2026-02-26 11:59 | Visitor | 2026-02-26 11:55 | 2026-02-26 11:59
474 | 9b00a156-fe58-4b3b-8af4-8713636301fe | Nina.TAYLOR@education.gov.uk | TAYLOR, Nina | Nina | TAYLOR | Nina.TAYLOR@EDUCATION.GOV.UK |  | 2026-02-26 18:40 | Visitor | 2026-02-26 18:40 | 2026-02-26 18:40
475 | 2badd901-40c9-4728-86b8-d259e9e1a572 | Bukurije.BERISHA@EDUCATION.GOV.UK | BERISHA, Bukurije | Bukurije | BERISHA | Bukurije.BERISHA@EDUCATION.GOV.UK |  | 2026-02-27 07:50 | Visitor | 2026-02-27 07:50 | 2026-02-27 07:50
476 | a5e8fb3d-e2dc-4f24-89e1-f1fcc2989a21 | Derek.COOMBES@education.gov.uk | COOMBES, Derek | Derek | COOMBES | Derek.COOMBES@EDUCATION.GOV.UK |  | 2026-02-27 14:59 | Visitor | 2026-02-27 14:59 | 2026-02-27 14:59
477 | 0a7f09ed-e9cc-46b6-a4d1-8d0a86c2571b | Joanna.MCCONVILLE@education.gov.uk | MCCONVILLE, Joanna | Joanna | MCCONVILLE | Joanna.MCCONVILLE@EDUCATION.GOV.UK |  | 2026-03-02 22:07 | Visitor | 2026-03-02 14:01 | 2026-03-02 22:07
478 | f5a89f0a-b41c-4269-947b-3270d673ff74 | Lauren.BATTERSBY@education.gov.uk | BATTERSBY, Lauren | Lauren | BATTERSBY | Lauren.BATTERSBY@EDUCATION.GOV.UK |  | 2026-03-02 15:30 | Visitor | 2026-03-02 15:30 | 2026-03-02 15:30
479 | 8807d580-4a11-40cb-981d-23a5a5528895 | Ola.OKE@education.gov.uk | OKE, Ola | Ola | OKE | Ola.OKE@EDUCATION.GOV.UK |  | 2026-03-02 15:33 | Visitor | 2026-03-02 15:33 | 2026-03-02 15:33
480 | b8406252-abfb-45b1-868e-5830f7b7fb93 | Magnus.HUNTLEY@education.gov.uk | HUNTLEY, Magnus | Magnus | HUNTLEY | Magnus.HUNTLEY@EDUCATION.GOV.UK |  |  | Visitor | 2026-03-02 16:23 | 2026-03-02 16:23
481 | 6cfb2804-3f73-4db0-a6cf-b4ceb8b8aec7 | Lewis12.EVANS@education.gov.uk | EVANS, Lewis12 | Lewis12 | EVANS | Lewis12.EVANS@EDUCATION.GOV.UK |  |  | Visitor | 2026-03-02 17:11 | 2026-03-02 17:11
482 | 9cb84d45-67d8-4a76-9256-6f3e2fbd9699 | Will.LOWE@education.gov.uk | LOWE, Will | Will | LOWE | Will.LOWE@EDUCATION.GOV.UK |  |  | Visitor | 2026-03-02 17:12 | 2026-03-02 17:12
483 | d34760a7-edc4-486a-9aff-c52e174e7cf3 | Justine.HEAD@education.gov.uk | HEAD, Justine | Justine | HEAD | Justine.HEAD@EDUCATION.GOV.UK |  | 2026-03-03 07:53 | Visitor | 2026-03-03 07:53 | 2026-03-03 07:53
484 | 49d77e23-9c2e-48e4-96da-c5dd7cbc2383 | Frederich.MAAFO@education.gov.uk | MAAFO, Frederich | Frederich | MAAFO | Frederich.MAAFO@EDUCATION.GOV.UK |  |  | Visitor | 2026-03-03 14:02 | 2026-03-03 14:02
485 | fad0f32e-451b-4c31-a6d1-2c1daf644815 | Amandeep.SAMRA@education.gov.uk | SAMRA, Amandeep | Amandeep | SAMRA | Amandeep.SAMRA@EDUCATION.GOV.UK |  | 2026-03-03 14:06 | Visitor | 2026-03-03 14:06 | 2026-03-03 14:06
486 | aa5d12c5-e138-44c9-867c-f2ea13846dc4 | Stacy.BROWN@education.gov.uk | BROWN, Stacy | Stacy | BROWN | Stacy.BROWN@EDUCATION.GOV.UK |  | 2026-03-03 17:14 | Visitor | 2026-03-03 17:14 | 2026-03-03 17:14
487 | 6b0ce092-f1e8-4c6b-af06-ef8c3687f277 | Robert.OMALLEY@education.gov.uk | OMALLEY, Robert | Robert | O’MALLEY | Robert.OMALLEY@education.gov.uk |  | 2026-03-05 13:40 | Visitor | 2026-03-05 13:39 | 2026-03-05 13:40
488 | 952d2c38-ac6f-4bf8-8b8a-af5ba79138ca | Jason.POOLE@education.gov.uk | POOLE, Jason | Jason | POOLE | Jason.POOLE@EDUCATION.GOV.UK |  | 2026-03-05 14:14 | Visitor | 2026-03-05 14:14 | 2026-03-05 14:14
489 | 687614fc-aa8b-479b-92b4-ede5da18e3c4 | Harry.WARREN@education.gov.uk | WARREN, Harry | Harry | WARREN | Harry.WARREN@EDUCATION.GOV.UK |  | 2026-03-05 14:27 | Visitor | 2026-03-05 14:27 | 2026-03-05 14:27
490 | c579ac82-bfd8-4c8d-9c17-0769a821b9e8 | Kirsty.TAYLOR@education.gov.uk | TAYLOR, Kirsty | Kirsty | TAYLOR | Kirsty.TAYLOR@EDUCATION.GOV.UK |  | 2026-03-10 15:37 | Visitor | 2026-03-10 15:37 | 2026-03-10 15:37
491 | c9b2bf7d-9d2b-41a9-b8b9-f9eb4b298a6a | Katie.BROOKS@education.gov.uk | BROOKS, Katie | Katie | BROOKS | Katie.BROOKS@EDUCATION.GOV.UK |  | 2026-03-11 15:09 | Visitor | 2026-03-11 14:58 | 2026-03-11 15:09
492 | 2e3004d0-8c16-4d7d-aa74-c01e2af76a67 | Robert.HARRISON@education.gov.uk | HARRISON, Robert | Robert | HARRISON | Robert.HARRISON@EDUCATION.GOV.UK |  | 2026-03-17 09:45 | Visitor | 2026-03-17 09:45 | 2026-03-17 09:45

## BusinessAreas
Id | Name | Description | SortOrder | IsActive | CreatedAt | UpdatedAt
1 | Commercial | Procuring, and supporting the procurement of, goods and services for DfE. | 10 | True | 2025-10-31 11:01 | 2025-11-24 16:24
2 | Customer Experience and Design | Customer Experience and Design | 20 | True | 2025-10-31 11:02 | 2025-11-24 16:24
3 | Enterprise Data for Insight | Internal data and technology | 34 | True | 2025-10-31 11:02 | 2025-11-27 12:07
4 | Children and Families | Services supporting families and children | 7 | True | 2025-10-31 11:02 | 2025-11-27 12:08
5 | Funding and Financial Oversight | Funding services | 50 | True | 2025-10-31 11:03 | 2025-11-26 07:47
6 | Operations and Infrastructure | Internal operations, technology, networks, infrastructure and support. | 60 | True | 2025-10-31 11:03 | 2025-11-24 16:24
7 | Regions - DO NOT USE | Services for academies and trusts | 9999 | True | 2025-10-31 11:04 | 2025-11-27 12:08
8 | Schools Digital | Services supporting teachers and school leaders | 80 | True | 2025-10-31 11:04 | 2025-11-26 07:48
9 | Skills and Growth | Adult education, apprenticeships, and skills development services. | 90 | True | 2025-10-31 11:05 | 2025-11-26 07:49
10 | Strategy and Transformation | Departmental strategy and design | 100 | True | 2025-10-31 11:05 | 2026-01-13 12:22
11 | Regional Digital Services |  | 70 | True | 2025-11-24 11:09 | 2025-11-24 16:24
12 | Sector Facing Services |  | 85 | True | 2025-11-24 11:09 | 2025-11-24 16:24
13 | Central Operations | Governance and assurance function for DDT. | 5 | True | 2025-11-24 11:27 | 2025-11-24 11:27
14 | Enterprise Delivery Service | Enterprise Delivery Service | 36 | True | 2025-11-26 09:08 | 2025-11-27 12:07
15 | Customer Service Enterprise Operations | Customer Service Enterprise Operations | 25 | True | 2025-11-26 09:16 | 2025-11-26 09:16
16 | Cyber Information Security and Data Governance | Cyber, Information Security and Data Governance | 27 | True | 2025-11-26 10:11 | 2026-02-10 07:29
17 | Enterprise Data for Funding and Oversight |  | 32 | True | 2025-11-27 09:55 | 2025-11-27 12:07
18 | Enterprise Data for Access and Sharing |  | 30 | True | 2025-11-27 09:55 | 2026-01-13 12:23
19 | AI Alignment - Now Inactive - sits within Strategy & Transformation | DDT Division lead by Fay Skevington | 0 | True | 2026-01-05 15:14 | 2026-02-11 16:59
20 | Technology Operations and Information Management | Technology Operations and Knowledge Information Management division, provide and support the core technology services required to enable DfE staff to carry out their responsibilities efficiently and securely, both in our offices and remotely. | 105 | True | 2026-01-06 11:19 | 2026-01-13 12:22

## Phases
Id | Name | Description | SortOrder | IsActive | CreatedAt | UpdatedAt
1 | Discovery | Exploring the problem space | 10 | True | 2025-10-31 11:06 | 2025-10-31 11:06
2 | Alpha | Testing options with hypothesis | 20 | True | 2025-10-31 11:06 | 2025-10-31 11:06
3 | Did not progress | Project stopped after discovery or alpha | 30 | True | 2025-10-31 11:06 | 2025-10-31 11:06
4 | Private beta | Building and refining options with a closed group. | 40 | True | 2025-10-31 11:07 | 2025-10-31 11:07
5 | Public beta | Building and refining options with all users. | 50 | True | 2025-10-31 11:07 | 2025-10-31 11:07
6 | Live | Continuously improving | 60 | True | 2025-10-31 11:07 | 2025-10-31 11:07
7 | Decommissioning | Process to retire service. Users migrated, if required. Data archived, and activities managed to safely close service. | 70 | True | 2025-10-31 11:08 | 2025-10-31 11:08
8 | Decommissioned | Service has formally ended. Relevant data archived, users migrated, and formal closure documentation completed. | 80 | True | 2025-10-31 11:08 | 2025-10-31 11:08
9 | Idea |  | 1 | True | 2025-10-31 11:08 | 2025-10-31 11:08
10 | Request |  | 2 | True | 2025-10-31 11:09 | 2025-10-31 13:01
11 | Triage |  | 3 | True | 2025-10-31 11:09 | 2025-10-31 13:01
12 | Explore |  | 4 | True | 2025-10-31 11:09 | 2025-10-31 13:02
13 | Build |  | 5 | True | 2025-10-31 13:02 | 2025-10-31 13:02
14 | Test |  | 6 | True | 2025-10-31 13:02 | 2025-10-31 13:02
15 | Deploy |  | 7 | True | 2025-10-31 13:02 | 2025-10-31 13:02
16 | Run |  | 8 | True | 2025-10-31 13:02 | 2025-10-31 13:02

## ActivityTypes
Id | Name | Description | SortOrder | IsActive | CreatedAt | UpdatedAt
1 | Change/Improve project |  | 10 | True | 2025-11-20 14:08 | 2025-11-20 14:08
2 | Cross-cutting function |  | 20 | True | 2025-11-20 14:08 | 2025-11-20 14:08
3 | Live service |  | 30 | True | 2025-11-20 14:08 | 2025-11-20 14:08
4 | New service in development |  | 40 | True | 2025-11-20 14:08 | 2025-11-20 14:08
5 | Wishlist |  | 50 | True | 2025-11-20 14:08 | 2025-11-20 14:08

## DirectoratesLookup
Id | Name | Description | SortOrder | IsActive | CreatedAt | UpdatedAt
1 | Digital |  | 10 | True | 2025-11-21 14:44 | 2025-11-21 14:44
2 | Data |  | 20 | True | 2025-11-21 14:44 | 2025-11-21 14:44
3 | Technology |  | 30 | True | 2025-11-21 14:44 | 2025-11-21 14:44
4 | SARDIS |  | 40 | True | 2025-11-21 14:46 | 2025-11-21 14:46

## RiskAppetite
Id | Name | Description | SortOrder | IsActive | CreatedAt | UpdatedAt
1 | Averse | Avoidance of risk and uncertainty in achievement of key deliverables or initiatives is key objective. Activities undertaken will only be those considered to carry virtually no inherent risk. | 10 | True | 2025-11-20 14:10 | 2025-11-20 14:10
2 | Minimal | Preference for very safe business delivery options that have a low degree of inherent risk with the potential for benefit/return not a key driver. Activities will only be undertaken where they have a low degree of inherent risk. | 20 | True | 2025-11-20 14:10 | 2025-11-20 14:10
3 | Cautious | Preference for safe options that have low degree of inherent risk and only limited potential for benefit. Willing to tolerate a degree of risk in selecting which activities to undertake to achieve key deliverables or initiatives, where we have identified scope to achieve significant benefit and/or realise an opportunity. Activities undertaken my carry a high degree of inherent risk that is deemed controllable to a large extent. | 30 | True | 2025-11-20 14:10 | 2025-11-20 14:10
4 | Open | Willing to consider all options and choose one most likely to result in successful delivery while providing an acceptable level of benefit. Seek to achieve a balance between a high likelihood of successful delivery and a high degree of benefit and value for money. Activities themselves may potentially carry, or contribute to, a high degree of residual risk. | 40 | True | 2025-11-20 14:10 | 2025-11-20 14:10
5 | Eager | Eager to be innovative and to choose options based on maximising opportunities and potential higher benefit even if those activities carry a very high residual risk. | 50 | True | 2025-11-20 14:11 | 2025-11-20 14:11

## RagStatuses
Id | Name | Description | SortOrder | IsActive | CssClass | CreatedAt | UpdatedAt
1 | Green | Successful delivery of the project/programme to time, cost and quality appears highly likely. The project is on track to hit targets and deliver the intended outcomes and benefits. There are no major outstanding issues at this stage that appear to significantly threaten delivery. | 1 | True | badge badge-green | 2026-01-15 | 2026-02-11 16:32
2 | Amber-Green | Successful delivery appears probable, however constant attention will be needed to ensure risks do not materialise into major issues threatening delivery. There are issues to address in Project Management, Capacity and Capability, and/or Performance. However, it is likely the project will hit targets and deliver the intended outcomes and benefits. | 2 | True | badge badge-amber-green | 2026-01-15 | 2026-02-11 16:32
3 | Amber | Some issues, may impact delivery | 3 | False | badge badge-amber | 2026-01-15 | 2026-01-15 09:06
4 | Amber-Red | Successful delivery of the project/programme is in doubt with major risks apparent in several key areas. Urgent action is needed to ensure these are addressed, and to decide whether resolution is feasible On current trajectory, the project / programme is unlikely to hit the intended targets or deliver intended outcomes and benefits. | 4 | True | badge badge-amber-red | 2026-01-15 | 2026-02-11 16:33
5 | Red | Successful delivery of the project/programme is in significant doubt. There are major issues with project management, capability and capacity, and/or performance which require urgent and decisive action to resolve. On current trajectory, the project/programme will not hit its intended targets or deliver intended outcomes and benefits, therefore, may need re-baselining and/or overall viability re-assessed | 5 | True | badge badge-red | 2026-01-15 | 2026-02-11 16:33

## DeliveryPriorities
Id | Name | Summary | Description | SortOrder | IsActive | CssClass | CreatedAt | UpdatedAt
1 | High | Critical delivery focus | Reserved for urgent projects with significant ministerial or statutory drivers. | 1 | True | badge badge-high | 2025-11-14 | 2025-11-14
2 | Medium | Important delivery focus | Projects with clear departmental value that may tolerate minor delay. | 2 | True | badge badge-medium | 2025-11-14 | 2025-11-14
3 | Low / Optional | Routine delivery focus | Foundational or exploratory work that can flex if higher priorities emerge. | 3 | True | badge badge-low | 2025-11-14 | 2026-02-09 09:29
4 | Critical / Essential |  |  | 0 | True | badge badge-high | 2026-02-09 09:26 | 2026-02-09 09:29

## RiskTiers
Id | Code | Name | Description | Summary | SortOrder | IsActive | CreatedAt | UpdatedAt
1 | PROJECT | Project-level risk | Tactical risks that directly affect the delivery of a single project, product, or service. Managed day-to-day by delivery teams. Examples: Supplier delays, resource gaps, accessibility issues, technology bugs, dependency on another service. | Within a discrete project or service | 1 | True | 2025-10-17 20:25 | 2025-10-17 20:25
2 | PROGRAMME | Programme-level risk | Strategic and operational risks that threaten delivery across multiple projects in a programme. Managed by programme boards and senior responsible owners (SROs). Examples: Conflicting priorities across projects, funding shortfalls, interdependencies, benefits not realised. | Across a set of related projects | 2 | True | 2025-10-17 20:25 | 2025-10-17 20:25
3 | PORTFOLIO | Portfolio-level risk | Risks affecting the achievement of strategic objectives within a portfolio (e.g. Digital Portfolio, Transformation Portfolio). Examples: Competing resource demand, cross-programme technology dependencies, change fatigue. | Across multiple programmes or a business area | 3 | True | 2025-10-17 20:25 | 2025-10-17 20:25
4 | DEPARTMENT | Department-level risk | High-level or strategic risks that could impact departmental objectives or public reputation. Usually captured in the Departmental Risk Register. Examples: Failure to deliver strategic outcomes, budgetary control, workforce capability, cyber security, major policy change. | Across the entire department (e.g. DfE) | 4 | True | 2025-10-17 20:25 | 2025-10-17 20:25
5 | CROSS_GOVERNMENT | Cross-government / systemic risk | Risks that transcend departmental boundaries and could impact public sector capability, continuity, or reputation. Managed by Cabinet Office / HMT via Government Risk Register. Examples: Major data breach across departments, shared platform failure (e.g. Notify, GOV.UK), policy shifts, economic shocks. | Across multiple departments or sectors | 5 | True | 2025-10-17 20:25 | 2025-10-17 20:25

## RiskTypes
Id | Code | Name | Description | Summary | IsActive | Severity | CreatedAt | UpdatedAt
1 | STRATEGY | Strategy risk | Risks arising from identifying and pursuing a strategy that is poorly defined, based on flawed or inaccurate data, or fails to support the delivery of commitments, plans, or objectives due to a changing macro-environment (political, economic, social, technological, environmental, or legislative change). | Poorly defined or outdated strategic direction. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
2 | GOVERNANCE | Governance risk | Risks arising from unclear plans, priorities, authorities, and accountabilities, and/or ineffective or disproportionate oversight of decision-making or performance. | Weak oversight, unclear accountability, or poor governance. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
3 | OPERATIONS | Operations risk | Risks arising from inadequate, poorly designed, ineffective, or inefficient internal processes resulting in fraud, error, impaired customer service, non-compliance, or poor value for money. | Failures in internal processes or delivery operations. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
4 | LEGAL | Legal risk | Risks arising from a defective transaction, a claim being made, or other legal events that result in liability or loss, or from a failure to meet legal or regulatory requirements or to protect assets (e.g. intellectual property). | Exposure to legal, regulatory, or contractual liabilities. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
5 | PROPERTY | Property risk | Risks arising from property deficiencies or poorly designed or ineffective safety management leading to non-compliance, harm, or injury to employees, contractors, service users, or the public. | Property, estate, or safety management deficiencies. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
6 | FINANCIAL | Financial risk | Risks arising from failure to manage finances in line with requirements, leading to poor returns, unmanaged assets or liabilities, lack of value for money, or non-compliant reporting. | Ineffective financial control or value-for-money failure. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
7 | COMMERCIAL | Commercial risk | Risks arising from weaknesses in the management of commercial partnerships, supply chains, or contracts, resulting in poor performance, inefficiency, fraud, or unmet business objectives. | Failures in contracts, suppliers, or commercial management. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
8 | PEOPLE | People risk | Risks arising from ineffective leadership, poor culture, lack of capability or capacity, inappropriate behaviours, industrial action, or breaches of employment law or HR policy. | Leadership, culture, or workforce capacity/capability issues. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
9 | TECHNOLOGY | Technology risk | Risks arising from technology not delivering the expected services due to inadequate or deficient system design, development, performance, or resilience. | Technology failures or insufficient system resilience. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
10 | INFORMATION | Information risk | Risks arising from a failure to produce or use robust, suitable, and appropriate data and information, or to exploit data to its full potential. | Data quality, availability, or misuse issues. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
11 | SECURITY | Security risk | Risks arising from a failure to prevent unauthorised or inappropriate access to information or assets, including cyber security breaches or GDPR non-compliance. | Cyber, data, or physical security breaches. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
12 | PROJECT | Project/Programme risk | Risks that programmes and projects are not aligned with strategic priorities, or fail to deliver intended benefits to time, cost, or quality. | Programme or project delivery failures. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
13 | REPUTATIONAL | Reputational risk | Risks arising from adverse events, ethical breaches, sustainability failures, or poor quality or innovation leading to loss of reputation or trust. | Loss of stakeholder trust or public confidence. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13

## ActionSources
Id | Code | Name | Description | Summary | SortOrder | IsActive | CreatedAt | UpdatedAt
1 | RISK | Risk | Action created to mitigate, treat, or manage a risk. These actions are typically focused on reducing impact or likelihood of risk materialisation. | Action arising from a risk | 1 | True | 2025-10-17 20:35 | 2025-10-17 20:35
2 | ISSUE | Issue | Action created to resolve, workaround, or close an issue. These actions address problems that have already materialised and require remediation. | Action arising from an issue | 2 | True | 2025-10-17 20:35 | 2025-10-17 20:35
3 | MILESTONE | Milestone | Action created to deliver a milestone or track progress towards milestone completion. These actions are typically project or programme delivery activities. | Action arising from a milestone | 3 | True | 2025-10-17 20:35 | 2025-10-17 20:35
4 | SERVICE_ASSESSMENT | Service Assessment | Action created as a result of a service assessment review. These actions may be created by external assessment teams or third-party reviewers and typically address recommendations or compliance requirements. | Action from service assessment | 4 | True | 2025-10-17 20:35 | 2025-10-17 20:35

## Divisions
Id | Name | Description | SortOrder | IsActive | CreatedAt | UpdatedAt
1 | Digital and Technology |  | 10 | True | 2026-02-11 17:45 | 2026-02-11 17:45
2 | Data |  | 20 | True | 2026-02-11 17:46 | 2026-02-11 17:46

## Missions
Id | Title | Description | Theme | OwnerUserId | StartDate | EndDate | Status | IsDeleted | CreatedAt | UpdatedAt
1 | Family Security (tackling child poverty, keeping children safe) |  | Break Down Barriers to Opportunity |  | 2024-12-05 |  | Active | False | 2025-10-31 11:58 | 2025-10-31 11:58
2 | Skills for opportunity and growth |  | Break Down Barriers to Opportunity |  | 2024-12-05 |  | Active | False | 2025-10-31 11:58 | 2025-10-31 11:58
3 | Every child achieving and thriving |  | Break Down Barriers to Opportunity |  | 2024-12-05 |  | Active | False | 2025-10-31 11:59 | 2025-10-31 11:59
4 | Best start in life |  | Break Down Barriers to Opportunity |  | 2024-12-05 |  | Active | False | 2025-10-31 11:59 | 2025-10-31 11:59

## Objectives
Id | Title | Theme | Description | OwnerUserId | ThemeSroUserId | OutcomeSroUserId | MissionId | StartDate | EndDate | Status | RagStatus | SuccessMeasures | ProgressPercent | IsDeleted | CreatedAt | UpdatedAt
1 | Joined-Up services that empower Parents and Carers | Delivering Digitally | [7 empty] | active |  |  |  | False | 2025-10-20 11:48 | 2025-10-20 12:39
2 | Services that help learners progress between education stages | Delivering Digitally | [7 empty] | active |  |  |  | False | 2025-10-20 12:39 | 2025-10-20 13:24
3 | Joined-up school services that support improvement & productivity | Delivering Digitally | [7 empty] | active |  |  |  | False | 2025-10-20 12:40 | 2025-10-20 12:40
4 | Workforce services that address quality and sufficiency gaps | Delivering Digitally | [7 empty] | active |  |  |  | False | 2025-10-20 12:40 | 2025-10-20 12:40
5 | Services that deliver accurate and timely funding to DfE sectors | Delivering Digitally | [7 empty] | active |  |  |  | False | 2025-10-20 12:40 | 2025-10-20 12:40
6 | Trusted data from end to end | Powered by Data | [7 empty] | active |  |  |  | False | 2025-10-20 12:40 | 2025-10-20 12:40
7 | Ready for any question | Powered by Data | [7 empty] | active |  |  |  | False | 2025-10-20 12:41 | 2025-10-20 12:41
8 | Data-driven school system | Powered by Data | [7 empty] | active |  |  |  | False | 2025-10-20 12:41 | 2025-10-20 12:41
9 | Efficient multi-agency information sharing | Powered by Data | [7 empty] | active |  |  |  | False | 2025-10-20 12:41 | 2025-10-20 12:41
10 | AI-enabled business operations | The Right Technology | [7 empty] | active |  |  |  | False | 2025-10-20 12:42 | 2025-10-20 12:42
11 | Unified platforms for scale, efficiency and resilience | The Right Technology | [7 empty] | active |  |  |  | False | 2025-10-20 12:42 | 2025-10-20 12:42
12 | Exceptional workplace technology | The Right Technology | [7 empty] | active |  |  |  | False | 2025-10-20 12:42 | 2025-10-20 12:42
13 | Secure by design | The Right Technology | [7 empty] | active |  |  |  | False | 2025-10-20 12:42 | 2025-10-20 12:42
14 | The right people are in the right roles, with skills matched to organisation needs | DDaT Skills and Expertise | [7 empty] | active |  |  |  | False | 2025-10-20 12:42 | 2025-10-20 12:42
15 | DfE workforce upskilling | DDaT Skills and Expertise | [7 empty] | active |  |  |  | False | 2025-10-20 12:43 | 2025-10-20 12:43
16 | Safe and effective digital and AI tools for teaching and learning | Sector Capability | [7 empty] | active |  |  |  | False | 2025-10-20 12:43 | 2025-10-20 12:43
17 | Safe and effective case management systems in CSC | Sector Capability | [7 empty] | active |  |  |  | False | 2025-10-20 12:43 | 2025-10-20 12:43
18 | All schools to safe and reliable tech baseline | Sector Capability | [7 empty] | active |  |  |  | False | 2025-10-20 12:43 | 2025-10-20 12:43
19 | School workforce digital and data capability building | Sector Capability | [7 empty] | active |  |  |  | False | 2025-10-20 12:44 | 2025-10-20 12:44
20 | Local authority digital and data capability building | Sector Capability | [7 empty] | active |  |  |  | False | 2025-10-20 12:44 | 2025-10-20 12:44

## RagHistory
Id | ProjectId | RagStatusLookupId | RagStatus | Justification | PathToGreen | ChangedByEmail | ChangedByName | ChangedAt
1 | 6 |  | Amber-Green | testing |  | Louise.CLARK@EDUCATION.GOV.UK | Louise.CLARK@EDUCATION.GOV.UK | 2025-11-24 15:15
2 | 6 |  | Amber-Green | testing | testing | Louise.CLARK@EDUCATION.GOV.UK | Louise.CLARK@EDUCATION.GOV.UK | 2025-11-24 15:15
3 | 6 |  | Green | testing | testing | Louise.CLARK@EDUCATION.GOV.UK | Louise.CLARK@EDUCATION.GOV.UK | 2025-11-24 15:15
4 | 179 |  | Green | Initial status. |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk | 2025-11-25 12:02
5 | 196 |  | Amber-Green | Project is AG as project is on-track but recruitment has roles to be filled to start full delivery |  | Ruth.MEDLOCK@EDUCATION.GOV.UK | Ruth.MEDLOCK@EDUCATION.GOV.UK | 2025-11-28 11:16
6 | 196 |  | Amber-Green | Project is AG as project is on-track but recruitment has roles to be filled to start full delivery | Chasing through Commercial to land the resources | Ruth.MEDLOCK@EDUCATION.GOV.UK | Ruth.MEDLOCK@EDUCATION.GOV.UK | 2025-11-28 11:16
7 | 144 |  | Amber-Green |  | Limitations with staff leave/retention | Ruth.MEDLOCK@EDUCATION.GOV.UK | Ruth.MEDLOCK@EDUCATION.GOV.UK | 2025-11-28 11:36
8 | 143 |  | Amber-Green |  | We expect the TEC forms commission to be completed in the next few weeks which will alleviate pressure and move us closer to returning to green. | Ruth.MEDLOCK@EDUCATION.GOV.UK | Ruth.MEDLOCK@EDUCATION.GOV.UK | 2025-11-28 11:46
9 | 143 |  | Amber-Green | Currently we have a number of high profile and competing commissions which is stretching our resource and capacity, this has been exacerbated by a priority tech forms commission which is causing delays. | We expect the TEC forms commission to be completed in the next few weeks which will alleviate pressure and move us closer to returning to green. | Ruth.MEDLOCK@EDUCATION.GOV.UK | Ruth.MEDLOCK@EDUCATION.GOV.UK | 2025-11-28 11:46
10 | 144 |  | Amber-Green | Limited resources due to staff leave and significant risks around talent retention | Limitations with staff leave/retention | Ruth.MEDLOCK@EDUCATION.GOV.UK | Ruth.MEDLOCK@EDUCATION.GOV.UK | 2025-11-28 11:52
12 | 53 |  | Amber-Green | User figures for HfEYP in October stayed consistent with the September peak, with over 120,000 page views. 'Amber' status reflects EYCDT where reduced policy team capacity, escalated from a risk to an issue, limits changes digital can action to make training more inclusive for reception settings. |  | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2025-12-03 15:47
13 | 53 |  | Amber-Green | User figures for HfEYP in October stayed consistent with the September peak, with over 120,000 page views. 'Amber' status reflects EYCDT where reduced policy team capacity, escalated from a risk to an issue, limits changes digital can action to make training more inclusive for reception settings. | We’re giving policy a clear, prioritised list of requests to ensure feedback on the most urgent items. We’re also adjusting the roadmap to focus on work needing minimal policy input (e.g. UR for pre-module confidence checks) until capacity improves and offering support by reviewing video scripts or SME draft content as it is returned. | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2025-12-03 15:47
14 | 24 |  | Amber-Red | Work continues in the assessment space, focussing on direct observations, and is progressing according to the digital roadmap; however, this roadmap is based on the current shape of the programme which is not fully aligned with the views of the new minister. There is a risk that developing the digital service based on unclear programme requirements does not deliver optimal value. |  | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2025-12-03 15:58
15 | 24 |  | Amber-Red | Work continues in the assessment space, focussing on direct observations, and is progressing according to the digital roadmap; however, this roadmap is based on the current shape of the programme which is not fully aligned with the views of the new minister. There is a risk that developing the digital service based on unclear programme requirements does not deliver optimal value. | The team are working closely with policy colleagues to help support discussions with the new minister over these coming weeks, and preparing for a potential shift from the current portfolio-based assessment model to one more closely aligned with that of the Teachers Early Career Framework. | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2025-12-03 15:58
16 | 133 |  | Green | Broadly on track with no major issues |  | Tracey.DALE@EDUCATION.GOV.UK | Tracey.DALE@EDUCATION.GOV.UK | 2025-12-04 19:19
17 | 17 |  | Amber-Green | Overall Rag is Amber. The API and Lakehouse are being refactored and due to being held up with issues with commercials with system C impacting schedule. | Refactor of Silver and gold layers and Commercials in place and approved, draft commercials with System C & Azeus have signed . | Tracey.DALE@EDUCATION.GOV.UK | Tracey.DALE@EDUCATION.GOV.UK | 2025-12-04 19:27
18 | 135 |  | Green | Green for overall Schedule: We are on track to deliver Results amended data which includes two versions. The initial version with quality assurance feedback, then the second and final version in the new year which will also be quality assured. |  | Tracey.DALE@EDUCATION.GOV.UK | Tracey.DALE@EDUCATION.GOV.UK | 2025-12-04 19:56
19 | 153 |  | Amber-Green | Delivery has been split into 2 phases to enable DEI to be removed from the solution by April 2026. Replanning Phase 1 and cutover estimates to ensure we can meet targets. |  | Tracey.DALE@EDUCATION.GOV.UK | Tracey.DALE@EDUCATION.GOV.UK | 2025-12-04 19:57
20 | 153 |  | Amber-Green | Delivery has been split into 2 phases to enable DEI to be removed from the solution by April 2026. Replanning Phase 1 and cutover estimates to ensure we can meet targets. | Delivery has been split into 2 phases to enable DEI to be removed from the solution by April 2026. Replanning Phase 1 and cutover estimates to ensure we can meet targets. | Tracey.DALE@EDUCATION.GOV.UK | Tracey.DALE@EDUCATION.GOV.UK | 2025-12-04 19:57
21 | 179 |  | Amber-Green | Internal auditing team has been disbanded and now audits are coming to Jake which is not his role to do audits. | Either recruit an auditor role, or ensure all audits are procured externally. | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk | 2025-12-04 23:26
22 | 72 |  | Amber-Green | Risks around readiness of AI tools for internal delivery which could lead to portfolios pursing AI based solutions which do not align with expects standards and impact security. | Increase Governance. Implement comms plan. | Tracey.DALE@EDUCATION.GOV.UK | Tracey.DALE@EDUCATION.GOV.UK | 2025-12-09 14:03
23 | 167 |  | Amber-Green | Still waiting to engage with internal infrastruture engineer | engage infrastructure engineer and link to live sharepoint library | Tracey.DALE@EDUCATION.GOV.UK | Tracey.DALE@EDUCATION.GOV.UK | 2025-12-15 13:57
24 | 202 |  | Green | Our product manager has limited capacity in addition to this the solution is looking to be more around the quality and timeliness of data but not an issue with real time data. | Our product manager has limited capacity in addition to this the solution is looking to be more around the quality and timeliness of data but not an issue with real time data. | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2025-12-18 13:00
25 | 202 |  | Green | Project complete |  | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2025-12-18 13:00
26 | 71 |  | Amber-Green | The lack of a joined-up operating model in DDT means Enterprise Architecture is unable to drive strategic decision-making in DfE, leading to sub-optimal / inconsistent delivery and operations, where efficiency opportunities are lost and cost/risk increases for DfE. | Influence DDT operating model development with target architecture / model, grow EA / Business Architecture capability in both the architecture team and across portfolios, drive alignment with the target architecture in all portfolios and domains, and with Service Delivery Revolution. | Tracey.DALE@EDUCATION.GOV.UK | Tracey.DALE@EDUCATION.GOV.UK | 2025-12-18 13:07
27 | 208 |  | Amber-Red | Overall delivery confidence is Amber/Red due to the unconfirmed EdTech scope and providers. There is the unknown financial impact of supplier agreements, and the risk of delays caused by a late start and commercial challenges, despite the team’s accelerated efforts to meet the March deadlines. | Agree the scope and tools for EdTech. Commercial engagement with EdTech to understand if any financial implications. | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-01-07 15:59
28 | 200 |  | Amber-Green | The programme is delivering sensitive change, some of which is waiting on senior permissions to enable us to mobilise the programme under the defined scope. | We are planning communications materials to mitigate key risks as the top priority. | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-01-07 16:58
29 | 196 |  | Green | See update | Chasing through Commercial to land the resources | Ruth.MEDLOCK@EDUCATION.GOV.UK | Ruth.MEDLOCK@EDUCATION.GOV.UK | 2026-01-14 08:47
30 | 1 | 1 | Green | Delivery on track. |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk | 2026-01-15 09:14
31 | 15 | 2 | Amber-Green | Significant amount of change to merge 20 manuals, and a range of guidance. Moving to Amber-Green due to removal of "Amber" | Good planning, product and delivery management for the project with the HOPS. | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk | 2026-01-15 10:49
32 | 6 |  | Amber-Green | Resource from DesignOps has dropped off - rescoping work to ensure deliverables are realistic | testing | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-01-15 16:57
33 | 159 | 2 | Amber-Green | Work has been paused whilst other business priorities (MOG with DWP) and decisions (Future design of DDT and underpinning divisions) are concluded. |  | Stuart.BALNAVES@EDUCATION.GOV.UK | Stuart.BALNAVES@EDUCATION.GOV.UK | 2026-01-28 14:03
34 | 159 |  | Amber-Green | Work has been paused whilst other business priorities (MOG with DWP) and decisions (Future design of DDT and underpinning divisions) are concluded. | Work for transition of skills work is progressing as planned and awaiting agreement with DWP for next steps. Clear accountability internally has supported this work. Awaiting decision as to future shape of DDT (Through appointment of new Director) expect this to conclude in March 2026. Work will re-commence from here. | Stuart.BALNAVES@EDUCATION.GOV.UK | Stuart.BALNAVES@EDUCATION.GOV.UK | 2026-01-28 14:06
41 | 146 |  | Amber-Green | Some final policy questions to be confirmed but confidence in MVS delivery for April is higher. | Surfacing our outstanding questions to policy. | Rose.DUNSTALL@EDUCATION.GOV.UK | Rose.DUNSTALL@EDUCATION.GOV.UK | 2026-01-29 15:08
42 | 126 |  | Amber-Green | Currently on track, a few areas still to clarify but confidence is high | Working across teams to resolve. | Rose.DUNSTALL@EDUCATION.GOV.UK | Rose.DUNSTALL@EDUCATION.GOV.UK | 2026-01-29 15:10
43 | 154 |  | Amber-Green | Delay in go live - delivery date pushed back | N/A | Rose.DUNSTALL@EDUCATION.GOV.UK | Rose.DUNSTALL@EDUCATION.GOV.UK | 2026-01-29 15:12
44 | 147 |  | Amber-Green | Delay in delivery until April due to reprioritisation. | AS SMT are supporting any ways we can bring the work back into 25-26. | Rose.DUNSTALL@EDUCATION.GOV.UK | Rose.DUNSTALL@EDUCATION.GOV.UK | 2026-01-29 15:14
46 | 80 |  | Amber-Green | Issues: 1) Lack of clarity on financial processes in-year and in business planning. There is a risk that we do not secure enough in business planning to continue the rollout to new professions and to accommodate allowance changes as people develop. Close working with finance colleagues on this. 2) Capacity of DDs and teams to provide information and participate in recruitment and assessment. 3) Capacity of CBP team - two people – is limited. | This is a BAU activity which us unlikely to ever be completely green as there will always be blockers and risks but it continues to provide strong vfm so no major cause for concern. | Catherine.WILSON@EDUCATION.GOV.UK | Catherine.WILSON@EDUCATION.GOV.UK | 2026-01-29 15:40
47 | 137 |  | Amber-Green | Pending service assessment and transition to NCS who are onboarding a receiving team currently. | No reds in Service Assessment and onboarding team ready to transition to | Kuldip.OSBORNE@EDUCATION.GOV.UK | Kuldip.OSBORNE@EDUCATION.GOV.UK | 2026-01-29 16:09
48 | 56 |  | Amber-Red | We know the current digital product does not meet users needs. By shifting effort to ensuring the product is scalable, future‑proof design and architecture, we expect smoother delivery and the ability to move at greater scale. | ​ Our path to green relies on completing and agreeing feasibility against the agreed proposition. Once that’s done, we can move into scalable design with confidence in the approach. | Shelley.BRIGGS@EDUCATION.GOV.UK | Shelley.BRIGGS@EDUCATION.GOV.UK | 2026-02-02 08:07
49 | 87 |  | Green | N/A This is a duplicate entry |  | Shelley.BRIGGS@EDUCATION.GOV.UK | Shelley.BRIGGS@EDUCATION.GOV.UK | 2026-02-02 08:08
50 | 164 |  | Green | This was Green in Burts last input, dont know its been caried over as Amber green. project is on track. |  | Helen.TAVERNER@EDUCATION.GOV.UK | Helen.TAVERNER@EDUCATION.GOV.UK | 2026-02-02 10:21
51 | 160 |  | Green | This was GREEN in Burts last entry, so not sure why its Amber Green here. Project on track |  | Helen.TAVERNER@EDUCATION.GOV.UK | Helen.TAVERNER@EDUCATION.GOV.UK | 2026-02-02 10:29
52 | 163 |  | Amber-Green | We still have the ambition to deliver within the original timeline (31/3/2026) however, this work may still extend to July 2026 given previous complications and delays. We will have a better understanding of the timeline once the approved option paper is delivered to IT. Keeping the rating as Amber due to this. | We still have the ambition to deliver within the original timeline (31/3/2026) however, this work may still extend to July 2026 given previous complications and delays. We will have a better understanding of the timeline once the approved option paper is delivered to IT. Keeping the rating as Amber due to this. | Helen.TAVERNER@EDUCATION.GOV.UK | Helen.TAVERNER@EDUCATION.GOV.UK | 2026-02-02 10:31
53 | 73 |  | Amber-Green | The project is waiting on the last upload to happen, but this requires Service Now team to make the update. This has been scheduled for w/c 9th March on the basis the SN upgrade all goes to plan without any issues. | Final bulk upload | Ushma.GILL@EDUCATION.GOV.UK | Ushma.GILL@EDUCATION.GOV.UK | 2026-02-02 12:07
54 | 206 |  | Amber-Green | Overall delivery confidence continues to be Amber/Green, scope on track, no significant risks or issues identified. We remain on track for the March deadline, with workstream re-alignment planning in progress. | Complete refinement of the detailed workstream plan and conclude re‑alignment planning to confirm all March‑critical deliverables | Lorraine.COLEY@EDUCATION.GOV.UK | Lorraine.COLEY@EDUCATION.GOV.UK | 2026-02-02 12:51
55 | 44 | 1 | Green | all major milestones achieved, currently in a BAU state and have been since October 2025 |  | Kristi.BEAK@EDUCATION.GOV.UK | Kristi.BEAK@EDUCATION.GOV.UK | 2026-02-02 13:53
56 | 91 | 1 | Green | No issues and progressing smoothly. |  | Joe.YOUNG@EDUCATION.GOV.UK | Joe.YOUNG@EDUCATION.GOV.UK | 2026-02-02 15:25
57 | 186 | 1 | Green | Deliverables are progressing against miletone |  | Angela.SCALE@EDUCATION.GOV.UK | Angela.SCALE@EDUCATION.GOV.UK | 2026-02-02 15:32
58 | 153 | 1 | Green | Delivery has been split into 2 phases to enable DEI to be removed from the solution by April 2026. Replanning Phase 1 and cutover estimates to ensure we can meet targets. | Delivery has been split into 2 phases to enable DEI to be removed from the solution by April 2026. Replanning Phase 1 and cutover estimates to ensure we can meet targets. | Daniel.KUMAR@EDUCATION.GOV.UK | Daniel.KUMAR@EDUCATION.GOV.UK | 2026-02-02 16:00
59 | 182 | 2 | Amber-Green | Working through user feedback |  | Angela.SCALE@EDUCATION.GOV.UK | Angela.SCALE@EDUCATION.GOV.UK | 2026-02-02 16:10
60 | 182 |  | Amber-Green | Working through feedback from users. | Scheduling a DAC audit and peer review service assessment | Angela.SCALE@EDUCATION.GOV.UK | Angela.SCALE@EDUCATION.GOV.UK | 2026-02-02 16:14
61 | 45 | 2 | Amber-Green | Due to tight delivery timescale and RBAC design slightly delayed due to a decision required on phase 2 and unplanned emergency team leave. |  | Daniel.KUMAR@EDUCATION.GOV.UK | Daniel.KUMAR@EDUCATION.GOV.UK | 2026-02-02 16:38
62 | 45 |  | Amber-Green | Due to tight delivery timescale and RBAC design slightly delayed due to a decision required on phase 2 and unplanned emergency team leave. | Production infrastructure to be built. Can pick this up now as a decision on phase 2 approach has been made to continue to develop the calculation engine in Databricks. | Daniel.KUMAR@EDUCATION.GOV.UK | Daniel.KUMAR@EDUCATION.GOV.UK | 2026-02-02 16:39
63 | 188 | 1 | Green | Service in scope has now been confirmed |  | Angela.SCALE@EDUCATION.GOV.UK | Angela.SCALE@EDUCATION.GOV.UK | 2026-02-02 16:41
64 | 200 |  | Amber-Green | The programme is delivering sensitive change, some of which is waiting on senior permissions to enable us to mobilise the programme under the defined scope. | We are planning communications materials to mitigate key risks as the top priority. | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-02-02 17:00
65 | 136 |  | Green | Broadly on track |  | Daniel.KUMAR@EDUCATION.GOV.UK | Daniel.KUMAR@EDUCATION.GOV.UK | 2026-02-02 17:02
66 | 220 |  | Amber-Green | Project is awaiting resource (action in progress). Once resource in place, status can be changed to green. | Awaiting resource | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-02-02 17:04
67 | 134 |  | Green | Broadly on track |  | Daniel.KUMAR@EDUCATION.GOV.UK | Daniel.KUMAR@EDUCATION.GOV.UK | 2026-02-02 17:06
68 | 221 |  | Amber-Green | Engagement with stakeholders has started but awaiting Business Analysis resource starting before can start the actual capability review work. Status will be Green once we have confirmed date for BA starting which is due imminently. | Awaiting BA resource | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-02-02 17:09
69 | 204 |  | Green | Progressing to plan |  | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-02-02 17:14
70 | 135 |  | Green | Green for overall Schedule: We are on track to deliver Results amended data which includes two versions. The initial version with quality assurance feedback, then the second and final version in the new year which will also be quality assured. |  | Daniel.KUMAR@EDUCATION.GOV.UK | Daniel.KUMAR@EDUCATION.GOV.UK | 2026-02-02 17:15
71 | 46 |  | Green | Broadly on track |  | Daniel.KUMAR@EDUCATION.GOV.UK | Daniel.KUMAR@EDUCATION.GOV.UK | 2026-02-02 17:22
72 | 210 |  | Amber-Green | Currently inducting our architect | Once architect is fully inducted we should be green | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-02-02 18:45
73 | 229 |  | Green | on track |  | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-02-02 18:47
74 | 228 |  | Green | on track |  | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-02-02 18:47
75 | 224 |  | Green | on track |  | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-02-02 18:48
76 | 227 |  | Green | Programme is currently progressing well towards interim goals to deliver a POC within the FY. Startegy work next FY will focus on use cases, and cross governemnt link up. |  | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-02-02 18:49
77 | 230 |  | Amber-Green | This workstream is in the early stages. RAG remains AmberGreen until the plan is agreed and implementation begins. | progression of planning and implementation | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-02-02 18:50
78 | 223 |  | Amber-Green | Overall position is good, but some uncertainty remains around objectives, especially around the work on SEND data. | Agreement need on objectives | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-02-02 18:50
79 | 225 |  | Amber-Green | Engagement with the pillars is going well and we are capturing their priorities. Test and learn approach on how best to support conversations in DDaT Committee. The next phase around strategic prioritisation might prove to be tricky, hence amber/green rather than green | agree strategic prioritisation milestones | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-02-02 18:52
80 | 226 |  | Amber-Green | Just started | planning milestones and technical redesign in progress | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-02-02 18:53
81 | 211 |  | Green | Project is paused whilst procurement options are explored |  | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-02-02 18:56
82 | 122 |  | Amber-Green | some project delays and missed milestones but we are assured that this will not affect delivery | monitoring delays and milestones | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-02-02 19:01
83 | 141 |  | Green | on track |  | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-02-02 19:02
84 | 184 | 2 | Amber-Green | Some work still required to address ownership and measurement on a minority of controls in the foundation systems space |  | Mark2.PHILLIPS@EDUCATION.GOV.UK | Mark2.PHILLIPS@EDUCATION.GOV.UK | 2026-02-02 19:45
85 | 184 |  | Amber-Green | Some work still required to address ownership and measurement on a minority of controls in the foundation systems space | Create a governance mechanism to be able to address controls where ownership is not aligned with area of responsibility which could fix the issue Address measurement issues with regard to Group memberships and / or naming of policies causing a red measurement when control is in place (Dev time constraint) | Mark2.PHILLIPS@EDUCATION.GOV.UK | Mark2.PHILLIPS@EDUCATION.GOV.UK | 2026-02-02 19:48
86 | 185 | 2 | Amber-Green | Governance mechanism to escalate risk is struggling to operate with low levels of risk input from the assurance process. This is being addressed with an iteration to the assurance mechanism but will take time to show whether this addresses the issue and allows the governance escalations to work effectively |  | Mark2.PHILLIPS@EDUCATION.GOV.UK | Mark2.PHILLIPS@EDUCATION.GOV.UK | 2026-02-02 19:57
87 | 185 |  | Amber-Green | Governance mechanism to escalate risk is struggling to operate with low levels of risk input from the assurance process. This is being addressed with an iteration to the assurance mechanism but will take time to show whether this addresses the issue and allows the governance escalations to work effectively | By end of February Iteration of the CIS Risk assessment mechanism to address issues with risk thresholds. Creation of a rollout plan for the CIS assessment for lower criticality services in line with the SCA By end of March Monitor input to the governance mechanism to evaluate success of CIS update | Mark2.PHILLIPS@EDUCATION.GOV.UK | Mark2.PHILLIPS@EDUCATION.GOV.UK | 2026-02-02 20:02
88 | 184 |  | Amber-Green | Some work still required to address ownership and measurement on a minority of controls in the foundation systems space | Create a governance mechanism to be able to address controls where ownership is not aligned with area of responsibility which could fix the issue - GRC - By end of March Address measurement issues with regard to Group memberships and / or naming of policies causing a red measurement when control is in place (Dev time constraint) - By end March | Mark2.PHILLIPS@EDUCATION.GOV.UK | Mark2.PHILLIPS@EDUCATION.GOV.UK | 2026-02-02 20:03
89 | 187 | 1 | Green | Contact and governance is now in place and this has transitioned to business as usual |  | Angela.SCALE@EDUCATION.GOV.UK | Angela.SCALE@EDUCATION.GOV.UK | 2026-02-02 21:23
90 | 190 |  | Amber-Green | See update text for reason. | To agree next steps for mitigating the risks outlined below and redefine the role of the current website in meeting the broader digital parenting hub commitments outlined in the BSiL strategy. | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2026-02-03 10:16
91 | 25 |  | Green | Discovery completed successfully. |  | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2026-02-03 10:17
92 | 191 |  | Green | See update text. |  | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2026-02-03 10:19
93 | 193 |  | Green | Performance Summary (15/12/25 – 28/01/26) The site recorded 10,730 sessions, with 9,959 unique users and 9,815 new users during this reporting period. Average engagement remained strong, with users spending 1 minute 56 seconds actively engaged on the site. Support content pages continued to perform well. High‑traffic pages included Home, Leaving Care Allowance, Higher Education Bursary, and Your Rights, all sustaining strong user engagement. The average scroll depth increased to 55.7%, showing deeper content interaction across long‑form pages. The translate function was used 33 times, the print function 7 times, and there were 223 outbound link clicks, indicating ongoing use of key features and strong progression from guidance to external services. Traffic analysis shows that Direct and Organic Search continue to dominate acquisition, with Direct accounting for 329 new users and Organic Search for 287, together representing around 90% of all new user journeys. |  | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2026-02-03 10:24
94 | 189 |  | Green | on track |  | Tracey.DALE@EDUCATION.GOV.UK | Tracey.DALE@EDUCATION.GOV.UK | 2026-02-03 12:33
95 | 17 |  | Amber-Green | The API and Lakehouse are being refactored | Refactor of Silver and gold layers and Commercials in place and approved, draft commercials with System C & Azeus have signed . | Amanda.STRINE@EDUCATION.GOV.UK | Amanda.STRINE@EDUCATION.GOV.UK | 2026-02-03 12:54
96 | 6 |  | Amber-Green | Reduced pressure on delivery as core features have been delivered. Still reliant on Andy Jones as developer. | Make more of the product configurable and work with ServiceNow team with integration into CMDB/CSDM model. | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk | 2026-02-03 13:01
97 | 27 |  | Amber-Red | No Change. | Same as last month: Escalation of concerns about NHSE engagement | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2026-02-03 13:16
98 | 192 |  | Green | Discovery completed successfully. |  | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2026-02-03 13:18
99 | 53 |  | Amber-Green | Its actually Amber but that option has gone? | We continue to provide policy with a clear, prioritised list of requests to support progress on the most urgent items. We have reviewed returned video scripts and SME draft content, but these remain dependent on policy review and the required clearance stages | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2026-02-03 13:22
100 | 195 |  | Amber-Green | No change | Agree non project team owner for accreditation process issues. Continue to work with 3rd parties to ensure all can adopt solution. | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2026-02-03 13:24
101 | 155 |  | Green | DfE site has been soft launched, and the team are on track to meet the timescales for the school's email and Campaign launch. |  | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2026-02-03 13:25
102 | 104 |  | Green | Deliver Phase 1a Alpha outputs (problem statement, day‑5 dataset, case‑tracking prototype, feasibility assessment), implement tactical fixes to stabilise operations, provide evidence to inform a safe Beta decision, secure SRO approval for Phase 1b, maintain CPA alignment, ensure strong governance and separation of Alpha/tactical work, and confirm continued analytical capability via the NCVPP/College of Policing extension. |  | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2026-02-03 13:26
103 | 24 |  | Amber-Red | The digital team completed its work at the end of last year following a shift in ministerial direction: the programme will now be supplier-led, and the supplier will provide the digital learning platform instead of DfE developing it in-house. The programme has also expanded to cover early career development, advanced child protection principles, and leadership, and is now called the Social Work National Professional Development Programme. Digital continues to advise and support policy with new digital requirements and procurement. | n/a | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2026-02-03 13:28
104 | 48 |  | Amber-Red | The dedicated digital team for SfSW was stepped down late last year as there is no ongoing need for active development. The site remains live with static content, supported by our technical architect to ensure service continuity. Digital is working with policy on the long-term plan for the site and any interim content updates needed. | n/a | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2026-02-03 13:29
105 | 72 | 2 | Amber-Green | Risks around readiness of AI tools for internal delivery which could lead to portfolios pursing AI based solutions which do not align with expects standards and impact security. Some blockers in ED Chat and Records management poc impacting schedule. | Increase Governance. Implement comms plan. | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-03 13:54
106 | 72 |  | Amber-Green | Risks around readiness of AI tools for internal delivery which could lead to portfolios pursing AI based solutions which do not align with expects standards and impact security. Some blockers in ED Chat and Records management poc impacting schedule. | Increase Governance. Implement comms plan. | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-03 14:02
107 | 167 |  | Red | "The project has been assigned a Red RAG status due to a significant delivery risk identified during recent planning recalibration. Following a detailed review of scope, tasks, and dependencies, the team has confirmed that the remaining workload equates to approximately six months of effort, while the current project timeline allows for only three months of delivery time. Updated delivery planning and sequencing work has highlighted that the original estimates and assumptions no longer align with what is required to meet the agreed outcomes. As a result, the project is now operating under a schedule shortfall, with no viable contingency within the current timeframe. This Red status reflects the project’s inability to deliver to scope within the existing plan without intervention, such as a revised scope, or a change to the delivery timeline with supporting budget. Further work is underway to develop mitigation options and present a revised, achievable delivery approach." | If ownership of the project remains with the existing contracted team, delivery of the remaining work can be completed within the proposed three‑month extension of the private Beta. To avoid further delays, the project should not be transitioned to a new team, as onboarding and knowledge transfer would extend timelines beyond the current three‑month window. Maintaining continuity with the current team will return the item to a viable plan and move it toward Green. | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-02-03 14:14
108 | 71 |  | Amber-Green | The lack of a joined-up operating model in DDT means Enterprise Architecture is unable to drive strategic decision-making in DfE, leading to sub-optimal / inconsistent delivery and operations, where efficiency opportunities are lost and cost/risk increases for DfE. | Influence DDT operating model development with target architecture / model, grow EA / Business Architecture capability in both the architecture team and across portfolios, drive alignment with the target architecture in all portfolios and domains, and with Service Delivery Revolution. | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-03 14:20
109 | 69 | 2 | Amber-Green | No capacity for any additional work or incident resolution from SDT team resource – if urgent development/resolution of incidents is required for EDD, ICA, IEBT, SISL or SDT supported EDD services we will be unable to do this due to team being at capacity and no additional resource available. |  | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-03 14:33
110 | 69 |  | Amber-Green | No capacity for any additional work or incident resolution from SDT team resource – if urgent development/resolution of incidents is required for EDD, ICA, IEBT, SISL or SDT supported EDD services we will be unable to do this due to team being at capacity and no additional resource available. | Current team is stretched and at risk of burnout, no capacity for incident resolution, high priority work or illness cover if required. Paused work for improvements that aren't essential. CBP now in place although still awaiting CRM developer recruitment | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-03 14:34
111 | 67 | 1 | Green | In beta testing: (1) Per-workspace feature flags , allows us to opt-in individual workspaces to new features so teams can test new functionality and provide feedback (2) Custom fields - Collect more data from users when they subscribe to your API (3) Webhooks - Send subscription events (create/update/delete) to external systems to allowing tracking/authorisation of API users In alpha testing: API import consolidation – Will allow users to import any kind of API using the same consistent JSON definition file format as the API export feature. API analytics phase 1 (senior managers) - building working prototypes UX for home page + onboarding & service design Migrations and onboarding ongoing |  | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-03 14:49
112 | 67 |  | Green | In beta testing: (1) Per-workspace feature flags , allows us to opt-in individual workspaces to new features so teams can test new functionality and provide feedback (2) Custom fields - Collect more data from users when they subscribe to your API (3) Webhooks - Send subscription events (create/update/delete) to external systems to allowing tracking/authorisation of API users In alpha testing: API import consolidation – Will allow users to import any kind of API using the same consistent JSON definition file format as the API export feature. API analytics phase 1 (senior managers) - building working prototypes UX for home page + onboarding & service design Migrations and onboarding ongoing | Status: Decom has been delayed to April 2026. FaUAPI team is already supporting API team in establishing a clear timeline to ensure potential impacts are minimised. This is still on track. Mitigation: handover plans in place, option to utilise BA if needed Mitigation: handover plans in place, expect poss delivery slowdown | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-03 14:49
113 | 67 | 2 | Amber-Green | In beta testing: (1) Per-workspace feature flags , allows us to opt-in individual workspaces to new features so teams can test new functionality and provide feedback (2) Custom fields - Collect more data from users when they subscribe to your API (3) Webhooks - Send subscription events (create/update/delete) to external systems to allowing tracking/authorisation of API users In alpha testing: API import consolidation – Will allow users to import any kind of API using the same consistent JSON definition file format as the API export feature. API analytics phase 1 (senior managers) - building working prototypes UX for home page + onboarding & service design Migrations and onboarding ongoing | Status: Decom has been delayed to April 2026. FaUAPI team is already supporting API team in establishing a clear timeline to ensure potential impacts are minimised. This is still on track. Mitigation: handover plans in place, option to utilise BA if needed Mitigation: handover plans in place, expect poss delivery slowdown | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-03 14:49
114 | 69 |  | Amber-Green | No capacity for any additional work or incident resolution from SDT team resource – if urgent development/resolution of incidents is required for EDD, ICA, IEBT, SISL or SDT supported EDD services we will be unable to do this due to team being at capacity and no additional resource available. | Current team is stretched and at risk of burnout, no capacity for incident resolution, high priority work or illness cover if required. Paused work for improvements that aren't essential. CBP now in place although still awaiting CRM developer recruitment | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-03 14:53
115 | 67 |  | Amber-Green | In beta testing: (1) Per-workspace feature flags , allows us to opt-in individual workspaces to new features so teams can test new functionality and provide feedback (2) Custom fields - Collect more data from users when they subscribe to your API (3) Webhooks - Send subscription events (create/update/delete) to external systems to allowing tracking/authorisation of API users In alpha testing: API import consolidation – Will allow users to import any kind of API using the same consistent JSON definition file format as the API export feature. API analytics phase 1 (senior managers) - building working prototypes UX for home page + onboarding & service design Migrations and onboarding ongoing | Status: Decom has been delayed to April 2026. FaUAPI team is already supporting API team in establishing a clear timeline to ensure potential impacts are minimised. This is still on track. Mitigation: handover plans in place, option to utilise BA if needed Mitigation: handover plans in place, expect poss delivery slowdown | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-03 14:53
116 | 65 | 2 | Amber-Green | There is a risk that standards will not be adopted if we are unable to gain consensus via governance and IE Community. Issue: unable to upload drafted standards to Find & Use Standards for approval as parts of the template do not copy over correctly. A call has been arranged to see if this can be resolved. |  | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-03 14:59
117 | 65 |  | Amber-Green | There is a risk that standards will not be adopted if we are unable to gain consensus via governance and IE Community. Issue: unable to upload drafted standards to Find & Use Standards for approval as parts of the template do not copy over correctly. A call has been arranged to see if this can be resolved. | Continue to socialise and review standards with IE community. | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-03 14:59
118 | 65 |  | Amber-Green | There is a risk that standards will not be adopted if we are unable to gain consensus via governance and IE Community. Issue: unable to upload drafted standards to Find & Use Standards for approval as parts of the template do not copy over correctly. A call has been arranged to see if this can be resolved. | Continue to socialise and review standards with IE community. | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-03 14:59
119 | 66 |  | Amber-Green | Service Lines have been slow to engage with the Cost Avoidance Advisory service. Significant number of Reserved Instances due to expire in February/March 2026 impacting on several service lines. | The team is working hard to identify cost savings for Service Lines, but some have not been very responsive in agreeing to a workshop, either delaying in agreeing to a meeting or just not responding to e-mails, despite it clearly identifying the potential savings. The team will be considering how to mitigate this at the next Azure Governance board. Reaching out to services lines affected to determine if their future plans are likely to affect the decision to renew the expiring Reserved Instances. | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-03 15:03
120 | 66 | 1 | Green | Service Lines have been slow to engage with the Cost Avoidance Advisory service. Significant number of Reserved Instances due to expire in February/March 2026 impacting on several service lines. | The team is working hard to identify cost savings for Service Lines, but some have not been very responsive in agreeing to a workshop, either delaying in agreeing to a meeting or just not responding to e-mails, despite it clearly identifying the potential savings. The team will be considering how to mitigate this at the next Azure Governance board. Reaching out to services lines affected to determine if their future plans are likely to affect the decision to renew the expiring Reserved Instances. | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-03 15:04
121 | 57 |  | Green | Implementation of strategy delayed due capacity of key stakeholders and potential appetite for slow adoption. |  | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-03 15:08
122 | 70 |  | Green | ServiceNow Tickets Closed in Month and Open at Month End |  | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-03 16:49
123 | 66 | 2 | Amber-Green | Service Lines have been slow to engage with the Cost Avoidance Advisory service. Significant number of Reserved Instances due to expire in February/March 2026 impacting on several service lines. | The team is working hard to identify cost savings for Service Lines, but some have not been very responsive in agreeing to a workshop, either delaying in agreeing to a meeting or just not responding to e-mails, despite it clearly identifying the potential savings. The team will be considering how to mitigate this at the next Azure Governance board. Reaching out to services lines affected to determine if their future plans are likely to affect the decision to renew the expiring Reserved Instances. | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-03 16:52
124 | 120 | 1 | Green | Not currently active |  | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-04 11:16
125 | 2 |  | Amber-Green | Not explicitly stated but some problems with ADA migration reported. There have been some difficulties with the more complex queries due to functionality differences between SQL and Databricks. E.g. CROSS APPLY not being compatible with Databricks, but overall the conversion is still progressing well. | Continue with ADA migration. | Tracey.DALE@EDUCATION.GOV.UK | Tracey.DALE@EDUCATION.GOV.UK | 2026-02-04 13:57
126 | 183 | 2 | Amber-Green | Resource identification and onboarding has impacted delivery |  | Angela.SCALE@EDUCATION.GOV.UK | Angela.SCALE@EDUCATION.GOV.UK | 2026-02-04 13:57
127 | 5 |  | Amber-Green | An additional Business Analyst has joined the team to help recover analysis and scoping work that fell behind at the end of last year. Until this work is back on track, we cannot downgrade the red risk associated with March deliverables, which may remain until March. We are expecting two new data engineers to join the team, but onboarding is taking longer than anticipated. This delay, combined with one of our current engineers nearing the end of their contract, poses a risk to delivering the Beta Phase MVP. If retention is not possible, our capacity and velocity will be reduced, putting delivery at greater risk | Onboard additional resource, clarify scope and schedule. | Tracey.DALE@EDUCATION.GOV.UK | Tracey.DALE@EDUCATION.GOV.UK | 2026-02-04 14:01
128 | 117 |  | Amber-Green | Analysis and moderation continues | Completion of analysis and moderation to present baseline to CISO and stakeholders | Angela.SCALE@EDUCATION.GOV.UK | Angela.SCALE@EDUCATION.GOV.UK | 2026-02-04 15:42
129 | 64 | 2 | Amber-Green | Unavailability of data could mean that Funding features are functionally ready, but empty data sets are displayed/​ Availability of MYEE to all potential users might be inhibited due to a significant minority of organisations (~13%) not having a DSI account or approver.​ Reputational risk if proposed launch date (25.02) delayed due to GDS assessment requiring/recommending service stays in private beta pending remedial work​ |  | Paul.RAINE@EDUCATION.GOV.UK | Paul.RAINE@EDUCATION.GOV.UK | 2026-02-05 12:08
133 | 64 |  | Amber-Green | Unavailability of data could mean that Funding features are functionally ready, but empty data sets are displayed/​ Availability of MYEE to all potential users might be inhibited due to a significant minority of organisations (~13%) not having a DSI account or approver.​ Reputational risk if proposed launch date (25.02) delayed due to GDS assessment requiring/recommending service stays in private beta pending remedial work​ | This risk is actively managed. A Platform Data Team representative is embedded within the delivery team, and the dependency and risk is visible, understood, and tracked with the Data team to ensure readiness and alignment to release timelines.​ | Paul.RAINE@EDUCATION.GOV.UK | Paul.RAINE@EDUCATION.GOV.UK | 2026-02-05 12:10
135 | 64 |  | Amber-Green | Unavailability of data could mean that Funding features are functionally ready, but empty data sets are displayed/​ Availability of MYEE to all potential users might be inhibited due to a significant minority of organisations (~13%) not having a DSI account or approver.​ Reputational risk if proposed launch date (25.02) delayed due to GDS assessment requiring/recommending service stays in private beta pending remedial work​ | Not enough space to provide detail of path to green | Paul.RAINE@EDUCATION.GOV.UK | Paul.RAINE@EDUCATION.GOV.UK | 2026-02-05 12:11
136 | 23 |  | Amber-Green | (1) Architecture supplier MadeTech has lost their renewal bid, meaning 2 critical resources will leave DfE. (2) FSM Expansion needs a coordinating DM role across us and the School Census teams but Board/SRO don’t seem to accept this risk. | (1) Unfortunately we lost the Principal Developer resource as they’d been reassigned. New staff coming online but it’s a big loss (2) We met with FSM Policy to explain our case but are yet to hear if the SRO is able to provide a mitigation. We believe 3m of an experienced DM would be enough to mitigate and have provided indicative costs and Key Deliverables. | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-05 12:20
137 | 158 | 1 | Green | Currently reported under CRM Delivery |  | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-05 14:46
138 | 212 |  | Green | Katharine Beer join us as a senior interaction designer. Katharine has been working closely with the developers and Oli on the user journey mapping to further determine pain points and opportunities to improve the process, as well as detailing the journey users of the service will go to when submitting their InvestCo business cases. |  | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK | 2026-02-09 11:41
139 | 152 |  | Amber-Green | Wider DFE Tech queries/issues have required re-consideration of Q4's OKRs. | Approval to reconsider OKRs | Rhiannon.BARNES@EDUCATION.GOV.UK | Rhiannon.BARNES@EDUCATION.GOV.UK | 2026-02-09 15:15
140 | 31 |  | Amber-Green | Delivery challenges & Mitigations Resource Constraints: Short‑term capacity gaps (notably Service Support and enabling roles) are being mitigated through interim cover, phased onboarding of new joiners, and prioritisation of critical BAU activity. Dependency on External Data & Policy Change: Delivery risks linked to Ofsted data availability and evolving policy are being managed through early technical preparation, mock data usage, and close engagement with policy teams. | Onboarding of required roles will assist in delivery. | Rhiannon.BARNES@EDUCATION.GOV.UK | Rhiannon.BARNES@EDUCATION.GOV.UK | 2026-02-09 15:16
141 | 34 |  | Green | On hold there is no RAG status. |  | Rhiannon.BARNES@EDUCATION.GOV.UK | Rhiannon.BARNES@EDUCATION.GOV.UK | 2026-02-09 15:19
142 | 124 | 2 | Amber-Green | This project is subject to test and learn, business rules need to be reviewed each time testing is carried out on new data sets. The initial data set iterated to accuracy over 90%. Accuracy on record for destruction is currently 16% for the extended data set. The records management team are reviewing the results and updating business rules to be tested. |  | Sue.WHARAM@education.gov.uk | Sue.WHARAM@education.gov.uk | 2026-02-10 12:29
143 | 51 | 2 | Amber-Green | Fixing RAG from legacy Amber/Green |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk | 2026-02-10 15:26
144 | 41 | 2 | Amber-Green | Fixing RAG from legacy Amber/Green |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk | 2026-02-10 15:26
145 | 47 | 2 | Amber-Green | Fixing RAG from legacy Amber/Green |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk | 2026-02-10 15:27
146 | 49 | 2 | Amber-Green | Fixing RAG from legacy Amber/Green |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk | 2026-02-10 15:27
147 | 21 | 4 | Amber-Red | Fixing RAG from legacy Amber/Red |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk | 2026-02-10 15:28
148 | 16 | 2 | Amber-Green | Fixing RAG from legacy Amber/Green |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk | 2026-02-10 15:28
149 | 119 | 2 | Amber-Green | Fixing RAG from legacy Amber/Green |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk | 2026-02-10 15:28
150 | 26 | 2 | Amber-Green | Fixing RAG from legacy Amber/Green |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk | 2026-02-10 15:29
151 | 115 | 2 | Amber-Green | Fixing RAG from legacy Amber/Green |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk | 2026-02-10 15:29
152 | 58 | 2 | Amber-Green | Fixing RAG from legacy Amber/Green |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk | 2026-02-10 15:29
153 | 16 | 1 | Green | Fixing RAG from legacy Amber/Green to Green. We have met delivery targets in deploying new functionality that will extend our user base. We are now designing improvements that will make it easier for our growing user base to use our service. We have exceeded our targets for the year. |  | Carmel.KENNEDY@EDUCATION.GOV.UK | Carmel.KENNEDY@EDUCATION.GOV.UK | 2026-02-16 09:31
154 | 119 |  | Green | Service is in BAU. All intended service operations and data publications successfully implemented as planned. |  | Sabina.RATTAN@EDUCATION.GOV.UK | Sabina.RATTAN@EDUCATION.GOV.UK | 2026-02-19 13:45
155 | 154 | 1 | Green | on track | N/A | Rose.DUNSTALL@EDUCATION.GOV.UK | Rose.DUNSTALL@EDUCATION.GOV.UK | 2026-02-24 11:54
156 | 146 | 1 | Green | We're feeling confident based on what we know now and how close to delivery we are. | Surfacing our outstanding questions to policy. | Rose.DUNSTALL@EDUCATION.GOV.UK | Rose.DUNSTALL@EDUCATION.GOV.UK | 2026-02-24 11:56
157 | 167 | 2 | Amber-Green | Some challenges are being experienced in accessing computer vision (Computer vision is a field of AI that teaches computers to “see” and understand visual information — a bit like giving them eyesight.) but exploring options with the AI centre of excellence and Microsoft. Some issues getting access to live sharepoint. Portfolios are slow at giving us data for our demo. | Work with the AI CofE and IT team on access to share point. Engage more with pilot portfolios for test information | Julie.JENKINS@EDUCATION.GOV.UK | Julie.JENKINS@EDUCATION.GOV.UK | 2026-02-24 12:46
158 | 126 |  | Amber-Green | The change of circumstance part of the April delivery has been delayed due to other commitments. There is also nervousness about new requirements arising that will derail delivery. | Working across teams to resolve. We are triaging any conflicting requests as they come in. | Rose.DUNSTALL@EDUCATION.GOV.UK | Rose.DUNSTALL@EDUCATION.GOV.UK | 2026-02-24 14:10
159 | 147 | 1 | Green | Back on track to deliver for end of March | AS SMT are supporting any ways we can bring the work back into 25-26. | Rose.DUNSTALL@EDUCATION.GOV.UK | Rose.DUNSTALL@EDUCATION.GOV.UK | 2026-02-24 14:12
160 | 237 | 4 | Amber-Red | Due to the scope for the discovery being unclear and seemingly large, there is a risk that we may not be able to complete the discovery in the previously set out timescales of mid May. |  | Sally.CASEY@EDUCATION.GOV.UK | Sally.CASEY@EDUCATION.GOV.UK | 2026-02-25 10:32
161 | 237 |  | Amber-Red | Due to the scope for the discovery being unclear and seemingly large, there is a risk that we may not be able to complete the discovery in the previously set out timescales of mid May. | Specific actions: - Desk research starting to understand the landscape further to narrow down the scope to focus on specific areas required - Agreement on scope required - Potential to review end timescale for the discovery dependent on scope Responsible parties: Sally Casey, Ayaz Akram, Emily Sadler, Ana Alencar Target dates: Agreement on scope and timescales by end of March | Sally.CASEY@EDUCATION.GOV.UK | Sally.CASEY@EDUCATION.GOV.UK | 2026-02-25 10:34
162 | 137 | 1 | Green | All green assessment with one amber for NCS to take forward. | No reds in Service Assessment and onboarding team ready to transition to | Kuldip.OSBORNE@EDUCATION.GOV.UK | Kuldip.OSBORNE@EDUCATION.GOV.UK | 2026-02-25 13:04
163 | 205 | 4 | Amber-Red | The programme status has decreased to Amber/Red. Confidence in delivering the strategic objectives remains high; however, the current risk position is expected to affect the Proof of Concept timeline, with post‑March slippage anticipated but no impact on key outcomes. | • DPIA and all data sharing agreements are approved for Wonde, MIS suppliers, and EdTech partners. • Commercial approach for engagement with MIS suppliers who have registered an interest in the pilot is agreed. • Terms and Conditions are formally agreed and signed with MIS suppliers and the aggregator (Wonde). • Increased uptake of EdTech providers registering their interest. And an understand of the quality of data any financial implications • Understanding whether there will be any financial implications associated with the ingestion of the data | Lorraine.COLEY@EDUCATION.GOV.UK | Lorraine.COLEY@EDUCATION.GOV.UK | 2026-02-27 13:39
164 | 207 | 4 | Amber-Red | Delivery timescales are at significant risk : Wonde - Although the T&L- DPIA has finally been signed off Wonde are looking at a variation of the current DfE agreement to include the DS PoC (this is a recent development). Wonde are also drafting T&Cs for the PoC, that will need to be agreed in conjunction with the revised DfE agreement, before any live data can be ingested. MIS- further engagement with Arbor is blocked pending conversations about the right commercial approach, discussion with Commercial colleagues is ongoing , to determine the best way forward | Work with colleagues from DfE Commercials to define an approach, that addresses PoC T&Cs between MIS Providers Arbor & Compass that can be applied to other MIS Providers who might express an interest in participating in the PoC. Wonde contract variation approved and signed off by the Commercial team. | Lorraine.COLEY@EDUCATION.GOV.UK | Lorraine.COLEY@EDUCATION.GOV.UK | 2026-02-27 13:41
165 | 45 | 1 | Green | All key deliverables and milestones are on track for the reporting period | Production infrastructure to be built. Can pick this up now as a decision on phase 2 approach has been made to continue to develop the calculation engine in Databricks. | Daniel.KUMAR@EDUCATION.GOV.UK | Daniel.KUMAR@EDUCATION.GOV.UK | 2026-02-27 15:28
166 | 64 | 1 | Green | The service of Manage your education estate has now launched successfully. Previously recorded risks around unavailability of data, unavailability of MYEE to all potential users, and service assessment and/or accessibility audit outcomes delaying release date were not realised. An onboarding approach, including clear step-by-step DSI provisioning guidance and communications to reduce friction has been deployed. Adoption metrics are being actively monitored throughout Public Beta to inform further interventions. Post- accessibility audit triage completed. Remediation plan agreed with prioritised actions aligned to impact and feasibility. Progress tracked through to ensure timely resolution. ITHC scheduling and scope under review (managed centrally via the programme). Public Beta phase will be used to strengthen operational controls, security posture, and documentation of formal processes. | Not enough space to provide detail of path to green | Kathryn.KING@EDUCATION.GOV.UK | Kathryn.KING@EDUCATION.GOV.UK | 2026-02-27 16:36
167 | 219 | 1 | Green | Decision making tool was finalised at the beginning of February and taken to Triage on 04.02. This will be used to support scoping conversations pre-Triage and ensure more consistent conversations at Triage meetings. | Continue with current activity to create first draft of tool | Jo.WRIGHT@EDUCATION.GOV.UK | Jo.WRIGHT@EDUCATION.GOV.UK | 2026-03-02 07:38
168 | 219 |  | Green | Decision making tool was finalised at the beginning of February and taken to Triage on 04.02. This will be used to support scoping conversations pre-Triage and ensure more consistent conversations at Triage meetings. |  | Jo.WRIGHT@EDUCATION.GOV.UK | Jo.WRIGHT@EDUCATION.GOV.UK | 2026-03-02 07:38
169 | 73 | 1 | Green | The project is now closed ahead of the original timeline. | Final bulk upload | Ushma.GILL@EDUCATION.GOV.UK | Ushma.GILL@EDUCATION.GOV.UK | 2026-03-02 09:09
170 | 4 | 2 | Amber-Green | RAG is amber-green. The project has just started, and we have made good progress, but we need to gather more information on the scope and problem area before determining likely outcomes of the Alpha project. | Continue to work with relevant stakeholders to clarify scope and schedule. | Tracey.DALE@EDUCATION.GOV.UK | Tracey.DALE@EDUCATION.GOV.UK | 2026-03-02 12:49
171 | 209 | 4 | Amber-Red | Funding for the project in FY26/27 still to be agreed | Work ongoing to establish funding | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-03-02 17:00
172 | 221 | 1 | Green | Progressing as planned | Awaiting BA resource | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-03-02 17:06
173 | 209 | 1 | Green | Proceeding to plan | Work ongoing to establish funding | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-03-02 17:20
174 | 223 | 4 | Amber-Red | "Data spine is reporting Amber on several workstreams due to issues engaging the sector. Strategically not a problem at this stage, just moves timelines to the right which could cause issues justifying the spend on the programme. More widely, long term work on data strategy hasn't progressed - partially due to other priorities, partially as without a CDO in place, there are some outstanding questions around the future of this work." | Data spine have been setting expectations around delivery dates so if one workstream does move to the right it won't come as a shock. | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk | 2026-03-02 17:28
175 | 232 | 2 | Amber-Green | Code review work has been more challenging than anticipated due to higher volumes of Git Hub findings than originally expected, which is taking time to triage. Expectation is similar challenge as the testing continues with ADO. Automation being used to accelerate capture and analysis. Targeted penetration testing lead time has taken longer than anticipated, with the external resource availability limitations. | Finalise code based reviews and undertake penetration tests to feed into overall reporting. | Alison.Dunne@EDUCATION.GOV.UK | Alison.Dunne@EDUCATION.GOV.UK | 2026-03-02 23:20
176 | 42 | 2 | Amber-Green | Awaiting update |  | Jo.WRIGHT@EDUCATION.GOV.UK | Jo.WRIGHT@EDUCATION.GOV.UK | 2026-03-03 12:56
177 | 126 | 4 | Amber-Red | Funding rules publication and announcements are now due much later than planned, anything unexpected from these will impact on delivery timeliness. The change of circumstance part of the April delivery has been delayed due to other commitments. There is also nervousness about new requirements arising that will derail delivery. | Working across teams to resolve. We are triaging any conflicting requests as they come in. | Jo.WRIGHT@EDUCATION.GOV.UK | Jo.WRIGHT@EDUCATION.GOV.UK | 2026-03-03 12:57
178 | 38 | 2 | Amber-Green | Awaiting update. |  | Jo.WRIGHT@EDUCATION.GOV.UK | Jo.WRIGHT@EDUCATION.GOV.UK | 2026-03-03 12:59
179 | 86 | 2 | Amber-Green | Awaiting Update. |  | Jo.WRIGHT@EDUCATION.GOV.UK | Jo.WRIGHT@EDUCATION.GOV.UK | 2026-03-03 13:00
180 | 193 | 2 | Amber-Green | Metrics: analysis of performance metrics presents some areas where data hasn’t enabled comparability of insights over time. Analysis underway to address this and enable the team to give a full view of performance. Translation: high-level testing of sample translations with first-language speakers highlighted some issues with accuracy, clarity and appropriateness of automatic translation. A banner is being implemented to ensure users know that translations are AI-driven on every page where the translator is used. | Same as RAG Justification. | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2026-03-03 13:08
181 | 155 | 2 | Amber-Green | Require funding to be identified for 26/27 UCD support given rapidly changing policy in this area and new campaigns. Seeking joint DSIT / DFE funding. | As per RAG justification. | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2026-03-03 13:18
182 | 104 | 2 | Amber-Green | Path to Green: Alpha outputs delivered: minimum day‑5 SIN dataset, feasibility assessment, CSIN/reporting prototypes, and internal case‑tracking concept to reduce manual reconciliation. Clear decision gate: SRO decision on whether to proceed to Beta once Alpha defines scope, timeline and cost for Phase 1b. Parallel tactical fixes (Laura Bailey): strengthen live dashboard/briefing processes and reduce duplication. Alignment across system: integrate Panel Secretariat and CSIRT processes and case‑management lifecycle into design to eliminate duplication and clarify data flows. Continuity secured: progress extension of NCVPP/CoP cooperation agreement to maintain analytical capacity until end of FY26-27 whilst SIDD team’s work progresses. | As per RAG justification | Sue.MOLYNEUX@EDUCATION.GOV.UK | Sue.MOLYNEUX@EDUCATION.GOV.UK | 2026-03-03 16:51
183 | 233 | 1 | Green | Work progressing to align elements of inhousing. Regular NEET board established. | Monthly update not required for Jan as this project was added to COMPASS after the submission date. Path to green will be updated as part of the February monthly update. | Jo.WRIGHT@EDUCATION.GOV.UK | Jo.WRIGHT@EDUCATION.GOV.UK | 2026-03-04 10:49
184 | 233 | 2 | Amber-Green | Project has only just started and there are too many unknowns at this point to rate as Green - as we move through the coming months and complete our initial phases we will have greater clarity over delivery. | Project has only just started and there are too many unknowns at this point to rate as Green - as we move through the coming months and complete our initial phases we will have greater clarity over delivery. | Ruth.MEDLOCK@EDUCATION.GOV.UK | Ruth.MEDLOCK@EDUCATION.GOV.UK | 2026-03-04 13:48
185 | 26 |  | Green | All on track for agreed milestones. |  | Daniel.MARSDEN@EDUCATION.GOV.UK | Daniel.MARSDEN@EDUCATION.GOV.UK | 2026-03-05 14:28
186 | 215 | 1 | Green | Delivery has been reset, MVP approach agreed and new scope in definition, all deliverables are tracking green currently and the team are working to schedule |  | Amna.HALIM@EDUCATION.GOV.UK | Amna.HALIM@EDUCATION.GOV.UK | 2026-03-10 10:04

## Successes
Id | ProjectId | SuccessDescription | RecordedByEmail | RecordedByName | RecordedAt | IsReportedToSlt | SltResponse | SltRespondedByEmail | SltRespondedByName | SltRespondedAt
9 | 1 | Migration of BuRT to COMPASS completed with data quality being worked through to align to the same categorisations as FIPS, allowing for a smoother transition between COMPASS as delivery to FIPS as operational reporting. | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-26 21:43 | True
12 | 205 | Significant progress made on the programme overall in December: 1. Agreed PoC data domains: attainment (non-statutory), SEND & behaviour. 2.Engaged with WONDE to enable the ingestion of attainment (non-statutory), SEND, and behaviour data in January at no additional cost under the existing contract. 3.Completed and submitted DSIT Business Case | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-01-07 16:22 | False
13 | 16 | New Progress tracking feature, enabling users to record and update the status of their progress against meeting core recommendations published on 12 November. New MAT as a school feature, enabling MATs to log in and update statuses on behalf of a school in their trust, released on 12 November. Standards landing page improvements to improve visibility of core standards published on gov.uk on 21 January. | Carmel.KENNEDY@education.gov.uk | KENNEDY, Carmel | 2026-01-21 14:19 | True
14 | 1 | Completed introductory sessions with PMO contacts across DDT divisions. Monthly commission was issued on COMPASS in January with drop in sessions offered to support contacts. | Tracey.DALE@education.gov.uk | DALE, Tracey | 2026-01-27 11:17 | False
15 | 159 | Work with Amazon UK (August - December), using AI to analyse true reasons for customer contact. Means we have clarity as to why customers / users engage with our service and can now begin to understand which matters can be automated (AI/Self Serve / Self Help videos etc) and those contacts which may require human intervention to to complexity or vulnerability. | Stuart.BALNAVES@education.gov.uk | BALNAVES, Stuart | 2026-01-28 14:12 | False
16 | 159 | Best practise discussions and learning has taken place across public and private sector businesses to take learning from other AI / Automation programmes and their barriers and failures to reduce the risks of work needing to be done in Customer Service. | Stuart.BALNAVES@education.gov.uk | BALNAVES, Stuart | 2026-01-28 14:14 | False
17 | 159 | Working with customer service industry leaders (Disney and Amazon) to draw on operational models used in operational customer service delivery, reducing pitfalls and creating frameworks that bring Blueprint for Modern Digital Government to life. | Stuart.BALNAVES@education.gov.uk | BALNAVES, Stuart | 2026-01-28 14:17 | False
18 | 213 | FDS - FDS GO LIVE has been pushed back as Opex was not comfortable . Opex wants to Go Live at the end of April. DEV , UAT and SIT Integration testing completed. Currently setting up the AnM integration in FDS. is blocked as networks needed approval from Data owners of AnM data as the prod data will be moved to test Subscription. In Parallel Proceeding on the Prod ENV creation. | Lavanya.GANESULA@education.gov.uk | GANESULA, Lavanya | 2026-01-28 16:43 | False
19 | 137 | Has now gone into Private Beta | Kuldip.OSBORNE@education.gov.uk | OSBORNE, Kuldip | 2026-01-29 16:10 | False
20 | 171 | MVP launched on time (Dec 2025) before DSIT campaign live (campaign itself delayed) | Kuldip.OSBORNE@education.gov.uk | OSBORNE, Kuldip | 2026-01-29 16:24 | False
21 | 218 | Team travelled to Belfast for UR with secondary schools. Followed by York and Birmingham the following week. | Kuldip.OSBORNE@education.gov.uk | OSBORNE, Kuldip | 2026-01-29 16:32 | False
25 | 164 | The team has successfully transitioned across to new CXOne instance by implementing necessary changes. | Helen.TAVERNER@education.gov.uk | TAVERNER, Helen | 2026-01-30 10:01 | False
26 | 89 | We are successfully delivering the 26/27 funding data policy changes within tight timelines. | Lavanya.GANESULA@education.gov.uk | GANESULA, Lavanya | 2026-01-30 13:15 | False
27 | 89 | We recently completed the updates for the DSG and NMSS funding streams, enabling users to begin onboarding funding data for the new schemas. | Lavanya.GANESULA@education.gov.uk | GANESULA, Lavanya | 2026-01-30 13:16 | False
28 | 89 | .Net version upgrade - Backend V8 to V10 | Lavanya.GANESULA@education.gov.uk | GANESULA, Lavanya | 2026-01-30 13:16 | False
29 | 89 | Technical story - Angular version upgrade from v19 to v21 | Lavanya.GANESULA@education.gov.uk | GANESULA, Lavanya | 2026-01-30 13:16 | False
30 | 89 | OnBoarded new schema DSG - 26/27 | Lavanya.GANESULA@education.gov.uk | GANESULA, Lavanya | 2026-01-30 13:17 | False
31 | 91 | Multi Process and memory optimization | Lavanya.GANESULA@education.gov.uk | GANESULA, Lavanya | 2026-01-30 13:29 | False
32 | 91 | Data Science report optimization | Lavanya.GANESULA@education.gov.uk | GANESULA, Lavanya | 2026-01-30 13:29 | False
33 | 133 | Live QRD data loaded to silver tables to enable accurate development of outstanding processes | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-02 14:50 | False
34 | 133 | Matching Build and Stewardship Tool deployed into Pre-prod | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-02 14:50 | False
35 | 133 | ILR SN14 delivery | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-02 14:51 | False
36 | 133 | NCCIS 24/25 delivery | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-02 14:51 | False
38 | 153 | Engineering work on SC Spr is complete and tested, meaning we have a full end to end dataset running on Databricks | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-02 16:17 | False
39 | 153 | Assurance of all datasets, and SC Spring in particular, is demonstrating huge reductions in data run times and also validating that the CLDS 2.0 builds are working as expected | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-02 16:18 | False
40 | 45 | Assurance for KS4 June Unamended and 16-18 Unamended is complete & SecDev and SecTest built on pre-prod. | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-02 16:43 | False
41 | 45 | All of the pipelines are built except for the AnM ones for 16-18. | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-02 16:43 | False
42 | 136 | Work on assuring the EDAP and Databricks unamended processes. | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-02 16:59 | False
43 | 134 | Work on assuring the EDAP and Databricks unamended processes. | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-02 17:03 | False
44 | 135 | Delivery of Result Amended | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-02 17:13 | False
45 | 135 | Support of AAD 2.0 | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-02 17:13 | False
46 | 135 | Welcoming of new Product Owner and Data Analyst Ben Fortescue (Leonie’s temporary replacement) | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-02 17:13 | False
47 | 52 | We had just under 1000 attendees for the Monitor Your School Attendance webinar | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-02 17:14 | False
48 | 52 | Release 8 (R8) comms to 20,000 schools sent out. | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-02 17:14 | False
49 | 52 | The Delivery team completed high-level planning against our new prioritised milestones for 2026. | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-02 17:15 | False
50 | 46 | Uploading the KS4 revised data onto the portal to plan | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-02 17:22 | False
51 | 17 | Gone Live with QA Dashboard on VYED and shared with Coventry | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-03 12:52 | False
52 | 17 | Commercial agreement in place for additional 8 LAs | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-03 12:53 | False
53 | 64 | Key Milestone - Complete GDS Peer Review (incl. Tech Assessment)​ Due Date - ​​19.01.26​ Status - ​Complete​ Comments​ -​ Delivered as planned. Detailed and constructive feedback received to support Public Beta readiness.​ Actual Date Complete​ - 19.01.26​ | Paul.RAINE@education.gov.uk | RAINE, Paul | 2026-02-05 12:06 | True
54 | 16 | Extending plan technology for your school to MAT Trusts as well as school users, enabling MAT users to review, update and complete self-assessments on behalf of a school in their Trust | Carmel.KENNEDY@education.gov.uk | KENNEDY, Carmel | 2026-02-16 10:05 | False
55 | 16 | 25/26 FY uptake target of 10% of schools using the service was met in Nov 25 | Carmel.KENNEDY@education.gov.uk | KENNEDY, Carmel | 2026-02-16 10:39 | False
56 | 16 | 25/26 FY stretch target of 15% of schools and 15% trusts using the service, was met in Feb 26 | Carmel.KENNEDY@education.gov.uk | KENNEDY, Carmel | 2026-02-16 10:40 | True
57 | 1 | First commission on COMASS completed for January 2026. 72.1% of returns were completed with the majority of divisions having a 90-100% return rate, which is a significant return rate for the first commission on a new sysstem. PMO will work with divisions who struggled to submit their returns. | Tracey.DALE@education.gov.uk | DALE, Tracey | 2026-02-23 10:54 | False
58 | 52 | User Research for Similar Schools completed | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-24 11:07 | False
59 | 167 | A safe play environment has been set up for exploration | Julie.JENKINS@education.gov.uk | JENKINS, Julie | 2026-02-24 14:06 | False
60 | 167 | Real insights can be ingested, surfaced and traced back to the source | Julie.JENKINS@education.gov.uk | JENKINS, Julie | 2026-02-24 14:07 | False
61 | 167 | Roadshows demonstrating the product to wider portfolios and groups have been scheduled and are taking place. | Julie.JENKINS@education.gov.uk | JENKINS, Julie | 2026-02-24 14:08 | False
62 | 164 | The team successfully enhanced and shared the monthly high-level dashboard with the senior leadership (Jane and Shaf) earlier this month. The enhanced version now contains information about performance measures for various DfE services that we manage in-house within CSEO. | Helen.TAVERNER@education.gov.uk | TAVERNER, Helen | 2026-02-25 14:46 | False
63 | 17 | Single view dashboard released and live. | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-25 15:09 | False
64 | 52 | Automated DQ priority score to track issues over time and provide efficiencies for LiveOps | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-26 09:32 | False
65 | 52 | Started work on new policy priority - Attendance Heatmaps (visual calendar representation) | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-26 09:33 | False
66 | 46 | 2024/25 Key Stage 4 Data: All KS4 data has now been shared on the CYPMD portal for this data cycle | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-26 10:24 | False
67 | 46 | 2024/25 Key Stage 4 Data: The next data shared will be KS4 Cohort Data in June 2026 (opening date TBC) | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-26 10:25 | False
68 | 46 | 2024/25 16-18 Data: 16-18 revised data, along with Value Added data, was made available on the CYPMD portal (to plan) on 5th February | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-26 10:25 | False
69 | 46 | 2024/25 16-18 Data: 16-18 Retention data is on track to be sent to the DCI team 10th March for upload to the portal 17th March | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-26 10:25 | False
70 | 46 | 2024/25 Key Stage 2 Data: All KS2 data has now been shared on the CYPMD portal for this data cycle | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-26 10:25 | False
72 | 46 | Preparation for 2026 Cycle: Drafting of April launch communications and associated documents continues | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-26 10:26 | False
73 | 46 | 2026 CYPMD communication schedule has been drafted and is being reviewed | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-26 10:26 | False
74 | 46 | CYPMD change backlog prioritisation has completed and work will now commence to progress | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-26 10:27 | False
75 | 46 | Development requirements are being discussed and scoped in order that work can be scheduled with the DCI team for the portals and Apprenticeships team for Zendesk | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-26 10:27 | False
76 | 46 | A workshop has been held with the KS, matching and AO data collection teams to agree delivery timeframes for matched AO data in the new cycle | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-26 10:27 | False
77 | 46 | End of data cycle risk workshop scheduled to assess risks and mitigations in advance of the next data cycle commencing | Amanda.STRINE@education.gov.uk | STRINE, Amanda | 2026-02-26 10:27 | False
78 | 153 | Priority datasets have been complete in build and test | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-27 13:29 | False
79 | 153 | Assurance has gone well and validated substantial savings in time for a data run will occur once re-platforming happens | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-27 13:29 | False
80 | 45 | Completed the KS2 Assurance | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-27 15:33 | False
81 | 45 | Completed the Pre-prod SecDev and SecTest build | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-27 15:33 | False
82 | 45 | Implementing the new RBACs on pre-prod | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-27 15:33 | False
83 | 135 | Assurance activities are providing good understanding of any minor issues that have been rectified. | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-27 15:36 | False
84 | 134 | Assurance going well on final | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-27 15:37 | False
85 | 136 | Completion of the retention process. | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-27 15:38 | False
86 | 46 | 16-18 Revised data shared on the CYPMD portal | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-27 15:40 | False
87 | 46 | 16-18 Value Added Revised data shared on the CYPMD portal | Daniel.KUMAR@education.gov.uk | KUMAR, Daniel | 2026-02-27 15:40 | False
91 | 64 | The Manage your education estate service was successfully released into public beta overnight on 25 February 2026, on time, and to plan. That means that all responsible bodies and settings can now access it. The service received 5000 visits in its first two days from 300 unique visitors on day one, and 170 on day two. 450 visitors viewed the data page. | Kathryn.KING@education.gov.uk | KING, Kathryn | 2026-02-27 16:55 | True
92 | 133 | HESA stewardship completed, with priority cohorts stewarded. | unknown@example.com | Unknown User | 2026-03-02 11:01 | False
93 | 182 | Private BETA launch Jan 2026 | Alison.Dunne@education.gov.uk | DUNNE, Alison | 2026-03-02 13:53 | False
94 | 210 | - Successfully launched the Internal Productivity & AI Forum - STA Capability Review Pilot has progressed to analysis and reporting findings | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-03-02 17:10 | False
95 | 230 | "• Early drafting of a clear, structured comms plan • Positive initial feedback on case study approach • Rapid progress on tools to support engagement • Strong collaboration with colleagues contributing to the first set of case studies" | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-03-02 17:24 | False
96 | 117 | All portfolio self-assessments completed | Alison.Dunne@education.gov.uk | DUNNE, Alison | 2026-03-02 22:10 | False
97 | 232 | All portfolio self assessment questionnaires were completed by the end of January | Alison.Dunne@education.gov.uk | DUNNE, Alison | 2026-03-02 23:04 | False

## Outcomes
Id | ProjectId | Outcome | MeasureOfSuccess | ConfidenceLevel | ConfidenceExplanation | AchievementStatus | AchievementNotes | SortOrder | CreatedByEmail | CreatedByName | CreatedAt | UpdatedAt

## Needs
Id | ProjectId | Title | Need | Source | Validated | ValidationNotes | ValidatedAt | SortOrder | CreatedByEmail | CreatedByName | CreatedAt | UpdatedAt
1 | 1 | Strategic visibility | C-level leaders need a reliable, up-to-date view of departmental performance and risk, so they can make confident strategic decisions and intervene early when necessary. | Assumption | No |  |  | 1 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-17 12:51 | 2025-11-17 12:58
2 | 1 | Portfolio control | Directors and Deputy Directors need clear insight into how their portfolio is performing against milestones, objectives, and standards, so they can direct resources and support teams effectively. | Assumption | No |  |  | 2 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-17 12:58 | 2025-11-17 12:58
3 | 1 | Programme assurance | SROs need one place to track delivery progress, risks, issues, actions, and decisions across their programme, so they can provide assurance and demonstrate control to governance boards. | Assumption | No |  |  | 3 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-17 12:58 | 2025-11-17 12:58
4 | 1 | Unified service management | Service Owners need a single tool for managing risks, issues, actions, milestones, and compliance tasks, so they don’t rely on multiple spreadsheets or duplicate reporting. | Assumption | No |  |  | 4 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-17 13:57 | 2025-11-17 13:57
5 | 1 | Standards oversight | Heads of Profession need visibility of how services and teams meet professional standards, so they can focus support, reduce non-compliance, and uphold quality across the department. | Assumption | No |  |  | 5 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-17 14:10 | 2025-11-17 14:10
6 | 1 | Fair and transparent prioritisation | Central Operations leads need a structured process for receiving, assessing, and prioritising requests for support, so resources can be allocated consistently and transparently. | Assumption | No |  |  | 6 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-17 14:10 | 2025-11-17 14:25
7 | 1 | End-to-End traceability | Programme and Portfolio Managers need to understand how events link together—risks, issues, actions, decisions—so they can identify impacts, manage dependencies, and maintain accurate reporting. | Assumption | No |  |  | 7 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-17 17:49 | 2025-11-17 17:49
8 | 1 | Consistent assurance data | Assurance, governance, and control functions need standardised reporting and consistent data, so they can provide proportionate oversight without repeatedly requesting evidence. | Assumption | No |  |  | 8 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-17 17:49 | 2025-11-17 17:49
9 | 1 | Standards compliance insight | Standards Owners need to see where services meet or fall short of standards, so they can identify patterns, prioritise interventions, and support teams to improve. | Assumption | No |  |  | 9 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-17 17:50 | 2025-11-17 17:50
10 | 1 | Lifecycle clarity | Service Owners and Delivery Leads need to know what governance, assurance, compliance, and evidence are required at each stage of the lifecycle, so they can prepare the right things at the right time. | Assumption | No |  |  | 10 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-17 17:50 | 2025-11-17 17:50
11 | 1 | Organisational health monitoring | Senior leaders need clear indicators on service health, risks, milestones, and performance trends, so they can identify systemic issues and direct investment effectively. | Assumption | No |  |  | 11 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-17 17:50 | 2025-11-17 17:50
12 | 1 | Integrated operational management | Live service teams need one place to record day-to-day operational issues such as incidents, accessibility concerns, and compliance gaps, so service health can be monitored consistently. | Assumption | No |  |  | 12 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-17 17:51 | 2025-11-17 17:51
13 | 1 | Board-ready insight | Governance board members need a holistic picture of delivery and operational readiness, so they can make proportionate and timely decisions. | Assumption | No |  |  | 13 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-17 18:03 | 2025-11-17 18:03
14 | 1 | Capability & quality insight | Heads of Profession across UCD, Engineering, Architecture, and Data need insight into team capability, delivery quality, and emerging risks, so they can shape training, standards, and support. | Assumption | No |  |  | 14 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-17 18:03 | 2025-11-17 18:03

## ProblemStatements
Id | ProjectId | ProblemStatement | CreatedByEmail | CreatedByName | CreatedAt | UpdatedAt
1 | 1 | The Department for Education delivers a large and varied portfolio of digital services, products, programmes, and operational activities. Information about performance, risks, issues, decisions, actions, compliance, strategic objectives, and service health is currently fragmented across multiple tools, spreadsheets, bespoke processes, and disconnected reporting cycles. This creates duplicated work, inconsistent data quality, opaque governance, and an inability to form a reliable, real-time view of departmental delivery and operational risk. Teams cannot easily trace how risks link to milestones, or how actions connect to issues, decisions, objectives, service assessments, and standards compliance. Strategic reporting relies heavily on manual consolidation, which delays insight and weakens decision-making. Assurance functions lack a single mechanism to monitor compliance across the lifecycle, while delivery teams face repeated evidence requests and inconsistent expectations from governance bodies. As demand increases and services become more interdependent, the department requires a unified, authoritative platform that provides visibility, reduces duplication, improves confidence in data, and supports consistent governance across delivery and live operations. | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-17 12:50 | 2025-11-18 11:44
2 | 15 | DfE DDT does not have cohesive guidance to help people delivering products and services in/for DfE - to understand the standards, processes, patterns and ways of working that they need to follow, and the support available to them. Where guidance exists, it is spread across numerous disconnected manuals, each with different content structures, styles, and ownership. This fragmentation results in duplication, gaps, outdated or conflicting guidance. It creates unnecessary complexity and cost, delivers a poor user experience as it is difficult to find, trust, and apply the information they need. This results in a lack of awareness of and adherence to standards, and results in products and services that aren't designed and delivered in an efficient, consistent, high-quality way. | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-18 11:44 | 2025-11-18 11:44
3 | 6 | We don’t have a consistent understanding of our users and services. As a result, we don’t efficiently deliver joined up, high quality outcomes or fully understand the current value, innovation opportunities and potential savings. | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-25 08:55 | 2025-11-25 08:55
4 | 202 | The Department for Education (DfE) faces ongoing challenges in effectively responding to key Post-16 Skills issues—such as forecasting, FE attendance, NEET rates, and more—due to a lack of timely, actionable data. To address this, the DfE will undertake a proof of concept (PoC) for real-time data collection from FE colleges in FY26/27. The PoC must be supported by a clear narrative and evidence base to gain buy in from the FE sector. The core challenge is to demonstrate how real-time data can enhance decision-making, policy responsiveness, and programme outcomes to help solve these challenges as well as identify gaps and overlap across the Post 16 landscape e.g. fixing the same problem.. | Tracey.DALE@EDUCATION.GOV.UK | DALE, Tracey | 2025-12-15 15:12 | 2025-12-15 15:12
5 | 205 | A huge amount of potentially valuable data which could make DfE aims much easier to achieve is currently locked up in commercial systems. | Tracey.DALE@EDUCATION.GOV.UK | DALE, Tracey | 2025-12-15 15:54 | 2025-12-15 15:54
6 | 200 | OFFSEN - details redacted | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-01-07 16:53 | 2026-01-07 16:53
7 | 81 | How might we ensure that young people know all the options and support that are available to them across the journey of leaving care (approaching leaving and having left care)​ ​ | Becky.LOFTUS@education.gov.uk | LOFTUS, Becky | 2026-01-13 10:16 | 2026-01-13 10:16
8 | 168 | Parents, carers, and responsible adults feel unconfident and overwhelmed when it comes to effectively keeping young people safe online. There's so much information out there, but it's hard to know what to trust or where to start. By raising awareness of the online risks young people face and offering a single, trusted place to find clear, practical steps, parents, carers and trusted adults will feel informed and confident to protect the young people in their care. | Becky.LOFTUS@education.gov.uk | LOFTUS, Becky | 2026-01-13 10:19 | 2026-01-13 10:19
9 | 137 | People seeking government-funded* education and training opportunities struggle to find all relevant options that match their needs, while searching online for suitable courses or training. Options are fragmented across different websites requiring awareness of the different offerings, multiple searches and often needing to know the exact name to find something. There's no unified, intuitive way to see what's available. This leads to missed opportunities; people may not find the best-fit course, may not enrol at all, or may start a course that doesn't suit them and drop out. * Users unlikely to use this terminology, they’ll talk about recognised qualifications, assured courses etc. | Clare.AROLKER@EDUCATION.GOV.UK | AROLKER, Clare | 2026-01-13 10:55 | 2026-01-13 10:55
10 | 3 | The Data Directorate is not coherent in its data service offering for analytical data end-users across the DfE as we have different offerings across our estate including on CIP and DfE T1. | Tracey.DALE@EDUCATION.GOV.UK | DALE, Tracey | 2026-01-26 13:39 | 2026-01-26 13:39
11 | 160 | Across the Department Providers, Citizens, Learners, and Parents experience complexity and confusion when they seek help to do, find or report something to DfE. This results in confusion for the customer because of multiple entry points to different internal teams and inefficiency for the taxpayer as multiple technologies exist and service partnership procurements occur. It also drives duplication across departments people and resources. This workstream seeks to centralise external facing service teams, bringing together knowledge, technology and people to create one consistent service point, with published SLA for the Department. In turn creating efficiency for the taxpayer and simplicity and clarity for the customers we serve. | Stuart.BALNAVES@EDUCATION.GOV.UK | BALNAVES, Stuart | 2026-01-28 08:45 | 2026-01-28 11:48
12 | 160 | A disjointed service offer is creating additional cost burdens across staffing levels, technology and commercial contracts. In turn this is impacting stakeholder experience and perception of the department. | Stuart.BALNAVES@EDUCATION.GOV.UK | BALNAVES, Stuart | 2026-01-28 08:45 | 2026-01-28 08:45
13 | 164 | Customer Service teams are generating a significant volume of data that highlights recurring failures in organisational processes, policies, and communications. However, this data needs to be analysed to produce actionable insights, that can be consistently acted upon across the business. Currently, the same issues continue to surface, driving customers to seek support for problems that could otherwise be prevented. Over the last 12 months, unplanned customer contact has generated 11% of the total annual workload with a high proportion of enquiries linked to avoidable failure points already identified by front-line teams. This unnecessary contact is placing pressure on Customer Service capacity, creating longer wait times, and negatively affecting customer experience. Additionally, unresolved friction in process and communication flows is contributing to increased operational costs, inefficiencies, and reduced trust in our ability to resolve recurring issues. The scope of this problem includes the capture, analysis, and escalation of customer data, along with the organisational mechanisms for addressing root causes related to broken or unclear processes, outdated or inconsistent policies, and insufficient or confusing communications. | Stuart.BALNAVES@EDUCATION.GOV.UK | BALNAVES, Stuart | 2026-01-28 13:30 | 2026-02-19 16:54
14 | 159 | The Department for Education delivers a wide range of services to citizens, providers, and stakeholders. However, the absence of a unified Customer Service Digital Strategy has led to inconsistent service experiences, siloed design decisions, and digital processes that do not fully account for customer support needs. As a result, customer demand is rising in avoidable areas, with an estimated 4% of annual contact volumes driven directly by gaps or failures in existing digital journeys. Current digital services do not consistently follow the modern government blueprint for service design—services that should be simple, consistent, and digital by default, while ensuring that individuals who are vulnerable or experiencing complex challenges can still access a human “hand to hold” when needed. In several cases, digital services have been designed or deployed without adequately considering the end‑to‑end customer experience, leading to confusion, incomplete journeys, or a lack of clarity around next steps. This has created service pressures across the front line customer service teams, increasing operational workload and reducing capacity to support customers who genuinely require personalised assistance. The problem is exacerbated by fragmented decision‑making across programmes, where service and digital design choices are often made in isolation. This reduces the ability to share insight, reuse capability, or maintain consistent user journeys across the DfE estate. It also prevents customer insight from being systematically incorporated into service design, meaning issues that generate avoidable contact can persist for long periods before they are addressed. Without an overarching Customer Service Digital Strategy, DfE lacks the coordinated customer governance standards, and insight‑driven feedback loops needed to design digital services that are both efficient and truly user‑centred. This limits the Department’s ability to reduce failure demand, automate simple enquiries, and improve service quality at scale | Stuart.BALNAVES@EDUCATION.GOV.UK | BALNAVES, Stuart | 2026-01-28 13:40 | 2026-01-28 14:02
15 | 219 | DDT is receiving an increasing volume of requests without additional capacity, making it harder to focus on the work that delivers the greatest strategic value. Strengthening the demand triage process ensures that only initiatives aligned with portfolio roadmaps and DDT’s strategic outcomes progress, improving efficiency, clarity, and resource use | Louise.CLARK@EDUCATION.GOV.UK | CLARK, Louise | 2026-01-29 10:54 | 2026-01-29 10:54
16 | 171 | Parents, carers, and responsible adults feel unconfident and overwhelmed when it comes to effectively keeping young people safe online.​ There's so much information out there, but it's hard to know what to trust or where to start. ​ By raising awareness of the online risks young people face and offering a single, trusted place to find clear, practical steps, parents, carers and trusted adults will feel informed and confident to protect the young people in their care. | Kuldip.OSBORNE@EDUCATION.GOV.UK | OSBORNE, Kuldip | 2026-01-29 16:18 | 2026-01-29 16:18
17 | 204 | Business problem: how can STA continue with its digital transformation given significantly constrained resources? Is there a better structure that would enable this to happen?’. Purpose: Help STA become more efficient, optimise processes, make better use of its resources, improve data and decision-making, engage stakeholders, align with strategic goals, and reduce costs | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-01-30 10:41 | 2026-01-30 10:41
18 | 91 | Providing a solution for non developers to create and deploy digital forms to reduce bottlenecks and competition for resources. | Joe.YOUNG@EDUCATION.GOV.UK | YOUNG, Joe | 2026-02-02 15:30 | 2026-02-02 15:39
19 | 117 | ALBs face limitations in cyber maturity, due diligence, and digital infrastructure, creating systemic vulnerabilities and increasing DfE’s exposure to reputational, financial, and data risks.​ Recent high-profile cyber incidents and a joint Cabinet Office/NCSC letter underscore unacceptable technology risks across public sector ALBs.​ ​ The Government Security Strategy, Functional Standard GovS 007, and government Cyber Action Plan (CAP) mandate stronger departmental oversight of ALBs, with clear accountability for sector-wide resilience.​ ​ | Angela.SCALE@EDUCATION.GOV.UK | SCALE, Angela | 2026-02-04 11:33 | 2026-02-04 11:41
20 | 183 | Secure By Design is a crucial principle for ensuring that systems are designed and architected with security considerations embedded from the outset. Retrofitting security afterwards is significantly more difficult and expensive and always yields poorer results. | Angela.SCALE@EDUCATION.GOV.UK | SCALE, Angela | 2026-02-04 13:54 | 2026-02-04 13:54
21 | 232 | We face an increasingly complex and hostile cyber threat environment, with heightened risks to government services and data. Recent security and data incidents both within and outside our organisation have shown the need for greater visibility, stronger controls, and faster risk mitigation | Angela.SCALE@EDUCATION.GOV.UK | SCALE, Angela | 2026-02-04 21:47 | 2026-03-05 12:03
22 | 233 | Over recent months, the team have been reviewing the future of NCCIS ahead of the Access Ltd contract ending in March 2026. Team can't extend or re-award the contract due to Cabinet Office rules on open procurement. There are concerns around value for money, and the system has seen little development since 2006. We also believe Access Ltd has become complacent. However, open procurement would require building a new bespoke system—Access Ltd owns the IP and is unlikely to sell. This route could cost at least double the current contract value as we would need to find money for discovery and development costs in addition to running costs. Instead, team is exploring an in-house solution. Options include collecting anonymised data from LA CCIS systems or finding another independent method for tracking NEET levels and holding LAs accountable. March 2027 assuming we can extend contract with existing supplier for another year otherwise March 2026 | Nabeel.RAUF@EDUCATION.GOV.UK | RAUF, Nabeel | 2026-02-09 10:55 | 2026-02-09 10:55
23 | 234 | Education settings are hindered in their support for children and young people with special educational needs and disabilities (SEND) by inconsistent approaches to the recording, monitoring and sharing of needs, provision and progress, fragmented systems and tools, a lack of guidance and support for monitoring early concerns, limited and delayed information sharing within and between settings, particularly at transition points | Emily.SADLER@EDUCATION.GOV.UK | SADLER, Emily | 2026-02-13 16:27 | 2026-02-13 16:27
24 | 136 | The Learner Data Service (LDS) is an annual process for collecting, matching, processing, validating and checking the Department's business critical datasets on learner participation and achievement, children and early years. | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-02-18 13:41 | 2026-02-18 13:41
25 | 238 | The Learner Data Service (LDS) is an annual process for collecting, matching, processing, validating and checking the Department's business critical datasets on learner participation and achievement, children and early years. | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-02-20 15:45 | 2026-02-20 15:45
26 | 135 | The Learner Data Service (LDS) is an annual process for collecting, matching, processing, validating and checking the Department's business critical datasets on learner participation and achievement, children and early years. | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-02-20 15:46 | 2026-02-20 15:46
27 | 134 | The Learner Data Service (LDS) is an annual process for collecting, matching, processing, validating and checking the Department's business critical datasets on learner participation and achievement, children and early years. | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-02-20 15:47 | 2026-02-20 15:47
28 | 133 | The Learner Data Service (LDS) is an annual process for collecting, matching, processing, validating and checking the Department's business critical datasets on learner participation and achievement, children and early years. | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-02-20 15:47 | 2026-02-20 15:47
29 | 45 | The Learner Data Service (LDS) is an annual process for collecting, matching, processing, validating and checking the Department's business critical datasets on learner participation and achievement, children and early years. | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-02-20 15:48 | 2026-02-20 15:48
30 | 153 | The Learner Data Service (LDS) is an annual process for collecting, matching, processing, validating and checking the Department's business critical datasets on learner participation and achievement, children and early years. | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-02-20 15:49 | 2026-02-20 15:49
31 | 167 | We hold valuable user research insights, but it is fragmented and under used with no standard way of managing or leveraging insights. Teams struggle to find and use UR insights, leading to a duplication in research and an inconsistent use of evidence. | Julie.JENKINS@EDUCATION.GOV.UK | JENKINS, Julie | 2026-02-24 13:59 | 2026-02-24 13:59
32 | 237 | Educational practitioners in mainstream primary and secondary schools can experience challenges in both the identification of special educational needs and disabilities (SEND) and the selection of appropriate support. ​ These challenges include:​ - identifying special educational needs and disabilities (SEND) early and accurately​ - finding an approach to identification that is timely and evidence-based​ - easily accessing trusted, evidence-informed strategies to respond to needs once identified​ These challenges can make it difficult to support children and young people. Without accurate identification or easy access to trusted strategies, support offered will not be as effective. This impacts the long-term outcomes and wellbeing of children and young people with SEND.​ ​ This can lead to needs going unmet or escalating and create barriers to a successful transition into adulthood. This then adds pressure on the wider SEND system.​ | Sally.CASEY@EDUCATION.GOV.UK | CASEY, Sally | 2026-02-25 10:16 | 2026-02-25 10:16
33 | 17 | The Department for Education does not have timely oversight of children’s social care (CSC) at national or local authority (LA) level due to the lack of frequency, consistency and quality of the data flowing in and out of the department. The department’s ability to understand, improve and support the needs of LAs and frontline workers most effectively is therefore inhibited. | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 15:23 | 2026-02-25 15:23
34 | 124 | The digital heap (legacy digital records) grows year on year, with no substantive plan to review for destruction/preservation. The team do all of this work manually and is not resourced adequately to do this work due tot he volume Embracing technology may transform the way we deliver this work, making us more efficient and timely in our destructions/preservation. | Sue.WHARAM@education.gov.uk | WHARAM, Sue | 2026-03-02 08:53 | 2026-03-02 08:53
35 | 46 | The Learner Data Service (LDS) is an annual process for collecting, matching, processing, validating and checking the Department's business critical datasets on learner participation and achievement, children and early years. | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 13:39 | 2026-03-02 13:39
36 | 64 | The Education Estates Directorate (EED) is responsible for stewarding around £8bn of annual capital investment across England’s education estate. However, the current landscape has evolved in a fragmented and uncoordinated way, resulting in multiple disconnected systems, inconsistent data standards, and limited trust in the information used to inform investment and delivery decisions. The data EED currently holds on estate condition, capacity and historic investment is not sufficiently timely or sophisticated enough to enable the department’s ambitions for funding decisions to move away from time and resource consuming bid-based funding rounds. EED cannot easily join-up different data sets to provide consistent and comparable insight across the estate. There are quality issues with the data that result in low levels of confidence in its ability to support complex decision making, provide meaningful support for project delivery or to challenge contractors, or for the directorate to assure that funding is consistently targeted where it delivers the greatest value. As the policy environment shifts and RBs are expected to collect and manage and digitally curate their data by 2029, the absence of a coherent digital infrastructure presents a material risk to value for money, safety and strategic oversight. This investment establishes a coordinated digital foundation for EED and RBs by implementing a Common Data Environment, a single front door through MYEE, a customer help and triage service, and a digital project delivery tool. Together, these enable a trusted single source of truth, two-way data exchange with RBs, and integrated decision making from assessment through to delivery. | Kathryn.KING@EDUCATION.GOV.UK | KING, Kathryn | 2026-03-02 17:29 | 2026-03-02 17:30
37 | 229 | DfE’s growing role in advising and enabling the use of AI across the education sector presents opportunities but also significant governance and ethical risks. There is a need to ensure that DfE’s AI strategy, guidance and oversight arrangements are sufficiently clear, consistent and embedded to provide assurance that AI is being promoted and used responsibly, effectively and in line with government expectations. | Arti.BHANDERI@EDUCATION.GOV.UK | BHANDERI, Arti | 2026-03-09 16:34 | 2026-03-09 16:34
38 | 228 | The rapid adoption of AI across DfE and the education sector risks inconsistent and insufficiently assured use without a clear, shared principles‑based framework to guide ethical, transparent and responsible decision‑making. | Arti.BHANDERI@EDUCATION.GOV.UK | BHANDERI, Arti | 2026-03-09 16:43 | 2026-03-09 16:43
39 | 224 | AI activity across DfE is growing but remains fragmented, creating risks to coherence, assurance, duplication of effort/ resource and strategic alignment without a clear central function to lead and coordinate AI activity. | Arti.BHANDERI@EDUCATION.GOV.UK | BHANDERI, Arti | 2026-03-09 16:46 | 2026-03-09 16:46

## ProblemStatementHist
Id | ProjectProblemStatementId | ProblemStatement | ChangedByEmail | ChangedByName | ChangedAt
1 | 1 | The Department for Education delivers a large and varied portfolio of digital services, products, programmes, and operational activities. Information about performance, risks, issues, decisions, actions, compliance, strategic objectives, and service health is currently fragmented across multiple tools, spreadsheets, bespoke processes, and disconnected reporting cycles. This creates duplicated work, inconsistent data quality, opaque governance, and an inability to form a reliable, real-time view of departmental delivery and operational risk. Teams cannot easily trace how risks link to milestones, or how actions connect to issues, decisions, objectives, service assessments, and standards compliance. Strategic reporting relies heavily on manual consolidation, which delays insight and weakens decision-making. Assurance functions lack a single mechanism to monitor compliance across the lifecycle, while delivery teams face repeated evidence requests and inconsistent expectations from governance bodies. As demand increases and services become more interdependent, the department requires a unified, authoritative platform that provides visibility, reduces duplication, improves confidence in data, and supports consistent governance across delivery and live operations. | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-18 11:44
2 | 1 | DfE DDT does not have cohesive guidance to help people delivering products and services in/for DfE - to understand the standards, processes, patterns and ways of working that they need to follow, and the support available to them. Where guidance exists, it is spread across numerous disconnected manuals, each with different content structures, styles, and ownership. This fragmentation results in duplication, gaps, outdated or conflicting guidance. It creates unnecessary complexity and cost, delivers a poor user experience as it is difficult to find, trust, and apply the information they need. This results in a lack of awareness of and adherence to standards, and results in products and services that aren't designed and delivered in an efficient, consistent, high-quality way. | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-18 11:44
3 | 11 | A disjointed service offer is creating additional cost burdens across staffing levels, technology and commercial contracts. In turn this is impacting stakeholder experience and perception of the department. | Stuart.BALNAVES@EDUCATION.GOV.UK | BALNAVES, Stuart | 2026-01-28 10:45
4 | 11 | Across the Department Providers, Citizens, Learners, and Parents experience complexity and confusion when they seek help to do, find or report something to DfE. This results in confusion for the customer because of multiple entry points to different internal teams and inefficiency for the taxpayer as multiple technologies exist and service partnership procurements occur. It also drives duplication across departments people and resources. This workstream seeks to centralise external facing service teams, bringing together knowledge, technology and people to create one consistent service point, with published SLA for the Department. In turn creating efficiency for the taxpayer and simplicity and clarity for the customers we serve. | Stuart.BALNAVES@EDUCATION.GOV.UK | BALNAVES, Stuart | 2026-01-28 10:57
5 | 11 | Across the Department Providers, Citizens, Learners, and Parents experience complexity and confusion when they seek help to do, find or report something to DfE. This results in confusion for the customer because of multiple entry points to different internal teams and inefficiency for the taxpayer as multiple technologies exist and service partnership procurements occur. It also drives duplication across departments people and resources. This workstream seeks to centralise external facing service teams, bringing together knowledge, technology and people to create one consistent service point, with published SLA for the Department. In turn creating efficiency for the taxpayer and simplicity and clarity for the customers we serve. | Stuart.BALNAVES@EDUCATION.GOV.UK | BALNAVES, Stuart | 2026-01-28 11:48
6 | 14 | The Department for Education delivers a wide range of services to citizens, providers, and stakeholders. However, the absence of a unified Customer Service Digital Strategy has led to inconsistent service experiences, siloed design decisions, and digital processes that do not fully account for customer support needs. As a result, customer demand is rising in avoidable areas, with an estimated 4% of annual contact volumes driven directly by gaps or failures in existing digital journeys. Current digital services do not consistently follow the modern government blueprint for service design—services that should be simple, consistent, and digital by default, while ensuring that individuals who are vulnerable or experiencing complex challenges can still access a human “hand to hold” when needed. In several cases, digital services have been designed or deployed without adequately considering the end‑to‑end customer experience, leading to confusion, incomplete journeys, or a lack of clarity around next steps. This has created service pressures across the front line customer service teams, increasing operational workload and reducing capacity to support customers who genuinely require personalised assistance. The problem is exacerbated by fragmented decision‑making across programmes, where service and digital design choices are often made in isolation. This reduces the ability to share insight, reuse capability, or maintain consistent user journeys across the DfE estate. It also prevents customer insight from being systematically incorporated into service design, meaning issues that generate avoidable contact can persist for long periods before they are addressed. Without an overarching Customer Service Digital Strategy, DfE lacks the coordinated customer governance standards, and insight‑driven feedback loops needed to design digital services that are both efficient and truly user‑centred. This limits the Department’s ability to reduce failure demand, automate simple enquiries, and improve service quality at scale | Stuart.BALNAVES@EDUCATION.GOV.UK | BALNAVES, Stuart | 2026-01-28 14:02
7 | 13 | Customer Service teams are generating a significant volume of insight that highlights recurring failures in organisational processes, policies, and communications. However, these insights are not being consistently acted upon across the business. As a result, the same issues continue to surface, driving customers to seek support for problems that could otherwise be prevented. Over the last 12 months, unplanned customer contact has generated 11% of the total annual workload with a high proportion of enquiries linked to avoidable failure points already identified by front-line teams. This is unnecessary contact is placing pressure on Customer Service capacity, creating longer wait times, and negatively affecting customer experience. Additionally, unresolved friction in process and communication flows is contributing to increased operational costs, inefficiencies, and reduced trust in our ability to resolve recurring issues. The scope of this problem includes the capture, analysis, and escalation of customer insight, along with the organisational mechanisms for addressing root causes related to broken or unclear processes, outdated or inconsistent policies, and insufficient or confusing communications. | Stuart.BALNAVES@EDUCATION.GOV.UK | BALNAVES, Stuart | 2026-01-28 15:13
8 | 13 | Customer Service teams are generating a significant volume of data that highlights recurring failures in organisational processes, policies, and communications. However, this data needs to be analysed to produce actionable insights, that can be consistently acted upon across the business. Currently, the same issues continue to surface, driving customers to seek support for problems that could otherwise be prevented. Over the last 12 months, unplanned customer contact has generated 11% of the total annual workload with a high proportion of enquiries linked to avoidable failure points already identified by front-line teams. This unnecessary contact is placing pressure on Customer Service capacity, creating longer wait times, and negatively affecting customer experience. Additionally, unresolved friction in process and communication flows is contributing to increased operational costs, inefficiencies, and reduced trust in our ability to resolve recurring issues. The scope of this problem includes the capture, analysis, and escalation of customer data, along with the organisational mechanisms for addressing root causes related to broken or unclear processes, outdated or inconsistent policies, and insufficient or confusing communications. | Stuart.BALNAVES@EDUCATION.GOV.UK | BALNAVES, Stuart | 2026-01-28 15:15
9 | 18 | Providing a solution for none developers to create and deploy digital forms to reduce bottlenecks and competition for resources. | Joe.YOUNG@EDUCATION.GOV.UK | YOUNG, Joe | 2026-02-02 15:39
10 | 19 | ALBs face limitations in cyber maturity, due diligence, and digital infrastructure, creating systemic vulnerabilities and increasing DfE’s exposure to reputational, financial, and data risks.​ ​ | Angela.SCALE@EDUCATION.GOV.UK | SCALE, Angela | 2026-02-04 11:34
11 | 19 | ALBs face limitations in cyber maturity, due diligence, and digital infrastructure, creating systemic vulnerabilities and increasing DfE’s exposure to reputational, financial, and data risks.​ Recent high-profile cyber incidents and a joint Cabinet Office/NCSC letter underscore unacceptable technology risks across public sector ALBs.​ ​ ​ | Angela.SCALE@EDUCATION.GOV.UK | SCALE, Angela | 2026-02-04 11:34
12 | 19 | ALBs face limitations in cyber maturity, due diligence, and digital infrastructure, creating systemic vulnerabilities and increasing DfE’s exposure to reputational, financial, and data risks.​ Recent high-profile cyber incidents and a joint Cabinet Office/NCSC letter underscore unacceptable technology risks across public sector ALBs.​ ​ The Government Security Strategy, Functional Standard GovS 007, and government Cyber Action Plan (CAP) mandate stronger departmental oversight of ALBs, with clear accountability for sector-wide resilience.​ ​ | Angela.SCALE@EDUCATION.GOV.UK | SCALE, Angela | 2026-02-04 11:41
13 | 19 | ALBs face limitations in cyber maturity, due diligence, and digital infrastructure, creating systemic vulnerabilities and increasing DfE’s exposure to reputational, financial, and data risks.​ Recent high-profile cyber incidents and a joint Cabinet Office/NCSC letter underscore unacceptable technology risks across public sector ALBs.​ ​ The Government Security Strategy, Functional Standard GovS 007, and government Cyber Action Plan (CAP) mandate stronger departmental oversight of ALBs, with clear accountability for sector-wide resilience.​ ​ | Angela.SCALE@EDUCATION.GOV.UK | SCALE, Angela | 2026-02-04 11:41
14 | 21 | We face an increasingly complex and hostile cyber threat environment, with heightened risks to government services and data. Recent security and data incidents both within and outside our organisation have shown the need for greater visibility, stronger controls, and faster risk mitigation | Angela.SCALE@EDUCATION.GOV.UK | SCALE, Angela | 2026-02-04 21:47
15 | 13 | Customer Service teams are generating a significant volume of data that highlights recurring failures in organisational processes, policies, and communications. However, this data needs to be analysed to produce actionable insights, that can be consistently acted upon across the business. Currently, the same issues continue to surface, driving customers to seek support for problems that could otherwise be prevented. Over the last 12 months, unplanned customer contact has generated 11% of the total annual workload with a high proportion of enquiries linked to avoidable failure points already identified by front-line teams. This unnecessary contact is placing pressure on Customer Service capacity, creating longer wait times, and negatively affecting customer experience. Additionally, unresolved friction in process and communication flows is contributing to increased operational costs, inefficiencies, and reduced trust in our ability to resolve recurring issues. The scope of this problem includes the capture, analysis, and escalation of customer data, along with the organisational mechanisms for addressing root causes related to broken or unclear processes, outdated or inconsistent policies, and insufficient or confusing communications. | Clare.CHARLESWORTH@EDUCATION.GOV.UK | CHARLESWORTH, Clare | 2026-02-19 16:54
16 | 32 | Educational practitioners in mainstream primary and secondary schools can experience challenges in both the identification of special educational needs and disabilities (SEND) and the selection of appropriate support. ​ ​ These challenges include:​ ​ identifying special educational needs and disabilities (SEND) early and accurately​ finding an approach to identification that is timely and evidence-based​ easily accessing trusted, evidence-informed strategies to respond to needs once identified​ ​ These challenges can make it difficult to support children and young people. Without accurate identification or easy access to trusted strategies, support offered will not be as effective. This impacts the long-term outcomes and wellbeing of children and young people with SEND.​ ​ This can lead to needs going unmet or escalating and create barriers to a successful transition into adulthood. This then adds pressure on the wider SEND system.​ | Sally.CASEY@EDUCATION.GOV.UK | CASEY, Sally | 2026-02-25 10:16
17 | 36 | The Education Estates Directorate (EED) is responsible for stewarding around £8bn of annual capital investment across England’s education estate. However, the current landscape has evolved in a fragmented and uncoordinated way, resulting in multiple disconnected systems, inconsistent data standards, and limited trust in the information used to inform investment and delivery decisions. The data EED currently holds on estate condition, capacity and historic investment is not sufficiently timely or sophisticated enough to enable the department’s ambitions for funding decisions to move away from time and resource consuming bid-based funding rounds. EED cannot easily join-up different data sets to provide consistent and comparable insight across the estate. There are quality issues with the data that result in low levels of confidence in its ability to support complex decision making, provide meaningful support for project delivery or to challenge contractors, or for the directorate to assure that funding is consistently targeted where it delivers the greatest value. | Kathryn.KING@EDUCATION.GOV.UK | KING, Kathryn | 2026-03-02 17:30
18 | 21 | We face an increasingly complex and hostile cyber threat environment, with heightened risks to government services and data. Recent security and data incidents both within and outside our organisation have shown the need for greater visibility, stronger controls, and faster risk mitigation | Angela.SCALE@EDUCATION.GOV.UK | SCALE, Angela | 2026-03-05 12:03

## ProjectMissions
Id | ProjectId | MissionId | CreatedAt
2 | 218 | 3 | 2026-01-27 13:30
3 | 217 | 2 | 2026-02-06 11:53
4 | 21 | 2 | 2026-02-06 11:55
5 | 20 | 2 | 2026-02-06 11:56
6 | 143 | 3 | 2026-02-06 11:57
7 | 142 | 3 | 2026-02-06 12:30
8 | 216 | 3 | 2026-02-06 12:31
9 | 213 | 3 | 2026-02-06 12:32
10 | 30 | 3 | 2026-02-06 12:35
11 | 49 | 3 | 2026-02-06 12:35
12 | 47 | 3 | 2026-02-06 12:38
15 | 39 | 2 | 2026-02-06 12:39
16 | 48 | 1 | 2026-02-06 14:05
17 | 227 | 3 | 2026-02-06 14:10
18 | 24 | 1 | 2026-02-06 14:12
19 | 132 | 3 | 2026-02-06 14:14
20 | 88 | 3 | 2026-02-06 14:16
21 | 127 | 2 | 2026-02-06 14:42
22 | 37 | 3 | 2026-02-09 07:38
23 | 35 | 3 | 2026-02-09 07:38
24 | 36 | 3 | 2026-02-09 07:39
25 | 34 | 3 | 2026-02-09 07:40
26 | 33 | 3 | 2026-02-09 07:40
27 | 234 | 3 | 2026-02-13 12:36
28 | 235 | 3 | 2026-02-13 16:15
29 | 236 | 3 | 2026-02-13 16:20
30 | 237 | 3 | 2026-02-13 16:25
31 | 239 | 3 | 2026-02-19 12:12
32 | 240 | 3 | 2026-02-19 16:07
33 | 64 | 3 | 2026-02-27 17:01
34 | 258 | 1 | 2026-03-03 13:33
35 | 259 | 4 | 2026-03-03 13:42

## ResourceFunding
Id | ProjectId | ResourceType | ProgrammeFundedPercentage | AdminFundedPercentage | Notes | CreatedAt | UpdatedAt
1 | 1 | Permanent | 0.00 | 100.00 |  | 2025-11-04 14:08 | 2025-11-04 14:08
2 | 6 | Permanent | 0.00 | 100.00 |  | 2025-11-12 15:08 | 2025-11-12 15:08
3 | 6 | MSP | 100.00 | 0.00 |  | 2025-11-12 15:08 | 2025-11-12 15:08
4 | 7 | Permanent | 0.00 | 100.00 |  | 2025-11-13 07:54 | 2025-11-13 07:54

## ResourceFundingHist
Id | ProjectId | ResourceType | Count | ProgrammeFundedPercentage | AdminFundedPercentage | Notes | ChangedAt | ChangedByEmail | ChangedByName
1 | 1 | Permanent | 5.00 | 0.00 | 100.00 |  | 2025-11-04 14:08 | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk
2 | 6 | Permanent | 5.00 | 0.00 | 100.00 |  | 2025-11-12 15:08 | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk
3 | 6 | MSP | 1.00 | 100.00 | 0.00 |  | 2025-11-12 15:08 | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk
4 | 7 | Permanent | 1.00 | 0.00 | 100.00 |  | 2025-11-13 07:54 | Louise.CLARK@EDUCATION.GOV.UK | Louise.CLARK@EDUCATION.GOV.UK

## ProjectContacts
Id | ProjectId | UserId | Role | Name | Email | RoleDescription | SortOrder | FundingArrangement | TimeAllocation | EmploymentType | TeamStatus | LeaveReason | LeftAt | CreatedAt | UpdatedAt
1 | 1 | 1 | Head of Design | JONES, Andy | Andy.JONES@education.gov.uk |  | 1 | Admin | 25% | Permanent | current |  |  | 2025-10-31 11:12 | 2026-01-29 10:50
2 | 1 | 3 | Not specified | CLARK, Louise | Louise.CLARK@education.gov.uk |  | 1 | Not specified |  | Permanent | current |  |  | 2025-10-31 11:14 | 2025-11-17 10:06
3 | 1 | 4 | Head of PMO | WRIGHT, Jo | Jo.WRIGHT@education.gov.uk |  | 1 | Not specified |  | Permanent | current |  |  | 2025-10-31 11:14 | 2025-11-21 14:35
4 | 1 | 5 | Not specified | PATEL, Prina | Prina.PATEL@education.gov.uk |  | 1 | Not specified |  | Permanent | current |  |  | 2025-10-31 11:14 | 2025-11-16 17:16
5 | 1 | 6 | Not specified | DALE, Tracey | Tracey.DALE@education.gov.uk |  | 1 | Not specified |  | Permanent | current |  |  | 2025-10-31 11:15 | 2025-11-16 17:16
6 | 1 | 17 | Deputy Director for Strategy and Efficiency | KEELEY, Daniel | Daniel.KEELEY@education.gov.uk |  | 1 | Admin |  | Permanent | previous | Dan had input into initial development but is not continuously involved. | 2026-01-08 14:44 | 2025-10-31 11:16 | 2026-01-08 14:44
7 | 2 | 92 | Project Lead | Louise Shutt | louise.shutt@education.gov.uk |  | 1 | Not specified |  | Permanent | current |  |  | 2025-10-31 11:50 | 2025-12-18 15:29
8 | 2 | 93 | Project Lead | Rachel Mountcastle | rachel.mountcastle@education.gov.uk |  | 1 | Not specified |  | Permanent | current |  |  | 2025-10-31 11:50 | 2026-01-26 13:42
9 | 5 | 93 | Project Lead | Rachel Mountcastle | rachel.mountcastle@education.gov.uk |  | 1 | Not specified |  | Permanent | current |  |  | 2025-10-31 11:52 | 2026-01-26 13:45
10 | 5 | 92 | Project Lead | Louise Shutt | louise.shutt@education.gov.uk |  | 1 | Not specified |  | Permanent | current |  |  | 2025-10-31 11:52 | 2026-01-26 13:45
11 | 3 | 92 | Project Lead | Louise Shutt | louise.shutt@education.gov.uk |  | 1 | Not specified |  | Permanent | current |  |  | 2025-10-31 11:52 | 2025-12-22 11:10
12 | 3 | 93 | Project Lead | Rachel Mountcastle | rachel.mountcastle@education.gov.uk |  | 1 | Not specified |  | Permanent | current |  |  | 2025-10-31 11:53 | 2025-12-22 11:10
13 | 6 | 23 | Product Manager | KELMAN, Paul | Paul.KELMAN@education.gov.uk |  | 1 | Admin | 25% | Permanent | current |  |  | 2025-11-12 14:27 | 2026-02-03 13:04
14 | 6 | 24 | Delivery Manager | OSBORNE, Kuldip | Kuldip.OSBORNE@education.gov.uk |  | 1 | Admin | Less than 25% | Permanent | current |  |  | 2025-11-12 14:27 | 2026-02-03 13:04
15 | 6 | 2 | Content Designer | LYONS, Kerry | Kerry.LYONS@education.gov.uk |  | 1 | Admin | 25% | Permanent | current |  |  | 2025-11-12 14:27 | 2026-02-03 13:03
16 | 6 | 25 | User Researcher | DUMBELL, Adam | Adam.DUMBELL@education.gov.uk |  | 1 | Admin | 25% | Permanent | current |  |  | 2025-11-12 14:28 | 2026-02-03 13:03
17 | 6 | 26 | Service Designer | CLARKE, Sammi | Sammi.CLARKE@EDUCATION.GOV.UK |  | 1 | Admin | Less than 25% | Permanent | current |  |  | 2025-11-12 14:29 | 2026-02-03 13:03
18 | 6 | 27 | Business Analyst | MORRIS, Sherene | Sherene.MORRIS@education.gov.uk |  | 1 | Admin | 50% | Permanent | current |  |  | 2025-11-12 14:29 | 2026-02-03 13:03
19 | 6 | 28 | Test Analyst | SHIWANI, Shalini | Shalini.SHIWANI@education.gov.uk |  | 1 | Admin | 100% | MSP | current |  |  | 2025-11-12 14:30 | 2026-02-03 13:03
20 | 6 | 29 | Head of Business Analysis | SAUNDERSON, Emily | Emily.SAUNDERSON@education.gov.uk |  | 1 | Admin | Less than 25% | Permanent | current |  |  | 2025-11-12 14:30 | 2026-02-03 13:03
21 | 6 | 1 | Head of Design | JONES, Andy | Andy.JONES@education.gov.uk | Also dev and interaction design | 1 | Admin | 25% | Permanent | current |  |  | 2025-11-12 14:31 | 2026-02-03 13:03
22 | 7 | 4 | Owner | WRIGHT, Jo | Jo.WRIGHT@education.gov.uk |  | 1 | Not specified |  | Permanent | current |  |  | 2025-11-13 07:51 | 2025-11-16 17:40
23 | 7 | 5 | DDT Risk Lead | PATEL, Prina | Prina.PATEL@education.gov.uk |  | 1 | Not specified |  | Permanent | current |  |  | 2025-11-13 07:52 | 2025-11-16 17:40
24 | 7 | 3 | DDT Risk owner | CLARK, Louise | Louise.CLARK@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2025-11-13 07:53 | 2025-11-26 09:35
25 | 1 | 21 | Lead Service Designer | KAMPASI, Juliet | Juliet.KAMPASI@education.gov.uk |  | 7 | Admin | 25% | Permanent | current |  |  | 2025-11-16 17:17 | 2026-01-29 10:50
26 | 15 | 1 | Head of Design | JONES, Andy | Andy.JONES@education.gov.uk |  | 1 | Admin | 50% | Permanent | current |  |  | 2025-11-17 08:05 | 2026-02-21 15:49
27 | 15 | 30 | Head of User Research | ADAMS, Tom | Tom.ADAMS@education.gov.uk |  | 2 | Admin | Less than 25% | Permanent | current |  |  | 2025-11-17 08:05 | 2026-02-21 15:49
28 | 15 | 31 | Head of Product | BLANCHARD, Debbie | Debbie.BLANCHARD@education.gov.uk |  | 3 | Admin | Less than 25% | Permanent | current |  |  | 2025-11-17 08:05 | 2026-02-21 15:50
29 | 15 | 29 | Head of Business Analysis | SAUNDERSON, Emily | Emily.SAUNDERSON@education.gov.uk |  | 4 | Not specified |  | Permanent | current |  |  | 2025-11-17 08:05 | 2025-11-17 08:05
30 | 15 | 32 | Head of Architecture | SLOWEN, Luke | Luke.SLOWEN@education.gov.uk |  | 5 | Not specified |  | Permanent | current |  |  | 2025-11-17 08:06 | 2025-11-17 08:06
31 | 15 | 3 | Head of Central Operations | CLARK, Louise | Louise.CLARK@education.gov.uk |  | 6 | Not specified |  | Permanent | current |  |  | 2025-11-17 08:12 | 2025-11-17 08:12
32 | 15 | 2 | Content Designer | LYONS, Kerry | Kerry.LYONS@education.gov.uk |  | 7 | Admin | 75% | Permanent | current |  |  | 2025-11-17 09:26 | 2026-02-21 15:49
33 | 15 | 4 | Head of PMO | WRIGHT, Jo | Jo.WRIGHT@education.gov.uk |  | 8 | Not specified |  | Permanent | current |  |  | 2025-11-18 09:31 | 2025-11-18 09:31
34 | 179 | 1 | Head of Design | JONES, Andy | Andy.JONES@education.gov.uk |  | 1 | Not specified |  | Permanent | current |  |  | 2025-11-20 14:14 | 2025-11-20 14:14
35 | 179 | 7 | Senior Accessibility Specialist | LLOYD, Jake | Jake.LLOYD@education.gov.uk |  | 2 | Not specified |  | Permanent | current |  |  | 2025-11-22 11:21 | 2025-11-22 11:21
36 | 197 | 1 | Head of Design | JONES, Andy | Andy.JONES@education.gov.uk |  | 1 | Admin | 100% | Permanent | current |  |  | 2025-11-25 17:14 | 2025-11-25 17:14
37 | 197 | 30 | Head of User Research | ADAMS, Tom | Tom.ADAMS@education.gov.uk |  | 2 | Admin | 100% | Permanent | current |  |  | 2025-11-25 17:15 | 2025-11-25 17:15
38 | 197 | 31 | Head of Product | BLANCHARD, Debbie | Debbie.BLANCHARD@education.gov.uk |  | 3 | Admin | 100% | Permanent | current |  |  | 2025-11-25 17:15 | 2025-11-25 17:15
39 | 197 | 32 | Head of Architecture | SLOWEN, Luke | Luke.SLOWEN@education.gov.uk |  | 4 | Admin | 100% | Permanent | current |  |  | 2025-11-25 17:15 | 2025-11-25 17:15
40 | 197 | 29 | Head of Business Analysis | SAUNDERSON, Emily | Emily.SAUNDERSON@education.gov.uk |  | 5 | Admin | 100% | Permanent | current |  |  | 2025-11-25 17:16 | 2025-11-25 17:16
41 | 199 | 7 | Senior Accessibility Specialist | LLOYD, Jake | Jake.LLOYD@education.gov.uk |  | 1 | Admin | 100% | Permanent | current |  |  | 2025-11-27 08:52 | 2025-11-27 08:52
42 | 199 | 2 | Senior Content Designer | LYONS, Kerry | Kerry.LYONS@education.gov.uk |  | 2 | Admin | 100% | Permanent | current |  |  | 2025-11-27 08:52 | 2025-11-27 08:52
43 | 199 | 25 | User Researcher | DUMBELL, Adam | Adam.DUMBELL@education.gov.uk |  | 3 | Admin | 100% | Permanent | current |  |  | 2025-11-27 08:52 | 2025-11-27 08:52
44 | 198 | 2 | Senior Content Designer | LYONS, Kerry | Kerry.LYONS@education.gov.uk |  | 1 | Admin | Less than 25% | Permanent | current |  |  | 2025-11-27 09:01 | 2025-11-27 09:01
45 | 198 | 78 | Service Assessment Lead | DUNN, Michael | Michael.DUNN@education.gov.uk |  | 2 | Admin | 100% | Permanent | current |  |  | 2025-11-27 09:01 | 2025-11-27 09:01
46 | 198 | 77 | Spend Control Lead | PERKINS, Gary | Gary.PERKINS@education.gov.uk |  | 3 | Admin | 100% | Permanent | current |  |  | 2025-11-27 09:01 | 2025-11-27 09:01
47 | 198 | 25 | User Researcher | DUMBELL, Adam | Adam.DUMBELL@education.gov.uk |  | 4 | Admin | Less than 25% | Permanent | current |  |  | 2025-11-27 09:02 | 2025-11-27 09:02
48 | 1 | 2 | Senior Content Designer | LYONS, Kerry | Kerry.LYONS@education.gov.uk |  | 8 | Admin | Less than 25% | Permanent | previous | Only for content review | 2026-01-29 10:50 | 2025-11-27 09:32 | 2026-01-29 10:50
49 | 54 | 82 | Head of PMO | BLUNT, Anne-Marie | Anne-Marie.BLUNT@education.gov.uk |  | 1 | Admin |  | Permanent | previous | Added in error. Should have been added to governance contacts. | 2025-11-27 10:17 | 2025-11-27 10:15 | 2025-11-27 10:17
50 | 209 | 91 | Delivery Manager | LOWTHER, Jonathan | Jonathan.LOWTHER@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2025-12-18 12:26 | 2025-12-18 12:26
51 | 200 | 95 | G6 Programme Lead | LAMB, Annaliese | Annaliese.LAMB@EDUCATION.GOV.UK |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-05 12:09 | 2026-01-05 12:09
52 | 200 | 96 | Programme Delivery Manager | WATERFIELD, John | John.WATERFIELD@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-01-05 12:46 | 2026-01-05 12:46
53 | 200 | 97 | Delivery Manager (Find User Insights Project) | JENKINS, Julie | Julie.JENKINS@education.gov.uk |  | 3 | Admin |  | Permanent | current |  |  | 2026-01-05 12:46 | 2026-01-05 12:46
54 | 200 | 24 | Delivery Manager (Find Information about Products and Services) | OSBORNE, Kuldip | Kuldip.OSBORNE@education.gov.uk |  | 4 | Admin |  | Permanent | current |  |  | 2026-01-05 12:47 | 2026-01-05 12:47
55 | 205 | 98 | G6 Programme Lead | CHACHOU, George | George.CHACHOU@education.gov.uk |  | 1 | Admin | 100% | Permanent | current |  |  | 2026-01-05 12:51 | 2026-01-05 12:54
56 | 205 | 99 | Senior Product Manager | KLAASSEN, Jenny | Jenny.KLAASSEN@education.gov.uk |  | 2 | Admin | 100% | Permanent | current |  |  | 2026-01-05 12:52 | 2026-01-05 12:53
57 | 205 | 100 | Senior Data Architect | ROTHWELL, Mick | Mick.ROTHWELL@education.gov.uk |  | 3 | Admin |  | MSP | current |  |  | 2026-01-05 12:53 | 2026-01-05 12:57
58 | 205 | 101 | Delivery Manager | HAMMOND, Mark | Mark.HAMMOND@education.gov.uk |  | 4 | Admin | 100% | Permanent | current |  |  | 2026-01-05 12:53 | 2026-01-05 15:25
59 | 205 | 102 | Delivery Manager (WS1) | BAINS, Angela | Angela.BAINS@education.gov.uk |  | 5 | Admin | 100% | Permanent | current |  |  | 2026-01-05 12:54 | 2026-01-05 12:54
60 | 205 | 103 | Delivery Manager | BEHESHTI-SHIRAZI, Katherine | Katherine.BEHESHTI-SHIRAZI@education.gov.uk |  | 6 | Programme | 100% | Permanent | previous | Transfer to another project | 2026-01-05 12:55 | 2026-01-05 12:55 | 2026-01-05 12:55
61 | 205 | 104 | Delivery Manager (WS2) | WIERZEWSKA, Joanna | Joanna.WIERZEWSKA@education.gov.uk |  | 7 | Admin | 100% | Permanent | current |  |  | 2026-01-05 12:56 | 2026-01-05 12:56
62 | 205 | 105 | Delivery Manager (WS3) | KING, Lisa | Lisa.KING@education.gov.uk |  | 8 | Admin | 100% | MSP | current |  |  | 2026-01-05 12:57 | 2026-02-17 10:47
63 | 46 | 106 | Delivery Manager | SMITH, Sam | Sam.SMITH@education.gov.uk |  | 1 | Programme |  | MSP | current |  |  | 2026-01-05 14:07 | 2026-01-05 14:10
64 | 202 | 110 | Delivery Manager | MCWHIRTER, Paul | Paul.MCWHIRTER@EDUCATION.GOV.UK |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-05 16:02 | 2026-01-05 16:02
65 | 204 | 111 | Delivery Manager | PADAM, Hardeep | Hardeep.PADAM@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-05 16:10 | 2026-01-05 16:10
66 | 210 | 112 | G6 Programme Lead | MANIK, Tejinder | Tejinder.MANIK@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-05 16:11 | 2026-01-05 16:11
67 | 187 | 61 | Head of ALB & Sector | DUNNE, Alison | Alison.Dunne@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-07 15:32 | 2026-02-02 21:05
68 | 184 | 121 | Head of Governance Risk and Compliance | PHILLIPS, Mark2 | Mark2.PHILLIPS@EDUCATION.GOV.UK |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-07 15:35 | 2026-02-03 14:53
69 | 184 | 122 | Head of Cyber Operations | STANLEY, Clare | Clare.STANLEY@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-01-07 15:35 | 2026-02-03 15:37
70 | 185 | 121 | Head of Governance Risk and Compliance | PHILLIPS, Mark2 | Mark2.PHILLIPS@EDUCATION.GOV.UK |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-07 15:37 | 2026-02-02 16:48
71 | 206 | 102 | Delivery Manager | BAINS, Angela | Angela.BAINS@education.gov.uk |  | 1 | Admin | 100% | Permanent | current |  |  | 2026-01-07 15:38 | 2026-01-07 15:38
72 | 188 | 121 | Head of Governance Risk and Compliance | PHILLIPS, Mark2 | Mark2.PHILLIPS@EDUCATION.GOV.UK |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-07 15:43 | 2026-02-02 16:36
73 | 207 | 104 | Delivery Manager | WIERZEWSKA, Joanna | Joanna.WIERZEWSKA@education.gov.uk |  | 1 | Admin | 100% | Permanent | current |  |  | 2026-01-07 15:56 | 2026-01-07 15:56
74 | 208 | 105 | Delivery Manager | KING, Lisa | Lisa.KING@education.gov.uk |  | 1 | Admin | 75% | MSP | current |  |  | 2026-01-07 16:04 | 2026-01-07 16:04
75 | 200 | 123 | Change Manager | SPATARO, Blanche | Blanche.SPATARO@education.gov.uk |  | 5 | Admin |  | Permanent | current |  |  | 2026-01-07 16:59 | 2026-01-07 16:59
76 | 200 | 124 | Change Manager | RUSSELL, Judith | Judith.RUSSELL@EDUCATION.GOV.UK |  | 6 | Admin |  | Permanent | current |  |  | 2026-01-07 17:00 | 2026-01-07 17:00
77 | 167 | 97 | Delivery Manager | JENKINS, Julie | Julie.JENKINS@education.gov.uk |  | 1 | Admin | 100% | Permanent | current |  |  | 2026-01-07 17:01 | 2026-01-07 17:01
78 | 166 | 17 | S &T DD | KEELEY, Daniel | Daniel.KEELEY@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-08 14:20 | 2026-01-08 14:20
79 | 205 | 17 | Strategy & Transformation DD | KEELEY, Daniel | Daniel.KEELEY@education.gov.uk |  | 9 | Admin |  | Permanent | current |  |  | 2026-01-08 14:22 | 2026-01-15 16:35
80 | 206 | 17 | Strategy & Transformation DD | KEELEY, Daniel | Daniel.KEELEY@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-01-08 14:23 | 2026-01-15 16:21
81 | 207 | 17 | Strategy & Transformation DD | KEELEY, Daniel | Daniel.KEELEY@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-01-08 14:24 | 2026-01-15 16:42
82 | 208 | 17 | S & T DD | KEELEY, Daniel | Daniel.KEELEY@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-01-08 14:24 | 2026-01-08 14:24
83 | 167 | 10 | DD | BARTON, Sam | Sam.BARTON@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-01-08 14:25 | 2026-03-03 17:11
84 | 167 | 486 | Product Manager | BROWN, Stacy | Stacy.BROWN@education.gov.uk |  | 3 | Admin | 100% | MSP | current |  |  | 2026-01-08 14:25 | 2026-03-03 17:15
85 | 210 | 17 | S & T DD | KEELEY, Daniel | Daniel.KEELEY@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-01-08 14:26 | 2026-01-08 14:26
86 | 209 | 17 | S & T DD | KEELEY, Daniel | Daniel.KEELEY@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-01-08 14:27 | 2026-01-08 14:27
87 | 202 | 17 | Strategy & Transformation DD | KEELEY, Daniel | Daniel.KEELEY@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-01-08 14:27 | 2026-01-15 17:01
88 | 204 | 17 | S & T DD | KEELEY, Daniel | Daniel.KEELEY@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-01-08 14:28 | 2026-01-08 14:28
89 | 168 | 130 | Product Manager | SHARMA, Deepak | Deepak.SHARMA@education.gov.uk |  | 1 | Programme | 100% | Permanent | current |  |  | 2026-01-13 10:20 | 2026-01-13 10:20
90 | 137 | 131 | Product Manager | AROLKER, Clare | Clare.AROLKER@education.gov.uk |  | 1 | Programme | 75% | Permanent | current |  |  | 2026-01-13 10:21 | 2026-01-13 10:22
91 | 15 | 132 | Head of Delivery Management | CHILCOTT, Laura | Laura.CHILCOTT@EDUCATION.GOV.UK |  | 9 | Admin | 25% | Permanent | current |  |  | 2026-01-13 12:11 | 2026-01-13 12:11
92 | 197 | 132 | Head of Delivery Management | CHILCOTT, Laura | Laura.CHILCOTT@EDUCATION.GOV.UK |  | 6 | Admin | 100% | Permanent | current |  |  | 2026-01-13 12:12 | 2026-01-13 12:12
93 | 160 | 140 | G6 Deputy for SRO | CHARLESWORTH, Clare | Clare.CHARLESWORTH@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-15 14:45 | 2026-01-15 14:45
94 | 159 | 140 | G6 - Deputy for SRO | CHARLESWORTH, Clare | Clare.CHARLESWORTH@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-15 14:47 | 2026-01-15 14:47
95 | 161 | 140 | G6 - Deputy for SRO | CHARLESWORTH, Clare | Clare.CHARLESWORTH@education.gov.uk |  | 1 | Programme |  | Permanent | current |  |  | 2026-01-15 14:48 | 2026-02-19 16:30
96 | 162 | 140 | G6 - Deputy for SRO | CHARLESWORTH, Clare | Clare.CHARLESWORTH@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-15 14:48 | 2026-01-15 14:48
97 | 164 | 452 | G6 - Deputy for SRO | ALLEN, Paul2 | Paul2.ALLEN@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-15 14:49 | 2026-02-19 16:56
98 | 163 | 140 | G6 - Deputy for SRO | CHARLESWORTH, Clare | Clare.CHARLESWORTH@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-15 14:50 | 2026-01-15 14:50
99 | 206 | 142 | Solution Architect | APPLETON-POWER, Robin | Robin.APPLETON-POWER@education.gov.uk |  | 3 | Admin | 100% | MSP | current |  |  | 2026-01-15 16:24 | 2026-01-15 16:24
100 | 206 | 143 | Solution Architect | HARDIE, Margaret | Margaret.HARDIE@education.gov.uk |  | 4 | Admin | 100% | MSP | current |  |  | 2026-01-15 16:25 | 2026-01-15 16:25
101 | 206 | 144 | Data Architect | JAIN, Sankalp | Sankalp.JAIN@education.gov.uk |  | 5 | Admin | 100% | MSP | current |  |  | 2026-01-15 16:26 | 2026-01-15 16:26
102 | 206 | 145 | Data Architect | PODILI, Venkata | Venkata.PODILI@education.gov.uk |  | 6 | Admin | 100% | MSP | current |  |  | 2026-01-15 16:26 | 2026-01-15 16:26
103 | 206 | 146 | Solution Architect (Apprentice) | JONES, Chris7 | Chris7.JONES@education.gov.uk |  | 7 | Admin | 100% | Permanent | current |  |  | 2026-01-15 16:28 | 2026-01-15 16:28
104 | 206 | 147 | Data Modeller (DSP) | AMITESH, Kumar | Kumar.AMITESH@education.gov.uk |  | 8 | Admin | 100% | MSP | current |  |  | 2026-01-15 16:29 | 2026-01-15 16:29
105 | 206 | 148 | Data Modeller (DSP) | SAHU, Prasanta | Prasanta.SAHU@education.gov.uk |  | 9 | Admin | 100% | MSP | current |  |  | 2026-01-15 16:29 | 2026-01-15 16:29
106 | 206 | 149 | Data Architect | CHOWDHURY, Jayasree | Jayasree.CHOWDHURY@education.gov.uk |  | 10 | Admin | 100% | MSP | current |  |  | 2026-01-15 16:30 | 2026-01-15 16:30
107 | 206 | 150 | Data Solutions Architect | KIRTON, Matthew | Matthew.KIRTON@education.gov.uk |  | 11 | Admin | 100% | MSP | current |  |  | 2026-01-15 16:32 | 2026-01-15 16:32
108 | 206 | 151 | Data Analyst | WHALLEY, Simon | Simon.WHALLEY@education.gov.uk |  | 12 | Admin |  | MSP | current |  |  | 2026-01-15 16:32 | 2026-01-15 16:32
109 | 205 | 152 | PMO Support | SERIKI, Victoria | Victoria.SERIKI@education.gov.uk |  | 10 | Admin | 100% | MSP | previous | Contract ended | 2026-01-15 16:36 | 2026-01-15 16:36 | 2026-01-15 16:36
110 | 205 | 153 | Comms Lead | RABIN, Wayne | Wayne.RABIN@education.gov.uk |  | 11 | Admin | 100% | MSP | previous | Contract ended | 2026-01-15 16:37 | 2026-01-15 16:37 | 2026-01-15 16:37
111 | 205 | 42 | Governance Manager | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 12 | Admin | 75% | Permanent | previous | Re-prioritisation within division portfolio | 2026-02-17 10:45 | 2026-01-15 16:37 | 2026-02-17 10:45
112 | 205 | 138 | PMO Support | DICKENS, Joel | Joel.DICKENS@education.gov.uk |  | 13 | Admin | 100% | MSP | current |  |  | 2026-01-15 16:38 | 2026-01-15 16:38
113 | 205 | 114 | PMO Support | COLEY, Lorraine | Lorraine.COLEY@education.gov.uk |  | 14 | Admin | 100% | MSP | current |  |  | 2026-01-15 16:38 | 2026-01-15 16:38
114 | 207 | 118 | Data Delivery Manager | O'HARA, Richard | Richard.O'HARA@education.gov.uk |  | 3 | Admin | 100% | Permanent | current |  |  | 2026-01-15 16:42 | 2026-01-15 16:42
115 | 207 | 154 | Business Analyst | HODGSON, Paul | Paul.HODGSON@education.gov.uk |  | 4 | Admin | 100% | MSP | current |  |  | 2026-01-15 16:43 | 2026-01-15 16:43
116 | 207 | 155 | Business Analyst | ATTWELL, Craig | Craig.ATTWELL@education.gov.uk |  | 5 | Admin | 100% | MSP | current |  |  | 2026-01-15 16:43 | 2026-01-15 16:43
117 | 207 | 156 | Data Analyst | LINGAMPALLY, Srinivas | Srinivas.LINGAMPALLY@education.gov.uk |  | 6 | Admin | 100% | MSP | current |  |  | 2026-01-15 16:44 | 2026-01-15 16:44
118 | 207 | 157 | Data Analyst | OLORODE, MOLORODE | Myla.OLORODE@education.gov.uk |  | 7 | Admin | 100% | MSP | current |  |  | 2026-01-15 16:45 | 2026-01-15 16:45
119 | 207 | 158 | User Researcher | WARNER, Emily | Emily.WARNER@education.gov.uk |  | 8 | Admin | 100% | MSP | current |  |  | 2026-01-15 16:46 | 2026-01-15 16:46
120 | 207 | 159 | User Researcher | SONDE, Reni | Reni.SONDE@education.gov.uk |  | 9 | Admin | 100% | MSP | current |  |  | 2026-01-15 16:46 | 2026-01-15 16:46
121 | 207 | 160 | Data Engineer | LUGOPINO, Daniel | Daniel.LUGOPINO@education.gov.uk |  | 10 | Admin | 50% | MSP | current |  |  | 2026-01-15 16:47 | 2026-01-15 16:47
122 | 207 | 161 | Test Engineer | GELLA, Niharika | Niharika.GELLA@education.gov.uk |  | 11 | Admin | 50% | MSP | current |  |  | 2026-01-15 16:47 | 2026-01-15 16:47
123 | 207 | 162 | Infra Engineer | CLARKE, Russell | Russell.CLARKE@education.gov.uk |  | 12 | Admin | 50% | Permanent | current |  |  | 2026-01-15 16:48 | 2026-01-15 16:48
124 | 205 | 163 | Strategy Lead | TOWNSEND, Oliver | Oliver.TOWNSEND@EDUCATION.GOV.UK |  | 15 | Admin | Less than 25% | Permanent | current |  |  | 2026-01-15 16:50 | 2026-02-17 10:49
125 | 211 | 108 | Delivery Manager | LANGLEY, Georgina | Georgina.LANGLEY@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-20 15:54 | 2026-01-20 15:54
126 | 52 | 179 | Product Owner | COLQUHOUN, Alison | Alison.COLQUHOUN@education.gov.uk |  | 1 | Admin | 100% | Permanent | current |  |  | 2026-01-21 16:51 | 2026-01-21 16:51
127 | 52 | 113 | PMO Lead | STRINE, Amanda | Amanda.STRINE@education.gov.uk |  | 2 | Programme | 100% | MSP | current |  |  | 2026-01-21 16:51 | 2026-01-21 16:51
128 | 52 | 190 | Technical Delivery Manager | PAINE, Laura | Laura.PAINE@education.gov.uk |  | 3 | Programme | 100% | MSP | current |  |  | 2026-01-26 16:13 | 2026-01-26 16:13
129 | 52 | 191 | Delivery Manager | LIDHER, Monty | Monty.LIDHER@education.gov.uk |  | 4 | Programme | 100% | Permanent | current |  |  | 2026-01-26 16:36 | 2026-01-26 16:36
130 | 52 | 119 | PMO | MURFITT, Nikki | Nikki.MURFITT@education.gov.uk |  | 5 | Programme | 75% | MSP | current |  |  | 2026-01-26 16:37 | 2026-01-26 16:37
131 | 90 | 195 | Delivery Manager | SINGH, Abhishek | Abhishek.SINGH@education.gov.uk |  | 1 | Admin |  | MSP | current |  |  | 2026-01-27 07:20 | 2026-01-27 07:20
132 | 90 | 194 | Product Manager | SPARKS, Robert | Robert.SPARKS@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-01-27 07:21 | 2026-01-27 07:21
133 | 214 | 196 | Delivery Manager | HILLS, Ami | Ami.HILLS@education.gov.uk |  | 1 | Admin |  | MSP | current |  |  | 2026-01-27 07:23 | 2026-01-27 07:23
134 | 214 | 197 | Product Manager | KEMM, Chris | Chris.KEMM@education.gov.uk |  | 2 | Admin |  | MSP | current |  |  | 2026-01-27 07:23 | 2026-01-27 07:23
135 | 91 | 198 | Product Manager | YOUNG, Joe | Joe.YOUNG@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-27 07:25 | 2026-01-27 07:25
136 | 91 | 199 | Delivery Manager | GANESULA, Lavanya | Lavanya.GANESULA@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-01-27 07:25 | 2026-01-27 07:25
137 | 92 | 200 | Product Manager | THIPPESWAMY, Ravi | Ravi.THIPPESWAMY@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-27 07:26 | 2026-01-27 07:26
138 | 92 | 194 | Product Manager | SPARKS, Robert | Robert.SPARKS@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-01-27 07:26 | 2026-01-27 07:26
139 | 92 | 195 | Delivery Manager | SINGH, Abhishek | Abhishek.SINGH@education.gov.uk |  | 3 | Admin |  | MSP | current |  |  | 2026-01-27 07:26 | 2026-01-27 07:26
140 | 89 | 198 | Product Manager | YOUNG, Joe | Joe.YOUNG@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-27 07:27 | 2026-01-27 07:27
141 | 89 | 199 | Delivery Manager | GANESULA, Lavanya | Lavanya.GANESULA@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-01-27 07:27 | 2026-01-27 07:27
142 | 43 | 201 | Delivery Manager | ABDULLAHI, Amina | Amina.ABDULLAHI@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-27 07:27 | 2026-01-27 07:27
143 | 43 | 202 | Product Manager | LOTAY, Rupinder | Rupinder.LOTAY@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-01-27 07:27 | 2026-01-27 07:27
144 | 215 | 203 | Delivery Manager | HALIM, Amna | Amna.HALIM@education.gov.uk |  | 1 | Admin |  | MSP | current |  |  | 2026-01-27 07:28 | 2026-01-27 07:28
145 | 215 | 204 | Product Manager | DAVIES, Beth6 | Beth6.DAVIES@education.gov.uk |  | 2 | Admin |  | MSP | current |  |  | 2026-01-27 07:28 | 2026-01-27 07:28
146 | 213 | 199 | Delivery Manager | GANESULA, Lavanya | Lavanya.GANESULA@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-27 07:29 | 2026-01-27 07:29
147 | 213 | 205 | Lead Technical Architect | DARBY, Robin | Robin.DARBY@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-01-27 07:29 | 2026-01-27 07:29
148 | 216 | 206 | Product Manager | LEAR, Tor | Tor.LEAR@education.gov.uk |  | 1 | Admin |  | MSP | current |  |  | 2026-01-27 07:29 | 2026-01-27 07:29
149 | 216 | 207 | Delivery Manager | SHARPE, Samantha | Samantha.SHARPE@education.gov.uk |  | 2 | Admin |  | MSP | current |  |  | 2026-01-27 07:30 | 2026-01-27 07:30
150 | 170 | 31 | HOP - PM | BLANCHARD, Debbie | Debbie.BLANCHARD@education.gov.uk |  | 1 | Admin | Less than 25% | Permanent | current |  |  | 2026-01-27 15:30 | 2026-01-27 15:30
151 | 170 | 29 | HOP - BA | SAUNDERSON, Emily | Emily.SAUNDERSON@education.gov.uk |  | 2 | Admin | Less than 25% | Permanent | current |  |  | 2026-01-27 15:31 | 2026-01-27 15:31
152 | 170 | 210 | Strategy and Transformation | KARATHODOROU, Alexandra | Alexandra.KARATHODOROU@education.gov.uk |  | 3 | Admin | Less than 25% | Permanent | current |  |  | 2026-01-27 15:31 | 2026-01-27 15:31
153 | 170 | 211 | Central Operations | GANDY, Kathryn | Kathryn.GANDY@education.gov.uk |  | 4 | Admin | Less than 25% | Permanent | current |  |  | 2026-01-27 15:32 | 2026-01-27 15:32
154 | 170 | 168 | PDM | BRIGGS, Shelley | Shelley.BRIGGS@education.gov.uk |  | 5 | Admin | Less than 25% | Permanent | current |  |  | 2026-01-27 15:32 | 2026-01-27 15:32
155 | 219 | 4 | DDT Demand Lead | WRIGHT, Jo | Jo.WRIGHT@education.gov.uk |  | 1 | Admin | Less than 25% | Permanent | current |  |  | 2026-01-29 13:08 | 2026-01-29 13:08
156 | 80 | 209 | Hd of Capability Based Pay | WILSON, Catherine | Catherine.WILSON@education.gov.uk |  | 1 | Admin | 100% | Permanent | current |  |  | 2026-01-29 14:22 | 2026-01-29 14:22
157 | 80 | 217 | DDT Capability Based Pay (CBP) Manager | STEWART, Jordine | Jordine.STEWART@education.gov.uk |  | 2 | Admin | 100% | Permanent | current |  |  | 2026-01-29 14:23 | 2026-01-29 14:23
158 | 220 | 91 | Delivery Manager | LOWTHER, Jonathan | Jonathan.LOWTHER@education.gov.uk |  | 1 | Programme |  | Permanent | current |  |  | 2026-01-30 10:54 | 2026-01-30 10:54
159 | 222 | 210 | Delivery Manager | KARATHODOROU, Alexandra | Alexandra.KARATHODOROU@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-30 15:43 | 2026-01-30 15:43
160 | 224 | 220 | Delivery Manager | BHANDERI, Arti | Arti.BHANDERI@education.gov.uk |  | 1 | Admin | 100% | Permanent | current |  |  | 2026-01-30 15:54 | 2026-01-30 15:54
161 | 223 | 163 | Delivery Manager | TOWNSEND, Oliver | Oliver.TOWNSEND@EDUCATION.GOV.UK |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-30 15:55 | 2026-01-30 15:55
162 | 225 | 210 | Delivery Manager | KARATHODOROU, Alexandra | Alexandra.KARATHODOROU@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-30 16:01 | 2026-01-30 16:01
163 | 226 | 221 | EO | DOMINGUEZ, Stuart | Stuart.Dominguez@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-30 16:09 | 2026-01-30 16:09
164 | 227 | 163 | Strategy Lead | TOWNSEND, Oliver | Oliver.TOWNSEND@EDUCATION.GOV.UK |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-30 17:27 | 2026-01-30 17:27
165 | 228 | 220 | Strategy Lead | BHANDERI, Arti | Arti.BHANDERI@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-30 17:30 | 2026-01-30 17:30
166 | 229 | 220 | Strategy Lead | BHANDERI, Arti | Arti.BHANDERI@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-30 17:32 | 2026-01-30 17:32
167 | 230 | 222 | Strategic Comms Lead | GILL, Kiranjit | Kiranjit.GILL@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-01-30 17:36 | 2026-01-30 17:36
168 | 158 | 224 | product manager | BROMLEY, Giverny | Giverny.BROMLEY@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-02 08:37 | 2026-02-02 08:37
169 | 182 | 61 | Head of ALB & Sector | DUNNE, Alison | Alison.Dunne@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-02 14:06 | 2026-02-02 14:06
170 | 117 | 61 | Head of ALB & Sector | DUNNE, Alison | Alison.Dunne@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-02 14:36 | 2026-02-02 14:36
171 | 186 | 229 | Head of Data Governance | BENNETT, Mike | Mike.BENNETT@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-02 15:24 | 2026-02-02 15:24
172 | 220 | 112 | Programme Lead | MANIK, Tejinder | Tejinder.MANIK@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-02-02 17:05 | 2026-02-02 17:05
173 | 221 | 112 | Programme Lead | MANIK, Tejinder | Tejinder.MANIK@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-02 17:07 | 2026-02-02 17:07
174 | 221 | 110 | Delivery Manager | MCWHIRTER, Paul | Paul.MCWHIRTER@EDUCATION.GOV.UK |  | 2 | Admin |  | Permanent | current |  |  | 2026-02-02 17:07 | 2026-02-02 17:07
175 | 204 | 112 | Programme Lead | MANIK, Tejinder | Tejinder.MANIK@education.gov.uk |  | 3 | Admin |  | Permanent | current |  |  | 2026-02-02 17:12 | 2026-02-02 17:12
176 | 122 | 108 | Delivery Manager | LANGLEY, Georgina | Georgina.LANGLEY@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-02 18:57 | 2026-02-02 18:57
177 | 69 | 88 | Head of Solutions Delivery | McINTOSH, Iain | Iain.McINTOSH@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-03 14:37 | 2026-02-03 14:37
178 | 72 | 232 | Head of Programme Delivery | BAL, Tirath | Tirath.BAL@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-03 14:39 | 2026-02-03 14:39
179 | 71 | 32 | Head of Profession for Architecture | SLOWEN, Luke | Luke.SLOWEN@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-03 14:42 | 2026-02-03 14:42
180 | 67 | 88 | Head of Solutions Delivery | McINTOSH, Iain | Iain.McINTOSH@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-03 14:51 | 2026-02-03 14:51
181 | 65 | 235 | Head of Profession for Infrastructure | EVANS, Huw | Huw.EVANS@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-03 14:58 | 2026-02-03 14:58
182 | 66 | 237 | Head of Profession for Infrastructure | WILSON, Mark10 - Digital & Technology | Mark10.WILSON@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-03 15:04 | 2026-02-03 15:04
183 | 57 | 238 | Head of Identity Systems | JARVIS, Joe | Joe.JARVIS@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-03 15:12 | 2026-02-03 15:12
184 | 183 | 57 | Head of Transformation | SCALE, Angela | Angela.SCALE@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-04 16:28 | 2026-02-04 16:28
185 | 23 | 88 | Head of Solutions Delivery | McINTOSH, Iain | Iain.McINTOSH@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-05 12:40 | 2026-02-05 12:40
186 | 23 | 252 | Product Manager | HOWARD, Ian | Ian.HOWARD@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-02-05 12:40 | 2026-02-05 12:40
187 | 16 | 172 | Delivery Manager | KENNEDY, Carmel | Carmel.KENNEDY@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-10 09:03 | 2026-02-10 09:03
188 | 205 | 49 | Enterprise Data for Insight DD | RICHARDSON, Corinne | Corinne.RICHARDSON@education.gov.uk |  | 16 | Admin |  | Permanent | current |  |  | 2026-02-17 10:47 | 2026-02-17 10:47
189 | 205 | 412 | Comms Lead | WALKLETT-LYNCH, Laura | Laura.WALKLETT-LYNCH@education.gov.uk |  | 17 | Admin | 100% | Permanent | current |  |  | 2026-02-17 10:48 | 2026-02-17 10:48
190 | 136 | 248 | Programme Manager | BROWNBRIDGE, Joanne | Joanne.BROWNBRIDGE@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-18 11:50 | 2026-02-18 11:50
191 | 134 | 248 | Programme Manager | BROWNBRIDGE, Joanne | Joanne.BROWNBRIDGE@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-18 11:51 | 2026-02-18 11:51
192 | 135 | 248 | Programme Manager | BROWNBRIDGE, Joanne | Joanne.BROWNBRIDGE@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-18 11:51 | 2026-02-18 11:51
193 | 153 | 248 | Programme Manager | BROWNBRIDGE, Joanne | Joanne.BROWNBRIDGE@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-18 11:52 | 2026-02-18 11:52
194 | 45 | 248 | Programme Manager | BROWNBRIDGE, Joanne | Joanne.BROWNBRIDGE@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-18 11:52 | 2026-02-18 11:52
195 | 133 | 248 | Programme Manager | BROWNBRIDGE, Joanne | Joanne.BROWNBRIDGE@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-18 11:53 | 2026-02-18 11:53
196 | 136 | 425 | Delivery Manager | WALL, John | John.WALL@EDUCATION.GOV.UK |  | 2 | Admin |  | Permanent | current |  |  | 2026-02-18 20:08 | 2026-02-18 20:08
197 | 134 | 425 | Delivery Manager | WALL, John | John.WALL@EDUCATION.GOV.UK |  | 2 | Admin |  | Permanent | current |  |  | 2026-02-18 20:09 | 2026-02-18 20:09
198 | 135 | 431 | Delivery Manager | THOMAS, Jon-Pierre | Jon-Pierre.THOMAS@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-02-18 20:09 | 2026-02-18 20:10
199 | 133 | 432 | Delivery Manager | KHAN, Khilat | Khilat.KHAN@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-02-18 20:11 | 2026-02-18 20:11
200 | 45 | 433 | Delivery Manager | PATRICK, Claire-Louise | Claire-Louise.PATRICK@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-02-18 20:11 | 2026-02-18 20:11
201 | 153 | 434 | Delivery Manager | BOOTH, Niall1 | Niall1.BOOTH@education.gov.uk |  | 2 | Admin |  | MSP | current |  |  | 2026-02-18 20:12 | 2026-02-18 20:12
202 | 238 | 248 | Programme Manager | BROWNBRIDGE, Joanne | Joanne.BROWNBRIDGE@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-18 20:13 | 2026-02-18 20:13
203 | 238 | 435 | Programme Manager | CHANDLER, Mark | Mark.CHANDLER@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-02-18 20:13 | 2026-02-18 20:13
204 | 136 | 435 | Programme Manager | CHANDLER, Mark | Mark.CHANDLER@education.gov.uk |  | 3 | Admin |  | Permanent | current |  |  | 2026-02-19 11:36 | 2026-02-19 11:36
205 | 161 | 219 | Lead Product Manager | PHILIPSON, Paul | Paul.PHILIPSON@education.gov.uk |  | 2 | Programme |  | Permanent | current |  |  | 2026-02-19 16:30 | 2026-02-19 16:46
206 | 243 | 140 | G6 - Deputy for SRO | CHARLESWORTH, Clare | Clare.CHARLESWORTH@education.gov.uk |  | 1 | Programme |  | Permanent | current |  |  | 2026-02-19 16:41 | 2026-02-19 16:41
207 | 243 | 219 | Lead Product Manager | PHILIPSON, Paul | Paul.PHILIPSON@education.gov.uk |  | 2 | Programme |  | Permanent | current |  |  | 2026-02-19 16:42 | 2026-02-19 16:42
208 | 160 | 136 | Lead Delivery Manager | CUNNINGHAM, Luke | Luke.CUNNINGHAM@education.gov.uk |  | 2 | Programme |  | Permanent | current |  |  | 2026-02-19 16:45 | 2026-02-19 16:45
209 | 245 | 140 | G6 - Deputy for SRO | CHARLESWORTH, Clare | Clare.CHARLESWORTH@education.gov.uk |  | 1 | Programme |  | Permanent | current |  |  | 2026-02-19 16:53 | 2026-02-19 16:53
210 | 245 | 450 | Lead Product Manager | LUMLEY, James | James.LUMLEY@EDUCATION.GOV.UK |  | 2 | Programme |  | Permanent | current |  |  | 2026-02-19 16:53 | 2026-02-19 16:53
211 | 164 | 188 | Data Manager | ALI, Mohammad | Mohammad.ALI@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-02-19 16:57 | 2026-02-19 16:57
212 | 163 | 136 | Lead Delivery Manager | CUNNINGHAM, Luke | Luke.CUNNINGHAM@education.gov.uk |  | 2 | Programme |  | Permanent | current |  |  | 2026-02-19 16:59 | 2026-02-19 16:59
213 | 241 | 140 | G6 - Deputy for SRO | CHARLESWORTH, Clare | Clare.CHARLESWORTH@education.gov.uk |  | 1 | Programme |  | Permanent | current |  |  | 2026-02-20 09:00 | 2026-02-20 09:00
214 | 241 | 219 | Lead Product Manager | PHILIPSON, Paul | Paul.PHILIPSON@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-02-20 09:00 | 2026-02-20 09:00
215 | 15 | 25 | User Researcher | DUMBELL, Adam | Adam.DUMBELL@education.gov.uk |  | 10 | Admin | 50% | Permanent | current |  |  | 2026-02-21 15:50 | 2026-02-21 15:50
216 | 195 | 252 | Product Manager | HOWARD, Ian | Ian.HOWARD@education.gov.uk |  | 1 | Admin |  | Permanent | current |  |  | 2026-02-25 14:33 | 2026-02-25 14:33
217 | 182 | 381 | Product Manager | FENNER, Andy | Andy.FENNER@education.gov.uk |  | 2 | Admin |  | MSP | current |  |  | 2026-02-26 11:59 | 2026-02-26 11:59
218 | 182 | 473 | Delivery Manager | FOLINO, Giulio | Giulio.FOLINO@education.gov.uk |  | 3 | Admin |  | MSP | current |  |  | 2026-02-26 11:59 | 2026-02-26 11:59
219 | 182 | 382 | Team Leader | PATEL-MISTRY, Arati | Arati.PATEL-MISTRY@education.gov.uk |  | 4 | Admin | 50% | Permanent | current |  |  | 2026-03-02 13:42 | 2026-03-02 13:42
220 | 210 | 481 | Delivery support | EVANS, Lewis12 | Lewis12.EVANS@education.gov.uk |  | 3 | Admin | 100% | MSP | current |  |  | 2026-03-02 17:11 | 2026-03-02 17:11
221 | 210 | 482 | Consultant | LOWE, Will | Will.LOWE@education.gov.uk |  | 4 | Admin |  | MSP | current |  |  | 2026-03-02 17:12 | 2026-03-02 17:12
222 | 117 | 477 | ALB Cyber Oversight Lead | MCCONVILLE, Joanna | Joanna.MCCONVILLE@education.gov.uk |  | 2 | Admin | 100% | Permanent | current |  |  | 2026-03-02 22:09 | 2026-03-02 22:09
223 | 117 | 484 | Cyber governance | MAAFO, Frederich | Frederich.MAAFO@education.gov.uk |  | 3 | Admin | 100% | MSP | current |  |  | 2026-03-03 14:02 | 2026-03-03 14:02
224 | 230 | 489 | Delivery Manager | WARREN, Harry | Harry.WARREN@education.gov.uk |  | 2 | Admin |  | Permanent | current |  |  | 2026-03-05 14:27 | 2026-03-05 14:27

## ProjectObjectives
Id | ProjectId | ObjectiveId | CreatedAt
3 | 6 | 11 | 2025-11-12 15:07
4 | 7 | 3 | 2025-11-13 07:09
5 | 7 | 6 | 2025-11-13 07:09
6 | 7 | 11 | 2025-11-13 07:09
13 | 15 | 15 | 2025-11-18 11:45
14 | 15 | 14 | 2025-11-18 11:45
15 | 15 | 4 | 2025-11-18 11:45
16 | 15 | 9 | 2025-11-18 11:45
17 | 15 | 12 | 2025-11-18 11:45
18 | 15 | 11 | 2025-11-18 11:45
19 | 179 | 6 | 2025-11-20 14:15
20 | 179 | 12 | 2025-11-20 14:15
21 | 179 | 11 | 2025-11-20 14:15
23 | 1 | 12 | 2025-11-21 12:49
24 | 1 | 11 | 2025-11-21 12:49
25 | 197 | 15 | 2025-11-25 17:11
26 | 197 | 14 | 2025-11-25 17:11
27 | 197 | 4 | 2025-11-25 17:11
28 | 197 | 6 | 2025-11-25 17:11
29 | 197 | 12 | 2025-11-25 17:11
30 | 197 | 11 | 2025-11-25 17:11
31 | 198 | 11 | 2025-11-25 21:58
32 | 199 | 12 | 2025-11-27 08:50
33 | 199 | 11 | 2025-11-27 08:50
34 | 209 | 6 | 2025-12-18 12:22
35 | 209 | 13 | 2025-12-18 12:22
36 | 210 | 10 | 2025-12-18 12:59
37 | 210 | 12 | 2025-12-18 12:59
38 | 210 | 13 | 2025-12-18 12:59
39 | 210 | 11 | 2025-12-18 12:59
40 | 212 | 12 | 2026-01-08 11:56
41 | 213 | 11 | 2026-01-20 13:33
42 | 214 | 5 | 2026-01-20 13:37
43 | 215 | 5 | 2026-01-20 13:42
44 | 215 | 4 | 2026-01-20 13:42
45 | 215 | 8 | 2026-01-20 13:42
46 | 215 | 6 | 2026-01-20 13:42
47 | 215 | 12 | 2026-01-20 13:42
48 | 215 | 11 | 2026-01-20 13:42
49 | 216 | 3 | 2026-01-20 13:44
50 | 216 | 5 | 2026-01-20 13:44
51 | 216 | 12 | 2026-01-20 13:44
52 | 219 | 6 | 2026-01-28 12:01
53 | 219 | 12 | 2026-01-28 12:01
54 | 219 | 11 | 2026-01-28 12:01
55 | 80 | 14 | 2026-01-29 14:55
56 | 224 | 10 | 2026-01-30 15:53
57 | 227 | 8 | 2026-01-30 17:26
58 | 227 | 9 | 2026-01-30 17:26
59 | 228 | 10 | 2026-01-30 17:30
60 | 229 | 10 | 2026-01-30 17:32
63 | 184 | 11 | 2026-02-02 14:39
64 | 182 | 18 | 2026-02-02 15:21
65 | 186 | 6 | 2026-02-02 15:26
68 | 188 | 12 | 2026-02-02 16:38
69 | 188 | 13 | 2026-02-02 16:38
70 | 188 | 11 | 2026-02-02 16:38
71 | 117 | 13 | 2026-02-04 11:30
72 | 117 | 11 | 2026-02-04 11:30
73 | 183 | 13 | 2026-02-04 13:52
74 | 232 | 13 | 2026-02-04 21:19
75 | 232 | 11 | 2026-02-04 21:19
76 | 234 | 2 | 2026-02-13 12:36
77 | 234 | 8 | 2026-02-13 12:36
78 | 235 | 8 | 2026-02-13 16:15
79 | 236 | 8 | 2026-02-13 16:20
80 | 237 | 8 | 2026-02-13 16:25
81 | 205 | 3 | 2026-02-17 10:53
82 | 205 | 8 | 2026-02-17 10:53
83 | 205 | 18 | 2026-02-17 10:53
84 | 205 | 16 | 2026-02-17 10:53
85 | 205 | 19 | 2026-02-17 10:53
86 | 205 | 11 | 2026-02-17 10:53
87 | 241 | 14 | 2026-02-19 15:28
88 | 241 | 4 | 2026-02-19 15:28
89 | 241 | 7 | 2026-02-19 15:28
90 | 241 | 6 | 2026-02-19 15:28
91 | 241 | 17 | 2026-02-19 15:28
92 | 241 | 12 | 2026-02-19 15:28
94 | 240 | 1 | 2026-02-19 16:09
95 | 240 | 13 | 2026-02-19 16:09
96 | 242 | 7 | 2026-02-19 16:37
97 | 242 | 16 | 2026-02-19 16:37
98 | 242 | 10 | 2026-02-19 16:37
99 | 244 | 4 | 2026-02-19 16:52
100 | 244 | 7 | 2026-02-19 16:52
101 | 244 | 12 | 2026-02-19 16:52
102 | 246 | 15 | 2026-02-23 13:41
103 | 246 | 14 | 2026-02-23 13:41
104 | 246 | 4 | 2026-02-23 13:41
105 | 246 | 7 | 2026-02-23 13:41
106 | 246 | 10 | 2026-02-23 13:41
107 | 246 | 12 | 2026-02-23 13:41
108 | 246 | 13 | 2026-02-23 13:41
109 | 246 | 11 | 2026-02-23 13:41
110 | 223 | 8 | 2026-03-09 14:53
111 | 223 | 9 | 2026-03-09 14:53
112 | 223 | 7 | 2026-03-09 14:53
113 | 223 | 6 | 2026-03-09 14:53
114 | 230 | 15 | 2026-03-11 12:08
115 | 230 | 14 | 2026-03-11 12:08

## ProjectProducts
Id | ProjectId | ProductDocumentId | ProductFipsId | ProductTitle | ProductDescription | ProductUrl | CreatedAt | UpdatedAt
1 | 1 |  | OTU-077 | COMPASS Reporting |  |  | 2025-11-04 10:14 | 2025-11-04 10:14
3 | 3 |  | HHF-436 | Analytical Data Access (ADA) |  |  | 2025-11-06 13:27 | 2025-11-06 13:27
5 | 197 |  | VQE-288 | Find Information about Products and Services |  |  | 2025-11-25 17:12 | 2025-11-25 17:12
6 | 197 |  | OTU-077 | COMPASS Reporting |  |  | 2025-11-25 17:12 | 2025-11-25 17:12
7 | 197 |  | VRM-926 | Accessibility and inclusion manual |  |  | 2025-11-25 17:13 | 2025-11-25 17:13
8 | 197 |  | NEQ-753 | Accessibility issues and statement service |  |  | 2025-11-25 17:13 | 2025-11-25 17:13
9 | 199 |  | OTU-077 | COMPASS Reporting |  |  | 2025-11-27 08:53 | 2025-11-27 08:53
10 | 199 |  | NEQ-753 | Accessibility issues and statement service |  |  | 2025-11-27 08:53 | 2025-11-27 08:53
11 | 199 |  | VQE-288 | Find Information about Products and Services |  |  | 2025-11-27 08:54 | 2025-11-27 08:54
12 | 15 |  | VQE-288 | Find Information about Products and Services |  |  | 2025-12-02 09:27 | 2025-12-02 09:27
13 | 15 |  | OTU-077 | COMPASS Reporting |  |  | 2025-12-02 09:27 | 2025-12-02 09:27
14 | 6 |  | SUM-255 | Find information about products and services |  |  | 2025-12-03 14:32 | 2025-12-03 14:32
15 | 167 |  | SUM-255 | Find information about products and services |  |  | 2026-01-14 16:41 | 2026-01-14 16:41
17 | 90 |  | GVO-497 | Funding and Contracting Service |  |  | 2026-01-27 17:27 | 2026-01-27 17:27
18 | 90 |  | OIW-841 | Funding Data Service |  |  | 2026-01-27 17:28 | 2026-01-27 17:28
19 | 90 |  | LHB-455 | Manage Your Education & Skills Funding |  |  | 2026-01-27 17:28 | 2026-01-27 17:28
20 | 219 |  | OFO-109 | COMPASS Reporting |  |  | 2026-01-28 12:05 | 2026-01-28 12:05

## StatusUpdates
Id | ProjectId | Narrative | CreatedByEntraId | CreatedByName | CreatedByEmail | CreatedByUserId | UpdatedByUserId | CreatedAt | UpdatedAt | IsBulkImport
1 | 16 | 24/10/25 Standards: - IT support standard being prepared for launch on 17 November in time for the Schools and Academies Show - new gov.uk landing page with policy stakeholders for review. The changes will reflect the "core standards" ahead of launch Plan tech: - MVP build almost all at testing phase or release ready. - Core recommendations have all been signed off by stakeholders and being 2id in contentful. - Mapping of old questions to new recommendations complete to support existing users to understand the changes we've made - Set up gov.notify and prepared comms to let users know about the service changes. Banner is ready to be implemented. Comms will go out a week before launch. - Minor accessibility issues resolved - Aiming to launch MVP by 12 November in time for the Schools and Academies Show on 19 November. Service downtime for release is expected to last for 3 hours. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
2 | 17 | The API and Lakehouse are being refactored and due to being held up with issues with commercials with system C impacting schedule - refactoring sliver and gold layers. Improvement work continues on improving the public dashboard - working on servere absences. Continuing iteration and build of private Dashboard. Will work on Testing API with CMS providers, D2I and or LAs. Progress during this period - -Public Dashboard OFSTED update -UR for Private Dahsboard ongoing -Private Dashboard MVP build underway alongside final QA page (UaT) -Prototyping of Private Dashboard continuing -Severe absence in main -7 LAs connected to SIT environment |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
3 | 18 | 16/10/25 - Work to start in November to map all technical services within the CMDB |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
4 | 19 | 25/06/24: This has been on hold for a long while and not going to go ahead as originally planned. A new deliverable will be added once we have procured a team to do the work. 26/09/24: This has now been overtaken by new deliverables which we are reporting on at a more granular level. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
5 | 20 | The application window closed on 21 March. We received 753 applications for Turing Scheme funding in academic year 2024/25. This represents an 21.6% increase from the 619 applications received in year 3 (note - this information has not yet been shared publicly). This represents the conclusion of the application process for AY24/25 and the design and development focus now shifts to the development of functionality to support the assessment, appeals, payment and grant management processes. Longer term, and subject to SR approval, the team will launch the application process for the fifth year of the scheme (academic year 2025/26). The application window is expected to open in early 2025, although minimal changes are required to the application portal. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
6 | 21 | Development delays resulted in a transition to a contingency offline solution (spreadsheets) to ensure the payment of funds to organisations taking part in the Turing Scheme. The contingency replicated the design of the digital solution and enabled organisations starting Turing Scheme placements in September 2024 to submit details of payments and payment requests. This solution enabled payments to be made to 81 organisations in August, 83 providers in September and 310 organisations in October. New delivery date planned for 31/01/2025. While the contingency option has enabled participating organisations to receive the funding they need to support students on international placements, it has required significant developer input to prepare for and enable the extraction of placement data into the CRM. This has resulted in developer resource being diverted away frrom the development of the monthly reporting process through which organisations submit details of expenditure, expected expenditure and placements. The monthly reporting functionality is expected to launch in w/c 4 November and the final reporting functionality is expected to go live by the end of January 2025. This will complete the development of the service supporting the fourth year of the scheme. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
7 | 22 | Due to recent ministerial steers leading to the decision not to do extensions of the DPS1 and DPS2 contracts, and with no plans to undertake a DPS3 at this time, the Skills Bootcamps leadership team have reviewed the value that would be gained from having the supplementary data collection for Grants providers and deemed that the added value isn’t enough to warrant the costs of the project, especially with added pressures to reduce spend within the department. Notification was received on 22nd August and the project will fully close down on 30th August. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
8 | 23 | Agree non project team owner for accreditation process issues. Continue to work with 3rd parties to ensure all can adopt solution. Replacement of ECS legacy system in 2025. The Replacement project has reviewed the end-to-end process for eligibility checking and determined what the overall process and technology should look like in the post-ECS environment. Now in Beta we are building two products as an MVP: a hub – the Entitlements Checking Engine (ECE), and replacement spokes for both School Meals and Childcare. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
9 | 24 | The status has been moved to Amber/Green due to the delays to the procurement specification which was due to go out to the sector in October 2025 but will likely fall into the start of the new year now, following the request from the new minister Josh MacAlister to revisit and amend the Post Qualifying Standard (PQS). The digital service, however, is not currently blocked by this decision and are able to proceed as per the current plan, whilst the PQS is being re-drafted. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
10 | 25 | We've extended the early years workforce register discovery by a sprint due to a slower than anticipated start. Work is continuing on the qualifications side to explore opportunities to improve how we manage qualifications date. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
11 | 26 | A new team is now in place to work on this product until March 2026. A GDS assessment is planned for after the next round of updates. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
12 | 27 | Lack of ownership of NHSE of their elements of the work needed to progress with the NHS number as the SUI and the use of their systems to enable the pilots to take place. Amber/red due to lack of progress on resolving issues. Escalation of concerns about NHSE engagement. To improve the use of technology to share information between agencies working with children and families (schools, police, health and children's social care) and to explore the use of a consistent child identifier (CCI), also referred to as a Single Unique Identifier (SUI), to enable this. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
13 | 28 | All required IT changes have already been made by HMRC, and LA third-party suppliers have all provided roadmaps for delivery. Successful delivery involves handoffs between multiple digital systems – these all need to be assured with no degree of risk for this project to be Green. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
14 | 29 | MEPS currently paused. Transferred to Rob Rodney/Schools digital division who will review the project. Prior to pause, work was focusing only on the first component (Search, Filter and View - Unauthenticated) before moving on to the next component. Progress had been made as follows - * Initial meetings held with assessors for the Alpha assessment. A peer assessent will be undertaken during the coming period. * Fourth Show and Tell took place on 25/02/2025 (approx. 87 attendees). * Teach-in session with Teacher services took place on 13/02/2025. Architecture and Helpdesk parts to be rescheduled (ran out of time). |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
15 | 30 | 11/09/2025 Reason for delivery confidence rating: We are performing well, with strong engagement from schools and record numbers of jobseekers. We launched the All School Roles MVP in March, which has seen a significant uptick in the number of schools signed up to the service, to over 87% of schools in scope. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
16 | 31 | Key Highlights: - MSI delivered the monitoring phase and began iteration 2 of mandation, with contact management improvements underway. - FAST completed its final deliverables and transitioned successfully to CI, marking a key milestone in product consolidation. - Innovation launched MPC and shifted focus to AI discovery, aligning with strategic objectives. - CAT progressed .Net migration and achieved infrastructure standardisation, supporting long-term technical resilience. - Service Support (SS) maintained high SLA performance and user satisfaction, despite ongoing resource constraints. Areas Requiring Attention: - EAT remains Amber-Green, with extended timelines and reliance on external accessibility audits. While delivery is progressing, dependencies and testing limitations present risks to future milestones. - CI is managing increased scope due to handovers from FAST and MPC, alongside SEND/CSC delivery challenges. Engagement gaps in user testing and overlapping priorities are impacting delivery pace. Risks to Delivery Confidence: - Contract re-procurement remains a strategic risk due to tight timelines and limited commercial support. - White Paper reforms continue to introduce uncertainty, affecting planning and capacity management for Q4 and beyond. - CI delivery risk due to scope increase and SEND/CSC engagement issues. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
17 | 32 | FIAT has been handed over to the Continuous Improvement team |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
18 | 33 | Product is managed by our Performance analysis & service support team (PASS) It is performing well and there are no concerns. Key metrics: - average availability has been 100% in the last 30 days and average response time has been 34ms SFSO & RG colleagues are successfully managing governance concerns within ReCaST. Successful progression of the continuous improvements entered through the new front door process for SFSO. Service reviews are scheduled with SFSO. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
19 | 34 | 06.06.25 - Continues to be on hold, and probably will be for some time – There is a power app supporting the business processes now so it’s not as important as it was to get of legacy tech. The external application process though does need significant improvement; but that will fall into another one of our projects in the medium term, External Applications. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
20 | 35 | MFSP continues to receive predominantly positive feedback, only receiving one disatisified response since the start of May. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
21 | 36 | Product is now managed by our Performance analysis & service support team (PASS) |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
22 | 37 | Previous update stands as tool is replaced by FIAT. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
23 | 38 | Work is ongoing on bug fixes with no clear date identifed on when all will be cleared. IEBT put on hold until current identified bugs are cleared. Amber RAG due to schedule delays. PSR resources will be extended on current Data POs and transferred to Teacher Services at a later date to prevent standing Java developers down. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
24 | 39 | All work is on track with limited large scale development and a focus on minor enhancements, and ongoing service maintenance and operations. The past period has seen a number of enhancements to improve the AO user experience in terms of data visibility and to extend the DfE admin interface to give greater functionality that reduces reliance on technical development support. Testing ahead of summer 2025 results has completed successfully. There are no major concerns/issues to note. Work continues to progress the potential for a future transfer of the results service to AOs. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
25 | 40 | 11/09/2025 Website: Project is reliable, with planned improvements to improve performance and enhance user experience. CRM: Team moved outside IR35 in October 2023 but is still aligned with the rest of the service, with continuous improvements alongside major development work. GSE: Growth continues organically with the service but there is little active development of the service due to team and budget constraints. We are instead focusing on ‘keeping the lights on’ and ensuring the service complies with governance requirements. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
26 | 41 | 11/09/2025 Reason for delivery confidence rating: The new recruitment cycle started well, without issue for Find or Apply opening. Offer and acceptance rates in the first 10 weeks have been encouraging however we are noticing lower submission rates of applications (particularly for Primary courses and international candidates; we continue to monitor. Send trainee data direct project delivery is dependent upon SRS vendors AND Providers being ready – this is being mitigated through ongoing engagement with both groups, but remains a delivery risk Summarise actions being undertaken to bring the project back to green: Close collaboration with key external and internal stakeholders to assess and address key concerns. Summarise the business impact, if any: Send trainee data direct risk to 25/26 ITT collection – any vendors/providers who have not successfully integrated with the Register API could still use the CSV bulk upload or the manual entry routes. There is also inclusion of backstop clause in case DfE requires HESA to collect the 25/26 ITT collection if insufficient numbers of providers are ready, |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
27 | 42 | 11/09/2025 Reason for delivery confidence rating: In the previous claim window we received over 21,315 claims and £73.9m has been paid to teachers across all user journeys to date (over £108m paid by DfE including tax). All claim services have now been closed. With the service now closed we are focusing on improving our existing services, particularly the FE service and the implementation of a permanent alternative IDV route for users who cannot verify their identity using GOV One Login. We also successfully completed the EY service private beta assessment in May, receiving an amber rating, and are preparing for public beta launch in September. We have removed the Early Career Payments service from Claim, now that this policy has ended. We are also making changes to accommodate Year 2 requirements to the IRP user journey. We also supported the DfE's teacher pay announcement with the launch of the Teacher Pay Calculator on GOV.UK. The proposed solution to accessing HE Qualifications from alternative sources once DQT is decommissioned (which was a blocker for checking claims next year) has been progressed and the data has been tested with claim successfully. The main risk for Claim continues to be civil servant resource, with both product managers, delivery manager, and the interaction designer leaving the Claim service. Since then, a new product manager and service designer has joined the team as well as a contractor delivery manager from Version 1. Whilst resource has been replaced, a significant amount of knowledge and experience on claim has been lost. Summarise actions being undertaken to bring the project back to green: Working with SMT regarding resource risk for Claim Handovers are in place to help knowledge transfer with new claim members |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
28 | 43 | Final pre-production testing and any subsequent remedial development work is almost complete. The plan to meet the target go-live date of 10 November 2025 is on track. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
29 | 44 | 07/05/25 - PMO discussion with delivcery team. Confirmed that this is a programme of delivery. Will work to confirm high-level milestones within the programme over the coming months. Overall - the service is delivering basic needs with strong user satisfaction. Pain points remain and crucially the service does not have the capacity to scale in line with its FBC requirements. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
30 | 45 | Overall programme rag remains amber/green, with individual project RAGS, which can be seen below, ranging from Amber/red to Green. Delivery details are recorded on the individual progreamme updates. After delivering the intial data cycle, work is now onoing to iterate the product, with work to replace DEI and moving to Databricks identfied, alongside the current delivery cycle. KS2 - Green. KS4 - Amber/Green. 16-18 - Green LDS 2.0 (improve & re-platform) - Green. (Requirement to be off DEI by September 2027 (Planned for April 2026.) |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
31 | 46 | School Checking schedule is currently on track, with key milestones outlined below. Following completion of the KS4 & 16-18 Autumn Live Checking Exercise, scrutiny is underway with outcome to be provided to MDP on 03/11. KS4 - 16 June - Complete KS2 - 08 September - Complete KS4 & 16-18 Autumn - Complete KS4 & 16-18 LR2 File - 20 Nov 16-18 L3 VA Data - 20 Nov |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
32 | 47 | 11/09/2025 Reason for delivery confidence rating: AB portal work not throwing off roadmap as much, amber green as there are still lots of dependencies across teams but delivery momentum is picking up. Combined ECF/NPQ data model which causes bugs, data quality issues and high volumes of support tickets. High civil servant to contractor ratio on the programme. Summarise actions being undertaken to bring the project back to green: New regular meetings on AB portal and NPQ dependencies with TRN to manage considerable dependencies |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
33 | 48 | A service that supports the career development of child and family social workers by showcasing DfE funded development programmes. There has been a decision to pause work on the service from December. Completing the information architecture restructure work will put the service in a much better place from an accessibility and usability perspective. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
34 | 49 | 31/10/25 Reason for delivery confidence rating: All teaching record data supporting services across Schools Digital is now soley coming from TRS, not DQT. The Operations and Support team have a console to view and manage queries from users about their Teaching Record. Much is still in MVP but with clear plans for critical improvements. How we're getting to GREEN DQT decommissioning is in progress and being conducted at pace to reduce the risk of the vulnerabilities highlighted on DQT (more valuable to spend resource effort on deommissioning DQT than fixing the vulnerabilities ahead of decommissioning). Roadmap of prioritised development to complete key features e.g. integration with OneLogin |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
35 | 50 | 31/10/25 Reason for delivery confidence rating: The service is in Public Beta, with all users transitioned from the legacy service. We continue to monitor service metrics for any elements of the service that require attention. The main concerns relate to misunderstandings of when the service is required. Summarise actions being undertaken to bring the project back to green: N/A, although looking at how we can improve guidance and work with the policy team on the longer-term future of the service (ultimately seeking to decommission the service, which requires DBS buy-in). DBS have indicated, for the first time, they are open to discussions now (11 March 2025) Policy team starting to engage with actions needed to progress decommissioning due to other priorites. This was escalated in June 2025 |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
36 | 51 | 11/09/2025 Reason for delivery confidence rating: When we launched the service in February 2023, we saw much higher than anticipated demand – particularly from teachers who qualified in the newly eligible countries. Whilst demand levels have significantly decreased and we are beginning to see a reduction in the size of the backlog we know that eligible candidates are still facing wait times that are outside the service level agreement and associated correspondence is causing additional burden. We are reviewing the priorities for delivery as there are currently two high priority workstreams (implementing recommendations agree by the minister and further information/decline) Summarise actions being undertaken to bring the project back to green: We have streamlined new functionality to enable the rapid decline of ineligible applicants. We have created a model to assess how surges will impact our backlog and inform future policy change. We have rolled out a new workflow to differentiate between higher and lower skilled tasks to enable support staff to take more burden off assessors. Agreed policy interventions will safeguard the service against future spikes in applications. To reduce the number of offline processes and make the assessment process more efficient and robust we are analysing correspondence data and exploring opportunities to bring more processes within service. Policy are reviewing our approach to global roll out and will provide advice to ministers in the next month. Updates to the way we build our delivery plan should enable foresight into the work that is coming up and better review resourcing requirements to avoid competing prioritise across both workstreams Summarise the business impact, if any: high volume of applicants risks long delays and high workloads for assessors |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
37 | 52 | Attendance data mandating successfully went live on 21st August 2024. Work is on track to continue to iterate the product during this financial year. 99.57% of schools are sharing their daily attendance data. The team continue to work with Wonde to improve DQ and CBDS data fields. Product live and stable, with iterations happening for additional features/services. AtO sign off received. The following features were released on 1st September for new acamic year. - Removed from Roll (MVP2 Download) - Postcode Functionality - LA Learners Postscode - Attendance Return Reports 10 Days Continuous Unathorised Absence Return & Sickness Return (non-postcode) - Session Level Code Breakdowns - Transitional Years Data Sept released to schools on 09/09/2025 |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
38 | 53 | There are three work strands, two of which are on track: maintenance of Help for early years providers, and delivering changes to the EY Child Development Training so that it meets the needs of Reception-based staff. We are extending timelines for the third work strand - publishing guidance around EYFS profile assessments for reception teachers on HfEYP - due to delays on content production following EY policy restructure. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
39 | 54 | Our last show and tell was on 3rd October 2025, our next one is planned for 31st October 2025. We did a demo of the Education Record to the Permanent Secretary during her visit to Coventry, she was impressed by how simple the service was for Schools and how easy it was for pupils to get access to their own data. We had the Education Record Steering Group on 6th October, there were no concerns/objections raised on our next steps and we have some actions to take forward. The submission for the minister has been shared for feedback. We have a SoW in place with People for Research for a round of UR with pupils, we are also planning a round of UR focused on accessibility. We have started working on a video for schools to use to explain the purpose of the Education Record, and we have started on our communications material in preparation of the national roll out. We have released an update to Issue Education Record with a simplified issuing journey for schools, this was developed based on feedback from our pilot schools. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
40 | 55 | Our last show and tell was on 3rd October 2025, our next one is planned for 31st October 2025. We have updated our user guidance based on user feedback and helpdesk queries, this is going for sign-off and will then be published on gov.uk. We are drafting comms to send out to apprenticeship providers following R14 to encourage them to transfer from LET to ELD. We released new functionality for additional learning aims to be added to a learner who is already enrolled on a course, and we are continuing with the developent work for non-funded apprenticeships. We have just completed a round of UR looking at reporting which covered ELD alongside SLD, VYED etc We have designed some updates to the service (e.g. additional content, inclusion of ILR codes alongside descriptions) based on UR feedback and provider queries. We delivered a webinar at the very end of September to over 70 employer providers, we were able to demo the new service, explain the benefits and answer questions from the participants |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
41 | 56 | Following the recent strategy refresh, we’ve now structured our operating model around three core priorities. This shift began yesterday and is designed to help us deliver incrementally and at pace. We’ve also started work on deliverables to support resourcing for the “Cool Tool for School” initiative, which will enable us to move forward with delivery in that area. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
42 | 57 | November: Final draft of strategy document to be shared with stakeholders and a Q&A session. Strategy to be shared with Tech SLT for sign-off – 21/11/25. Strategy published and engagement and comms with communities of practice to ensure awareness. Continue to prepare for implementation phase. October: Options paper developed and shared with Tech SLT on ownership model of the IDAMs space. Strategy reviewed to ensure all stakeholder comments resolved and where applicable addressed in the next version of Strategy document Continue to prepare for implementation phase. Initial engagement with DSiT about digital IDs and implications in the education space. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
43 | 58 | Programme launched September 2025, goverance launched. Projects will be stood up over the coming months. Phonics project launched Tuesday 16.09.2025. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
44 | 59 | Headset fresh completed Oct 16th 2024. 4084 headsets issued by the project. Including BAU, 63% of staff now have a noise cancelling headset Multiple projects in train to maintain, assure and improve all core services as listed. Videoconferencing refresh successfully completed (April - May 2024). Mobile refresh commenced (ongoing) from April 2024. Headset refresh commenced April 2024. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
45 | 60 | Ongoing hardware refresh programme and associated technical upgrades throughout DfE estate. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
46 | 61 | 23/9/24 CoPilot is underway with the Champions already trained and the community channel set up. Initial workshops for the main cohort started this week, with training and follow-up workshops over the coming weeks. Second tranche of licenses have been issued today. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
47 | 62 | GPA has confirmed the new target delivery date is Qtr 1 of FY26/27. GPA has confirmed DfE as their tech partner. Governance arrangments now agreed. DfE to assign DM yo the project to work with GPA and DfE Estates to avoid the risk of delays or missing key dates due to BAU pressures. First step is for GPA to share a clear set of requirements for SB. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
48 | 63 | 16/6/25 working with our 3rd party partners we are progressing the work and updating the LLM and utterances to make the returns for search results and CHAT interaction more DfE specific which will improve the end user experience. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
49 | 64 | Recent finance decisions have led to budget cuts, resulting in lost time on several projects and the offboarding of team members. This has placed key deliverables for the year at further risk, particularly within school-based nurseries. Last year, EDDDT successfully delivered a new CRM system. Although the development process was tumultuous and led to some DDT team burnout, the outcome was positive. However, the post-delivery assessment highlighted that early years policy teams need to provide DDT with more advance notice of upcoming requirements to ensure successful future phases. Currently, the early years policy team has approached DDT with a request to develop a new CRM system, giving less than a month for delivery. This short timeline has caused disruption within the teams. There has been an approach approved that should allow the dealine to be met for the announcement but a lack of clarity on future phase of development. In addition, other teams are facing challenges with development timelines, which may not be achievable within the timeframes set by policy areas in the education sector. Ways of working within teams are also under strain. Delivery plans are not being accurately reflected, which hinders senior decision-making. This issue stems from a combination of contractor quality and evolving policy priorities. We are also experiencing instability across some of our existing systems. Unlocking the necessary resources to implement meaningful fixes within the requested timeframes remains a challenge. Compounding this, we are receiving a number of expedited requests from other policy areas, which we are struggling to meet due to the ongoing financial pressures. Furthermore, there is currently no overarching strategy or roadmap in place. Actions have been taken to address this, including onboarding two lead product managers. However, they require time to consolidate existing DDT information across educational states to enable the creation of a clear vision and roadmap. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
50 | 65 | November: DM to make final checks on Access to Cloud Resources in ELZ standard then request approval from Standards Forum. Call arranged with HoP to develop a standard drafting process so that this can be shared across Infrastructure Services, socialised at the IE community and then move standards development into BAU. October 2025: Backlog was discussed and left with HoP to review on 20 October. Follow-up calls have been arranged to sign-off backlog. DM had a call with Standards forum admin lead regarding moving the Access to Cloud Resources in ELZ standard into approval as name/publishing issue has been resolved. Updated version (v 1.9) of Azure PIM for Resource roles pattern has been produced. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
51 | 66 | November: Prepare response to FinOps maturity assessment recommendations for SLT review. Develop approach to recharging Rubriks costs. Product tagging policy review Perform second pilot for CAAS Stage 2. Investigate SQL servers resilience work. October: Completed testing on CAAS tool enhancements.. Progressing CAAS Stage 1 engagements with existing service lines and initiating new ones. Continuing work on Open AI recharging. RD Farm completed. Continuing CAAS Stage 2 engagement, including work identifying a second service line to use in the pilot. Exploring addition of tables to the FinOps Power BI dashboard. Carried out a horizon scanning session to plan the next six months. Investigating unattached Azure recovery vaults. Started development of the FinOps newsletter to be released in November. FinOps Community of Practice, held on 15th October, focussed on workload optimisation. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
52 | 67 | November: User research workshop Awayday in Manchester Workshop to identify features reporting functionality Make recommendations following results of CMS trial Developing FaUAPI Teams Site beyond front page Fill in Service health check app Continue API migration; workspace notifications; new role types October: Completing ITHC improvements – final issue to be reviewed Developing FaUAPI Teams Site beyond front page. CMS trial of 3 systems recommended in DfE standard Workspace notification groups development New system role types in development |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
53 | 68 | November: Onboard ~60% of Vendor clients to ECE Launch Private Beta for Multi-Academy Trusts, Academies Launch Private Beta for LAs for EYPP & 2YO offer checks October: Onboard ~60% of Vendor clients to ECE Launch Private Beta for Multi-Academy Trusts, Academies Launch Private Beta for LAs for EYPP & 2YO offer checks |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
54 | 69 | November: Consolidated ITHC -ITHCs scheduled for all CRMs, EDD, ICA, IEBT, SISL, Employer and Provider completed, Turing and Breakfast Clubs scheduled for Dec. Reports to be received with prioritisation and planning for remediation of findings within our control, Microsoft will need to be contacted for advice on findings which are out of our control due to Dynamics being SAAS Turing - Y6 dev work and further refinements . NCA/SRP - Handover of SRP and NCA to Education Estates support services Qualys scanning - Planning for Provider; Employer; ICA; EDD; IEBT and Turing scans. Provider - Davina chatbot prototype and investigation into AI opportunities for case management completed October: Consolidated ITHC - Demo for Turing ITHC, All CRMs scoped and SoWs sent for approvals. Evergreen – Wave 2 updates to production completed for Turing (all SDT services completed). Provider- Bug fixes and Deployment of GDS framework updates to Prod complete, Removal of unused apps, security role review and updates. In progress - CX One: Create CI from phone call activity, Common ILR errors - journey change, Service Now Integration - Specialist referral Teams, Ofsted/CI&CRM reference changes, Apprenticeship Payment Journey, SCCU reports, new pages, status reasons and fields, Employer CRM into Provider – further requirements gathering. Workshop held on plans for future of Provider CRM – removal of unused fields and improvements that need to be made before other CRMs are migrated in Investigation into chat bot improvements completed and Davina chatbot prototype and investigation into AI opportunities for case management in progress Turing - Monthly reporting updates tested and deployed to Production, Y6 requirements refined and dev work . SISL – Accessibility audit completed with 1 minor finding, Review and prioritisation of Qualys scan results paused awaiting lead dev availability CIF– Handed over to Education Estates services to BAU team. Criticality scorecards - Completed for EDD, ICA, IEBT, SISL, Employer and Provider |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
55 | 70 | November 2025: Service Status and Capacity GREEN Network availability GREEN Hosting availability AMBER Recruitment and retention: AMBER October 2025: Service Status and Capacity GREEN Network availability GREEN Hosting availability GREEN Recruitment and retention: Amber |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
56 | 71 | November: Finalise the updated data and technology strategies, generate DG-level support, communicate to Directors, SLT, DDT, then DfE. Provide oversight on STA review, support Skills England (iFATE) with architecture review recommendations. Explore opportunities for corporate services review. Onboard managed service support for the Enterprise Data Model and business capability mapping, accelerate model development. Explore running business process/capability diagnostic with a wider group in DDT Deliver comms for data and technology strategies, Target Architectures, etc with Directors, SLT and portfolios. Publish the EA strategy. Finalise Data/Security Architect updates on the architecture capability framework, begin implementation of CBP for Data Architect. Onboard new architecture services contract, work through new SoWs, support portfolios to transition requirements across. October: Continued refinement of data and technology strategies Implementation plan for ‘first data service’ capital spend drafted Skills England architecture review completed, recommendations delivered Enterprise Data Model development continued, with a SoW for additional support drafted (awaiting new capability contract). Business architecture models continue to evolve, pilot business process diagnostic analysed + updated, exploring options to extend with Info Tech Developing narrative & comms for data and technology strategies, Target Architectures, etc with Directors, SLT and portfolios. EA strategy underway. Security / Data Architect updates drafted in the architecture capability framework, undergoing review before publishing New architecture services contract signed, new SoWs and templates created, supporting portfolios with contingency / transition requirements. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
57 | 72 | November: AI Adoption CoE roadmap updated. Changes will be implemented on how users access the Sandbox environment to FaUAPI. Engage with Schools Group workshops on potential AI use cases – 17th and 25th November Ed Chat – Service standards peer review scheduled; Private Beta launch with circa 200 DfE colleagues for 2-3 months planned – Beta focus is on colleagues in policy, strategy, legislation, grants, and finance profession but trial open to all. Records Management proof of concept - continue to build the functionality of the product. There is a potential roadblock in that the business rules provided by the KIM team are not robust enough to build an effective and accurate tool. October: Preparations for changes to be implemented on how users access the Sandbox environment to FaUAPI. Follow-up engagement with Schools Group following VCF workshops on potential use cases. One Big Thing communication and engagement – over 20% of all staff have completed the training in the first two weeks New form launched - AI Centre of Excellence Support & Requests - IT Help Centre |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
58 | 73 | Phase 3 (development and rollout planning in-progress) • Scorecard for new services onboarding Service Now is in testing. Proposed go-live, scheduled for third week of October. • Because Service Now limits user self-service for current offerings, the WG is manually collecting information using the prototype and will separately bulk upload scorecard responses. • There are three groups the project is working on; Enterprise Service Managers, embedded Service Managers and other (contact information is lacking or missing). • The goal is to collate and upload final results into Service Now by end of November 2025. There is circa of 300 plus service offerings requiring scorecards. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
59 | 74 | Budgets moved to relevant areas in most cases. Continuing to resolve any final areas where budgets need to be moved. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
60 | 75 | Luc Beer leading on commercial development for the central operations team. Developing commercial pipeline for DDT |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
61 | 76 | Review of service to take place following development of Central Operations function. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
62 | 77 | Budgets maximised in 2425. Review taking place on delivery of L&D following development of Central Operations team. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
63 | 78 | Team established within Central Ops. Vacancies within team being advertised. Appointed Demand Manager from OMS - starts 2nd June. Improved reporting through focused stakeholder engagement Governance review has started, initial data gathering has been completed. Discussion guide compiled ahead of next phase of data gathering reaching out to stakeholders across DDT. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
64 | 79 | Live service continues to function well. D&T Spend Controls pipeline for Q1 2024-25 authorised by CDDO. All Service Assessment and peer review requests met. RAG reflects ongoing challenge in meeting new CDDO guidance for D&T Spend Controls (v6) & Service Assessments. Continuing to pilot both processes and working with CDDO to develop transition plans. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
65 | 80 | Current net savings (committed) are £75k in 24-25 (rolling on to deliver £758k in 25-26) and a further £233k of new savings in 25-26. There are a further £331k of likely savings in 25-26 (where jobs have been offered). This is the tip of the iceberg; just from the current and imminent recruitment campaigns there could be a further £1.8m of net savings in 25-26 from only these first five professions. We expect to begin implementation for Security Architecture and Software Development in the next few months, with significant further savings potential. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
66 | 81 | New content added and content for those in the criminal justice system underway. Reuseable checker ("Get to an answer") being built as reusable component for this project, the FE recruitment site and other uses which have already been identified. Due to complete work by January when site will start to transition over to Families Digital team for continued running |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
67 | 86 | Ministers have been briefed on the DDT block. Minister Morgan has shown an interest in AI, we have sent several for information context notes requested, and submissions with decisions to be made (e.g. Evidence Board and Sector Fund). Work is beginning to pick up and teams are working on task and finish group projects for the next 100 days. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
68 | 87 | Following the recent strategy refresh, we’ve now structured our operating model around three core priorities. This shift began yesterday and is designed to help us deliver incrementally and at pace. We’ve also started work on deliverables to support resourcing for the “Cool Tool for School” initiative, which will enable us to move forward with delivery in that area. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
69 | 88 | PA: MPC report scheduled now live Strong work progress on Inspect and Adapt SS: - A major (P1) incident affecting multiple services was well managed through clear communication and strong coordination across teams, resulting in a swift and controlled resolution. - Delivery of live cases work for Prepare and Complete completed as planned, improving data accuracy and visibility. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
70 | 89 | Working on gov.uk re-redesign, tech debt and databricks migration |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
71 | 90 | CFS PI 13 Objectives ( 24/09/2025 to 16/12/25) 1 BAU support and tasks – IN PROGRESS 2 Adults performance management onboarding – IN PROGRESS 3 Complete frontend update for DfE rebrand – IN PROGRESS 4 Cosmos to SQL (work on four containers in PI 13) – IN PROGRESS 5 Tech Debt (Upgrade to TLS 1.3, Fix failing integration tests and upgrade ServiceBus package) – IN PROGRESS 6 Also support communicate funding, tenancy and data projects – IN PROGRESS CFS PI 12 Objectives (02/07/2025 to 23/09/2025) 1 BAU - clones, support, platform maintenance - COMPLETE 2 Adults PMP onboarding - COMPLETE 3 GAG specs to use data from multiple periods - COMPLETE 4 CFS UI Rebrand - Completed for v 4.10 5 Cosmos to SQL - PR, PVM, Calcs, data aggs - COMPLETE 6 Problem releasing big batches of providers - COMPLETE 7 Tenancy move support – Completed for PI 12 and some parts moved to PI 13 8 Test team support - COMPLETE 9 Ensuring zero value allocs are reprofiled for indicative to live providers -COMPLETE 10 Removing v3 grouping – investigation - COMPLETE CFS PI 11 Objectives (26/03/2025 to 01/07/2025) 1 Adults onboarding – COMPLETE 2 Cosmos to SQL - COMPLETE 3 .NET upgrade from version 6 to 8 - COMPLETE 4 Enable rule-based profiles to be applied for new openers in Pupil premium in bulk - COMPLETE 5 Support the refinement squad towards accessibility and compliance for CFS - COMPLETE CFS PI 10 Objectives (01/01/2025 to 25/03/2025) 1 Adults Onboarding - 25/26 Statements, - 25/26 Initial contracts, - Plan for -------- 2 Cosmos to SQL- Specs & DataSets: Deploy - Provider Results: Develop - COMPLETE 3 Platform Maintenance- EAPIM to FAUPI- .Net upgrade from 6 to 8 - COMPLETE 4 Ensure Obsolete Groups have no child providers - COMPLETE 5 Adding MS Clarity to CFS. -> Cookie consent - COMPLETE 6 Decouple CFS V3 COSMOS DBSimpler – Not COMPLETEd Deferred 7 Application of Rule Based Profiles For PP - COMPLETE CFS PI 9 Objectives (02/10/2024 to 24/12/2024) 1 Adult Phase 2 – Carried forward for PI 10 2 Service Enhancements - COMPLETE 3 GAG funding data onboarding 25/26 - COMPLETE 4 Central data discovery - COMPLETE 5 BAU activities - COMPLETE CFS PI 8 Objectives (10/07/2024 to 01/10/2024) 1 Enable Adults allocation team to calculate 25/26 allocations in CFS with data from FDS COMPLETE 2 Design solutions for integrating Adults funding data from CFS to MYESF and FCS to create statements and contracts COMPLETE 3 Complete the Cosmos to SQL for the policy container and develop solution for the datasets container COMPLETE 4 Onboard PSG and ILP Recon 24/25 funding data from FDS into CFS in time for the next allocations round COMPLETE 5 Complete the implementation of the reprofiling previously reprofiled allocations from the open date on refresh funding if there has been an allocation change COMPLETE 6 Set up RU tracking for Cosmos transactions COMPLETE 7 Complete the Disaster Recovery template by the end of September 2024 IN PROGRESS |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
72 | 91 | RQ delivered. Change summary behaviour work on track. Calculation and result component rebuild beginning. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
73 | 92 | FCS PI 13 Objectives ( 24/09/2025 to 16/12/25) - Rollover of TTF funding 2526 - Completed - Onboarding of TTF Y2 2526 - Completed - TEC construction Funding 2526 – In progress - CRM Wave-2 2025 upgrade – Completed - .NET Framework update from 6.0 to 8.0 - Completed (except 1 component that being picked up with 4.8 to 8.0 migration) - .NET Framework update from 4.8 to 8.0 - In progress - Angular package updates - In progress - Adult onboarding In year changes - In progress - Apprenticeship Agreement implementation - yet to start - FCS Digitisation – In progress FCS PI 12 Objectives (02/07/2025 to 23/09/2025) - Rollover SBPS 2526 – Completed - SSL certification renewals -Completed - Rollover of TTF funding 2526 - in progress - Onboarding of TTF Y2 2526 - In progress - Apprenticeship Agreement implementation - NA - CRM Wave-2 2025 upgrade – In progress - .NET Framework update from 6.0 to 8.0 - In progress - Angular package updates - In progress - Adult onboarding In year changes - In progress FCS PI 10 Objectives (01/01/2025 to 25/03/2025) - FCS Adult onboarding ASF– In progress - Rollover of Procured Non-Levy Apprenticeship 2526 – Completed - Rollover of EDSK Loans 2526 – Completed - CRM Wave 1 2025 upgrade – In progress - FCS Digitisation – In progress - App Levy Digitisation – Completed - LA and College confirmation report - Completed |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
74 | 104 | Discovery to complete on time (4 November). Discovery outputs to inform next steps (Alpha phase) towards the future data/digital solution. Continuing to progress the Action Plan for SINs. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
75 | 115 | Expansion of Plan Tech service Consultation on Standards 2030 vision. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
76 | 116 | A top 75 service - Services operating at high volumes. We did deal with a P2 in the last month, but that has been resolved. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
77 | 117 | Milestone - Analysis of returns and identification of risk landscape (end Dec 25) Update October 2025 Initial analysis is considering on maturity levels against the critical domains of the Cyber Assessment Framework (CAF), best practice and improvement opportunities. SEPT 25 UPDATE - All ALBs in scope of the cyber assurance return completed and returned the survey by the end of September. We will now focus on analysing the returns. Agree ALB Gov Assure participants for year 3 (end Oct 25) Targeted conversations are on-going to agree ALB Gov Assure arrangements for Year 3 AUG 25 UPDATE - Developed and launched a cyber assurance return for ALBs in July 2025. The return closes at the end of Sept 2025 and we will analyse the returns to better understand the risk ALB landscape. We will then identify and agree which ALBs will participate in Gov Assure for year 3. Update 20/02/2025 - ALB cyber security forum established, and relationships build across ALB network. Developing a questionnaire for ALBs to complete which will give us a better understanding of the level of cyber security risk across ALBs. Update 28/11/2024 (Alison Dunne) Scoping work is progressing well and inital engagment has been positive. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
78 | 118 | Work on track. For this financial year this will concentrate on supporting releases through the 23/24 publication cycle, with work to address known stability and security issues, including exploring move from T1 to CIP. A decision has been made to pause the work on the MVP until we have clarification on what a new system should look like. This was discussed as part of the SG2B in August 24. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
79 | 119 | Work continues to deliver the current release cycle. There are delays in data being provided which has led to the amber/green RAG. Delays have been communicated and impact is minimal. The following work is being completed- 1.Continued working on resolving ASP User Queries 2.Continued working on the BAU Data releases for 2023/24 |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
80 | 120 | November: Continue - Ed Estates Portfolio -Data activities, Purview adoption / data dictionary embedment. Continue - Data quality assurance working group – data literacy Explore discussions supporting central Data Governance lead – current rational of existing activities. Development of dev ops piece of work. Microsoft costings for Purview post scoping calls Publish Metadata standards. Bi Annual data Asset commission October: Continue - Ed Estates Portfolio -Data activities, Purview adoption / data dictionary embedment. Continue - Data quality assurance working group. Explore discussions supporting central Data Governance lead – current rational of existing activities. Business planning / supplier contract sows. Development of dev ops piece of work. Microsoft costings for Purview. Review Metadata standards. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
81 | 121 | May 2025: Continue embedding Data Quality Standard education and awareness 1fte - whilst overarching governance model develops. Data Quality standard published first 1/4 25- Cross gov data quality framework in use in some projects. Awaiting finalisation of output from Mapping on central list of important critical data gathered. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
82 | 122 | Content store: Major deliverables including the main build phase, data science tooling and content discoveries have been completed to a high standard. Slight delays of anonymised teacher and pupil content due to requiring further anonymisation checks. Contract has been extended to September/October 2025 to gather evidence to support the hypothesis agreed by the governance board and for a full cost-benefit analysis of the pilot. We are currently exploring options for moving the pilot into a beta service ready for a key decision point to be taken in Autumn 2025. The content store has been designated one of the Prime Minister’s AI Exemplars. Catalyst Fund (known externally as the AI Tools for Education Competition): 14 out 16 projects are progressing well. 2 contracts have been terminated. 1 contractor was issued with a default notice, but with ongoing support, they have rectified the default and the project is progressing. There have been delays in collation and availability of content via the content store which has meant that some of the suppliers' milestones have been delayed. 12 of the 14 remaining suppliers have agreed to extend contracts until May 2025 to account for this delay and to fully utilise the content store content to train their tools. 2 suppliers will conclude work as agreed in April 2025. Innovate UK awarded us £1m for a closed, second phase of the competition which will be open to successful projects from the first phase. The second phase will launch for applications on 14th July 2025. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
83 | 123 | 25.07.25 - new round of user research is underway with schools, who again have really stepped up to our ask and fully engaged with the processs. This direct involvement is really shaping our offer and the testing assures us that Users can interact fully with the guidance. Procuremement standards work continues, with the support of internal commercial colleagues and and school staff. This is still in the research phase, which is vital to getting this right for schools as this is such a major area for them when ensuring data prvacy when pricuring EdTech tools. June 2025. Procurement standards work has commenced with Commercial and Procurement colleages and the ICO. First phase is to bring together everthing that schools can rely on to support their procurement of EdTech. This will then be supported with procurement standards which will be developed by the group - ToR - monthly meetings, User Research is phase 2 as the guidance sourced in phase 1 will be the starting point for developing standards for schools, understanding what barriers schools need help to address |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
84 | 124 | 25.07.25 - structure of the tool has been developed to be interative starting with (redundant, obsolete and trivial) ROT, then phasing up ultimately result in identifying files for appraisal. Testing showed 60% accuracy so the team are currently looking at the business rules and updating the tool to increase the accuracy rate. The testing is against 22k records that have been reviewed by the records team, so we have assurance that we know which records the tool needs to identify. Whilst the rules are relatively straightforward the coding of the tool is complex to reflect human decision making. TNA remain interested in this project, meeting scheduled to update them with progress and involve them in the work as this progresses from ROT |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
85 | 125 | R03 for 25/26 opened on time over 99% of files process successfully at first attempt failures are re-submitted either by the provider or SLD team |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
86 | 126 | Sept milestone (removal of manual add option) is delayed while we investigate the slow take up in using the ILR option. Rating also reflects the outstanding questions about short courses policy and unpublished funding rules needed to inform payments work. Work is being prioritised around the most confirmed requirements. Likely rating will go A/R if we don't have critical info by November. Additional resources have now been added to the teams to support delivery of parallel projects. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
87 | 127 | Last week, the team continued focusing on investigating and detailing work for the next quarter including decommissioning of Skills Health Check and Digital Action Plans, as well as upgrades to the UK.GOV Frontend to ensure the service is aligned with GDS standards, this work has been finalised and project plans and development tickets for the quarter are ready to be implemented. One incident was raised and address for the DSS product which was resolved, and a change in Publish to the Course Directory supported a provider to add new courses, where they had been blocked. In addition, the maintainance backlog was reviewed to prioritise key changes for the National Career Service and Skills for Careers websites. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
88 | 128 | released 23/01/25 |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
89 | 129 | Key priorities and any work about to start:DATA Insights this sprint - Chatbot API testing, since inception earlier this year data provided through the API has had errors, we're helping Plianz test this - June monthly tasks, Any tasks which can't be automated such as manual refreshes and are completed monthly - Continued investigation into limiting dates users are able to enter into date selectors e.g no future dates - PowerBI Prime Performance Report Testing - Explore Sector & Landing Page Report Continuation, - Begin work into user tracking between NCS & SFC. Are we able to track our users across both National Careers Service & Skills for Careers Websites, this will lead to better understanding of user journeys and successful journeys These are all on track for this sprint. Key achievements/outcomes and successes (that we can celebrate, both in DDT and the wider department) |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
90 | 132 | FE workforce collection opened on 29th Sep and is planned to close on 26th November |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
91 | 133 | Work continues to deliver data, iterate the pipelines and move to Databricks. Delivery is on track. AO Summer results and Late results delivered as planned. Amber/green due to ongoing risks with CLDS 2.0 activity. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
92 | 134 | RAG remains green, with work progressing to plan. Work continues to iterate, replace DEI and move to Databricks (this will be monitored via the LDS 2.0 workstream (improve, replatform and transform LDS), whilst delivering the current 24/25 delivery cycle. Current progress - Delivery is currently on track. Uanmended data has been successfully delivered and the Checking exercise completed with no major issues.. The team are now working on delivery of the November data and resolving technical debt. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
93 | 135 | Amber/Green for overall Schedule: Cohort Amended data successfully signed off. This work was completed despite tight deadlines requiring continued monitoring of the delivery plan & robust risk manaagement, ensuring the checking exercise could go ahead as planned on 06/10, thus reducing RAG rating from Amber/Red to Amber/Green. The team continues to work towards future deliverables. Work continues to iterate, replace DEI and move to Databricks. This will be monitored via the LDS 2.0 workstream (improve, replatform and transform LDS) but the K4 team continue to support with this. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
94 | 136 | Unamended Data was delivered to CYPMD for the checking exercise on 6/10. The team are now working on late results and new developments for 25/26. Work continues to iterate, replace DEI and move to Databricks. This will be monitored via the LDS 2.0 workstream (improve, replatform and transform LDS). |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
95 | 137 | Find a Course, Find an Apprenticeship and Discover Uni data sets being brought together. Working towards agreement with Data challenges, especially around Find a Course data set, are biggest challenge for the project. Still struggling to get access to NCS GA data to inform our work. Microsoft AI resource lost due to MS reorg so some elements of AI behind, however bid put in for funding 26/27 and 27/28 from central AI funding pot. GDS approved move to Private Beta. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
96 | 138 | 02/05/25 - DDT PMO confirmed with Sam Rye this will be updated to reflect direction of travel for division. Deliverable to be updated by 31/05/25. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
97 | 139 | A risk of delivery due to no dedicated resource availability. Long terms plans need to be considered |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
98 | 140 | This strand was not concluded. There's been no meetings/movement on this for a few months. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
99 | 141 | Embedding Safety Expectations Through the content store, we have developed safety testing assets based on the safety expectations that developers can use to test the safety of their tools. We plan to test these assets with experts, and explore next steps for delivery. Google have recently confirmed to DfE and Ministers that they now meet the safety expectations. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
100 | 142 | Service is running well, but we are at capacity having taken on the Technical Excellence College form at short notice. Submit Financial Data progressing to timeline - Form has gone live and webinar with pilot group has been run, 16 participants will be taking part - Links to access form going out on 28/10/25 - Work underway to build email notification system and integration with powerapp RPA - Work underway to make effeciencies in monthly data refresh processes SRMSAC - SRMSAC annual refresh of form is complete, dashboard updates underway TEC - Waiting for final sign-off and go ahead on TEC work CSC - Alpha phase complete, work underway planning reporting side of work while data engineer is being recruited to develop backend College Financials - Prepatory work underway for FR2025 - Issue with expired App ID that prevented sharepoint transfers has been resolved College Financials Reclassification Discovery - Team has been onboarded - BAU processes and protoype have been mapped to inform projects next steps - UR round with colleges in planning |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
101 | 143 | Currently we have a number of high profile and competing commissions which is stretching our resource and capacity, this has been exacerbated by a priority tech forms commission which is causing delays. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
102 | 144 | Limited resources due to staff leave and significant risks around talent retention, continuing to deliver on key priorities. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
103 | 145 | GIAP successfully went through ORB on October 2024. Releases are progressing to schedule. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
104 | 146 | We are working at risk with lots of assumptions still to be confirmed or updated, and key Ministerial decisions still to be made. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
105 | 147 | Work now planned in and technical architecture being developed. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
106 | 148 | The School Accountability and Performance Discovery ended at the start of April – we had a service assessment and have since moved into Alpha. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
107 | 149 | Status: On Track- Sprint 9 concluded, with the Development of the FaC rebrand progressing as expected.Team have been able to review the changes as part of a new demo session implementedfrom the sprint retrospective.Scoping workshop for Publish to the Course Directory (PttCD) improvements took place with timelines and quick wins being the intial focus in sprint 10 - remaining scopeing work taking place in sprint 10.Key achievements/outcomes and successes (that we can celebrate, both in DDT and the wider department) |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
108 | 150 | Previous update stands |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
109 | 151 | Achievements: - Achieved Board Sign off for Public Beta - Almost finished all the ITHC items - Initial feedback form users has been positive |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
110 | 152 | CAT: * .Net GREEN Completed all goals for the sprint Found a faster way to complete the task list which has now accelerated progress We have replanned the completion of the with a view to being completed early Dec with a medium confidence vote. * Data AMBER due to risks raised re complexity of work. Mitigations in placeand need BA support for Ofsted report cards Completed the Delta live tables MVP and have a way forward on moving the data from silver to gold layer *Tech Ops AMBER due to needing to still plan Containers work Completed EAT environments Moved all alerts from slack to teams Completed the test data lake environments Started the prod data lake environments. Waiting for infra team to do their part before progressing to completion CI: Rebranding Prepare completed Rebranding Complete – work is done but cannot be released until .net rewrite tasklists are done. Rebranding ReCAST – With test. 3 bugs completed Identified recast items to complete Created a data map for prepare |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
111 | 153 | Phase 1 delivery has been fully planned and Phase 2 delivery plan is making progress. Delivered KS2 unamended assurance, KS4 Build is completed and KS4 June unamended assurance commenced. 16-18 Build is finished and 16-18 testing is ongoing. Modelling is completed for Phase 1. Phase 2 S4 Spike is going ahead with FLAT modelling. Dimensional modelling isn't going ahead. Requirement to be off DEI by September 2027 (contractually) but this is planned for April 2026 to alighn with the data cycle). |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
112 | 154 | Beta now underway. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
113 | 155 | Reduced risk now spending approval obtained so content to sit on combination of GCS campaign site and DSIT GOV.UK pages. The campaign site approval is time limited to 1 year so a longer term “parents information hub” still required to host information when this expires. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
114 | 156 | Agreement with sector reps has been achieved and conversations are ongoing about sector funding which is required. Further agreement between DDT and FG has been secured confirming that resource required to deliver termly collection will be provided by FG. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
115 | 157 | No live issues but concerns are being expressed that resource in the sector is being reduced at the same time we are asking for more data. Some LAs are already considering whether or not to respond to statutory returns. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
116 | 158 | 1. EoI form has been delivered by DDT and is now live. 2. The blueprint toolkit will be shared with pilot schools via Azure – solution being implemented by Technology colleagues 3. The requirements for medium term / pilot data will likely now be managed using ‘Achieve’ as school software suppliers were not supportive of our initial, preferred model. 4. Longer term data requirements. -- FG Analysts are being supported by Data colleagues to understand the problem space and consider options. Data Colleagues have given advice on pulling together requirements. This project will likely require significant development time and resources and until more is understood about the requirements and potential solutions this carries a significant risk against eventual delivery. RAG has been changed as ongoing concerns for delivery within the likely required timeframe. Decisions need to be taken very quickly about what the future data needs are to bring this back on track. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
117 | 159 | Delayed to Mid November in order to deal with recent commissions and the move of work from Skills to DWP. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
118 | 160 | The LRS CCN for Arvato is nearly complete and should be sent to Arvato by 20 October for an impact assessment. IT are now working on the system upgrade for LRS. Once this is complete we can schedule in testing. We are still waiting for information from DDT to understand the services they provide. We will be chasing this up w/c 20 October. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
119 | 161 | GDS Upgrade We have successfully deployed the GDS upgrade to the Customer Help Portal into production, marking the completion of a significant piece of work. This upgrade represents a major step forward in improving the user experience for our customers. The portal now features a more modern, intuitive interface that aligns with the design standards used across other government digital services, ensuring consistency and familiarity for users navigating between platforms. The deployment went smoothly, and the updated portal is now live and fully operational. The enhancements not only improve accessibility and usability but also reflect our commitment to delivering high-quality, user-centred digital services. This milestone is the result of collaborative effort across teams and demonstrates our ability to deliver impactful improvements efficiently and effectively. DfE Connect and Digital Consolidation We’re kicking off our first workshop with the DfE Connect team as part of their digital strategy reset. This session will focus on exploring opportunities for alignment across digital services, ensuring that our work supports a cohesive and integrated experience for users. We’re looking forward to contributing to the broader vision and helping shape the future of digital services within the department. Education Estates (Capital) Work continues in close collaboration with the Education Estates Team to migrate the use of 37 individual mailboxes into our Customer Help Portal. This initiative is a key part of our ongoing efforts to consolidate services and streamline communication channels. By centralising these interactions within the portal, we aim to significantly improve operational efficiency, reduce duplication, and provide a more consistent and transparent experience for both internal teams and external users. The migration will also enhance our ability to track and manage enquiries, ensuring quicker response times and better service outcomes. Davina Chatbot We’re currently developing a proof of concept for a generative AI-powered version of our chatbot, Davina, aimed at significantly enhancing customer experience. This new iteration will be capable of handling a broader range of queries with more natural, intelligent responses. Crucially, if Davina is unable to resolve a customer’s issue, it will automatically escalate the case to our CRM system—eliminating the need for the customer to repeat information or take additional steps. This seamless escalation not only reduces effort for the user but also ensures faster resolution and a more joined-up service experience. The proof of concept will help us evaluate the potential of Gen AI to transform how we support our users and deliver smarter, more responsive digital services. AI in Dynamics 365 We’re currently working with an AI developer to explore the feasibility of integrating AI functionality within Dynamics 365 to support case management. The goal is to assess how intelligent automation and natural language processing can assist agents by surfacing relevant information, suggesting next steps, and potentially pre-populating case details based on customer interactions. This could significantly reduce manual effort, improve response times, and enhance the overall quality of service. By embedding AI directly into the case management workflow, we’re aiming to empower agents with smarter tools and deliver a more seamless experience for both staff and customers. Bespoke Journeys We’re making strong progress with the prototype design for Portal 2.0, which will introduce tailored customer journeys based on user type and context. This next-generation portal will ensure that customers only see the options, content, and support relevant to their specific needs, reducing complexity and improving overall usability. By designing with personalisation at the core, we’re aiming to deliver a more efficient and intuitive experience that reflects the diversity of our users and the services they interact with. The prototype is already demonstrating how targeted design can simplify navigation and enhance customer satisfaction. Whistleblowing Project The whistleblowing mapping project is now nearing completion, with the full process successfully mapped across the department. This comprehensive exercise has provided valuable insights into how whistleblowing cases are currently handled, highlighting areas for improvement and greater consistency. A proposed new approach is now taking shape, designed to streamline the process and ensure robust handling of concerns. This proposal will soon be shared with the Complaints Board for review and feedback, marking an important step towards strengthening our overall complaints and safeguarding framework. CRM Next week, the team will be coming together for a full-day workshop focused on re-imagining Provider CRM as a modern, intuitive customer service tool. The session will centre around three key areas: layout and design, functionality, and processes. This collaborative effort will allow us to explore how the CRM can better support users through a cleaner interface, smarter features, and streamlined workflows. By taking a fresh look at how the system is structured and used, we aim to create a solution that not only meets current needs but is also scalable and adaptable for future service delivery. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
120 | 162 | As of 23rd October we are being told that there is now a formal plan to keep SLACK. This is being explored and we will review next steps once we know who made this decision and how that impacts on this deliverable. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
121 | 163 | The new whistle blowing process review took place 22/10/2025. Broad agreement except for two divisions that have been commissioned from elsewhere to work in a silo. This has been captured under Risk CSS014. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
122 | 164 | The team keeps producing, maintaining and enhancing an insight and reporting suite built primarily using Power BI and Microsoft CoPilot. The action-able service insights and management information (MI) are shared with the stakeholders to not only monitor performance of services against agreed SLAs/KPIs but also identify areas of improvements. Some of the highlights for this month are given below: • The team has now fully transitioned its data management processes from a legacy SQL-Server to Databricks platform for National helpline and Data Ops' telephony data. The new platform has enabled the team to automate some aspects of data linkage across various data sources thus helping the team save time and resource. The team will keep exploring and enhancing data management processes through further automation using APIs. • The National helpline (NHL) AI summary tool, to produce an automated summary/insights for each call, has now been fully developed, tested and implemented as BAU. The NHL team has seen an instant improvement in ticket summary quality since the implementation of this tool. The agent call wrap-up time has significantly improved which will help the division save agent time and resource going forward. The team showcased, in collaboration with Operational Data Science colleagues, the savings and improvements using this AI tool to Jane, Saheel and the permanent secretary during their recent visits to Coventry office this month and received good feedback. • The team shared with the senior leadership second iteration of a high-level dashboard containing performance summary for various in-house services that we manage within the division. The team received some positive and encouraging feedback from the senior leadership team. The monthly dashboard will continue to be enhanced based on the feedback in future iterations. • The team also produced monthly insights using external customer satisfaction surveys data. This helps customer service team identify any areas of improvements across the services and implement necessary actions to bring efficiencies and drive improvements. • Despite resource related issues, the team is confident that they will continue to perform their business critical BAU tasks along with dealing with any priority requirements to produce new insights and MI/reporting. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
123 | 165 | 18/08 Showcase delivered to Emily S and Mark J in prep for stakeholder show and tell. Ownership is required for SOW to move forward. 04/08 - First part of UR complete. Moving onto next phase. BA reviewing current processes and linking in with UR. 01/07 - BA started. Getting to know team and read background information. 17/06 - Both URs now started. Early background research and setting up of work ongoing. Relevant meetings organised. BA to link up and start in July. 04/06 - BA confirmed and one UR confirmed. Awaiting one more UR. 29/05 - Awaiting start date for BA. 2 x URs start first week of June. SOW working group now set up for collaboration on SOW in DfE to avoid duplication.. 13/05 - Awaiting invite for pilot with cabinet office. Resource TBC for exploring needs and requirements within DDT/DfE. Cross team meeting created for transparency and collaboration of this area. 03/04 - Next steps currently in discussion Alex B and awaiting feedback. Provisional plan to be discussed at review board for approval. 20/03 - Awaiting confirmation of direction and funding following meeting on the 19th March but meeting organised with Emily S and Mick R on 21st March to discuss approach to AI projects following wider developments. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
124 | 166 | 20250902: We are blocked on UR with Data Analysts and that is holding up a getting to a clearer definition of the project. We are addressing the gaps in stakeholder mapping and change management. Work is also underway on the necessary data needed to support the users and technology strategy.20250801: Where are planning fo r show and tells of the dashboard to the Data Analyst community for feedback. At the same time we will be exploring the requirements for requesting access and the updating of the data map. We also need to address the issues around requesting access and updating the data as part of the tactical solution. Cultural changes will be critical to the success to the project. We are looking at a service offering, and potential Service Owners from within the the Business. We are engaging with the DDT communities to understand what tools are available for a tactical solution and how they will interact with this service. We are also exploring great links with other projects within DDTi as a way of generating evidence of the benefits for sharing data across the Dept, and working with DDTi. 20250708: The project is currently completing engagements with linked services (IAR, People Services) to identify possible linkages across business processes and technology. We are working with the data mapping project on engagement with the analyst community (as they are likely to form a key part of the user group) with the aim of completing recruitment for some UR. Development continues on the dashboard with input from the data mapping team. The project is nearing the transition point for Alpha. 20250701: The project has finished it's third sprint and completed planning for sprint four. The project has now completed it's planning and proposals for securing an SRO and activity required prior to Alpha. In the next sprint, the team will be completing the as-is mapping of some linked services and complete UR on the latest version of the dashboard which shows the mapped information. 20250623: Successfully pitched a focussed scope for the project. Key follow up activities have been identified to align with the preferred scoping and a 5 year plan is being developed by the project. The requirements have been reworked and are being reviewed by the Data Architect and Data Analyst. User Research sessions have concluded and are being played back to the team at the end of the week. 20250617: We have now prepared our proposal for scope and priority on DIP. This has been captured in a note ahead of the meeting which has been sent to Emily and Tej. The User Research is finishing now and after the final interview, the analysis will be complete. The BA work will need to continue as requirements must be reframed to capture the change of focus. A DA/SA has been brought on board and is starting to look at the technical side of this project. Our DAn continues to work with the mapping team to get all the mapped information into the tool and is also picking up some analysis of data as it relates to potential capability in the future. 20250610: The main focus of our work currently is to develop a proposal on the scope and priority of this project. In particular, we will be looking to narrow this down and agree a focussed set of requirements and objectives which will aid deliverability. There is also some movement in the resource (loss of a BA and expected gain of a DA/SA) but this is being managed through resource currently onboarded through the Data Mapping project. Work on UR continues with analysis being finalised last week for presentation this week. On the dashboard work, some issues with the data have been resolved and new data loaded on to the tool. 20250603: We successfully delivered the first Show and Tell session which summarised all the work to date on this project (including work that happened as part of the Data Mapping Project). This marked the end of Sprint 1 and the project successfully completed all the usual ceremonies and are reflecting the outputs of our retro. We are now working through Sprint 2 with some of the key outputs to be Hypotheses documentation, UR analysis, and changes to our tactical dashboard. 20250527: We are continuing to complete our UR with additional participants from the data mapping project identified. The team will be delivering a show and tell on the progress to date for the project this week. 20250520: The project is working through Sprint 1 with work focussing on UR work, developing Alpha hypotheses and preparation for a show and tell at the end of the sprint covering all of the work to date on the project. 20250512: The project is conducting sprint planning this week working towards the end of Discovery. Work has been ongoing with the UR Phase 2 and planning for Phase 3. 20250428: We are defining the project's aim and vision statement and are working towards the end of the Discovery phase. A roadmap has been drawn out and it is expected that the Discovery phase will end in May. 20250331: The team delivered an internal review of their UR findings. The team are also linking in with Delivery Directory to understand links between the two projects. 20250324: We are continuing to work on the user research with the final sessions booked in for this week. Our Data Analyst and BA began working on loading more real data into the dashboard but encountered a SharePoint issue. This will be worked through this week with the aim of loading Families and Regions data into the tool. 20250317: A tactical solution has been developed which contains one area of mapped information. The focus is now on loading in the rest of the maps. User research continues and once complete will inform project requirements. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
125 | 167 | 20250908 Sprit 5 commenced - this will be a 3 week sprint due to DM absence on leave. Sprint details - Overview Strengthen the alpha by improving the search experience and interface design, and by developing and testing a range of concepts to explore alternative user journeys and deepen design insight. Ratify the governance framework approach with service owner and project sponsor. Set us up for success in alpha and beyond by defining OKR targets (alpha) based on baseline metrics, validating the governance framework with stakeholders, and preparing for scaling by understanding how our approach works for other portfolios. Sprint outcomes: Incorporate concept testing feedback into front-end design Refine service blueprint Detailed testing of search result relevance Finalise Test Strategy and plan, create test design for User Stories and Execute test for the delivered User stories Iterate existing concept designs based on user feedback Create alternative concept designs in-line with GDS and DfE standards Continue work on governance framework with service owner and senior stakeholders Set OKR targets for alpha based on baseline metrics Synthesis analysis of other portfolios’ libraries and share with team Service assessment preparation and key messaging Identify priority portfolios for post-alpha focus Sandbox has been accessed along with necessary components. Product has been developed to show successful search. 20250819 -Sprint 3 concluded and Sprint review completed. Sprint 4 started Sprint 4 Goal Progress the alpha by enabling the developer (user perspective) to submit queries and receive basic responses. Begin testing wire frames / early experiences with users to validate key assumptions, gather actionable insights and guide future iterations, finally establish baseline metrics to measure impact. OKR baseline data collection and target setting Continue core build to return a search response in the front end Prepare lo-fi concept designs and gather user feedback High level analyse of other portfolio libraries Continue to test assumptions with UCD roles and URs in wider portfolios Question guide for policy users Validate service design blueprint Continue updating architecture deck Design mechanics and incentives for sharing and reusing insights Create end-to-end user journey maps for Insight Trawler, Strategist, and Networker personas Developing Governance Approach 20250812 - Sprint 3 started. Azure sandbox finally up and running. 20250804 Sprint 2 concluded. Began validating the end-to-end user journey from insight completion to discovery, using sample data. Establish the high-level technical architecture that supports automated ingestion, accept UR teams specified tagging, and automated discovery. Defined the criteria for a "completed" insight. Develop product roadmap and success metrics by 1 Mapped out and validated the ‘To Be’ core user flow completing an insight - tagging - search - summary 2 Developing and test AI summarisation and tagging 3 Defining criteria for a completed insight 4 Documenting core requirements - detailed user stories 5 Architect designs to outline technical flow for automated ingestion and building of RAG pipelines RAID Log updated and issue surfaced 20250723 - Sprint 1 concluded - now in Alpha. Roadmap developed, MVP broken down into deliverable stories or components, Alpha requirements looked at by value and effort, as-is state analysis of schools user insights library, worked with key stakeholders to consider adoption, design requirement and business constraints, core tech spikes completed, developer on boarded and RAID log updated 20250707 - End of Sprint 0 and MVP must haves for Alpha documented. Sprint review concluded, back log refinement completed and goal/planning for Sprint 1 done. 20250623 - Project Kick off held and early planning session. Sprint 0 planning this week along with workshops UR: Problem space, user needs and pain points and defining the product vision and MVP. Additional resource needed - Developer (AI focus) and tester as we move into Alpha. 20250611 - kick off scheduled for 17/6/25 and links made with service mapping (workshop for service mapping an impact projects planned for 18/6/25). Back log and sprint planning scheduled and ways of working meeting planned. Formal start 23/6/25. 20250602- eSourcing Challenges: The Product Manager is scheduled to start on 16/06/25. This is a key role, and their delayed start has been a challenge. We have successfully onboarded the Service Manager, User Researcher (UR), and Solution Architect. Their integration into the team is progressing well. We are still waiting to receive the name of the Business Analyst (BA), which is causing some delays in finalising the team structure. A kick-off session will be organized once all team members are on board. This session is crucial to ensure everyone is aligned and has a shared understanding of the project goals and processes. Harman is working on finding temporary assignments for the SM and UR to keep them engaged and productive. 20250525 - PID timeline agreed with project sponsor. Resourcing in progress to complete discovery and alpha. Preparing 'kick off' sessions. Estimated start is beginning of June 2025. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
126 | 168 | Working with DSIT to create landing page for Media Literacy campaign for Jan 26 which also acts as the government site for parents information about keeping their child safe online. 4 month project to get from discovery and alpha to a live campaign site. Discovery phase complete and MVP being rapidly prototyped for round 2 testing. Access to GCS campaign site granted. Content process (including sign off) underway. MVP will be small and focused on the top tasks parents want to achieve with signposting to existing (charity) resources where possible. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
127 | 169 | August update: Alpha assessment completed and Green outcome. Beta has now started with an aim for an MVP and further iterations to be in available internally by End of Nov |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
128 | 170 | October status: Divisional roadshow almost complete. Staff survey analysed - leadership issues raised escalated to DDT's SLT. Other work will be taken forward by the skills and expertise objective team, including a research project to understand more about L&D needs in DDT and how far they are being met. Discussions underway with alternative supplier about SCS immersion day. BA bootcamp taking place early November. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
129 | 171 | UR supporting BSIL campaign site now complete. Survey work to support longer term project around parents hub for all ages complete and results shared. Mapping out government parent services and collating research ongoing. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
130 | 172 | Set up - improvements being made as the AI work develops |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
131 | 173 | Set up - improvements being made as the AI work develops |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
132 | 174 | Still being formulated |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
133 | 175 | On track |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
134 | 176 | The MVP is ongoing and is currently in UAT, which will include accessibility testing/audit. A revised expected delivery date will be discussed once the UAT is complete and we understand any further work required. Although to note that the SDT team's capacity is taken up by other priorities. Late delivery is impacting on our user researchers needing to continue to find schools research participants via other routes, which are normally chargeable and come with a time lag before the research can take place. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
135 | 177 | Currently defining internal processes (operational, finance and governance) to ensure viability. If not viable, project will end. Also currently waiting for commercial team resource to be assigned. If major delay in commercial resource, delivery date may slip. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
136 | 178 | Business case being produced. Waiting for commercial team resource to be assigned. If major delay in commercial resource, delivery date may slip. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
137 | 181 | The alpha phase has just kicked off and a number of new team members onboarded onto the team. The alpha roadmap and delivery plan are in development. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
138 | 182 | October 25 Update: We have almost completed a design refresh which we are testing with users, including the academies show in November. We will then concentrate on prepping for go live in late December or early January. Sept 25 Update: [Development of the Cyber Security Sector Hub is progressing well] Private beta launch - Jan 2026 We have launched round 2 user research with technical SMEs including. academy trust IT/Cyber Directors, NCSC, NCA, ICO and specialist police teams. We will be conducting further user research and promoting the hub launch at Schools and Academies show in November. The Cyber Security Standards self-assessment within the Plan your Technology service has launched, the tool helps schools understand where they have gaps in achieving the standards. We are working with colleagues in the RPA team in schools commercial on a pilot RPA scheme members to complete the self-assessment. This supports the longer term vision to include completion of plan your technology as condition of RPA cyber cover initially and ultimately achieving the standards themselves. It will also help increase use of the tool and give the department a better understanding of the risk landscape across the school sector. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
139 | 183 | SEPT 25 SSDLC - Continue with work developer community of practice on source code control and secrets management until December. GITHUB enterprise migration agreed at SLT and being communicated through COPS DCAP - Develop a governance and service wrapper for the Platform, continue with Gold/Silver onboarding and transition DCAP to a BAU team by December. SBD surgeries now established for projects in scope (AUG 25) Threat Modelling service offer established (Aug 25) Deliver pilot for CA for a digital service (end July 25) |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
140 | 184 | SEPT 25 UPDATE - Meetings have taken place with SRO's and will be held quarterly moving forward. Good progress is being made with the current set of mandated controls. (Aug 25) Agree remediation timeframes for mandated controls. Quarterly reviews with SROs taking place |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
141 | 185 | UPDATE SEPT 25 - New governance in place - the Cyber Risk Advisory Board (CRAB) has been stood up and the terms of reference will be agreed at the first meeting in October 2025. The CRAB board will feed into the new DDT governance framework. A central risk register has been established. It is currently under review to identify and escalate compound risks (AUG 25) Update intranet content to align with current assurance process (end Aug 25) |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
142 | 187 | Contract with JISC in place (Oct 25). Update October 25 Minister Smith sought advice from the Permanent Secretary and following definitive advice from legal on the unlawfulness of continuing with grant funding, in further advice to the Minister on 27th October we have again recommended the Minister approves the contract from 1st November; with the condition we aggressively try to drive down costs from day 1. The rating is Amber because on 27th October we still await a decision from the Minister ahead of the end of October deadline. UPDATE - SEPT 25 We have secured an extension to the current grant agreement with Jisc to continue to provide connectivity and cyber security to the FE sector in England until 31st October 2025. The notice period for both Transparency Agreement and Contract Award notices ended without any challenges. A submission is with Minister Smith as the final stage in the approval process to move to a contract from 1st November |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
143 | 188 | SEPT 25 UPDATE - Gov Assure Year 2 targeted improvement plan is at the final sign-off stage. Once agreed it will be shared with the services and remediation work, alongside Year 1 will continue and be tracked. GOV Assure year 3 - we have agreed Business Central be part of year 3 and another service will be identified shortly. Engagement work has commenced with business central team. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
144 | 189 | Discovery is on track with the scope and goals agreed and a delivery plan in place. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
145 | 190 | MVP launched 1 September - work continues to improve and evolve it following user research findings and wider x-gov parent-facing digital projects. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
146 | 191 | n/a – Discovery complete on 10 October 2025. Alpha business case signed off and Statement of Work being drafted. Anticipated Alpha start date XX. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
147 | 192 | Team capacity is stretched due to a shared resource pool across two concurrent projects. A two-week extension was agreed with policy and digital leadership, which has relieved the immediate pressure and the project is now rated Green. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
148 | 194 | No issues have been raised by LAs or third-party suppliers – project is Green. Project closure will be in October 2025. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
149 | 195 | Agree non project team owner for accreditation process issues (we have learned that some Schools are using checkers without DfE’s Accreditation process trapping or sanctioning this. Presently the legislation does not cover Schools driving an online process).Continue to work with third parties to ensure all can adopt solution. |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True
150 | 196 | • Project is Green as project has been through both demand triage and Board signoff • Budget lines are being put in to place • Operational Readiness Reviews prepared for the service decommission and commission • SoW's submitted and processing, some candidates coming through Cognizant • SIPOC on PIMS journey carried out + deep dive on Admin functionality carried out 'as is' • Creating the 'to be' process incorporating the UKRLP + PIMS approach • Setup of assumptions and Functional and Non-functional requirements • Drive to create the operational logic map 'to be' to be reviewed to allow technical design to follow |  |  |  | 1 |  | 2025-11-20 13:56 | 2025-11-20 13:56 | True

## MonthlyUpdates
Id | ProjectId | Year | Month | Narrative | CreatedByEntraId | CreatedByName | CreatedByEmail | CreatedByUserId | UpdatedByUserId | CreatedAt | UpdatedAt | SubmittedAt
1 | 1 | 2025 | 11 | test | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  |  | 2025-11-26 21:13 |  | 2025-12-10 11:11
2 | 196 | 2025 | 11 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2025-11-28 11:08 |  | 2025-12-10 12:12
3 | 125 | 2025 | 11 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2025-11-28 11:33 |  | 2025-12-10 12:12
4 | 144 | 2025 | 11 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2025-11-28 11:35 |  | 2025-12-10 11:39
5 | 54 | 2025 | 11 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2025-11-28 11:41 |  | 2025-12-10 11:38
6 | 55 | 2025 | 11 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2025-11-28 11:43 |  | 2025-12-10 11:37
7 | 132 | 2025 | 11 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2025-11-28 11:43 |  | 2025-12-10 11:37
8 | 142 | 2025 | 11 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2025-11-28 11:44 |  | 2025-12-10 11:36
9 | 143 | 2025 | 11 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2025-11-28 11:45 |  | 2025-12-10 11:36
10 | 6 | 2025 | 11 |  | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  |  | 2025-11-28 14:18 |  | 2025-11-28 14:19
11 | 15 | 2025 | 11 |  | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  |  | 2025-11-28 15:16 |  | 2025-11-28 15:16
12 | 189 | 2025 | 11 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2025-12-03 15:13 |  | 2025-12-03 15:14
13 | 190 | 2025 | 11 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2025-12-03 15:29 |  | 2025-12-03 15:30
14 | 193 | 2025 | 11 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2025-12-03 15:34 |  | 2025-12-03 15:34
15 | 25 | 2025 | 11 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2025-12-03 15:36 |  | 2025-12-03 15:36
16 | 27 | 2025 | 11 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2025-12-03 15:38 |  | 2025-12-03 15:38
17 | 191 | 2025 | 11 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2025-12-03 15:40 |  | 2025-12-03 15:40
18 | 192 | 2025 | 11 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2025-12-03 15:43 |  | 2025-12-03 15:43
19 | 53 | 2025 | 11 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2025-12-03 15:48 |  | 2025-12-03 15:48
20 | 195 | 2025 | 11 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2025-12-03 15:50 |  | 2025-12-03 15:50
21 | 155 | 2025 | 11 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2025-12-03 15:55 |  | 2025-12-03 15:55
22 | 104 | 2025 | 11 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2025-12-03 15:57 |  | 2025-12-03 15:57
23 | 24 | 2025 | 11 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2025-12-03 15:58 |  | 2025-12-03 15:58
24 | 48 | 2025 | 11 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2025-12-03 15:59 |  | 2025-12-03 15:59
25 | 52 | 2025 | 11 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2025-12-04 19:11
26 | 133 | 2025 | 11 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2025-12-04 19:22
27 | 17 | 2025 | 11 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2025-12-04 19:28
28 | 179 | 2025 | 11 | [6 empty] | 2025-12-04 23:25 |  | 2025-12-04 23:26
29 | 197 | 2025 | 11 | [6 empty] | 2025-12-05 15:31 |  | 2025-12-05 15:31
30 | 199 | 2025 | 11 |  | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  |  | 2025-12-08 13:32 |  | 2025-12-09 10:32
31 | 72 | 2025 | 11 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2025-12-09 09:43 |  | 2025-12-09 14:03
32 | 7 | 2025 | 11 |  | ef58175c-38bb-4aa4-b081-c5f0e49b2e10 | PATEL, Prina | Prina.PATEL@EDUCATION.GOV.UK |  |  | 2025-12-09 10:30 |  | 2025-12-09 10:31
33 | 165 | 2025 | 11 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2025-12-15 13:34 |  | 2025-12-15 13:35
34 | 166 | 2025 | 11 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2025-12-15 13:54
35 | 167 | 2025 | 11 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2025-12-15 13:57 |  | 2025-12-15 13:57
36 | 200 | 2025 | 11 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2025-12-15 13:58 |  | 2025-12-15 13:59
37 | 203 | 2025 | 11 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2025-12-15 15:32 |  | 2025-12-15 15:32
38 | 202 | 2025 | 11 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2025-12-15 15:32 |  | 2025-12-15 15:34
39 | 204 | 2025 | 11 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2025-12-16 09:21 |  | 2025-12-16 09:21
40 | 205 | 2025 | 11 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2025-12-16 10:19 |  | 2025-12-16 10:20
41 | 206 | 2025 | 11 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2025-12-16 11:26 |  | 2025-12-16 11:26
42 | 207 | 2025 | 11 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2025-12-17 14:35 |  | 2025-12-17 14:35
43 | 208 | 2025 | 11 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2025-12-17 14:36 |  | 2025-12-17 14:36
44 | 209 | 2025 | 11 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2025-12-18 12:29 |  | 2025-12-18 12:33
45 | 210 | 2025 | 11 | [6 empty] | 2025-12-18 13:02 |  | 2025-12-18 13:02
46 | 71 | 2025 | 11 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2025-12-18 13:05 |  | 2025-12-18 13:07
47 | 202 | 2025 | 12 | [6 empty] | 2026-01-05 15:46 |  | 2026-01-05 15:46
48 | 209 | 2025 | 12 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-01-05 16:14 |  | 2026-01-07 16:36
49 | 205 | 2025 | 12 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-01-07 14:33 |  | 2026-01-07 14:35
50 | 206 | 2025 | 12 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-01-07 15:20 |  | 2026-01-07 15:20
51 | 207 | 2025 | 12 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-01-07 15:45 |  | 2026-01-07 15:46
52 | 208 | 2025 | 12 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-01-07 15:58 |  | 2026-01-07 15:59
53 | 210 | 2025 | 12 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-01-07 16:47 |  | 2026-01-07 16:48
54 | 204 | 2025 | 12 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-01-07 16:51 |  | 2026-01-07 16:51
55 | 200 | 2025 | 12 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-01-07 16:57 |  | 2026-01-07 16:58
56 | 167 | 2025 | 12 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-01-07 17:03 |  | 2026-01-07 17:05
57 | 6 | 2025 | 12 |  | ae9d166e-7a5b-44a2-acfa-ee02c3c2ea24 | OSBORNE, Kuldip | Kuldip.OSBORNE@EDUCATION.GOV.UK |  |  | 2026-01-13 10:18 |  | 2026-01-15 16:57
58 | 197 | 2025 | 12 |  | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  |  | 2026-01-13 12:09 |  | 2026-01-13 12:10
59 | 15 | 2025 | 12 |  | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  |  | 2026-01-13 12:14 |  | 2026-01-13 12:15
60 | 199 | 2025 | 12 | [6 empty] | 2026-01-13 12:16 |  | 2026-01-13 12:16
61 | 179 | 2025 | 12 | [6 empty] | 2026-01-13 12:16 |  | 2026-01-13 12:16
62 | 198 | 2025 | 12 | [6 empty] | 2026-01-13 14:47 |  | 2026-01-13 14:47
63 | 196 | 2025 | 12 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-01-14 08:45
64 | 125 | 2025 | 12 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-01-14 08:48
65 | 144 | 2025 | 12 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-01-14 08:50
66 | 54 | 2025 | 12 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-01-14 08:51
67 | 55 | 2025 | 12 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-01-14 08:51
68 | 132 | 2025 | 12 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-01-14 08:52
69 | 142 | 2025 | 12 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-01-14 08:53
70 | 143 | 2025 | 12 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-01-14 08:54
71 | 1 | 2025 | 12 |  | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  |  | 2026-01-15 11:05 |  | 2026-01-15 11:06
72 | 165 | 2025 | 12 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-01-15 16:59
73 | 124 | 2025 | 12 |  | be9b390a-94b5-47c2-aa27-c503c315a3d0 | WHARAM, Sue | Sue.WHARAM@education.gov.uk |  |  | 2026-01-16 07:27
74 | 123 | 2025 | 12 |  | be9b390a-94b5-47c2-aa27-c503c315a3d0 | WHARAM, Sue | Sue.WHARAM@education.gov.uk |  |  | 2026-01-16 07:31
75 | 73 | 2026 | 1 |  | 976f27df-5486-4d6a-8afd-b46f95453e70 | GILL, Ushma | Ushma.GILL@EDUCATION.GOV.UK |  |  | 2026-01-20 15:37 |  | 2026-02-02 12:07
76 | 62 | 2026 | 1 |  | 976f27df-5486-4d6a-8afd-b46f95453e70 | GILL, Ushma | Ushma.GILL@EDUCATION.GOV.UK |  |  | 2026-01-20 15:39 |  | 2026-02-02 12:10
77 | 18 | 2026 | 1 |  | 73fa79c3-5d67-4a7a-bf30-12fa7da710d2 | RAE, Angus | Angus.RAE@EDUCATION.GOV.UK |  |  | 2026-01-21 10:33 |  | 2026-01-21 10:34
78 | 18 | 2025 | 12 | [6 empty] | 2026-01-21 10:34 |  | 2026-01-21 10:34
79 | 18 | 2025 | 11 | [6 empty] | 2026-01-21 10:34
80 | 16 | 2026 | 1 |  | f7abf0c1-9598-41e9-957a-3d7638a74856 | KENNEDY, Carmel | Carmel.KENNEDY@EDUCATION.GOV.UK |  |  | 2026-01-21 14:10
81 | 211 | 2025 | 12 | [6 empty] | 2026-01-22 13:49 |  | 2026-01-22 13:49
82 | 141 | 2025 | 12 | [6 empty] | 2026-01-22 14:16 |  | 2026-01-22 14:16
83 | 1 | 2026 | 1 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2026-01-27 11:19 |  | 2026-01-27 11:19
84 | 179 | 2026 | 1 |  | 32908ea6-3e40-4e69-9cff-3fa3c6aab41f | RYE, Samantha | Samantha.RYE@EDUCATION.GOV.UK |  |  | 2026-01-27 12:34
85 | 219 | 2026 | 1 |  | faaca2ab-4904-4f18-8228-4a011f6e4faf | CLARK, Louise | Louise.CLARK@EDUCATION.GOV.UK |  |  | 2026-01-28 12:37 |  | 2026-01-28 12:38
86 | 160 | 2026 | 1 |  | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | 2026-01-28 13:27 |  | 2026-02-02 10:29
87 | 159 | 2026 | 1 |  | 3189190b-a1ce-45e5-8a4f-3610efa00201 | BALNAVES, Stuart | Stuart.BALNAVES@EDUCATION.GOV.UK |  |  | 2026-01-28 14:20 |  | 2026-02-02 10:27
88 | 90 | 2026 | 1 |  | 53e52a08-4639-44ad-b2b3-2811de877217 | SPARKS, Robert | Robert.SPARKS@EDUCATION.GOV.UK |  |  | 2026-01-28 16:22 |  | 2026-02-09 14:10
89 | 163 | 2026 | 1 |  | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | 2026-01-29 09:00 |  | 2026-02-02 10:31
90 | 80 | 2026 | 1 |  | aba43bb4-6f1f-401b-959d-d4ecf70bf792 | WILSON, Catherine | Catherine.WILSON@EDUCATION.GOV.UK |  |  | 2026-01-29 14:33 |  | 2026-01-29 15:40
91 | 80 | 2026 | 2 |  | 32908ea6-3e40-4e69-9cff-3fa3c6aab41f | RYE, Samantha | Samantha.RYE@EDUCATION.GOV.UK |  |  | 2026-01-29 14:48 |  | 2026-03-02 14:40
92 | 80 | 2025 | 12 | [6 empty] | 2026-01-29 14:58
93 | 146 | 2026 | 1 |  | 067d5616-2c4b-4293-a08c-baa238a938bc | DUNSTALL, Rose | Rose.DUNSTALL@EDUCATION.GOV.UK |  |  | 2026-01-29 15:07 |  | 2026-01-29 15:08
94 | 126 | 2026 | 1 |  | 067d5616-2c4b-4293-a08c-baa238a938bc | DUNSTALL, Rose | Rose.DUNSTALL@EDUCATION.GOV.UK |  |  | 2026-01-29 15:08 |  | 2026-01-29 15:10
95 | 154 | 2026 | 1 |  | 067d5616-2c4b-4293-a08c-baa238a938bc | DUNSTALL, Rose | Rose.DUNSTALL@EDUCATION.GOV.UK |  |  | 2026-01-29 15:12 |  | 2026-01-29 15:12
96 | 147 | 2026 | 1 | [6 empty] | 2026-01-29 15:14 |  | 2026-01-29 15:14
97 | 116 | 2026 | 1 | [6 empty] | 2026-01-29 15:14 |  | 2026-01-29 15:14
98 | 137 | 2026 | 1 |  | ae9d166e-7a5b-44a2-acfa-ee02c3c2ea24 | OSBORNE, Kuldip | Kuldip.OSBORNE@EDUCATION.GOV.UK |  |  | 2026-01-29 16:07 |  | 2026-01-29 16:09
99 | 171 | 2026 | 1 |  | ae9d166e-7a5b-44a2-acfa-ee02c3c2ea24 | OSBORNE, Kuldip | Kuldip.OSBORNE@EDUCATION.GOV.UK |  |  | 2026-01-29 16:26 |  | 2026-01-29 16:26
100 | 218 | 2026 | 1 |  | ae9d166e-7a5b-44a2-acfa-ee02c3c2ea24 | OSBORNE, Kuldip | Kuldip.OSBORNE@EDUCATION.GOV.UK |  |  | 2026-01-29 16:32 |  | 2026-01-29 16:32
101 | 196 | 2026 | 1 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-01-30 08:42 |  | 2026-01-30 08:42
102 | 125 | 2026 | 1 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-01-30 08:44 |  | 2026-01-30 08:44
103 | 144 | 2026 | 1 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-01-30 08:45 |  | 2026-01-30 08:45
104 | 54 | 2026 | 1 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-01-30 08:46 |  | 2026-01-30 08:46
105 | 55 | 2026 | 1 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-01-30 08:47 |  | 2026-01-30 08:47
106 | 142 | 2026 | 1 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-01-30 08:51 |  | 2026-01-30 08:52
107 | 143 | 2026 | 1 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-01-30 08:52 |  | 2026-01-30 08:53
108 | 164 | 2026 | 1 |  | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | 2026-01-30 08:54 |  | 2026-02-02 10:21
109 | 132 | 2026 | 1 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-01-30 09:21 |  | 2026-01-30 09:22
110 | 161 | 2026 | 1 |  | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | 2026-01-30 10:59 |  | 2026-02-02 10:24
111 | 7 | 2026 | 2 |  | ef58175c-38bb-4aa4-b081-c5f0e49b2e10 | PATEL, Prina | Prina.PATEL@EDUCATION.GOV.UK |  |  | 2026-01-30 13:31 |  | 2026-03-02 07:43
112 | 7 | 2026 | 1 |  | ef58175c-38bb-4aa4-b081-c5f0e49b2e10 | PATEL, Prina | Prina.PATEL@EDUCATION.GOV.UK |  |  | 2026-01-30 13:32 |  | 2026-01-30 13:32
113 | 122 | 2025 | 12 | [6 empty] | 2026-01-30 18:05
114 | 92 | 2026 | 1 |  | 97b26ecf-01d6-4641-b70e-6558c3c45646 | THIPPESWAMY, Ravi | Ravi.THIPPESWAMY@EDUCATION.GOV.UK |  |  | 2026-02-02 07:51
115 | 56 | 2026 | 1 |  | 847721d6-8a9e-4a7a-8170-76096b429a8d | BRIGGS, Shelley | Shelley.BRIGGS@EDUCATION.GOV.UK |  |  | 2026-02-02 08:06 |  | 2026-02-02 08:07
116 | 87 | 2026 | 1 |  | 847721d6-8a9e-4a7a-8170-76096b429a8d | BRIGGS, Shelley | Shelley.BRIGGS@EDUCATION.GOV.UK |  |  | 2026-02-02 08:08 |  | 2026-02-02 08:08
117 | 92 | 2026 | 2 |  | 97b26ecf-01d6-4641-b70e-6558c3c45646 | THIPPESWAMY, Ravi | Ravi.THIPPESWAMY@EDUCATION.GOV.UK |  |  | 2026-02-02 08:08
118 | 91 | 2026 | 1 |  | e83f7a5b-59b4-4ac0-bf4a-a87587a40d7d | YOUNG, Joe | Joe.YOUNG@EDUCATION.GOV.UK |  |  | 2026-02-02 11:48 |  | 2026-02-09 14:11
119 | 205 | 2026 | 1 |  | 99e5d621-5a73-4f0a-bfe5-7f379240f3d8 | COLEY, Lorraine | Lorraine.COLEY@EDUCATION.GOV.UK |  |  | 2026-02-02 12:49 |  | 2026-02-02 12:50
120 | 206 | 2026 | 1 |  | 99e5d621-5a73-4f0a-bfe5-7f379240f3d8 | COLEY, Lorraine | Lorraine.COLEY@EDUCATION.GOV.UK |  |  | 2026-02-02 12:50 |  | 2026-02-02 12:51
121 | 207 | 2026 | 1 |  | 99e5d621-5a73-4f0a-bfe5-7f379240f3d8 | COLEY, Lorraine | Lorraine.COLEY@EDUCATION.GOV.UK |  |  | 2026-02-02 12:51 |  | 2026-02-02 12:52
122 | 208 | 2026 | 1 |  | 99e5d621-5a73-4f0a-bfe5-7f379240f3d8 | COLEY, Lorraine | Lorraine.COLEY@EDUCATION.GOV.UK |  |  | 2026-02-02 12:52 |  | 2026-02-02 12:52
123 | 44 | 2026 | 1 |  | d55d48a3-565f-4109-a5f6-63a8fbe9cb59 | BEAK, Kristi | Kristi.BEAK@EDUCATION.GOV.UK |  |  | 2026-02-02 13:55 |  | 2026-02-02 13:57
124 | 170 | 2026 | 1 |  | 32908ea6-3e40-4e69-9cff-3fa3c6aab41f | RYE, Samantha | Samantha.RYE@EDUCATION.GOV.UK |  |  | 2026-02-02 14:47 |  | 2026-02-02 14:47
125 | 91 | 2026 | 2 |  | e83f7a5b-59b4-4ac0-bf4a-a87587a40d7d | YOUNG, Joe | Joe.YOUNG@EDUCATION.GOV.UK |  |  | 2026-02-02 15:26 |  | 2026-02-18 10:29
126 | 153 | 2026 | 1 |  | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  |  | 2026-02-02 16:23 |  | 2026-02-02 16:24
127 | 209 | 2026 | 1 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-02-02 16:42 |  | 2026-02-02 16:42
128 | 45 | 2026 | 1 |  | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  |  | 2026-02-02 16:47 |  | 2026-02-02 16:48
129 | 133 | 2026 | 1 | [6 empty] | 2026-02-02 16:54 |  | 2026-02-02 16:54
130 | 200 | 2026 | 1 | [6 empty] | 2026-02-02 17:00 |  | 2026-02-02 17:00
131 | 136 | 2026 | 1 | [6 empty] | 2026-02-02 17:02 |  | 2026-02-02 17:02
132 | 220 | 2026 | 1 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-02-02 17:03 |  | 2026-02-02 17:04
133 | 134 | 2026 | 1 | [6 empty] | 2026-02-02 17:06 |  | 2026-02-02 17:06
134 | 221 | 2026 | 1 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-02-02 17:08 |  | 2026-02-02 17:09
135 | 204 | 2026 | 1 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-02-02 17:10 |  | 2026-02-02 17:14
136 | 135 | 2026 | 1 | [6 empty] | 2026-02-02 17:15 |  | 2026-02-02 17:15
137 | 46 | 2026 | 1 | [6 empty] | 2026-02-02 17:22 |  | 2026-02-02 17:22
138 | 52 | 2026 | 1 |  | 92796edb-6474-493d-a0a1-a61fe83fccca | STRINE, Amanda | Amanda.STRINE@EDUCATION.GOV.UK |  |  | 2026-02-02 17:32 |  | 2026-02-04 13:22
139 | 210 | 2026 | 1 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-02-02 17:39 |  | 2026-02-02 18:45
140 | 229 | 2026 | 1 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-02-02 18:46 |  | 2026-02-02 18:47
141 | 228 | 2026 | 1 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-02-02 18:47 |  | 2026-02-02 18:47
142 | 224 | 2026 | 1 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-02-02 18:48 |  | 2026-02-02 18:48
143 | 227 | 2026 | 1 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-02-02 18:48 |  | 2026-02-02 18:49
144 | 230 | 2026 | 1 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-02-02 18:49 |  | 2026-02-02 18:50
145 | 223 | 2026 | 1 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-02-02 18:50 |  | 2026-02-02 18:50
146 | 225 | 2026 | 1 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-02-02 18:51 |  | 2026-02-02 18:52
147 | 226 | 2026 | 1 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-02-02 18:53 |  | 2026-02-02 18:53
148 | 211 | 2026 | 1 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-02-02 18:55 |  | 2026-02-02 18:56
149 | 122 | 2026 | 1 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-02-02 18:59 |  | 2026-02-02 19:01
150 | 141 | 2026 | 1 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-02-02 19:02 |  | 2026-02-02 19:02
151 | 184 | 2026 | 1 |  | ebc20421-40e4-4b9c-96ce-982eacb84002 | PHILLIPS, Mark2 | Mark2.PHILLIPS@EDUCATION.GOV.UK |  |  | 2026-02-02 19:37 |  | 2026-02-04 15:05
152 | 188 | 2026 | 1 |  | ebc20421-40e4-4b9c-96ce-982eacb84002 | PHILLIPS, Mark2 | Mark2.PHILLIPS@EDUCATION.GOV.UK |  |  | 2026-02-02 19:50 |  | 2026-02-04 15:06
153 | 185 | 2026 | 1 |  | ebc20421-40e4-4b9c-96ce-982eacb84002 | PHILLIPS, Mark2 | Mark2.PHILLIPS@EDUCATION.GOV.UK |  |  | 2026-02-02 19:55 |  | 2026-02-04 15:06
154 | 187 | 2026 | 1 |  | 03f57944-a573-4abb-b765-28ecc11d00df | SCALE, Angela | Angela.SCALE@EDUCATION.GOV.UK |  |  | 2026-02-02 21:19 |  | 2026-02-04 15:04
155 | 189 | 2026 | 1 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-02-03 10:11 |  | 2026-02-03 12:33
156 | 190 | 2026 | 1 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-02-03 10:15 |  | 2026-02-03 10:16
157 | 25 | 2026 | 1 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-02-03 10:17 |  | 2026-02-03 10:17
158 | 191 | 2026 | 1 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-02-03 10:19 |  | 2026-02-03 10:19
159 | 193 | 2026 | 1 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-02-03 10:23 |  | 2026-02-03 10:24
160 | 17 | 2026 | 1 |  | 92796edb-6474-493d-a0a1-a61fe83fccca | STRINE, Amanda | Amanda.STRINE@EDUCATION.GOV.UK |  |  | 2026-02-03 12:36 |  | 2026-02-03 12:54
161 | 6 | 2026 | 1 |  | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  |  | 2026-02-03 13:00 |  | 2026-02-03 13:01
162 | 27 | 2026 | 1 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-02-03 13:15 |  | 2026-02-03 13:16
163 | 192 | 2026 | 1 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-02-03 13:17 |  | 2026-02-03 13:18
164 | 53 | 2026 | 1 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-02-03 13:21 |  | 2026-02-03 13:22
165 | 195 | 2026 | 1 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-02-03 13:23 |  | 2026-02-03 13:24
166 | 155 | 2026 | 1 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-02-03 13:25 |  | 2026-02-03 13:25
167 | 104 | 2026 | 1 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-02-03 13:26 |  | 2026-02-03 13:26
168 | 24 | 2026 | 1 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-02-03 13:27 |  | 2026-02-03 13:28
169 | 48 | 2026 | 1 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-02-03 13:29 |  | 2026-02-03 13:29
170 | 72 | 2026 | 1 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-02-03 14:01 |  | 2026-02-03 14:02
171 | 167 | 2026 | 1 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-02-03 14:13 |  | 2026-02-03 14:14
172 | 71 | 2026 | 1 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-02-03 14:13 |  | 2026-02-03 14:20
173 | 69 | 2026 | 1 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-02-03 14:29 |  | 2026-02-03 14:53
174 | 67 | 2026 | 1 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-02-03 14:47 |  | 2026-02-03 14:53
175 | 65 | 2026 | 1 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-02-03 14:56 |  | 2026-02-03 14:59
176 | 66 | 2026 | 1 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-02-03 15:00 |  | 2026-02-03 15:03
177 | 57 | 2026 | 1 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-02-03 15:06 |  | 2026-02-03 15:08
178 | 70 | 2026 | 1 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-02-03 16:47 |  | 2026-02-03 16:49
179 | 120 | 2026 | 1 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-02-03 16:51 |  | 2026-02-05 15:45
180 | 3 | 2026 | 1 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2026-02-04 13:53 |  | 2026-02-04 13:53
181 | 2 | 2026 | 1 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2026-02-04 13:54 |  | 2026-02-04 13:57
182 | 183 | 2026 | 1 |  | 03f57944-a573-4abb-b765-28ecc11d00df | SCALE, Angela | Angela.SCALE@EDUCATION.GOV.UK |  |  | 2026-02-04 13:56 |  | 2026-02-04 15:03
183 | 5 | 2026 | 1 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2026-02-04 14:00 |  | 2026-02-04 14:01
184 | 4 | 2026 | 1 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2026-02-04 14:02 |  | 2026-02-04 14:02
185 | 186 | 2026 | 1 |  | 03f57944-a573-4abb-b765-28ecc11d00df | SCALE, Angela | Angela.SCALE@EDUCATION.GOV.UK |  |  | 2026-02-04 15:33 |  | 2026-02-04 15:34
186 | 182 | 2026 | 1 |  | 03f57944-a573-4abb-b765-28ecc11d00df | SCALE, Angela | Angela.SCALE@EDUCATION.GOV.UK |  |  | 2026-02-04 15:36 |  | 2026-02-04 15:37
187 | 117 | 2026 | 1 |  | 03f57944-a573-4abb-b765-28ecc11d00df | SCALE, Angela | Angela.SCALE@EDUCATION.GOV.UK |  |  | 2026-02-04 15:40 |  | 2026-02-04 15:42
188 | 232 | 2026 | 1 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2026-02-05 10:08 |  | 2026-02-05 10:08
189 | 64 | 2026 | 1 |  | a23b8aca-1c7f-4ee6-8670-a5a2b8e790cb | RAINE, Paul | Paul.RAINE@EDUCATION.GOV.UK |  |  | 2026-02-05 12:03 |  | 2026-02-05 13:42
190 | 23 | 2026 | 1 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-02-05 12:17 |  | 2026-02-05 12:20
191 | 162 | 2026 | 1 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2026-02-05 14:51
192 | 158 | 2026 | 1 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2026-02-05 15:41 |  | 2026-02-05 15:41
193 | 212 | 2026 | 1 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-02-09 11:32 |  | 2026-02-09 11:41
194 | 31 | 2026 | 1 |  | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  |  | 2026-02-09 15:03 |  | 2026-02-09 15:16
195 | 33 | 2026 | 1 |  | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  |  | 2026-02-09 15:05 |  | 2026-02-09 15:17
196 | 152 | 2026 | 1 |  | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  |  | 2026-02-09 15:07 |  | 2026-02-09 15:15
197 | 32 | 2026 | 1 |  | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  |  | 2026-02-09 15:18 |  | 2026-02-09 15:18
198 | 34 | 2026 | 1 | [6 empty] | 2026-02-09 15:19 |  | 2026-02-09 15:19
199 | 37 | 2026 | 1 |  | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  |  | 2026-02-09 15:20 |  | 2026-02-09 15:21
200 | 35 | 2026 | 1 |  | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  |  | 2026-02-09 15:21 |  | 2026-02-09 15:22
201 | 88 | 2026 | 1 |  | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  |  | 2026-02-09 15:24 |  | 2026-02-09 15:25
202 | 151 | 2026 | 1 |  | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  |  | 2026-02-09 15:28 |  | 2026-02-09 15:28
203 | 36 | 2026 | 1 |  | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  |  | 2026-02-09 15:30 |  | 2026-02-09 15:30
204 | 124 | 2026 | 1 |  | be9b390a-94b5-47c2-aa27-c503c315a3d0 | WHARAM, Sue | Sue.WHARAM@education.gov.uk |  |  | 2026-02-10 13:36
205 | 233 | 2026 | 1 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2026-02-10 14:04 |  | 2026-02-10 14:11
206 | 234 | 2026 | 1 |  | 84d1af90-3a84-458f-893f-aa533b0571c0 | SADLER, Emily | Emily.SADLER@EDUCATION.GOV.UK |  |  | 2026-02-13 12:41 |  | 2026-02-13 12:45
207 | 235 | 2026 | 1 | [6 empty] | 2026-02-13 16:15 |  | 2026-02-13 16:15
208 | 237 | 2026 | 1 | [6 empty] | 2026-02-13 16:25 |  | 2026-02-13 16:25
209 | 236 | 2026 | 1 | [6 empty] | 2026-02-13 16:26 |  | 2026-02-13 16:26
210 | 119 | 2026 | 2 |  | 01633895-5ba6-4ac6-be83-0a3c88d4a8c5 | RATTAN, Sabina | Sabina.RATTAN@EDUCATION.GOV.UK |  |  | 2026-02-19 13:39 |  | 2026-02-19 13:45
211 | 145 | 2026 | 2 |  | 01633895-5ba6-4ac6-be83-0a3c88d4a8c5 | RATTAN, Sabina | Sabina.RATTAN@EDUCATION.GOV.UK |  |  | 2026-02-19 14:09 |  | 2026-02-19 14:10
212 | 6 | 2026 | 2 |  | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  |  | 2026-02-21 09:56 |  | 2026-02-26 20:12
213 | 15 | 2026 | 1 | [6 empty] | 2026-02-21 16:37
214 | 200 | 2026 | 2 | [6 empty] | 2026-02-22 20:58 |  | 2026-02-22 20:58
215 | 1 | 2026 | 2 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2026-02-23 10:59 |  | 2026-02-23 11:00
216 | 234 | 2026 | 2 |  | 337489ad-8849-40b8-8c1d-044502d64f84 | CORDINGLEY, Gaye | Gaye.CORDINGLEY@EDUCATION.GOV.UK |  |  | 2026-02-23 17:32 |  | 2026-02-26 16:56
217 | 128 | 2026 | 1 | [6 empty] | 2026-02-24 08:53
218 | 149 | 2026 | 2 |  | dc63b4e6-7088-459b-86cb-ddfab57b804a | DUNSTALL, Piers | Piers.DUNSTALL@EDUCATION.GOV.UK |  |  | 2026-02-24 09:14 |  | 2026-03-06 08:30
219 | 217 | 2026 | 2 |  | dc63b4e6-7088-459b-86cb-ddfab57b804a | DUNSTALL, Piers | Piers.DUNSTALL@EDUCATION.GOV.UK |  |  | 2026-02-24 09:38 |  | 2026-02-24 09:38
220 | 217 | 2026 | 1 | [6 empty] | 2026-02-24 09:38
221 | 129 | 2026 | 1 | [6 empty] | 2026-02-24 09:39
222 | 129 | 2026 | 2 |  | dc63b4e6-7088-459b-86cb-ddfab57b804a | DUNSTALL, Piers | Piers.DUNSTALL@EDUCATION.GOV.UK |  |  | 2026-02-24 09:40 |  | 2026-02-24 09:40
223 | 127 | 2026 | 2 |  | dc63b4e6-7088-459b-86cb-ddfab57b804a | DUNSTALL, Piers | Piers.DUNSTALL@EDUCATION.GOV.UK |  |  | 2026-02-24 09:41 |  | 2026-02-24 09:41
224 | 256 | 2026 | 2 |  | dc63b4e6-7088-459b-86cb-ddfab57b804a | DUNSTALL, Piers | Piers.DUNSTALL@EDUCATION.GOV.UK |  |  | 2026-02-24 11:36 |  | 2026-03-06 08:28
225 | 255 | 2026 | 2 |  | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | 2026-02-24 11:40 |  | 2026-02-27 09:11
226 | 254 | 2026 | 2 |  | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | 2026-02-24 11:41 |  | 2026-02-27 09:14
227 | 126 | 2026 | 2 | [6 empty] | 2026-02-24 11:50 |  | 2026-02-24 11:50
228 | 154 | 2026 | 2 |  | 067d5616-2c4b-4293-a08c-baa238a938bc | DUNSTALL, Rose | Rose.DUNSTALL@EDUCATION.GOV.UK |  |  | 2026-02-24 11:53 |  | 2026-02-24 11:54
229 | 146 | 2026 | 2 |  | 067d5616-2c4b-4293-a08c-baa238a938bc | DUNSTALL, Rose | Rose.DUNSTALL@EDUCATION.GOV.UK |  |  | 2026-02-24 11:55 |  | 2026-02-24 11:56
230 | 167 | 2026 | 2 |  | b6548968-6432-4b31-92a4-1a14b2521b44 | JENKINS, Julie | Julie.JENKINS@EDUCATION.GOV.UK |  |  | 2026-02-24 12:38 |  | 2026-02-24 14:51
231 | 147 | 2026 | 2 | [6 empty] | 2026-02-24 14:13 |  | 2026-02-24 14:13
232 | 116 | 2026 | 2 | [6 empty] | 2026-02-24 14:13 |  | 2026-02-24 14:13
233 | 52 | 2026 | 2 |  | 92796edb-6474-493d-a0a1-a61fe83fccca | STRINE, Amanda | Amanda.STRINE@EDUCATION.GOV.UK |  |  | 2026-02-24 16:42 |  | 2026-02-26 09:53
234 | 237 | 2026 | 2 |  | 54364aac-c110-4452-817e-340427ac1f35 | CASEY, Sally | Sally.CASEY@EDUCATION.GOV.UK |  |  | 2026-02-25 10:19 |  | 2026-03-03 09:09
235 | 137 | 2026 | 2 |  | ae9d166e-7a5b-44a2-acfa-ee02c3c2ea24 | OSBORNE, Kuldip | Kuldip.OSBORNE@EDUCATION.GOV.UK |  |  | 2026-02-25 13:03 |  | 2026-02-25 13:04
236 | 239 | 2026 | 2 |  | 4f2d5a27-fe15-40e5-8447-c396cfba2a77 | ALIPERTA, Lea | Lea.ALIPERTA@EDUCATION.GOV.UK |  |  | 2026-02-25 13:25
237 | 160 | 2026 | 2 |  | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | 2026-02-25 14:35 |  | 2026-02-27 09:29
238 | 163 | 2026 | 2 |  | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | 2026-02-25 14:36 |  | 2026-02-27 09:07
239 | 164 | 2026 | 2 |  | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | 2026-02-25 14:45 |  | 2026-02-27 10:04
240 | 17 | 2026 | 2 |  | 92796edb-6474-493d-a0a1-a61fe83fccca | STRINE, Amanda | Amanda.STRINE@EDUCATION.GOV.UK |  |  | 2026-02-25 15:08 |  | 2026-02-25 15:23
241 | 242 | 2026 | 2 |  | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | 2026-02-26 09:29 |  | 2026-02-27 10:26
242 | 161 | 2026 | 2 |  | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | 2026-02-26 09:30 |  | 2026-02-27 10:17
243 | 243 | 2026 | 2 |  | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | 2026-02-26 09:32 |  | 2026-02-27 10:27
244 | 245 | 2026 | 2 |  | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | 2026-02-26 09:40 |  | 2026-02-27 09:20
245 | 141 | 2026 | 2 |  | 0f9f7777-e6eb-4bd9-99af-fa0b883c2a83 | LANGLEY, Georgina | Georgina.LANGLEY@education.gov.uk |  |  | 2026-02-26 17:12 |  | 2026-03-05 14:13
246 | 122 | 2026 | 2 |  | 0f9f7777-e6eb-4bd9-99af-fa0b883c2a83 | LANGLEY, Georgina | Georgina.LANGLEY@education.gov.uk |  |  | 2026-02-26 17:14 |  | 2026-03-05 14:12
247 | 15 | 2026 | 2 |  | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  |  | 2026-02-26 20:13 |  | 2026-02-26 20:15
248 | 241 | 2026 | 2 |  | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | 2026-02-27 10:08 |  | 2026-02-27 10:08
249 | 238 | 2026 | 2 |  | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  |  | 2026-02-27 13:27 |  | 2026-03-02 11:43
250 | 153 | 2026 | 2 |  | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  |  | 2026-02-27 13:28 |  | 2026-03-02 11:42
251 | 205 | 2026 | 2 |  | 99e5d621-5a73-4f0a-bfe5-7f379240f3d8 | COLEY, Lorraine | Lorraine.COLEY@EDUCATION.GOV.UK |  |  | 2026-02-27 13:38 |  | 2026-02-27 13:39
252 | 206 | 2026 | 2 |  | 99e5d621-5a73-4f0a-bfe5-7f379240f3d8 | COLEY, Lorraine | Lorraine.COLEY@EDUCATION.GOV.UK |  |  | 2026-02-27 13:40 |  | 2026-02-27 13:40
253 | 207 | 2026 | 2 |  | 99e5d621-5a73-4f0a-bfe5-7f379240f3d8 | COLEY, Lorraine | Lorraine.COLEY@EDUCATION.GOV.UK |  |  | 2026-02-27 13:41 |  | 2026-02-27 13:41
254 | 208 | 2026 | 2 |  | 99e5d621-5a73-4f0a-bfe5-7f379240f3d8 | COLEY, Lorraine | Lorraine.COLEY@EDUCATION.GOV.UK |  |  | 2026-02-27 13:42 |  | 2026-02-27 13:42
255 | 185 | 2026 | 2 |  | ebc20421-40e4-4b9c-96ce-982eacb84002 | PHILLIPS, Mark2 | Mark2.PHILLIPS@EDUCATION.GOV.UK |  |  | 2026-02-27 14:45 |  | 2026-02-27 14:46
256 | 188 | 2026 | 2 |  | ebc20421-40e4-4b9c-96ce-982eacb84002 | PHILLIPS, Mark2 | Mark2.PHILLIPS@EDUCATION.GOV.UK |  |  | 2026-02-27 14:51 |  | 2026-02-27 14:51
257 | 133 | 2026 | 2 |  | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  |  | 2026-02-27 15:34 |  | 2026-03-02 11:36
258 | 135 | 2026 | 2 |  | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  |  | 2026-02-27 15:35 |  | 2026-03-02 10:31
259 | 134 | 2026 | 2 |  | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  |  | 2026-02-27 15:37 |  | 2026-03-02 10:16
260 | 136 | 2026 | 2 |  | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  |  | 2026-02-27 15:38 |  | 2026-03-02 10:03
261 | 46 | 2026 | 2 |  | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  |  | 2026-02-27 15:40 |  | 2026-03-02 10:47
262 | 64 | 2026 | 2 |  | d46c78e6-9f62-4213-8cc2-489763a4b444 | KING, Kathryn | Kathryn.KING@EDUCATION.GOV.UK |  |  | 2026-02-27 17:00 |  | 2026-03-05 07:46
263 | 219 | 2026 | 2 |  | c010c450-1cef-4ad2-8ac2-96870b5b3dd8 | WRIGHT, Jo | Jo.WRIGHT@EDUCATION.GOV.UK |  |  | 2026-03-02 07:39 |  | 2026-03-02 07:41
264 | 124 | 2026 | 2 |  | be9b390a-94b5-47c2-aa27-c503c315a3d0 | WHARAM, Sue | Sue.WHARAM@education.gov.uk |  |  | 2026-03-02 08:53 |  | 2026-03-02 15:41
265 | 184 | 2026 | 2 |  | 03f57944-a573-4abb-b765-28ecc11d00df | SCALE, Angela | Angela.SCALE@EDUCATION.GOV.UK |  |  | 2026-03-02 08:56 |  | 2026-03-02 08:58
266 | 183 | 2026 | 2 |  | 03f57944-a573-4abb-b765-28ecc11d00df | SCALE, Angela | Angela.SCALE@EDUCATION.GOV.UK |  |  | 2026-03-02 09:08 |  | 2026-03-02 09:10
267 | 73 | 2026 | 2 |  | 976f27df-5486-4d6a-8afd-b46f95453e70 | GILL, Ushma | Ushma.GILL@EDUCATION.GOV.UK |  |  | 2026-03-02 09:09 |  | 2026-03-02 09:10
268 | 62 | 2026 | 2 | [6 empty] | 2026-03-02 09:16 |  | 2026-03-02 09:16
269 | 159 | 2026 | 2 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2026-03-02 09:16 |  | 2026-03-02 09:17
270 | 90 | 2026 | 2 |  | 53e52a08-4639-44ad-b2b3-2811de877217 | SPARKS, Robert | Robert.SPARKS@EDUCATION.GOV.UK |  |  | 2026-03-02 09:47 |  | 2026-03-02 09:48
271 | 3 | 2026 | 2 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2026-03-02 12:36 |  | 2026-03-02 12:36
272 | 5 | 2026 | 2 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2026-03-02 12:38 |  | 2026-03-02 12:40
273 | 2 | 2026 | 2 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2026-03-02 12:42 |  | 2026-03-02 12:44
274 | 4 | 2026 | 2 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2026-03-02 12:46 |  | 2026-03-02 12:49
275 | 236 | 2026 | 2 |  | 0b3ddd1b-cbab-49b0-ab3f-1cf4f757191a | JINARAL, Tejas | Tejas.JINARAL@EDUCATION.GOV.UK |  |  | 2026-03-02 13:18 |  | 2026-03-02 13:19
276 | 182 | 2026 | 2 |  | 53b409ec-10a3-4b05-ad6d-d7ff8d9946f1 | DUNNE, Alison | Alison.Dunne@EDUCATION.GOV.UK |  |  | 2026-03-02 13:45 |  | 2026-03-02 15:00
277 | 246 | 2026 | 2 |  | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | 2026-03-02 13:52 |  | 2026-03-02 13:52
278 | 31 | 2026 | 2 |  | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  |  | 2026-03-02 14:19 |  | 2026-03-02 14:20
279 | 250 | 2026 | 2 |  | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | 2026-03-02 14:27 |  | 2026-03-02 14:45
280 | 248 | 2026 | 2 |  | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | 2026-03-02 14:29 |  | 2026-03-02 14:43
281 | 152 | 2026 | 2 |  | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  |  | 2026-03-02 14:31 |  | 2026-03-02 14:34
282 | 252 | 2026 | 2 |  | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  |  | 2026-03-02 14:31 |  | 2026-03-02 14:41
283 | 170 | 2026 | 2 |  | 32908ea6-3e40-4e69-9cff-3fa3c6aab41f | RYE, Samantha | Samantha.RYE@EDUCATION.GOV.UK |  |  | 2026-03-02 14:40 |  | 2026-03-02 14:40
284 | 151 | 2026 | 2 |  | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  |  | 2026-03-02 14:47 |  | 2026-03-02 14:47
285 | 32 | 2026 | 2 | [6 empty] | 2026-03-02 14:48 |  | 2026-03-02 14:48
286 | 33 | 2026 | 2 | [6 empty] | 2026-03-02 14:49 |  | 2026-03-02 14:49
287 | 34 | 2026 | 2 | [6 empty] | 2026-03-02 14:50 |  | 2026-03-02 14:50
288 | 36 | 2026 | 2 | [6 empty] | 2026-03-02 14:51 |  | 2026-03-02 14:51
289 | 35 | 2026 | 2 | [6 empty] | 2026-03-02 14:52 |  | 2026-03-02 14:52
290 | 37 | 2026 | 2 | [6 empty] | 2026-03-02 14:53 |  | 2026-03-02 14:53
291 | 88 | 2026 | 2 |  | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  |  | 2026-03-02 14:56 |  | 2026-03-02 14:56
292 | 56 | 2026 | 2 |  | 847721d6-8a9e-4a7a-8170-76096b429a8d | BRIGGS, Shelley | Shelley.BRIGGS@EDUCATION.GOV.UK |  |  | 2026-03-02 15:13 |  | 2026-03-02 15:15
293 | 87 | 2026 | 2 |  | 847721d6-8a9e-4a7a-8170-76096b429a8d | BRIGGS, Shelley | Shelley.BRIGGS@EDUCATION.GOV.UK |  |  | 2026-03-02 15:16 |  | 2026-03-02 15:16
294 | 16 | 2026 | 2 |  | f7abf0c1-9598-41e9-957a-3d7638a74856 | MURPHY, Carmel | Carmel.MURPHY@EDUCATION.GOV.UK |  |  | 2026-03-02 16:22 |  | 2026-03-02 16:22
295 | 209 | 2026 | 2 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-03-02 16:59 |  | 2026-03-02 17:20
296 | 204 | 2026 | 2 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-03-02 17:03 |  | 2026-03-02 17:04
297 | 220 | 2026 | 2 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-03-02 17:05 |  | 2026-03-02 17:05
298 | 221 | 2026 | 2 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-03-02 17:06 |  | 2026-03-02 17:07
299 | 210 | 2026 | 2 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-03-02 17:08 |  | 2026-03-02 17:09
300 | 229 | 2026 | 2 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-03-02 17:14 |  | 2026-03-02 17:14
301 | 228 | 2026 | 2 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-03-02 17:15 |  | 2026-03-02 17:15
302 | 224 | 2026 | 2 | [6 empty] | 2026-03-02 17:16 |  | 2026-03-02 17:16
303 | 230 | 2026 | 2 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-03-02 17:22 |  | 2026-03-02 17:24
304 | 225 | 2026 | 2 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-03-02 17:25 |  | 2026-03-02 17:26
305 | 223 | 2026 | 2 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-03-02 17:27 |  | 2026-03-02 17:28
306 | 257 | 2026 | 2 |  | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  |  | 2026-03-02 17:34 |  | 2026-03-02 17:35
307 | 45 | 2026 | 2 |  | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  |  | 2026-03-02 18:23 |  | 2026-03-02 18:23
308 | 117 | 2026 | 2 |  | 53b409ec-10a3-4b05-ad6d-d7ff8d9946f1 | DUNNE, Alison | Alison.Dunne@EDUCATION.GOV.UK |  |  | 2026-03-02 22:35 |  | 2026-03-02 22:48
309 | 232 | 2026 | 2 |  | 53b409ec-10a3-4b05-ad6d-d7ff8d9946f1 | DUNNE, Alison | Alison.Dunne@EDUCATION.GOV.UK |  |  | 2026-03-02 23:09 |  | 2026-03-02 23:39
310 | 186 | 2026 | 2 |  | d34760a7-edc4-486a-9aff-c52e174e7cf3 | HEAD, Justine | Justine.HEAD@EDUCATION.GOV.UK |  |  | 2026-03-03 07:59 |  | 2026-03-04 10:30
311 | 196 | 2026 | 2 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-03-03 08:55 |  | 2026-03-03 09:06
312 | 125 | 2026 | 2 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-03-03 08:58 |  | 2026-03-03 09:06
313 | 144 | 2026 | 2 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-03-03 08:59 |  | 2026-03-03 09:06
314 | 54 | 2026 | 2 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-03-03 09:00 |  | 2026-03-03 09:06
315 | 55 | 2026 | 2 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-03-03 09:00 |  | 2026-03-03 09:06
316 | 18 | 2026 | 2 |  | 73fa79c3-5d67-4a7a-bf30-12fa7da710d2 | RAE, Angus | Angus.RAE@EDUCATION.GOV.UK |  |  | 2026-03-03 09:01 |  | 2026-03-03 09:02
317 | 132 | 2026 | 2 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-03-03 09:01 |  | 2026-03-03 09:07
318 | 142 | 2026 | 2 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-03-03 09:02 |  | 2026-03-03 09:07
319 | 143 | 2026 | 2 |  | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  |  | 2026-03-03 09:03 |  | 2026-03-03 09:07
320 | 189 | 2026 | 2 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-03-03 12:37 |  | 2026-03-03 12:38
321 | 193 | 2026 | 2 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-03-03 13:06 |  | 2026-03-03 13:08
322 | 27 | 2026 | 2 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-03-03 13:11 |  | 2026-03-03 13:12
323 | 191 | 2026 | 2 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-03-03 13:12 |  | 2026-03-03 13:13
324 | 192 | 2026 | 2 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-03-03 13:14 |  | 2026-03-03 13:14
325 | 25 | 2026 | 2 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-03-03 13:15 |  | 2026-03-03 13:16
326 | 155 | 2026 | 2 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-03-03 13:19 |  | 2026-03-03 13:19
327 | 104 | 2026 | 2 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-03-03 13:20 |  | 2026-03-03 16:51
328 | 24 | 2026 | 2 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-03-03 13:24 |  | 2026-03-03 13:24
329 | 48 | 2026 | 2 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-03-03 13:24 |  | 2026-03-03 13:24
330 | 258 | 2026 | 2 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-03-03 13:35 |  | 2026-03-03 13:35
331 | 259 | 2026 | 2 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-03-03 13:43 |  | 2026-03-03 13:43
332 | 53 | 2026 | 2 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-03-03 14:13 |  | 2026-03-03 14:13
333 | 190 | 2026 | 2 |  | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  |  | 2026-03-03 17:15 |  | 2026-03-03 17:19
334 | 171 | 2026 | 2 | [6 empty] | 2026-03-04 10:49 |  | 2026-03-04 10:49
335 | 233 | 2026 | 2 |  | c010c450-1cef-4ad2-8ac2-96870b5b3dd8 | WRIGHT, Jo | Jo.WRIGHT@EDUCATION.GOV.UK |  |  | 2026-03-04 10:52 |  | 2026-03-04 13:49
336 | 211 | 2026 | 2 | [6 empty] | 2026-03-04 11:02 |  | 2026-03-04 11:02
337 | 72 | 2026 | 2 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-03-04 15:48 |  | 2026-03-04 15:48
338 | 71 | 2026 | 2 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-03-04 15:49 |  | 2026-03-04 15:49
339 | 69 | 2026 | 2 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-03-04 15:50 |  | 2026-03-04 15:51
340 | 65 | 2026 | 2 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-03-04 15:51 |  | 2026-03-04 15:52
341 | 23 | 2026 | 2 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-03-04 15:53 |  | 2026-03-04 15:53
342 | 67 | 2026 | 2 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-03-04 15:53 |  | 2026-03-04 15:54
343 | 66 | 2026 | 2 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-03-04 15:54 |  | 2026-03-04 15:54
344 | 57 | 2026 | 2 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-03-04 15:56 |  | 2026-03-04 15:56
345 | 70 | 2026 | 2 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-03-04 15:58 |  | 2026-03-04 15:58
346 | 195 | 2026 | 2 | [6 empty] | 2026-03-04 16:00 |  | 2026-03-04 16:00
347 | 212 | 2026 | 2 | [6 empty] | 2026-03-04 16:01 |  | 2026-03-04 16:01
348 | 44 | 2026 | 2 | [6 empty] | 2026-03-05 09:03 |  | 2026-03-05 09:03
349 | 222 | 2026 | 2 |  | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  |  | 2026-03-05 09:48 |  | 2026-03-05 09:48
350 | 26 | 2026 | 2 |  | f3e1f612-d430-4f14-b918-df815d949249 | MARSDEN, Daniel | Daniel.MARSDEN@EDUCATION.GOV.UK |  |  | 2026-03-05 14:27 |  | 2026-03-05 14:28
351 | 26 | 2026 | 1 | [6 empty] | 2026-03-05 14:29
352 | 39 | 2026 | 2 |  | f7f31ca6-8502-4d63-93e2-bac025095fa3 | SCOTT, David | David.SCOTT@EDUCATION.GOV.UK |  |  | 2026-03-05 17:30 |  | 2026-03-05 17:30
353 | 89 | 2026 | 2 |  | e83f7a5b-59b4-4ac0-bf4a-a87587a40d7d | YOUNG, Joe | Joe.YOUNG@EDUCATION.GOV.UK |  |  | 2026-03-06 10:36 |  | 2026-03-10 09:11
354 | 89 | 2026 | 1 | [6 empty] | 2026-03-10 09:12
355 | 215 | 2026 | 2 |  | f16be3e8-8523-460d-af95-7d6290fbf32b | HALIM, Amna | Amna.HALIM@EDUCATION.GOV.UK |  |  | 2026-03-10 10:03 |  | 2026-03-10 10:04
356 | 43 | 2026 | 2 |  | 9cdea143-507b-4b33-831b-9e2ddeae99c5 | MYERSCOUGH, Jennifer | Jennifer.MYERSCOUGH@EDUCATION.GOV.UK |  |  | 2026-03-10 15:33 |  | 2026-03-10 15:34
357 | 43 | 2026 | 1 | [6 empty] | 2026-03-10 15:34
358 | 158 | 2026 | 2 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-03-11 08:33 |  | 2026-03-11 08:34
359 | 120 | 2026 | 2 |  | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  |  | 2026-03-11 08:35 |  | 2026-03-11 08:35

## MonthlyNarratives
Id | ProjectMonthlyUpdateId | Narrative | CreatedByEntraId | CreatedByName | CreatedByEmail | CreatedByUserId | CreatedAt
5 | 2 | • Operational Readiness Reviews in flow, initial run through of paperwork • Discussions on existing 'as is' processes with IDP on UKRLP and Kam on PIMS to fill operational knowledge gaps • Planning 'to be' processes with internal team and discussions turning in to decisions | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2025-11-28 11:21
6 | 3 | R04 for 25/26 opened on time Over 99% of files process successfully at first attempt failures are re-submitted either by the provider or SLD team | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2025-11-28 11:33
7 | 4 | Limited resources due to staff leave and significant risks around talent retention, continuing to deliver on key priorities. | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2025-11-28 11:35
8 | 5 | We had the Education Record programme board on 19th November. We presented pilot findings and provided an update on progress of the ministerial submission. The session could have been better attended by board members - communicatons in readiness for the next board have been sent to attempt to increase attendance. The ministerial submission has been critiqued by various business areas and is now awaiting for final sign-off before decision | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2025-11-28 11:41
9 | 6 | We have designed a new help page within the service to include links to guidance for the service and related guidance (e.g. funding reports), these designs will be going out for user research. The new Gov.uk branding has gone live for the service. | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2025-11-28 11:43
10 | 7 | collection extended to 10 Dec 2025 | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2025-11-28 11:43
11 | 8 | Green - all projects progressing well and the pinch point created by taking in the Technical Excellence College form has been managed. However this has increased pressure on the Dec - March deliverables. | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2025-11-28 11:44
12 | 9 | The teams are all fully committed at present with the various work streams we have live at the moment and there is no capacity to increase our ability to deliver other work. | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2025-11-28 11:45
14 | 10 | Progressed well with the beta phase and rolled out to both Central Operations along with a diary study, and then wider department at DDT all-staff call. Overall good positive engagement and feedback. | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  | 2025-11-28 14:18
15 | 11 | Work started on information architecture for the new manual. With an initial landing page designed and shared around Heads of Profession for input and critique. | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  | 2025-11-28 15:16
16 | 12 | No change this month, project is just starting and UR has only just started in past couple of weeks. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2025-12-03 15:13
17 | 13 | No change this month, RAG staying the same! | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2025-12-03 15:29
18 | 14 | Phase changed to Live - RAG is still Green this month. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2025-12-03 15:34
19 | 15 | No change to RAG this month all on track. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2025-12-03 15:36
20 | 16 | No change to status this month, still Amber/Red RAG - Lack of ownership of NHSE of their elements of the work needed to progress with the NHS number as the SUI and the use of their systems to enable the pilots to take place. Amber/red due to lack of progress on resolving issues. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2025-12-03 15:38
21 | 17 | Alpha ends 23/1/2026 - RAG remains Green this month. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2025-12-03 15:40
22 | 18 | Discovery ended 28 November 2025, now carrying out Peer Review - RAG remains Green. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2025-12-03 15:43
23 | 19 | RAG updated to Amber and Path to Green added. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2025-12-03 15:48
24 | 20 | No change to RAG status this month. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2025-12-03 15:50
25 | 21 | No status change this month. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2025-12-03 15:55
26 | 22 | No change to status this month. Additional Aim detail added. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2025-12-03 15:57
27 | 23 | Status downgraded to Amber-Red and path to green added. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2025-12-03 15:58
28 | 24 | No change to RAG this month. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2025-12-03 15:59
32 | 25 | Attendance data mandating successfully went live on 21st August 2024. Work is on track to continue to iterate the product during this financial year. 99.64% of schools are sharing their daily attendance data. The team continue to work with Wonde to improve DQ and CBDS data fields. Product live and stable, with iterations happening for additional features/services. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2025-12-04 19:12
33 | 26 | MDP R&M - SC Aut25 provisional - delivery completed and re-delivery of 23-24 data. Work continues to deliver other datasets. Matching - Work continues to build; Shema changes and regression testing in SIT environment. AODC - Released QRD Early Nov syllabus and iGCSE update and SCDB 8 CLDS 2.0 (migration team) Work is currently on track to be ready for cutover of first datasets to Databricks 2.0 in March 2026 | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2025-12-04 19:22
35 | 27 | Progress made during this peirod- Public Dashboard OFSTED update UR for Private Dashboard ongoing QA Dashboard MVP build underway alongside final QA page (UaT) Prototyping of Private Dashboard continuing Severe absence in main 6 LAs connected to SIT environment | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2025-12-04 19:28
36 | 28 | No update provided this month |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk |  | 2025-12-04 23:25
37 | 29 | No update provided this month |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk |  | 2025-12-05 15:31
46 | 32 | Currently working through risk review process across DDT and aligning risk tiering with the Department's tier system. Preforming Gap analysis of risk reporting for DDT and central risk team/ Departments top tier tool | ef58175c-38bb-4aa4-b081-c5f0e49b2e10 | PATEL, Prina | Prina.PATEL@EDUCATION.GOV.UK |  | 2025-12-09 10:30
47 | 30 | Test | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  | 2025-12-09 10:32
50 | 31 | AI Adoption CoE roadmap updated. Engage with Schools Group workshops on potential AI use cases – 17th and 25th November Ed chat – Service standards peer review completed – blockers in moving some work forwards risks delay to pilot launch. Records Management proof of concept - continue to build the functionality of the product. There is a potential roadblock in that the business rules provided by the KIM team are not robust enough to build an effective and accurate tool. GIAA conducted an audit of governance and approved the methodology for AI Centre of Excellence without any changes. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2025-12-09 13:52
53 | 1 | Families Group and EDFO have completed updates on COMPASS. Feedback has been given and acted upon to improve the system. EDS reporting was delayed due to leave but will be completed in coming days. Feedback has been positive. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2025-12-10 11:09
54 | 33 | Confirmed with DDT strategy and transformation that his work is now completed and does not need to be reported on COMPASS. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2025-12-15 13:34
55 | 34 | Project has been closed. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2025-12-15 13:54
56 | 35 | Project has just moved into beta. Road map and delivery plan in place. Progress on track against these documents. No red risks. Still waiting to engage with internal infrastruture engineer | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2025-12-15 13:57
57 | 36 | As a whole some of the vision work has now taken place within SDRev as a programme. The programme does not have its own budget, schedule and as a result can be ranked as amber whilst certain priority mitigations are completed (see path to green). | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2025-12-15 13:58
58 | 37 | No change. Project just registered on COMPASS. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2025-12-15 15:32
59 | 38 | No change. Project just registered on COMPASS. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2025-12-15 15:32
60 | 39 | STA only added to COMPASS so no update this month. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2025-12-16 09:21
61 | 40 | Only added to COMPASS reporting in December so no update this month. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2025-12-16 10:19
62 | 41 | Completed engagement with trusts to understand user needs, including a full-day visit with SET (Sapientia), ARK & LIFT; further engagement planned. Conceptual target model remains on track. Defined architectural principles and identified data flows and duplication within the current DfE structure. Engaged with Attendance and ADA technical teams to ensure reuse and maximise learning. Prepared Non-Functional Requirements (NFRs). Drafted Design principles for the programme. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2025-12-16 11:26
63 | 42 | Due to start 17/11/25, actually started on 26/11/2025. Rated amber/ green due to delayed start caused by changes to scope and how workstreams will look like. MIS and Wonde were previously separated, now merged into one workstream. Major dependency on receiving data from Wonde and MIS. Unknown lead time to receiving data from Wonde. Unknown at this point what financial implications of engaging with Wonde and MIS will be. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2025-12-17 14:35
64 | 43 | Due to start 1/12/2025 New team joined DS from LDS to take this workstream forward. Scope yet to be defined, policy colleagues input needed. It is unknown at this point what financial implications of engaging with EdTech will be. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2025-12-17 14:36
67 | 44 | 01/12 - A stakeholder meeting between partners and internal stakeholders went ahead which aimed to align DfE colleagues with the wider context of the CTP investigations. The team have continued with amends to documentation and have completed the initial builds of MVP. 10/11 - A review of process has been successfully completed with the Cyber team and the team is taking forward the actions from that. MOU, HLD and SOM are all in draft and some of have been shared out for comment. An update with CENSED has been complete and a wider engagement scheduled for later in the week. The build within MDP is commencing at pace and we're expecting development to be completed shortly. 03/11 - The team are preparing for presenting to the Cyber team with the design documentation finished at this stage. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2025-12-18 12:31
69 | 45 | No update provided this month |  | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk |  | 2025-12-18 13:02
70 | 46 | Data and technology strategy summaries updated, initial pass of tech strategy initiatives with EDS Provided oversight on STA review, supported Skills England, SLC and Erasmus with architecture review recommendations SoWs signed off for managed service support for the Enterprise Data Model and business capability mapping, to accelerate model development. Finalised Data/Security Architect updates on the architecture capability framework, implementation of CBP for Data Architect underway. Onboarded new architecture services contract, several new SoWs reviewed and out for response, contract mobilisation complete. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2025-12-18 13:05
71 | 47 | No update provided this month |  | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk |  | 2026-01-05 15:46
75 | 49 | 1) First steering group meeting held on 03 of Dec with key DDT and policy stakeholders; agreed on PoC data domain focusing on attainment (non-statutory), SEND, and behaviour. 2) DSIT business case completed and submitted. 3) DPIA for WONDE completed; with Data Protection Office agreement. First draft for MIS & EdTech also completed. 4) DSAP completed and submitted; scheduled for discussion at the Data Sharing Panel on 7 January. 5) Resource plan revised to reflect adjusted workstreams (still in development to ensure required expertise and resources for March delivery). EdTech resource onboarded. 6) WS1 drafts for key architecture components completed, reviewed, and progressing to finalisation; alignment with DfE Enterprise Architecture confirmed. 7) WS2 (WONDE) engagement underway; WONDE agreed to share additional data under existing contract at no additional cost. Build activities started. 8) WS3 (EdTech) The team are creating a criteria to decide on which EdTech tools to prioritise which will be shared with Policy for agreement. 9) Agreed with i.AI team to include AI tutoring as a future domain within the data spine programme but, due to timing misalignment with Policy, i.Ai cannot be included in this phase. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-01-07 14:33
76 | 50 | " ​1.Solution Architecture (HLD & LLD): Initial draft peer reviewed and sign-off completed, this will continue to be iterated upon in line with the build in WS2. 2.Data Architecture: Conceptual Data Model: Peer reviewed and formally signed off with feedback, Agreed to track for iterative improvements. 3.Architectural Principles: Draft prepared. Peer reviewed and formally signed off with feedback, Agreed to track for iterative improvements. 4.Target Architecture & Strategic Roadmap work defined and mapped in ADO. 5.Non-Functional Requirements (NFRs): Draft completed; finalisation underway. " | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-01-07 15:20
77 | 51 | "1) Positive engagement with WONDE- agreement to provide DfE extra data at no cost. We gained access to WONDE's test environment. 2) Progress on MIS commercial - engaging with Emma Bagley - drafted notice of engagement - to go out as soon as it's ready (early new year). 3) Building of dev & test infrastructure has started. 4) Introduction with VYED team as well as two internal DfE analysts who will support us getting the best we can out of data from WONDE - once we ingest it. 5) Backlog in Azure DevOps shaping up- all epics created, most of key features and stories- ready for the first sprint in January 2026. " | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-01-07 15:45
78 | 52 | 1) Resource has been onboarded, and planning has been initiated. 2) Team have reached out to multiple colleagues and stakeholders to understand the problem space 3) Engagement and a workshop with the policy team have been conducted to discuss the scope and the tools to be used as part of the analysis. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-01-07 15:58
79 | 48 | 05/01 - Prior to the winter break, the team reviewed some of the initial feedback with the team on the MVP. The backlog has been refined ahead of work to improve and iterate the MVP solution. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-01-07 16:36
80 | 53 | Having made progress on what governance structure we need in place we are now setting up a sub-triage board and a process to receive PAS demand. Work is kicking off with the AI team on how things have been managed so far. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-01-07 16:47
81 | 54 | Project is progressing to plan | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-01-07 16:51
82 | 55 | Significant changes to the scope of the programme in terms of the order of its delivery. We are reassessing the plan and looking to play this back to senior stakeholders to ensure our plan is aligned. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-01-07 16:57
83 | 56 | Scope agreed - first milestone of sharing with SLT completed. Tool can ingest insights in test. Copied documents from SharePoint to Azure blob successfully. Cross portfolio sessions for business champions have taken place along with requirements gathering workshops. Discussion on D&T spend controls have confirmed these are not applicable to this project. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-01-07 17:03
84 | 57 | Moved into Beta phase | ae9d166e-7a5b-44a2-acfa-ee02c3c2ea24 | OSBORNE, Kuldip | Kuldip.OSBORNE@EDUCATION.GOV.UK |  | 2026-01-13 10:18
85 | 57 | Working on improving data quality and adding technology | ae9d166e-7a5b-44a2-acfa-ee02c3c2ea24 | OSBORNE, Kuldip | Kuldip.OSBORNE@EDUCATION.GOV.UK |  | 2026-01-13 10:19
86 | 58 | Workshop planned to start the Service Manual work to consolidate all existing manuals and guidance for DDT. | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  | 2026-01-13 12:09
87 | 59 | Workshop planned for January 20th which will outline the plan and goals for the project with HOPs, DesignOps, ReOps, and key stakeholders. | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  | 2026-01-13 12:14
88 | 60 | No update provided this month |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk |  | 2026-01-13 12:16
89 | 61 | No update provided this month |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk |  | 2026-01-13 12:16
90 | 62 | No update provided this month |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk |  | 2026-01-13 14:47
91 | 63 | • GDS Discovery completed with official feedback which is accepted • Project is Green as project is on-track and whilst recruitment still has roles to be filled this is not stopping delivery happening • Data lookups being developed • UR carried out on PIMS Admin & UKRLP Admin • UR planning for UKRLP API users, PIMS search users, PIMS upload users • Operational Readiness Reviews in flow, initial run through of paperwork • 'To be' processes are being mapped out with automations and rationalisations • Discussions around DSI and PP pointing to UKRLP as opposed to PIMS to allow authentication route for UKRLP users • Initial infrastructure now being built • Data cleansing GIAS - PIMS - UKRLP being looked through | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-01-14 08:45
92 | 64 | R05 for 25/26 opened on time over 99% of files process successfully at first attempt failures are re-submitted either by the provider or SLD team | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-01-14 08:48
93 | 65 | Limited resources due to staff leave and significant risks around talent retention | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-01-14 08:50
94 | 66 | Our last show and tell was on 19th December, our next one is planned for 30 January 2026. We have made updates to our promotional video and posters based on feedback from our last couple of rounds of user research. We have released new versions of both apps, this included some minor bug fixes and technical updates. We have also released a new version of Issue Education Record which includes the new branding. We have completed a round of UR with assistive tech users, the findings from this will help us identify areas for design review and areas where updates are needed. We have started the preparation work for our next IT Health Check and have have started the preparations for an external accessibility test. We are hoping to be able to make an announcement on the national pilot on 8th January, we are working with comms colleagues on this. | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-01-14 08:51
95 | 67 | Our last show and tell was on 19th December, our next one is planned for 30 January 2026. We have completed a round of user research on migration. We are planning further research in this space and are also starting some design work which will feed into development for next summer. We sent out a survey to users to get feedback on our designs for the ILR annual fields and are planning a survey to get feedback on our new help pages. Following the SLD board meeting earlier in December, we have started planning our work on the ILR changes for 26/27. We are nearing completion for non-funded apprenticeships and have started the development work for the first Skills Bootcamps user journeys. We have started some design and development work to support changes to the HE data collection requirements from R06. We have started the preparation work for an external accessibility test. | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-01-14 08:51
96 | 68 | collection extended to 9 Jan | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-01-14 08:52
97 | 69 | Green - all projects running to time except CSC FO which will finish Alpha 3 weeks later than planned, impact on Beta is being managed. TEC form went live on 15 December as agreed with the business. SRMSAC annual refresh of form is complete and ready to go live on 8 January 2026 as agreed with the business. College Financial - Finance Record Collection went live as planned 19 November. College Financial Reclassification Discovery on track to finish on 20 January 2026. Submit Financial Data - remains in Private Beta, opening up to a second tranche after lower than expected engagement in the first tranche. Childrens Social Care Financial Oversight Scheme - Alpha to run over to 23 January, planning end of phase playbacks and assessment for end January. Impact on Beta is being managed. | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-01-14 08:53
98 | 70 | The teams are all fully committed at present with the various work streams we have live at the moment and there is no capacity to increase our ability to deliver other work. | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-01-14 08:54
99 | 71 | Continuing to progress updates for work reporting and onboarding portfolios to monthly reporting. | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  | 2026-01-15 11:05
101 | 72 | Complete | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-01-15 16:59
102 | 73 | The records team focus for the AI Records project in December was the creation of new datasets for the AI tool testing. The work on the previous dataset had achieved 90+% accuracy for discard/review decisions. These datasets will test the tool to ascertain how the knowledge bases created respond to different datasets. The developer has this testing and when the records team receive (late Jan/Feb) feedback will be able to revisit the dataset development. The records team continue to investigate the wider digital review requirements which are part of the AI project, including possible solutions to the problem with the metadata discovery tool. | be9b390a-94b5-47c2-aa27-c503c315a3d0 | WHARAM, Sue | Sue.WHARAM@education.gov.uk |  | 2026-01-16 07:27
103 | 74 | Data Protection advice for photos in schools guidance has been cleared for publishing. CCTV and procurement is in final draft form and being reviewed for publishing. Procurement will be subject to user testing before being published to ensure it meets users requirements. | be9b390a-94b5-47c2-aa27-c503c315a3d0 | WHARAM, Sue | Sue.WHARAM@education.gov.uk |  | 2026-01-16 07:31
104 | 75 | This project will be completed by early Feb. Approx 400 classification scorecards records are now updated in service now. A mop-up to complete the project is scheduled for mid-Feb post the Service Now upgrade. | 976f27df-5486-4d6a-8afd-b46f95453e70 | GILL, Ushma | Ushma.GILL@EDUCATION.GOV.UK |  | 2026-01-20 15:37
105 | 76 | SB programme has been delayed. Still on track to deliver on DfE tech requirements. Due to the delay, commercial activity will commence FY26/27. | 976f27df-5486-4d6a-8afd-b46f95453e70 | GILL, Ushma | Ushma.GILL@EDUCATION.GOV.UK |  | 2026-01-20 15:39
106 | 77 | Over the past month, the CMDB programme has made strong progress in maturing DfE’s configuration management foundations. The teams have advanced core discovery activities, confirmed Mid Server access and whitelisting requirements, and begun enabling the Azure Service Graph connector to improve automated population of CMDB data. Early service‑mapping preparation has also moved forward, with access confirmed across dev, test and pre‑prod environments, while the service data model, requirements traceability matrix and initial test cases have been drafted and are now undergoing collaborative review. Technical recommendations from FlyForm are being internally validated to avoid any negative impacts on existing configuration, and the introduction of the new CMDB Manager has strengthened operational leadership and continuity. Next month, the focus will shift to finalising and signing off the validated recommendations, completing the review of the service data model, and commencing the first rounds of service mapping runs in non‑production; this will be supported by continued data‑quality improvement, CSDM alignment activities, and coordinated environment planning to ensure smooth progression toward the Digital Asset milestones. | 73fa79c3-5d67-4a7a-bf30-12fa7da710d2 | RAE, Angus | Angus.RAE@EDUCATION.GOV.UK |  | 2026-01-21 10:33
107 | 78 | No update provided this month |  | Angus.RAE@EDUCATION.GOV.UK | Angus.RAE@EDUCATION.GOV.UK |  | 2026-01-21 10:34
108 | 79 | No update provided this month |  | Angus.RAE@EDUCATION.GOV.UK | Angus.RAE@EDUCATION.GOV.UK |  | 2026-01-21 10:34
109 | 80 | Standards: - IT support standard published on 17 November. - Planned updates for Standards titles and descriptions on gov.uk to better reflect "core standards" in progress. Due to go live 22 January. Plan tech: - Progress tracking, core recommendations and MAT as a school view features were released on 12 November 2025. - Accessibility audit planning underway. - New DfE design deployed for Plan Tech product. - Designs for multi-school management prepared for concept testing with users. - School Readiness Insights discovery team onboarded and working towards a weighting model for measuring schools' readiness to meet the 2030 deadline. | f7abf0c1-9598-41e9-957a-3d7638a74856 | KENNEDY, Carmel | Carmel.KENNEDY@EDUCATION.GOV.UK |  | 2026-01-21 14:10
110 | 81 | No update provided this month |  | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk |  | 2026-01-22 13:49
111 | 82 | No update provided this month |  | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk |  | 2026-01-22 14:16
112 | 83 | Completed introductory sessions with PMO contacts across DDT divisions. Work is ongoing with divisions to ensure delivery pipeline accurately reflects work going on in Divisions. This will be ratified with DDs in coming weeks. Monthly commission was issued on COMPASS in January with drop in sessions offered to support contacts. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2026-01-27 11:19
113 | 84 | This item is being removed from the Customer Experience and Design COMPASS deliverables whilst we focus on reporting against our most strategically important deliverables | 32908ea6-3e40-4e69-9cff-3fa3c6aab41f | RYE, Samantha | Samantha.RYE@EDUCATION.GOV.UK |  | 2026-01-27 12:34
114 | 85 | Delivery of trial tool in progress. Expected to laucn on Monday 2 Feb but work still underway. | faaca2ab-4904-4f18-8228-4a011f6e4faf | CLARK, Louise | Louise.CLARK@EDUCATION.GOV.UK |  | 2026-01-28 12:37
115 | 86 | NHL on track to be transitioned to Arvato on 17 February 2026. Train the trainer began on 23 January 2026. Breakfast Club is due to be transitioned on the 15 April. CCN hasn’t been signed off yet but is due to be signed by the 30 January 2026. There was due to be a soft launch in February, however this is now not happening. We are still waiting for clarification who will take on the quarterly PLR report. We have extended this decision until the end of February 2026. | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  | 2026-01-28 13:27
116 | 87 | Work is currently on hold whilst we await decision on future of DDT divisional set up and new director. | 3189190b-a1ce-45e5-8a4f-3610efa00201 | BALNAVES, Stuart | Stuart.BALNAVES@EDUCATION.GOV.UK |  | 2026-01-28 14:20
117 | 88 | Progress against PI objectives 1 BAU - on track 2 Complete Adult onboarding- ASF PMP updates completed in CFS for the first time. Some work to support the second ALL PMP update left to complete in February. 3 Refinements for Adults funding in 26/27- Ran simulation for ALL 26/27 with financial year funding lines to make the model simpler and more flexible to work with. And are currently testing with FCS. 4 Fix the big batch release problem - Completed analysis of problem, successfully reproduced issue in lower CFS environment and are working on the POC for the solution to apply. 5 Continue the CFS containers transition from Cosmos to SQL - Completed implementation for data aggregations and calculations containers and completed first round of testing with bugs identified to fix before retesting. Completed the design for the calculation results container and starting SQL schema implementation. 6 Update the CFS UI for the refined user permissions journey- Completed most of the UI updates from the design. 7 Support tenancy project towards migrating CFS - Still working through bugs with the new CFS dev environment blocking starting with the new test environment. Successfully integration tested the existing CFS dev and test environments with the migrated FDS dev and test environments. 8 Support comms funding project - Supplied data for scalability investigation for Comms funding to test the solution with data for other streams. And support given for investigation into including calculations on statements. 9 Support the Data journey project - No work required from CFS on this project yet. 10 Tech debt: Working through the unit test cases for the ServiceBus package upgrade to use ServiceBusReceivedMessage on local environment before merging code into dev environment. Potential incoming need to be able to alter profile patterns for many providers has been analysed and a simple design has been created. The need has dissipated but the design is ready to pick up if the need arises again. | 53e52a08-4639-44ad-b2b3-2811de877217 | SPARKS, Robert | Robert.SPARKS@EDUCATION.GOV.UK |  | 2026-01-28 16:22
120 | 89 | Complaints Board went ahead on the 15 January 2026, and the main agenda was to discuss next steps on the new whistleblowing (WB) process. Main actions from the meeting were for individual meetings with the teams to discuss their IT systems and interactions. Feedback on the second draft of the new WB process. An IT evaluation form has also been sent to the teams to complete and return. Deadline for the feedback and return of the form is 30 January. Once the team receive the feedback, we will compile the information as an options paper and include feedback from the individual meetings. The Board approved options paper, including an agreed preference, will be sent to IT colleagues by the end of February 2026 to enable them to make an informed decision on the best way forward. | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  | 2026-01-29 09:00
122 | 90 | Consistent progress with large numbers of new joiners coming in January, February and March 2026. Data Architects have now been assessed and allowances will begin in February. Business case for Test Engineering is in the later stages with this expected to be the next profession to go live. Strong outcomes from the first round of Software Developer recruitment with 14 new joiners. Current net savings (committed only) are £1.75m in 25-26 and £4.99m in 26-27. | aba43bb4-6f1f-401b-959d-d4ecf70bf792 | WILSON, Catherine | Catherine.WILSON@EDUCATION.GOV.UK |  | 2026-01-29 14:44
124 | 91 | Consistent progress with large numbers of new joiners coming in January, February and March 2026. Data Architects have now been assessed and allowances will begin in February. Business case for Test Engineering is in the later stages with this expected to be the next profession to go live. Strong outcomes from the first round of Software Developer recruitment with 14 new joiners. Current net savings (committed only) are £1.75m in 25-26 and £4.99m in 26-27. | 32908ea6-3e40-4e69-9cff-3fa3c6aab41f | RYE, Samantha | Samantha.RYE@EDUCATION.GOV.UK |  | 2026-01-29 14:48
125 | 92 | No update provided this month |  | Catherine.WILSON@EDUCATION.GOV.UK | Catherine.WILSON@EDUCATION.GOV.UK |  | 2026-01-29 14:58
126 | 93 | Some final policy questions to be confirmed but confidence in MVS delivery for April is higher. | 067d5616-2c4b-4293-a08c-baa238a938bc | DUNSTALL, Rose | Rose.DUNSTALL@EDUCATION.GOV.UK |  | 2026-01-29 15:07
127 | 94 | Currently on track, a few areas still to clarify but confidence is high | 067d5616-2c4b-4293-a08c-baa238a938bc | DUNSTALL, Rose | Rose.DUNSTALL@EDUCATION.GOV.UK |  | 2026-01-29 15:08
128 | 95 | Delay in go live - delivery date pushed back to April 2026. | 067d5616-2c4b-4293-a08c-baa238a938bc | DUNSTALL, Rose | Rose.DUNSTALL@EDUCATION.GOV.UK |  | 2026-01-29 15:12
129 | 96 | No update provided this month |  | Rose.DUNSTALL@EDUCATION.GOV.UK | Rose.DUNSTALL@EDUCATION.GOV.UK |  | 2026-01-29 15:14
130 | 97 | No update provided this month |  | Rose.DUNSTALL@EDUCATION.GOV.UK | Rose.DUNSTALL@EDUCATION.GOV.UK |  | 2026-01-29 15:14
131 | 98 | This is now in Private Beta, readying or a cross government service assessment on 10 February and to transition over to National Careers Service | ae9d166e-7a5b-44a2-acfa-ee02c3c2ea24 | OSBORNE, Kuldip | Kuldip.OSBORNE@EDUCATION.GOV.UK |  | 2026-01-29 16:07
132 | 99 | MVP campaign site is live ahead of the campaign which has been delayed. Team continue to test and iterate the page and are looking at 3 options for approval after April | ae9d166e-7a5b-44a2-acfa-ee02c3c2ea24 | OSBORNE, Kuldip | Kuldip.OSBORNE@EDUCATION.GOV.UK |  | 2026-01-29 16:26
133 | 100 | UR completed with designated cohorts in both England and Northern Ireland. Analysis and school twinning pilot recommendations now to complete and handover over to the Devolved Union team and EPIC for pilot running | ae9d166e-7a5b-44a2-acfa-ee02c3c2ea24 | OSBORNE, Kuldip | Kuldip.OSBORNE@EDUCATION.GOV.UK |  | 2026-01-29 16:32
134 | 101 | • Project is Green as project is on-track • Data lookups continue to be developed • UKRLP Applicant journey worked out • UKRLP Admin journey started • Initial infrastructure built • Data fields agreed & created for UKRLP application • Data fields in progress for UKRLP administration • 'To be' processes mapped out with automations and rationalisations • UR in progress on URKLP Report/Search/API users • UR planned for PIMS Report/Search/API users • DPIA screening complete • Operational Readiness Reviews in flow • Arranging contractual Exit/TUPE discussions • Discovery for DSI and PP pointing to UKRLP as opposed to PIMS to allow authentication route for UKRLP users • Liaison through Hal & Pete to agree live infrastructure - going to AKS, investigate dynamic API lookup vs. stored lookups on the data sets Agree cost forecast vs. funding (through LRS modernisation split budgets) for UKPIMS | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-01-30 08:42
135 | 102 | R06 for 25/26 opened on time Over 99% of files process successfully at first attempt failures are re-submitted either by the provider or SLD team | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-01-30 08:44
136 | 103 | Resource pressure for projects, single point of failure, and staff turnover | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-01-30 08:45
137 | 104 | Our next show and tell is planned for 30 January 2026. We received ministerial approval for the national pilot on 24th December and the official announcement was on 8th January. We have written out to secondary schools, FE Colleges and Sixth Form Colleges to invite them to participate in the pilot, and we have held 6 webinars to provide additional information, support and guidance. We have been working with sector bodies (AoC, ASCL, NAEO) and combined authorities (GMCA) who are promoting the pilot alongside our DfE Comms. Our user researchers attended the BETT show to conduct in person user research and our designers have been working on changes identified from our accessbility user research as well as updates to our guidance website to include our promotional video and posters. We are in the final stages of testing our integration with the attendance data. | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-01-30 08:46
138 | 105 | Our next show and tell is planned for 30 January 2026. We went live on 21st January for non-funded apprenticeship provision. Emails were sent to LET providers who are in scope, we had a post on DfE Communities and we had an article in DfE Update to promote this. We updated our guidance on gov.uk to include non-funded provision and to make some small updates based on user feedback and helpdesk queries. We have completed a second round of user research on migration and are now finalising the design work in readiness for user stories being written. We have also completed a round of user research on the ELD help pages, this has identified a preferred prototype to take forward but there are some design updates needed. We completed the development work for the changes to the HE data collection requirements, and we are now working on Study Programmes and some updates based on user feedback (e.g. changes to the export screen, breaks in learning for individual aims) The design and business analysis work has started for the ILR changes for 26/27 | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-01-30 08:47
139 | 106 | Green - all projects adequately resourced and running to time, although BA capacity is stretched. This month we have; Undertaken some housekeeping on our Risk Protection Arrangements (RPA) weekly data refresh process to improve efficiency and RPA annual refresh development work has started. College Financial Data Collections - Governing body dashboard is being developed. Submit Financial Data remains in Private Beta with a possible 16 providers undertaking the next tranche. New User Researcher onboarded to work on that. Childen's Social Care Financial Oversight Team - some dependencies and blockers - project is rated Amber Green - but all are being worked though with the Product Owner. FE REclassification FR Discovery completed to schedule in January. | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-01-30 08:51
140 | 107 | The teams are all fully committed at present with the various work streams we have live at the moment and there is no capacity to increase our ability to deliver other work. we are currently working through a prioritisation process to focus resource | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-01-30 08:52
141 | 108 | The team keeps producing, maintaining, and enhancing an insight and reporting suite built primarily using Databricks, Power BI and Microsoft CoPilot. The action-able service insights and management information (MI) are shared with the stakeholders to not only monitor performance of services against agreed SLAs/KPIs but also identify areas of improvements. Some of the highlights for this month are given below: • The team has made good progress to further automate our data management processes using APIs to achieve our objective of end-to-end automation. • We have managed to automate data flows from CXOne platform to Databricks to Power BI using APIs for Data Operations team's telephony data along with National Helpline's ticketing data. • We are currently working to automate data flows for National Helpline's (NHL) telephony data too so that we can keep tracking NHL calls in future even when this helpline has moved to our external resourcing partner Arvatro. • We have been collaborating with Data Science colleagues to automate some of our processes using AI. • We have successfully developed an AI call summary tool with the help of our Data Science colleagues that is now deployed to get call summaries for National Helpline and Data Operations’ telephony data from CXOne. • We have now discussed and agreed some more requirements with Data Science. The new requirements are specific to use of AI to automate our Enquiry Queue Management (QM) process; automate producing enquiry summaries and themes and automate enquiry responses where appropriate for certain enquiry types. • We are currently in discussion with relevant stakeholders to agree timelines and resolve an issue that is preventing our Data Science colleagues from accessing Dynamics CRM data through a direct API connection. • The team shared with the senior leadership monthly high-level dashboard containing performance summary for various in-house services that we manage within the division. • The team received some positive and encouraging feedback from the senior leadership team. We are currently working towards enhancing the dashboard based on the feedback. • The next iteration, that we will send out in early February 2026 containing January 2026 data, would contain some new additions and enhancements. • The team has agreed a change freeze during the last week of every month. This will allow the team to publish and share the dashboard on the first working day of next month with the stakeholders. • Any feedback received during a month will be reviewed and prioritised accordingly. • The team is engaged with relevant stakeholders to put necessary actions in place to ensure MI is created and provided to track any enquiries or calls received around ‘Education Record’ service/app. • This will help our enquiries and telephony teams to plan and allocate resource as appropriate based on data/MI. • The team is also working to create a MI reporting solution containing Complaints data for our regional colleagues. • The new solution will allow our customers to self-serve their data needs and save us from manually producing and sharing data regularly. | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  | 2026-01-30 08:54
142 | 109 | The collection closed on 9 Jan and the data has been transferred to MI teams | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-01-30 09:21
143 | 110 | Education Estates (Capital) Work has progressed significantly to migrate the 37 individual Education estates teams to the customer help portal and PCRM. Workshops are now underway to capture requirements, with significant resource being pooled for the next phase, which is to deliver workshops with the aim of training the Education Estates teams. This initiative is a key part of our ongoing efforts to consolidate services and streamline communication channels. By centralising these interactions within the portal, we aim to significantly improve operational efficiency, reduce duplication, and provide a more consistent and transparent experience for both internal teams and external users. Progress has started on completing the portal pages within development and we expect the full dev work to take around 55 days, before user testing can commence. Davina Chatbot The Proof of concept AI powered chatbot concept has now passed the first stage of testing. The next stage is to deploy to the production PCRM environment, which will allow us to conduct user testing on a wider level whilst maintaining information security. Knowledge hubs are being utilised and reviewed to continue expand the capabilities of the chatbot. Development has enabled direct integration with CRM systems, allowing a seamless user experience, both externally and internally. This has potential to reduce customer interactions within the department significantly. AI in Dynamics 365 AI within Dynamics 365 is progressing as expected and early testing shows promise for natural language processing to assist agents by surfacing relevant information, recommending next steps and providing templates/prepopulating case details. With the seamless integration between our external AI (Davina) and internal dynamics 365 AI, we can build a system with out of the box functionality, enabling agents to be able to confidently integrate it in their day to day work. This work has been given the go ahead, however the Davina chatbot will be priority for our specialised AI developer. Bespoke Journeys Portal 2.0 has been designated its own project status and is now coming to the end of the discovery phase, following recent workshops to determine the scope and timescales of the project. A project hub is being created with interactive features to enable smooth progression of the project. Stakeholder analysis is ongoing and will help define the parameters of the project. By designing with personalisation at the core, we’re aiming to deliver a more efficient and intuitive experience that reflects the diversity of our users and the services they interact with. The prototype is already demonstrating how targeted design can simplify navigation and enhance customer satisfaction. This work is due to progress and has been assigned to be completed alongside the EE work. | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  | 2026-01-30 10:59
144 | 111 | Risk review sessions underway, expected to complete last session 1st week of February. Next steps to complete gap analysis and present to Board. | ef58175c-38bb-4aa4-b081-c5f0e49b2e10 | PATEL, Prina | Prina.PATEL@EDUCATION.GOV.UK |  | 2026-01-30 13:31
145 | 112 | Risk review sessions underway, expected to complete last session 1st week of February. Next steps to complete gap analysis and present to Board. | ef58175c-38bb-4aa4-b081-c5f0e49b2e10 | PATEL, Prina | Prina.PATEL@EDUCATION.GOV.UK |  | 2026-01-30 13:32
146 | 113 | No update provided this month |  | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk |  | 2026-01-30 18:05
147 | 114 | FCS PI 14 objectives (17/12/25 to 17/03/26) • Revision of Ofsted changes to EDSK and ASF Contracts - Completed • Apprenticeship Agreement variations for 24/25 - Completed • Contract improvements POC – Removal of T&C and all schedules from contracts of specific funding streams: Completed • Adult Loans (EDSK Loans) changes for 26/27 – testing with CFS - In progress • .NET 4.8 to Ver 6.0 migration – In progress • FCS Single tenancy migration – in progress | 97b26ecf-01d6-4641-b70e-6558c3c45646 | THIPPESWAMY, Ravi | Ravi.THIPPESWAMY@EDUCATION.GOV.UK |  | 2026-02-02 07:51
148 | 114 | As per objectives set for PI 14, the key BAU deliverables related to Ofsted changes, Apprenticeship Agreement variations, Contract improvement POC have been completed. There are other pieces of work such as Adult loans template changes, .NET migration to ver 8.0 and Single Tenancy migration that are currently being worked upon including a major incident related to Apprenticeship API being down. This incident is now resolved, awaiting it to be closed as of Feb 2nd. | 97b26ecf-01d6-4641-b70e-6558c3c45646 | THIPPESWAMY, Ravi | Ravi.THIPPESWAMY@EDUCATION.GOV.UK |  | 2026-02-02 07:54
149 | 115 | We know the current digital product does not meet users needs. By shifting effort to ensuring the product is scalable, future‑proof design and architecture, we expect smoother delivery and the ability to move at greater scale. | 847721d6-8a9e-4a7a-8170-76096b429a8d | BRIGGS, Shelley | Shelley.BRIGGS@EDUCATION.GOV.UK |  | 2026-02-02 08:06
150 | 116 | This is a duplicate entry | 847721d6-8a9e-4a7a-8170-76096b429a8d | BRIGGS, Shelley | Shelley.BRIGGS@EDUCATION.GOV.UK |  | 2026-02-02 08:08
151 | 117 | FCS PI 14 Objectives ( 17/12/25 to 17/03/26) • Changes to payments for funding streams that are now being moved to DWP organisation ( from DfE) - Analysis / changes • POC of Short course onboarding • Procured Non Levy Apps rollover • .NET 4.8 to Ver 6.0 migration – In progress • FCS Single tenancy migration – in progress | 97b26ecf-01d6-4641-b70e-6558c3c45646 | THIPPESWAMY, Ravi | Ravi.THIPPESWAMY@EDUCATION.GOV.UK |  | 2026-02-02 08:08
152 | 75 | As per the update above. Project is still on schedule to complete before the end of Feb 2026. | 976f27df-5486-4d6a-8afd-b46f95453e70 | GILL, Ushma | Ushma.GILL@EDUCATION.GOV.UK |  | 2026-02-02 09:12
153 | 76 | 1. Completed a baselined set of requirements for delivering Phase 1 which are due by May 2026 based on the currently programme timeline. 2. Baselined FY26/27 Business Planning commitments including income - deadline end of Feb 2026. 3. Media Suite (replacement of equipment) - define requirements and establish the route to market - deadline end of Feb 2026 4. Fully scope all SB Tech Provision for the three phases for a fully Managed Service - deadline end of Feb 2026. 5. Establish commercial routes to market - deadline Feb 2026. 6. Procurement activities commence March 2026 (Provision include, AV, Digital Signage, Room booking, Monitors for hubs, software. 7. Develop the Service Offer including future tooling to inform the Shared Services Agreement (SSA) including R&R's - deadline early April 2026. 8. Establish the SSA including Data Sharing Agreement. | 976f27df-5486-4d6a-8afd-b46f95453e70 | GILL, Ushma | Ushma.GILL@EDUCATION.GOV.UK |  | 2026-02-02 09:25
154 | 118 | Work on the calculation and result components continues to progress well. We are looking to migrate to the UK South form West Europe this month. | e83f7a5b-59b4-4ac0-bf4a-a87587a40d7d | YOUNG, Joe | Joe.YOUNG@EDUCATION.GOV.UK |  | 2026-02-02 11:48
155 | 119 | Programme remains on track to deliver the Proof of Concept in March, with strong progress continuing. While March remains our target, any adjustment would likely be a short slip into April if required for insights generation and playback. Key progress has been made: - Initial work has begun on the DfE Business Case for 2026 - DSIT engagement with positive feedback on BC submitted in Dec. - Internal engagement with RISE teams including RISE lead, Attainment National Programme, - Positive follow up with Sapientia, ARK and Lift MATs that are part of pilot. | 99e5d621-5a73-4f0a-bfe5-7f379240f3d8 | COLEY, Lorraine | Lorraine.COLEY@EDUCATION.GOV.UK |  | 2026-02-02 12:49
156 | 120 | WS1 progressing to plan. Key successes include: - Target architecture template and blueprint out for peer review - Solution architecture high-level design documentation start - Solution architecture Data Spine Identity Platform Management high level design for PoC out for review and sign off | 99e5d621-5a73-4f0a-bfe5-7f379240f3d8 | COLEY, Lorraine | Lorraine.COLEY@EDUCATION.GOV.UK |  | 2026-02-02 12:50
157 | 121 | WS2 continues to move forward, though a cautious status is recommended due to dependencies on the MIS suppliers and the need for close monitoring over the coming weeks. Key successes include: - MIS notice of engagement published and 3 responses received - DPIA progressing will with WONDE out for legal review and MIS with DPO - Infrastructure build completed | 99e5d621-5a73-4f0a-bfe5-7f379240f3d8 | COLEY, Lorraine | Lorraine.COLEY@EDUCATION.GOV.UK |  | 2026-02-02 12:51
158 | 122 | WS3 is progressing however continues to face challenges with EdTech Engagement. Progress has been made as follows - A revised approach agreed on how to approach EdTech supplies who have already engaged with Policy with invitations sent out. Three responses already received. - DPIA documentation in draft - Feasibility study underway with regards to engaging EdTech suppliers through MATs | 99e5d621-5a73-4f0a-bfe5-7f379240f3d8 | COLEY, Lorraine | Lorraine.COLEY@EDUCATION.GOV.UK |  | 2026-02-02 12:52
159 | 123 | We have a team in place maintaining the GHBS digital service and conducting small iterative improvements. We are planning for the programme of work to begin in April. | d55d48a3-565f-4109-a5f6-63a8fbe9cb59 | BEAK, Kristi | Kristi.BEAK@EDUCATION.GOV.UK |  | 2026-02-02 13:55
160 | 124 | The qualitative L&D needs survey is now complete and the final report has been presented to the skills and expertise team. Planning for the profession time and profession leadership agenda item at March's SLB is well underway. Ongoing discussions with DWP to understand more about different branches of their work in the skills and expertise space. Seeking ongoing feedback on the SCS training proposal, including from DDT Directors. | 32908ea6-3e40-4e69-9cff-3fa3c6aab41f | RYE, Samantha | Samantha.RYE@EDUCATION.GOV.UK |  | 2026-02-02 14:47
161 | 125 | Work on the calculation and result components continues to progress well. We are looking to migrate to the UK South form West Europe this month. | e83f7a5b-59b4-4ac0-bf4a-a87587a40d7d | YOUNG, Joe | Joe.YOUNG@EDUCATION.GOV.UK |  | 2026-02-02 15:26
162 | 126 | We have a go/no go meeting on 19th Feb with stakeholders to decide whether or not to proceed into the cutover to Databricks. Expecting that to go well based on where we are today. | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  | 2026-02-02 16:23
163 | 127 | 30/01 - Design documentation amended following work on pre-prod/prod environments. Team prepared for a session with partners on 2nd Feb. Continued engagement with wider teams on potential future scope of work. c | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-02-02 16:42
164 | 128 | Due to tight delivery timescale and RBAC design slightly delayed due to a decision required on phase 2 and unplanned emergency team leave. Production infrastructure to be built. Can pick this up now as a decision on phase 2 approach has been made to continue to develop the calculation engine in Databricks. | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  | 2026-02-02 16:47
165 | 129 | No update provided this month |  | Daniel.KUMAR@EDUCATION.GOV.UK | Daniel.KUMAR@EDUCATION.GOV.UK |  | 2026-02-02 16:54
166 | 130 | No update provided this month |  | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk |  | 2026-02-02 17:00
167 | 131 | No update provided this month |  | Daniel.KUMAR@EDUCATION.GOV.UK | Daniel.KUMAR@EDUCATION.GOV.UK |  | 2026-02-02 17:02
168 | 132 | 30/01 - Continuing to work with the wider programme to define approach and implement standardised processes, outputs, and comms. Desk research has been complete and project is awaiting resource. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-02-02 17:03
169 | 133 | No update provided this month |  | Daniel.KUMAR@EDUCATION.GOV.UK | Daniel.KUMAR@EDUCATION.GOV.UK |  | 2026-02-02 17:06
170 | 134 | 29/1 - Engaged with project stakeholders and draft PID created. Awaiting BA resource to be assigned. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-02-02 17:08
171 | 135 | Project is progressing to plan and on track | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-02-02 17:10
172 | 136 | No update provided this month |  | Daniel.KUMAR@EDUCATION.GOV.UK | Daniel.KUMAR@EDUCATION.GOV.UK |  | 2026-02-02 17:15
173 | 137 | No update provided this month |  | Daniel.KUMAR@EDUCATION.GOV.UK | Daniel.KUMAR@EDUCATION.GOV.UK |  | 2026-02-02 17:22
174 | 138 | The Attendance team have mainly focused this month around prioritisation planning against our newly agreed 2026 milestones. | 92796edb-6474-493d-a0a1-a61fe83fccca | STRINE, Amanda | Amanda.STRINE@EDUCATION.GOV.UK |  | 2026-02-02 17:32
175 | 139 | Work is progressing at pace as we review and integrate revised process. All known AI projects have been reviewed and prioritised with 11 projects in progress. We are now considering how we can apply the cost/benefit metrics we recently drew together to prioritisations as part of the governance process. Capability review pilots have commenced with STA, FE Oversight and Post-16 Awarding chosen and in progress. AI Steerco has now been replaced with the new productivity forum scheduled to have it's first meeting on 20 February. We are standing up a triage process and reporting dashboard to track AI and automation demand coming through to DDT. Further collaboration with the AI Innovation Unit has yielded some promising actions on how we can continue building a strong collaborative relationship and link up work, for example, with the SCS Awayday | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-02-02 17:39
176 | 139 | We are also currently agreeing the scope on reducing school guidance work. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-02-02 18:44
177 | 140 | Project added this reporting cycle | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-02-02 18:46
178 | 141 | Project added this reporting cycle | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-02-02 18:47
179 | 142 | Project added this reporting cycle | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-02-02 18:48
180 | 143 | Project added this reporting cycle | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-02-02 18:48
181 | 144 | Project added this reporting cycle | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-02-02 18:49
182 | 145 | Project added this reporting cycle | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-02-02 18:50
183 | 146 | Project added this reporting cycle | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-02-02 18:51
184 | 147 | Project added this reporting cycle | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-02-02 18:53
185 | 148 | We have paused this project as a decision has been taken to re-procure a flexible MSP contract to replace the current one when it expires in 01/09/2026 | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-02-02 18:55
186 | 149 | Content Store: Pilot activity concluded in November 2025. Current activity covers: - preparation production environment and work required for launch of Public Beta. This includes: o the completion of a peer review of closed beta (completed on 28/01/2026); o working through completion of the service health check app and operational readiness review; o implementation of actions required by security. - writing of final report on pilot outputs with the intention to publish this - Proof of concept/discovery project into Privacy Preserving Insights due to conclude in March 2026. The contract has been uplifted by a value of £1.5m (bringing total value to £6m) and due to expire on 01/09/2026. Catalyst Fund (known externally as the AI Tools for Education Competition): Three suppliers are all on track. Of the other two, Kita have faced delays project delays, but we are assured that this will not impact delivery. And stylus delayed their first milestone, but we are assured that their project is on track overall, with no impact to delivery. AI Big bets work - AI Benchmarking: New work with DSIT launched in October 2025 to assess and evaluate the current pedagogical and safety standards of AI models for developing personalised AI learning tools. Rubric development with teachers started with a small-scale proof of concept in mid-January and is due to finish at the end of February, before a larger-scale project launches in March/April. We will continue to work with DSIT by helping to review the results of the proof of concept and to shape the large-scale rubric development work from the DfE policy side, and we will also help set up procurement routes for the large-scale work. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-02-02 18:59
187 | 150 | An update to the safety expectations was published, addressing emerging harms, including cognitive offloading and emotional dependence. Now renamed as 'standards'. The UK Generative AI for Education Summit took place on 19th January with attendance from perm sec, Minister Bailey and SoS. We are exploring the steps to certification and assurance of education AI safety, in the short term as part of work with i.AI on potential AI tutors and long term via consultation following concessions in the Children's Wellbeing and School Bill. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-02-02 19:02
188 | 151 | We continue to work with the Service owners and the Continuous Assurance team to highlight controls which need addressing inside the foundation systems. There are some controls which sit in one area but the ability to fix the control sits within another. We are working on a mechanism to highlight and track these instances. | ebc20421-40e4-4b9c-96ce-982eacb84002 | PHILLIPS, Mark2 | Mark2.PHILLIPS@EDUCATION.GOV.UK |  | 2026-02-02 19:37
189 | 152 | Second service for Govassure this year selected and engaged in January. Additional resourcing required in order to expedite second service work put in place and work progressing well. | ebc20421-40e4-4b9c-96ce-982eacb84002 | PHILLIPS, Mark2 | Mark2.PHILLIPS@EDUCATION.GOV.UK |  | 2026-02-02 19:50
190 | 153 | Work has continued on iterating the assurance basis, and aligning assurance for services against a common control set which allows all services risk to be able to be centralised, and aggregated effectively. The work has included changing some thresholds for risk as well as aligning the risk management framework to a 5x5 grid which should address an issue where risk was not being raised from the new control set. With the Service Classifications now uploaded into the CMDB, work to rationalise the numbers and level of assurance has begun | ebc20421-40e4-4b9c-96ce-982eacb84002 | PHILLIPS, Mark2 | Mark2.PHILLIPS@EDUCATION.GOV.UK |  | 2026-02-02 19:55
191 | 154 | Minister Smith has agreed FENCSS contract and this is now in place. Contract management and governance is in place and this now becomes business as usual | 03f57944-a573-4abb-b765-28ecc11d00df | SCALE, Angela | Angela.SCALE@EDUCATION.GOV.UK |  | 2026-02-02 21:19
193 | 155 | To ensure the project remains aligned with broader Spending Review commitments, Minister Olivia Bailey has decided to pause the project at the end of the Discovery phase, rather than proceeding to Alpha. While the Department remains fully committed to the Best Start in Life strategy and continues to progress other parent-facing initiatives (such as childcare funding and parental complaints), this specific project can be more effectively paused and potentially revisited at a later date. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-02-03 10:11
194 | 156 | Campaign site is currently running successfully and as intended so far to support the new BSiL campaign between DHSC and DfE. However, the recent steer to pause the wider BSiL digital parenting hub project creates significant uncertainty around the future of the website, its broader digital strategic positioning, resourcing and ability to deliver on commitments outlined in the BSiL strategy. Communications are currently working to define next steps and how this is reported to Cabinet Office and No10 (both of whom have an interest in the project). | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-02-03 10:15
195 | 157 | EY Workforce Register Discovery completed December 2026. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-02-03 10:17
196 | 158 | Alpha assessment passed with 14/14 Greens and delivery milestones achieved. Received approval from policy DD's to proceed into Beta. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-02-03 10:19
197 | 155 | To ensure the project remains aligned with broader Spending Review commitments, Minister Olivia Bailey has decided to pause the project at the end of the Discovery phase, rather than proceeding to Alpha. While the Department remains fully committed to the Best Start in Life strategy and continues to progress other parent-facing initiatives (such as childcare funding and parental complaints), this specific project can be more effectively paused and potentially revisited at a later date. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-02-03 10:22
198 | 159 | Site MVP soft launch complete – working on content additions and technical handover to Families Digital (from CX team). | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-02-03 10:23
199 | 160 | We have gone live with the QA Dashboard Ingested first Live Alpha from Coventry Ingested into Pre-production 3 LAs Alphas (Redcar, Merton (BYO), Coventry) Signed commercials with system C | 92796edb-6474-493d-a0a1-a61fe83fccca | STRINE, Amanda | Amanda.STRINE@EDUCATION.GOV.UK |  | 2026-02-03 12:36
200 | 161 | Small iterations following user research round in November completed. Progressing research and development of new category implementation. | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  | 2026-02-03 13:00
201 | 162 | No update this month, still same concerns/issues. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-02-03 13:15
202 | 163 | Discovery completed in December 2026 (need to remove this from the 'live' projects). | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-02-03 13:17
203 | 164 | HfEYP remains live and stable. Despite a December dip, user figures were still 10% higher than the same month last year. The Amber status continues, reflecting ongoing EYCDT pressures. The policy team is now fully staffed with an SEO and HEO, but new members will need time to get up to speed, so the issue remains for now | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-02-03 13:21
204 | 165 | No change in status, build still going well however issues with third party suppliers may delay delivery. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-02-03 13:23
205 | 166 | DfE site has been soft launched, and the team are on track to meet the timescales for the school's email and Campaign launch | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-02-03 13:25
206 | 167 | Delivery confidence remains positive, with the updated scope now aligned to what Ministers require urgently: improving day‑5 SIN data quality, consolidating early case intelligence, and reducing reliance on labour‑intensive manual reconciliation across CSIN, spreadsheets, emails and calls. This first Alpha phase is exploratory only and will not commit the programme to any particular build or CPA direction until evidence is produced. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-02-03 13:26
207 | 168 | Project was stopped at the end of December (needs removing from live projects) | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-02-03 13:27
208 | 169 | Project was stopped end of December 2025. Needs removing from the live projects. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-02-03 13:29
209 | 170 | Delivery of potential new use cases and redesign of AI hub and service offer have been pushed back as we await decisions on additional funding/resource, and strategy for how use cases across DfE groups are triaged through to AI CoE. Research workshops started with some business areas across DfE to understand pain points and consider where AI may help Records Management proof of concept – user research playback of as-is process for business completed which will be used to design new solution. Ed Chat trial has been delayed due to required changes in architecture to enhance efficiency for AI token use, and challenges with agent integration. New Suppliers onboarded – Solirius and Hippo to transition away from the main incumbent by March 2026. | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-02-03 14:01
210 | 171 | "The project has been assigned a Red RAG status due to a significant delivery risk identified during recent planning recalibration. Following a detailed review of scope, tasks, and dependencies, the team has confirmed that the remaining workload equates to approximately six months of effort, while the current project timeline allows for only three months of delivery time. Updated delivery planning and sequencing work has highlighted that the original estimates and assumptions no longer align with what is required to meet the agreed outcomes. As a result, the project is now operating under a schedule shortfall, with no viable contingency within the current timeframe. This Red status reflects the project’s inability to deliver to scope within the existing plan without intervention, such as a revised scope, or a change to the delivery timeline with supporting budget. Further work is underway to develop mitigation options and present a revised, achievable delivery approach." Discussion taking place to identify and secure funding to extend the timelinw. Outcome has not been confirmed but a high level of confidence it will be available. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-02-03 14:13
211 | 172 | Started modelling business capabilities for Schools group. Provided EA input and alignment between Service Delivery Revolution work and Target Architecture / op model (in SD Rev). Developed the next layer of the EDM conceptual model and supporting narrative, several engagement sessions held. Engaged with Skills England and CapGemini, supporting the DfE to DWP reorganisation/migration project. Worked with commercial to resolve supplier issues on architecture capability contract. Onboarded new perm/contract architects into the community. 300% growth in perm architects (EA/TA) in 18m Workshopped high-level design + approach for a consolidated ‘service manual’, incorporating professional guidance, standards/patterns repo, compliance Delivered data architecture session with Gov Chief Data Architect and team Arranged xGov ‘Architecture Elevator’ training with Gov Chief Architect, scheduled for Feb for 8 DfE architects | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-02-03 14:13
212 | 173 | 3 x D365 G7 Devs roles live 45 Applications. Ifate/Skills England CRM – Dev onboarded and handover in progress, supplier exit Feb 11th. Investco (Caseflow CRM) Completed f2f workshops with the Investment Management team to map out the full business case journey Defined the data model and user access requirements Environments provisioned and project team established Basic portal provisioned for policy team access in development environment Engaged with design and user research communities across the department Provider BAU AI chatbot prototype created and tested, engaged with AI CoE regarding progress/next steps EED user journeys have been the bulk of this month's work, initial requirements built and tested. Further requirements have been requested Independent Schools user journeys have also been built in dev environments but unable to be deployed until EED work has gone to production due to tester capacity and conflicts Other work in progress - Customer insights improvements, SLA updates, Teams appointment sending via CRM Turing Application portal updates completed - deployed to prod, applications now open Assessment portal updates completed – deployed to test | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-02-03 14:29
215 | 174 | In beta testing: (1) Per-workspace feature flags , allows us to opt-in individual workspaces to new features so teams can test new functionality and provide feedback (2) Custom fields - Collect more data from users when they subscribe to your API (3) Webhooks - Send subscription events (create/update/delete) to external systems to allowing tracking/authorisation of API users In alpha testing: API import consolidation – Will allow users to import any kind of API using the same consistent JSON definition file format as the API export feature. API analytics phase 1 (senior managers) - building working prototypes UX for home page + onboarding & service design Migrations and onboarding ongoing | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-02-03 14:47
216 | 175 | Unable to upload drafted standards to Find & Use Standards for approval as parts of the template do not copy over correctly. A call has been arranged to see if this can be resolved. If this can be resolved, we can upload the following standards for approval : Inbound Internet Access, VM Network Access for RDP & SSH, Azure PIP. Depending on the response to the creation of standards process, we can start to socialise across the IE Community and start to move into BAU. | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-02-03 14:56
217 | 176 | CAAS Stage 1 engagements continue. Workshop booked for Work based Skills Directorate Admin – Apprenticeships on 24th February 2026 CAAS Stage 2 is currently on hold whilst there is a change in suppliers, and a reconsideration is being established in terms of the scope of work. Investigated Databricks and agreed to purchase 3-year shared reservation. Continuing investigating App service plans. Agreed a renewal plan for reserved instances expiring in February and March. | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-02-03 15:00
218 | 177 | Began Strategy engagement and comms with DDT SLT, DDT All Staff and communities of practice to ensure awareness. Started developing a plan for single tenancy options to share with stakeholders. | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-02-03 15:06
219 | 178 | Service Status and Capacity GREEN Network availability GREEN Hosting availability GREEN Recruitment and Retention GREEN | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-02-03 16:47
220 | 179 | This has now been removed and will be updated as Developer Secure Operations - DevSecOps 26-28 | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-02-03 16:51
221 | 179 | Metadata & Data Quality - Education Awareness is currently paused. Raqia Begum (service owner) is currently working on Developer Secure Operations Enablement - DevSecOps | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-02-04 11:16
222 | 180 | In phase 6, Oct 25 – Mar 26, we are going to be focusing on:​ Completing migration and parallel running of 80% of analysts​ 90% of legacy modelling areas offline​ Continue to embed Data Governance on ADA​ Build the foundations of “ADA as a live service” – beyond 2026​ Security & Data Recovery "real life" testing to be completed​ Load to Delta Lake first​ The above enables​ Lake being the main analytics platform with data being loaded there first.​ Migration for majority teams will be complete except for a small number of teams with complex use case or that business critical processes planned for phase 7.​ Decommission of legacy platforms (cost savings and simplification of estate)​ Better control and management of our data by enhanced Data Governance | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2026-02-04 13:53
223 | 181 | LEO & PPMD Integration and Development (LPID) – currently delivering agreed staggered approach for PO1 and PO2. Confirming requirements for Phase 2 with CARD. LEO BAU – The team switched off access at DWP to make a start on the dataset B production on the NPD server. Data was transferred to DWP before Christmas. LEO Flag Baking – We have the draft design completed. This will be presented to the 3 organisations early January. LEO Synthetic Data – synthetic data extract now being processed by UK Data Service, should be available for external access in the next few weeks. Disadvantage Funding – Dates for implementation of Pupil Premium and the NFF now highly likely to be 2028/29. Feasibility assessments are nearing completion (Jan for PP & Feb for NFF). We have a high level of confidence in being able to deliver against the requirements but will potentially require changes to digital services already used by schools and LEAs. Discussions are at an early stage. ADA Migration - Steady progress is continuing to be made converting the LEO BAU code. There have been some difficulties with the more complex queries due to functionality differences between SQL and Databricks. E.g. CROSS APPLY not being compatible with Databricks, but overall the conversion is still progressing well. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2026-02-04 13:54
224 | 182 | Delivery of agreed artefacts relating to DFE security obligations. Delivery of agreed supporting artefacts for development teams | 03f57944-a573-4abb-b765-28ecc11d00df | SCALE, Angela | Angela.SCALE@EDUCATION.GOV.UK |  | 2026-02-04 13:56
225 | 183 | We have successfully completed our end-to-end proof of concept, which is now undergoing testing by DSI. Last week, we transitioned from a successful Alpha phase into Beta. As part of this, we spent a day in London with Databricks to validate our approach, review lessons learned from Alpha, and plan for Beta. Since then, we have kicked off our first Beta sprint, which aims to build out the data without transformation dependencies in the DSI Extract API. An additional Business Analyst has joined the team to help recover analysis and scoping work that fell behind at the end of last year. Until this work is back on track, we cannot downgrade the red risk associated with March deliverables, which may remain until March. We are expecting two new data engineers to join the team, but onboarding is taking longer than anticipated. This delay, combined with one of our current engineers nearing the end of their contract, poses a risk to delivering the Beta Phase MVP. If retention is not possible, our capacity and velocity will be reduced, putting delivery at greater risk. We remain hopeful that new resources will be sufficiently skilled to become productive quickly and help bring delivery back on track. User research continues to explore strategies to engage the analyst community, ensuring we understand their ongoing needs as we conduct gap analysis and prepare a roadmap for future capability. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2026-02-04 14:00
226 | 184 | End of Discovery phase Discovery findings playback completed 12th December to inform next steps. Supplier Christmas break (22/12 – 02/01) Next steps - Further User research to expand on user needs and inform design iterations - Continuation of screen designs (Generic pages) - Creation of Azure DevOps backlog with technical requirements and acceptance criteria to be refined and estimated when new supplier development/test team onboard to the project (est Mid Feb) Summary of scope from Discovery/Alpha – Hippo SOW Completion of all generic page designs in FIGMA and signed off 31/03 Azure DevOps tickets ready for new supplier team to refine estimate and plan into Sprints. Approx. 40% will be ready for when the team land. Dependencies Timelines for delivery of the UI for generic screens dependent on Supplier team onboarding and estimations. SOW for Hippo extension post 31/03 In progress | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2026-02-04 14:02
227 | 185 | This is the first update for this project. Team are working towards milestones that are outlined. | 03f57944-a573-4abb-b765-28ecc11d00df | SCALE, Angela | Angela.SCALE@EDUCATION.GOV.UK |  | 2026-02-04 15:33
228 | 186 | private beta launched, stakeholder feedback being reviewed with a view of implementing, also we are in the process of engaging suppliers to do a DAC audit ahead of public beta, and we also have a peer review service assessment scheduled | 03f57944-a573-4abb-b765-28ecc11d00df | SCALE, Angela | Angela.SCALE@EDUCATION.GOV.UK |  | 2026-02-04 15:36
229 | 187 | Analysis of returns and moderation | 03f57944-a573-4abb-b765-28ecc11d00df | SCALE, Angela | Angela.SCALE@EDUCATION.GOV.UK |  | 2026-02-04 15:40
230 | 188 | Workstream only added to COMPASS on 4th February so first monthly update will be provided next month. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2026-02-05 10:08
231 | 189 | Manage Your Education Estate remains on track in private beta (invited users). Feedback from our Beta users has been positive. We are delivering funding lists, funding allocations (SCA/DFC), FE-specific content under 'Resources', and customer support enquiries routing to Customer Help Portal (CHP). Public Beta is planned for 25.02.26 (service open to all RBs), subject to GDS Service Assessment. The MyEE Product and UCD team are now shaping the post-launch roadmap with SIB engagement, so that the service can continue to evolve at pace in alignment with EE strategy.​ Key Milestone - Complete GDS Peer Review (incl. Tech Assessment)​ Due Date - ​​19.01.26​ Status - ​Complete​ Comments​ -​ Delivered as planned. Detailed and constructive feedback received to support Public Beta readiness.​ Actual Date Complete​ - 19.01.26​ Key Milestone - Conduct Accessibility Audit & Update Plan​ Due Date - ​​06.02.26​ Status - ​On Track ​ Comments​ -​ Audit must complete prior to Public Beta to meet service standard point 5. ‘Make sure everyone can use the service’​ Key Milestone - Private Beta Service Assessment​ Due Date - ​​11.02.26​ Status - ​On Track​ Comments​ -​ The MyEE Team actively preparing and responding to Peer Review actions.​ ’​ Key Milestone - MyEE Public Beta Release​ Due Date - 25.02.26​ Status - On Track​ Comments​ -​ New features will be deployed to production and the service made available to all responsible bodies.​ | a23b8aca-1c7f-4ee6-8670-a5a2b8e790cb | RAINE, Paul | Paul.RAINE@EDUCATION.GOV.UK |  | 2026-02-05 12:03
232 | 190 | Dev of the Free School Meals MVP for LAs is progressing well, currently on track for March rollout but resourcing risk does increase the risk slightly This work is a response to an issue where the Children’s Wellbeing & Families bill is delayed – we need this bill to enable us to rollout to Schools Foster families for childcare dev work is ongoing – we intend to pause this however and push resources onto the above MVP to derisk it We’ve added multiple Academy Trusts and new LAs to the Beta since Christmas Further monitoring and iterating based on beta feedback Early Years entitlements Beta is progressing very well, great feedback from participants on the new services We are deferring launch of the Working Families entitlement to post-March in order to derisk FSM, EYPP & 2YO | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-02-05 12:17
233 | 191 | Project currently paused. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2026-02-05 14:51
234 | 192 | Reporting on Breakfast club paused as at the present time it is reported as part of the CRM deliverable. It is envisaged that Breakfast Clubs will be reported on as a standalone works-trand in future. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2026-02-05 15:41
235 | 193 | Progress to date Our BA, Oli has mapped out the “To-be” journey for the service and has divided the entire business case process into 9 stages. Please see here for further details - To Be Process Map - Investment Management - Draft v0.1.pdf. The stages that we are focusing on to the end of March are Stages 1 – 2 which we are coining – through careful consideration with Katie’s team – “Registration” and “Initiation”. Both these stages enable users to register information about them, their policy area and the project/business case in question. It will also ensure that they can submit a case overview, so the I&BM team are able to triage the business cases in advance against things like, value, ministerial priority, risk etc. The user journey flow has now been mapped and some prototype screens have been designed by Katharine. We tested those screens with Katie and her team yesterday and we’re allowing some desk time to comment further. We’re pleased with how this is progressing. Katharine is also engaging an experienced content designer from within DDT who is going to look at these screens and provide feedback there. Katharine is also pulling together a bit of a user research plan on how we can test these screens with policy teams (case authors) and we are working closely with Phil Clayton to speak to lead keyholders on Monday to ask them to engage in some light touch UR work with us so we can gather their perspectives and needs/requirements on those same screens too. Our developers are working hard to build the CRM portal which should be complete fairly soon. Once this is done, this will free up their capacity to start building the registration user journey flow based on the feedback we get from the light touch UR. They’re currently thinking through what the data fields look like so the pre-work has already began here. AI elements We weren’t quite making the progress we had hoped for on the AI elements of this project, so we have hit reset on this and have approached Advania – who we already hold a close working relationship with. We met with them briefly this afternoon to set out our expectations and it was received positively. Giv and Iain are drafting a SoW for them, setting out requirements for this. We are thinking we will need some BA resource from them as well as AI engineer/developer resource. The idea is that the BA resource will review the work done to date from Oli, identifying opportunities for automation and AI and then the engineer/developer will work closely with us to integrate these solutions into the service. | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-02-09 11:32
236 | 194 | Overall programme health is Amber–Green, reflecting strong delivery across the majority of teams and sustained progress against strategic OKRs. Innovation, MSI, and live services continue to perform well, while discovery‑led and data‑dependent initiatives (notably complaints) are progressing as expected. Key risks around capacity and external dependencies are well understood, actively managed, and are not currently impacting delivery of OKRs. Strategic Prioritisation framework moved to Sharepoint and teams, on target to complete by the 6th February. Programme will be planning the Q1 deliverables in line with the priorities under the strategic backlog with a more lean and agile shift. Key Team Highlights MSI team: Delivery remains on track, with research activity supported by the RISE advisor, key API issues resolved, and continued progress on metrics and business benefits mapping. Innovation team: Continued strong momentum on AI initiatives, with clear epic ownership agreed, SLT agreed to continue, and early technical foundations progressing well. CAT team: Tech Ops and data enablement work progressed steadily, including Azure consolidation, supporting of CI work, and preparatory work for Ofsted report changes. Service Support (SS) team: BAU performance remains strong with service stability maintained, major incidents effectively managed, and optimisation and data quality automation delivering measurable benefits. EAT: Discovery activity remains on track, with design work completed, automated testing in place, and technical foundations laid ahead of MVP build activity. LSRP: Work has started and backlog of work created. School complaints: Discovery progressed well with extensive user research completed, early analysis underway, and concepts iterating based on insights from parents, schools and sector bodies Performance Analytics (PA) team: Maintained delivery against OKRs despite reduced capacity, progressing business benefits mapping and embedding the Continuous Improvement Framework. CI team: Strong delivery momentum with 40+ development tickets completed, including accessibility statements, DevOps unblocking, and early progress on Ofsted Report Cards and SEND Reform mapping. Delivery challenges & Mitigations Resource Constraints: Short‑term capacity gaps (notably Service Support and enabling roles) are being mitigated through interim cover, phased onboarding of new joiners, and prioritisation of critical BAU activity. Dependency on External Data & Policy Change: Delivery risks linked to Ofsted data availability and evolving policy are being managed through early technical preparation, mock data usage, and close engagement with policy teams. | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-02-09 15:03
237 | 195 | Product is managed by our Performance analysis & service support team (PASS) It is performing well and there are no concerns. | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-02-09 15:05
238 | 196 | CI: Mohammed continue working well with Chris in the Dev Ops space to help clear blocked tickets faster Started work on the OFSTED Report Cards in FAST Working with Data and EAT to map SEND Reform Completed Accessibility Statement tickets . | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-02-09 15:07
239 | 196 | CAT: Tech OPs Eleventy mapping shared with teams and communities to get pages reviewed by 6th Feb Agreed new structure Data Had a session with PASS re onboarding process for users and datasets. Follow on call this week. Ofsted start to build pipeline new Ofsted report changes based on what we know now Built a new API endpoint | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-02-09 15:09
240 | 197 | FIAT has been handed over to the Continuous Improvement team No further updates. | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-02-09 15:18
241 | 198 | No update provided this month |  | Rhiannon.BARNES@EDUCATION.GOV.UK | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-02-09 15:19
242 | 199 | Tool was replaced by FIAT no further updates. | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-02-09 15:20
243 | 200 | MFSP continues to receive predominantly positive feedback, no further updates. | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-02-09 15:21
244 | 201 | PA: Successfully secured SLT sign-off for EAT, confirming alignment and approval. Good progress on CIF implementation work SS: Completed all planned optimisation work, led by Abi, improving overall performance and efficiency. Effectively managed and resolved a P2 major incident, minimising impact and demonstrating strong team response. | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-02-09 15:24
245 | 202 | CD and IxD played back their outstanding design work Automated test scripts completed Multi-tenant API has been deployed to Dev and Test Interaction and engagement with Policy team Stakeholders have selected an option for the team to progress with. | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-02-09 15:28
246 | 203 | Product is now managed by our Performance analysis & service support team (PASS) | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-02-09 15:30
247 | 204 | There is no meaningful update this month - the Records Mgt team are currently reviewing the outputs of the latest testing (new data set) and developing improved business rules to drive up % accuracy. | be9b390a-94b5-47c2-aa27-c503c315a3d0 | WHARAM, Sue | Sue.WHARAM@education.gov.uk |  | 2026-02-10 13:36
248 | 205 | Monthly update not required for Jan as this project was added to COMPASS after the submission date. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2026-02-10 14:04
249 | 206 | Work newly added to COMPASS. | 84d1af90-3a84-458f-893f-aa533b0571c0 | SADLER, Emily | Emily.SADLER@EDUCATION.GOV.UK |  | 2026-02-13 12:41
250 | 207 | No update provided this month |  | Emily.SADLER@EDUCATION.GOV.UK | Emily.SADLER@EDUCATION.GOV.UK |  | 2026-02-13 16:15
251 | 208 | No update provided this month |  | Emily.SADLER@EDUCATION.GOV.UK | Emily.SADLER@EDUCATION.GOV.UK |  | 2026-02-13 16:25
252 | 209 | No update provided this month |  | Emily.SADLER@EDUCATION.GOV.UK | Emily.SADLER@EDUCATION.GOV.UK |  | 2026-02-13 16:26
253 | 80 | Multi-school management feature initial design concepts have undergone user testing and design iteration is now underway. SRI discovery is progressing well, having identified a weighting model for comparative analysis, they are now validating the model with service data. A formal process for delivering updates to standards is currently being agreed with policy stakeholders, with a view to refreshing core standards by Summer 2026. | f7abf0c1-9598-41e9-957a-3d7638a74856 | KENNEDY, Carmel | Carmel.KENNEDY@EDUCATION.GOV.UK |  | 2026-02-16 12:12
254 | 125 | Calculation and Result components successfully released. | e83f7a5b-59b4-4ac0-bf4a-a87587a40d7d | YOUNG, Joe | Joe.YOUNG@EDUCATION.GOV.UK |  | 2026-02-18 10:27
255 | 210 | Several data releases and change requests were successfully implemented, including MTC Final Data (12 Jan), Absence Provisional (21 Jan), and a broader production deployment at month end (Release 27.9.0). Cost reduction workstream: Work on Azure resources and CosmosDB rationalisation continued, targeting retention improvements, removal of unused containers, and alignment with Schools Digital infrastructure strategy to reduce and optimise BAU costs. Operationally, the team provided ongoing support through mailbox triage, user query resolution (including the post Christmas backlog), and engagement with CRM workflows. The team invested significant time in ITHC planning and aligning and updating governance reporting through service health check and transition planning and preparing handover documentation for service handover to another team within Schools Digital. | 01633895-5ba6-4ac6-be83-0a3c88d4a8c5 | RATTAN, Sabina | Sabina.RATTAN@EDUCATION.GOV.UK |  | 2026-02-19 13:39
256 | 211 | Steady start in Jan across all the GIAP service core areas. Preparation for data downloads across all datasets and feature development work continued smoothly, with enhancements to data validation, and data pipelines. Infrastructure and azure cost optimisation activity continued, including decommissioning of unused resources, Function App restoration, and database autoscaling. Service governance review commenced with ITHC scoping, Service Health check updates, documentation (Wiki), CRM mailbox management, and data publication calendar updates. Data releases progressed well, including timely publishing of the Cutumn census datasets. | 01633895-5ba6-4ac6-be83-0a3c88d4a8c5 | RATTAN, Sabina | Sabina.RATTAN@EDUCATION.GOV.UK |  | 2026-02-19 14:09
257 | 212 | No significant updates for this month | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  | 2026-02-21 09:56
258 | 213 | No update provided this month |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk |  | 2026-02-21 16:37
259 | 214 | No update provided this month |  | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk |  | 2026-02-22 20:58
260 | 215 | First commission on COMASS completed for January 2026. 72.1% of returns were completed with the majority of divisions having a 90-100% return rate, which is a significant return rate for the first commission on a new system. PMO will work with divisions who struggled to submit their returns to allow for a fuller divisional picture of the portfolio. Work continues to iterate the system, identifying and implementing improvements and developing reporting suites to meet user need. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2026-02-23 10:59
261 | 216 | Alpha ongoing - estimated completion date 29 May 2026. We have defined assumption and identified the riskiest ones, started engaging with the commercial team, planned our first two rounds of user research with schools and parents, conducted documentation and standardisation analysis, started modelling our potential market opportunity and started creating an as-is service map. We have also been supporting the mapping of SEND work across DDT. | 337489ad-8849-40b8-8c1d-044502d64f84 | CORDINGLEY, Gaye | Gaye.CORDINGLEY@EDUCATION.GOV.UK |  | 2026-02-23 17:32
262 | 217 | No update provided this month |  | Piers.DUNSTALL@EDUCATION.GOV.UK | Piers.DUNSTALL@EDUCATION.GOV.UK |  | 2026-02-24 08:53
263 | 218 | Key priorities and any work about to start: Status: On Track Sprint 26 - Provider On-boarding, Active Provider Journey deployed to PreProd with smoke and rebression testing being positive - Release 107 on track for Production release 19-Feb, with final reports on performance testing to be had Weds 18th - Provider On-boarding - Inactive journey work is now in developement making good progress alongside release support work - Design prototype MVP on data quality enhancements looking to next steps on any additional requirements, iterations and sign off to progress. Key achievements/outcomes and successes (that we can celebrate, both in DDT and the wider department): No update Any emerging barriers/issues/risks for escalation (and, for portfolio teams, to flag if this has been escalated to respective policy teams): No update | dc63b4e6-7088-459b-86cb-ddfab57b804a | DUNSTALL, Piers | Piers.DUNSTALL@EDUCATION.GOV.UK |  | 2026-02-24 09:14
264 | 219 | Key priorities and any work about to start: Status: On Track Sprint 9 (Start of Alpha) - SOW Alpha has been approved and we have started our kick off sessions this week 9th Feb 2026. - User surveys was sent out on 13th February to YP. We received a good response of 95/100 yesterday. We are hoping to send another set again this week. - We will be using early userzoom insights this week to help with prioritisation from a UCD persepctive Key achievements/outcomes and successes (that we can celebrate, both in DDT and the wider department): No update Any emerging barriers/issues/risks for escalation (and, for portfolio teams, to flag if this has been escalated to respective policy teams): No update | dc63b4e6-7088-459b-86cb-ddfab57b804a | DUNSTALL, Piers | Piers.DUNSTALL@EDUCATION.GOV.UK |  | 2026-02-24 09:38
265 | 220 | No update provided this month |  | Piers.DUNSTALL@EDUCATION.GOV.UK | Piers.DUNSTALL@EDUCATION.GOV.UK |  | 2026-02-24 09:38
266 | 221 | No update provided this month |  | Piers.DUNSTALL@EDUCATION.GOV.UK | Piers.DUNSTALL@EDUCATION.GOV.UK |  | 2026-02-24 09:39
267 | 222 | Key priorities and any work about to start: We are working towards Confirming the Big Query migration completed by Merkle has worked and relinking datasets Update big query forecast for this and the next financial year Small investigations into several older tickets to confirm need and possibilities Work to ingest data from Find a Course and apprenticeship APIs which will be saved in a dataset and used by the FEaT team Key achievements/outcomes and successes (that we can celebrate, both in DDT and the wider department): No update. Any emerging barriers/issues/risks for escalation (and, for portfolio teams, to flag if this has been escalated to respective policy teams): None. | dc63b4e6-7088-459b-86cb-ddfab57b804a | DUNSTALL, Piers | Piers.DUNSTALL@EDUCATION.GOV.UK |  | 2026-02-24 09:40
268 | 223 | Key priorities and any work about to start: Last week we focused on improving reliability of the Course Directory and supporting safe releases across services. We investigated why some courses were not being automatically archived as expected and completed the fix work needed to restore the scheduled clean-up behaviour. We also improved how search data is prepared during deployments by adding the required search index creation into the Course Directory release pipeline, reducing the risk of search issues after releases. Two user-facing defects were resolved: deleting a test venue no longer triggers a generic service error, and publishing changes after switching a course to “blended learning” no longer fails with an error. Alongside this, the team completed preparation, deployment support and performance testing for Release 107 (Find a Course / Course Directory) and Release 106 (DSS GDPR adjustments and service requests) across pre-production and production. We validated the accessibility scanning approach in production and completed additional investigations (including file upload edge cases and course count discrepancies) to feed into follow-on fixes. Finally, we wrapped up the initial analysis work for the .NET 10 upgrade, including installing and trialling the upgrade tooling, and completed testing to support decommissioning work in DSS environments. Key achievements/outcomes and successes (that we can celebrate, both in DDT and the wider department): No update Any emerging barriers/issues/risks for escalation (and, for portfolio teams, to flag if this has been escalated to respective policy teams): No update | dc63b4e6-7088-459b-86cb-ddfab57b804a | DUNSTALL, Piers | Piers.DUNSTALL@EDUCATION.GOV.UK |  | 2026-02-24 09:41
270 | 225 | New process launched for reviewing and updating Help Centre articles. Calendar launched end of January, next steps are to establish groups and data to feed into calendar to better inform CS enquiry teams of upcoming activities. First draft of CS Service Brochure (showcases digital portfolio across CSEO) complete with the final version to be available by end March 2026. | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  | 2026-02-24 11:40
271 | 226 | Data ops re-platforming project has successfully started. Planning for user research is underway with work continuing into March 2026 which will inform service design and build. | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  | 2026-02-24 11:41
272 | 227 | No update provided this month |  | Rose.DUNSTALL@EDUCATION.GOV.UK | Rose.DUNSTALL@EDUCATION.GOV.UK |  | 2026-02-24 11:50
273 | 228 | On track to complete build and go into private beta during April 2026. | 067d5616-2c4b-4293-a08c-baa238a938bc | DUNSTALL, Rose | Rose.DUNSTALL@EDUCATION.GOV.UK |  | 2026-02-24 11:53
274 | 229 | AS will be ready to support the new growth and skills product in April 2026 as planned. | 067d5616-2c4b-4293-a08c-baa238a938bc | DUNSTALL, Rose | Rose.DUNSTALL@EDUCATION.GOV.UK |  | 2026-02-24 11:55
275 | 230 | Budget for extending the FUI project to 30/06/26 is confirmed. The delivery plan is updated, with confidence that the private Beta will launch on time and to scope. The project is now Amber Green. Access to computer vision (field of AI that “see” and understand visual info) remains challenging, but options are being explored with the AI Centre of Excellence and Microsoft. Pilot portfolio workshops are progressing well and positively received. | b6548968-6432-4b31-92a4-1a14b2521b44 | JENKINS, Julie | Julie.JENKINS@EDUCATION.GOV.UK |  | 2026-02-24 12:38
276 | 231 | No update provided this month |  | Rose.DUNSTALL@EDUCATION.GOV.UK | Rose.DUNSTALL@EDUCATION.GOV.UK |  | 2026-02-24 14:13
277 | 232 | No update provided this month |  | Rose.DUNSTALL@EDUCATION.GOV.UK | Rose.DUNSTALL@EDUCATION.GOV.UK |  | 2026-02-24 14:13
278 | 233 | The Attendance team has evolved into a 'squad model' to enable flexibility to pivot and deliver new priorities. Began using the sizing tool for new requests coming in. Working on 1st drop of transition data for secondary schools following national offer day on 2nd March. Continuing to move at pace against our milestones. | 92796edb-6474-493d-a0a1-a61fe83fccca | STRINE, Amanda | Amanda.STRINE@EDUCATION.GOV.UK |  | 2026-02-24 16:42
279 | 234 | Discovery team onboarded 18th February and have started exploring the problem further and discussing goals for the project. Desk research questions have been identified and desk research is starting to narrow the scope of the work further. | 54364aac-c110-4452-817e-340427ac1f35 | CASEY, Sally | Sally.CASEY@EDUCATION.GOV.UK |  | 2026-02-25 10:19
280 | 235 | Transition over to NCS is almost complete. | ae9d166e-7a5b-44a2-acfa-ee02c3c2ea24 | OSBORNE, Kuldip | Kuldip.OSBORNE@EDUCATION.GOV.UK |  | 2026-02-25 13:03
281 | 236 | We have now agreed a similar schools model to use in testing, and have received an extract of this data from Ofsted. We are working with teams within DfE to decide ownership of this data set in the long term and how the service will receive it going forwards. Our content designers continue to work with policy leads responsible for the performance measures to ensure content is correctly displayed. There are two issues currently being worked through – inclusion of attendance data as part of our model vs the ABIE model and the inclusion of EYFS data for the primary school service. If changes are needed to the MVP, then this will need sign off from School Improvement policy leads. We are slightly delayed on the software build. Getting the infrastructure set up correctly with a working database structure and pipeline is taking longer than anticipated. This means we will need to rethink how we roll out the service to users at the end of March – and may need to phase rollout with moderated testing first to check accessibility and then proceed to unmoderated testing in April instead. Trust level view research is underway, with the first set of user research session starting on 2nd February. Analysis and findings will follow next month. | 4f2d5a27-fe15-40e5-8447-c396cfba2a77 | ALIPERTA, Lea | Lea.ALIPERTA@EDUCATION.GOV.UK |  | 2026-02-25 13:25
282 | 237 | The training for National Helpline has been completed and is on track to be transitioned on Monday 2 March. Breakfast Club Change Control Notice has now been signed off and is on track to transition on the 23 March. The team will be picking up the Personal Learning Record quarterly report and investigating if the report can be built in Zendesk. Education Estates Division went live on 25/2/26. | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  | 2026-02-25 14:35
283 | 238 | Feedback has now been received. Next steps will be to send the options paper to Paul Philipson. Paul will then review and work with IT to create wire frames with the recommended system, this can then be presented back to the board. We have a kick off meeting with Paul Philipson on Friday 27 February to discuss timescales. | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  | 2026-02-25 14:36
284 | 239 | The team is collaborating with Data Science to automate processes, including enquiry queue management, summarising themes, and generating responses. We’re resolving an issue affecting API access to Dynamics CRM data. We’re also developing MI reporting for regional and CSEO Complaints teams and conducting data cleansing to improve data quality and refresh times. | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  | 2026-02-25 14:45
285 | 240 | Single view dashboard went live. Ingested live data from Redcar, Merton, and East Riding. Started work on strategic delivery. | 92796edb-6474-493d-a0a1-a61fe83fccca | STRINE, Amanda | Amanda.STRINE@EDUCATION.GOV.UK |  | 2026-02-25 15:08
286 | 241 | The next testing phase is underway, using non sensitive customer enquiries to assess the chatbot’s accuracy and capabilities. Early results are positive, with only minor adjustments needed. After building a full set of test cases, the customer enquiry team will review the chatbot’s responses. Their insights will support the Help Centre Re platforming project, improving page accuracy and relevance while reducing customer contact. | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  | 2026-02-26 09:29
287 | 242 | The Help Centre Re-platforming project is based on requirements identified in Portal 2.0 workshops. This highlighted that the current Help Centre is not fit for purpose when used alongside an adapted portal 2.0. A project hub will be created to facilitate smooth progress. Risks are being identified and stakeholders contacted. Stakeholder requirement gathering is taking place. This work ties in with the data operations Migration project. | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  | 2026-02-26 09:30
292 | 244 | Team have been working with Provider CRM developer to configure Customer Insight Journeys. Demonstration to show CSEO SLT will take place in March 2026 to secure approval. If SLT approve the work following the demonstration, the team will be able to progress with the roll out of the changes. | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  | 2026-02-26 09:40
294 | 245 | An update to the safety expectations was published, addressing emerging harms, including cognitive offloading and emotional dependence. Now renamed as 'standards'. The UK Generative AI for Education Summit took place on 19th January with attendance from perm sec, Minister Bailey and SoS. We are exploring the steps to certification and assurance of education AI safety, in the short term as part of work with i.AI on potential AI tutors and long term via consultation following concessions in the Children's Wellbeing and School Bill. | 0f9f7777-e6eb-4bd9-99af-fa0b883c2a83 | LANGLEY, Georgina | Georgina.LANGLEY@education.gov.uk |  | 2026-02-26 17:12
296 | 246 | Content store: work required to launch public beta currently underway including preparation of production environment, operational readiness review, completion of underpinning documentation and other required assurance activities. Peer review completed on 28/01/2026 and awaiting final recommendations. ITHC scheduled for 23/03. Drafting of final report covering pilot (sept 25 - nov 26) underway - aim to publish by June 26. | 0f9f7777-e6eb-4bd9-99af-fa0b883c2a83 | LANGLEY, Georgina | Georgina.LANGLEY@education.gov.uk |  | 2026-02-26 17:14
297 | 247 | Started understanding the information archictecture and the build for the development environment. Planning to work with CentralOps and SME's on governance, assurance and compliance lifecycle actions; | 02f70415-5d66-4b88-af44-e21d0879808a | JONES, Andy | Andy.JONES@education.gov.uk |  | 2026-02-26 20:13
298 | 248 | Work has progressed to migrate 37 Education Estates teams to customer help portal and PCRM. Workshops to capture requirements are complete and development on bespoke customer solutions is finalised. All journeys are ready for go live utilising an MVP of the phase 1 operating model. Some teams will transition to phase 2 where mailboxes and other CRM’s are closed. Training and User acceptance training is showing positive results and go live on 25/02/26 is complete. This is essential work that consolidates services and streamlines communication channels. Progress on completing portal pages are in development This work is at risk due to funding not being secured by Education Estates, and commercial contracts in place might not have sufficient headroom to meet delivery timescales. Portal 2.0 is close to completing the discovery phase. A project hub is being created with interactive features to enable smooth progression of the project. Stakeholder analysis is ongoing and will help define parameters of the project. By designing with personalisation at the core, we will deliver a more efficient and intuitive experience that reflects the diversity of our users. The prototype is demonstrating how targeted design can simplify navigation and enhance customer satisfaction. | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  | 2026-02-27 10:08
299 | 243 | Work progressing and early testing shows promise for natural language processing to assist agents, surfacing relevant information, recommending next steps and providing templates/prepopulating case details. With seamless integration between our external AI (Davina) and internal dynamics 365 AI, we can build a system with out of the box functionality, enabling agents to be able to confidently integrate it in their day to day work. This work has been given the go ahead, however the Davina chatbot will be priority for our specialised AI developer. | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  | 2026-02-27 10:27
300 | 249 | Overall we are reporting green on LDS this month as all teams are on track for delivery as per key milestones, no key risks or issues have been reported to our Sub Programme Board. | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  | 2026-02-27 13:27
301 | 250 | Go ahead for re-platforming in Databricks given by Corrine Richardson on 19th February. Priority datasets that will be re-platformed first (SC SPRING, ILR, APC) are complete pending final assurance checks. On track for first migration to happen at the end of March. Work to re-platform remaining datasets is proceeding well. | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  | 2026-02-27 13:28
302 | 251 | While the programme continues to make positive progress, several emerging risks have arisen, including lower‑than‑expected EdTech engagement, delays to DPIA and data‑sharing agreement approvals, and a new commercial risk relating to the agreement of supplier Terms & Conditions. These risks are clearly understood, and targeted mitigation activity is underway in partnership with Commercial, Legal, and the Data Protection/sharing team to remove blockers and constraints. Wider engagement for Data Spine is progressing with engagement as follows; Two members of star chamber who are now joining our pilot and want to be part of this process from the beginning, - Ofsted colleagues responsible for the IDSR, National Institute of Teaching - they have done something similar working with Bromcom to bring together Teacher data and School accountability colleagues - looking at enrichment activities as part of new suite of accountability measures. Despite the increased risk profile and the complexities of the programme, overall confidence in delivering the strategic objectives remains high. Current mitigations are progressing as planned, post‑March slippage is now expected, but we do not anticipate to impact the achievement of the key outcomes of the PoC. Overall, the programme remains on a positive trajectory despite the complexies and challenges. . | 99e5d621-5a73-4f0a-bfe5-7f379240f3d8 | COLEY, Lorraine | Lorraine.COLEY@EDUCATION.GOV.UK |  | 2026-02-27 13:38
303 | 252 | Overall delivery confidence remains Amber/Green, with scope progressing as planned and no major risks or issues identified. We continue to be on track for the March deadline, and workstream realignment planning will continued to be monitored. A meeting with leadership and policy will be scheduled to validate and confirm the Vision; however, the date is still to be agreed, which may introduce potential delays. | 99e5d621-5a73-4f0a-bfe5-7f379240f3d8 | COLEY, Lorraine | Lorraine.COLEY@EDUCATION.GOV.UK |  | 2026-02-27 13:40
304 | 253 | The team is facing significant delays because Wonde, despite the DPIA finally being approved, is seeking a variation to the existing DfE agreement and drafting new PoC T&Cs that must be agreed before any live data ingestion can begin. Engagement with MIS suppliers is currently blocked while Commercial colleagues work through what the appropriate commercial route should be. Until blockers are removed, progress on PoC work will remain stalled. | 99e5d621-5a73-4f0a-bfe5-7f379240f3d8 | COLEY, Lorraine | Lorraine.COLEY@EDUCATION.GOV.UK |  | 2026-02-27 13:41
305 | 254 | Team continues to investigate ways to obtain EdTech data by broadening our selection criteria, reaching out to MATs, preparing for an engagement notice, and liaising with DfE project teams working with the EdTech providers. Team have gained access to DfE datasets for matching purposes and started early matching activities and standardisation. Process flows for data ingestion, technical diagrams, data architecture diagram and business flows updated to reflect EdTech data flows. | 99e5d621-5a73-4f0a-bfe5-7f379240f3d8 | COLEY, Lorraine | Lorraine.COLEY@EDUCATION.GOV.UK |  | 2026-02-27 13:42
306 | 255 | Security tracker coverage has now been aligned to the CMDB service definitions, and coverage level of assured services to this can now be measured. The CISRAM sheet calculations to enable better raising of assurance risks into the risk escalation process has had to be reworked as the initial change was still not producing results which would give enough input for the process to function. The idea is that this will be able to be rolled out by Mid March. Low and Medium SAQ rollout has started. Plan is that all services which were reclassified will go through this within the next calendar year to bring their assurance up to date. | ebc20421-40e4-4b9c-96ce-982eacb84002 | PHILLIPS, Mark2 | Mark2.PHILLIPS@EDUCATION.GOV.UK |  | 2026-02-27 14:45
307 | 256 | Both services nominated have been scoped and have undergone completion of CAF self-assessments. Additional resourcing was brought in to meet requirements for second service and bring in line with GovAssure schedule. Stage 4 (Independent Assurance Review) will commence week commencing 2nd March. On track to achieve March end target to deliver final assurance reporting. | ebc20421-40e4-4b9c-96ce-982eacb84002 | PHILLIPS, Mark2 | Mark2.PHILLIPS@EDUCATION.GOV.UK |  | 2026-02-27 14:51
308 | 257 | KS4 and 16–18 final data has now been shared with the teams for feedback. HESA delivery planned for 26/02. Changes from the EYC Summer input specification review have been documented. | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  | 2026-02-27 15:34
309 | 258 | We have received 'Final' data from MDP and are providing feedback with any issues that have been identified. We have been having daily calls throughout this period to communicate updates. So far there has been no major issues that have warranted a re-delivery. | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  | 2026-02-27 15:35
310 | 259 | Currently assuring KS2 Final data following redelivery. Assurance work for move to data bricks in progress | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  | 2026-02-27 15:37
311 | 260 | We have just received the 16-18 final data, and are currently running through process and assurance. Working is also progressing on the College groups reporting (expected to be completed by end of April). Assurance work for move to data bricks in progress. | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  | 2026-02-27 15:38
312 | 261 | Final 16-18 Retention data on track to be uploaded to the CYPMD portal in March (17th). Good progress being made on discussions relating to CI development work required for KS4 June CYPMD exercise. Drafting of April communications in progress. | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  | 2026-02-27 15:40
313 | 262 | MYEE successfully transitioned to Public Beta overnight on 25 February following a positive GDS Service Assessment. All RBs and Settings users can now access the service. During March, the team will focus on iterating on the live service and responding to stakeholder feedback. Enhancements will be implemented to improve key journeys and usability, to address findings from the recent accessibility audit and to strengthen technical resilience. | d46c78e6-9f62-4213-8cc2-489763a4b444 | KING, Kathryn | Kathryn.KING@EDUCATION.GOV.UK |  | 2026-02-27 17:00
314 | 263 | Decision making tool has been finalised and showcased at February Triage meeting. This will support scoping conversations going forward which in turn will lead to more consistent Triage conversations. | c010c450-1cef-4ad2-8ac2-96870b5b3dd8 | WRIGHT, Jo | Jo.WRIGHT@EDUCATION.GOV.UK |  | 2026-03-02 07:39
315 | 111 | Risk reviews sessions completed. Working on analysis and to consolidate the data to present an update for the board. | ef58175c-38bb-4aa4-b081-c5f0e49b2e10 | PATEL, Prina | Prina.PATEL@EDUCATION.GOV.UK |  | 2026-03-02 07:42
316 | 264 | The Records Managements (RM) are in the process of analysing the AI tools output from 4 new datasets RM curated in December. The object was to see how the tool performed using the criteria developed for the previous 'golden' dataset. Results saw a drastic drop (below 20% accuracy for discard), RM analysis is focused on granular and wider patterns in the results set. | be9b390a-94b5-47c2-aa27-c503c315a3d0 | WHARAM, Sue | Sue.WHARAM@education.gov.uk |  | 2026-03-02 08:53
317 | 265 | Some work still required to address ownership and measurement on a minority of controls in the foundation systems space | 03f57944-a573-4abb-b765-28ecc11d00df | SCALE, Angela | Angela.SCALE@EDUCATION.GOV.UK |  | 2026-03-02 08:56
318 | 266 | Delivery of agreed artefacts relating to DFE security obligations. Delivery of agreed supporting artefacts for development teams continues DFE has purchased GitHub Enterprise however GitHub Advanced Security is a must have to enable security to be built into CI/CD pipelines which is fundamental to secure software development. This is being costed for agreement and then implementation during March | 03f57944-a573-4abb-b765-28ecc11d00df | SCALE, Angela | Angela.SCALE@EDUCATION.GOV.UK |  | 2026-03-02 09:08
319 | 267 | All classifications are now updated in Service Now. Service Mgt own the overall framework. This project is now closed. | 976f27df-5486-4d6a-8afd-b46f95453e70 | GILL, Ushma | Ushma.GILL@EDUCATION.GOV.UK |  | 2026-03-02 09:09
320 | 268 | No update provided this month |  | Ushma.GILL@EDUCATION.GOV.UK | Ushma.GILL@EDUCATION.GOV.UK |  | 2026-03-02 09:16
321 | 269 | Work is currently on hold whilst we await decision on future of DDT divisional set up and new director. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2026-03-02 09:16
322 | 270 | Progress against PI objectives (1) BAU - on track with scheduled work (2) Complete Adult onboarding- Complete. Both ASF and ALL PMP updates were run through CFS successfully to produce contract amendments to be run through FCS. (3) Refinements for Adults funding in 26/27- Complete. Simulation successful in CFS but the data could not be ingested in FCS to produce the existing contract format. Therefore change reverted for 26/27. (4) Fix the big batch release problem - Completed development of solution and are currently dev-testing. (5) Continue the CFS containers transition from Cosmos to SQL - Deployed the change for the data aggregations into production. Currently testing and fixing bugs with the calculations container. Currently implementing the solution for the calculation results container. Completed the feasibility and schema design for the profiling container. (6) Update the CFS UI for the refined user permissions journey- Completed the UI updates from the design and currently in testing. (7) Support tenancy project towards migrating CFS - Completed testing and bug fixing with the new CFS dev environment and can now progress to test the new CFS test environment. Successfully integration tested the existing CFS sandbox, preprod and prod environments with the migrated FDS preprod and prod environments. (8) Support comms funding project - No support required from CFS in February. (9) Support the Data journey project - No work required from CFS on this project yet. (10) Tech debt: Completed local testing for the ServiceBus package upgrade to use ServiceBusReceivedMessage on local environment and ready to merge code into dev environment. Also, looking ahead to planning PI 15 by preparing feature candidates | 53e52a08-4639-44ad-b2b3-2811de877217 | SPARKS, Robert | Robert.SPARKS@EDUCATION.GOV.UK |  | 2026-03-02 09:47
324 | 271 | In phase 6, Oct 25 – Mar 26, we are going to be focusing on:​ Completing migration and parallel running for most analyst teams 70% of legacy modelling areas offline​ Continue to embed Data Governance on ADA​ Build the foundations of “ADA as a live service” – beyond 2026​ Security & Data Recovery "real life" testing to be completed​ Load to Delta Lake first​ The above enables​ Lake being the main analytics platform with data being loaded there first.​ Migration for majority teams will be complete except for a small number of teams with complex use case or that business critical processes planned for phase 7.​ Decommission of legacy platforms (cost savings and simplification of estate)​ Better control and management of our data by enhanced Data Governance | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2026-03-02 12:36
325 | 272 | Over the past month we have continued to progress through our Beta sprints, adding further data fields to the DSI Extract API and strengthening our delivery practices. Sprint 6 saw strong momentum with 12 new data fields added, and Sprint 7 made further progress, though the sprint goal was only partially met due to issues identified early in the quality of business rules. These have now been addressed, and an architectural review also surfaced design deviations which the team has planned to correct in the next sprint. Following testing of our PoC delivered in the Alpha phase, DSI have provided us with very positive feedback, giving us early confidence about continued system interoperability through the migration. We are now awaiting their formal results for validation of our Beta MVP scope, i.e. confirmation of the 33 mandatory / minimum set of fields required for the Extract API. Alongside this, our automated test strategy is now defined with a working proof of concept to ensure parity between Databricks and production outputs. Analysis capacity has improved following the addition of a new Business Analyst, but the backlog deficit from late last year continues to leave us with uncertainty and prevents us from downgrading the red risk associated with March deliverables. Engineering capacity also remains a concern: although a new data engineer has joined, delays in onboarding further planned resource and the confirmed departure of an existing engineer continue to impact confidence in velocity across the remaining Beta sprints. Despite these pressures, team capability and ways of working are maturing, and user research continues to develop Analyst‑focused objectives to shape the future roadmap. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2026-03-02 12:38
326 | 273 | LEO & PPMD Programme Planning – We’ve started to draft the 2026-2030 LEO & PPMD programme, with an aim to bring the final version to the May Board for sign off. LEO & PPMD Integration and Development (LPID) – PO1 is delivered, PO2 to be delivered end of the month. Phase 2 planning is going well, initial plans shared with CARD. LEO Flag Baking – Continues to be on track. We’re waiting for the amended data dictionaries from the third-party organisations, and DS team have advised we’ll need a DPIA screening document LEO Synthetic Data – Some unanticipated delays due to UK Data Service feedback regarding minimum metadata requirements. Working with Claire Crawford and co to provide necessary documentation LEO via ONS SRS I2.1 – Data has now been sent to ONS for ingest. We had a very successful workshop with ONS to determine how to speed up data ingest process to make data available faster. Pupil Premium Funding (PPF) – The Policy Lead is leaving the project at short notice with no replacement as yet, this is one of a number of unknowns which are being worked through. LEO RTI – Continues to be on track. Ours and DWPs forms have been drafted and we’re holding a joint workshop with DWP on 6 February 2026 to align final data requirements ahead of submission to HMRC LEO BAU – Good momentum on the December ’25 linking round, which is currently ahead of schedule. Most DWP linking is now complete, and the dataset will be returned to DfE shortly so the cleaning phase can resume. Delivery anticipated for end‑March. PPMD BAU - This has been paused recently due to prioritisation of the LPID project and development of the household linkage table, but we expect to restart the linking round in the coming weeks. Delivery is anticipated around April and will look to incorporate early outputs from the household linkage work ADA Migration – LEO BAU – Work continues on the more complex Databricks queries. Around 80% of the code has now been converted, with completion expected around March. LEO Learners – Steady progress here too, with 5 of 17 scripts converted. These are proving less complex than the BAU set. Completion expected around March. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2026-03-02 12:42
327 | 274 | Collect Modernisation Summary of scope from Discovery/Alpha – Hippo SOW The research and design for generic 'Portal' pages to be completed as planned for the end of the Hippo SOW 31/03. It has been agreed that an internal engineer will join the COLLECT team on a permanent basis in Feb after onboarding (date TBC) but likely to be the end February. Development of the designs has not yet begun due to dependency on resource being allocated to the team but expectation to start in March. Test resource not yet appointed but expected to join the team in this financial year, and then continued into the next financial year (internal conversations still underway). Summary of activity -User research to expand on user needs and inform design iterations (in person Darlington) - Continuation of screen designs (Generic pages) 40% of prioritised page designs created and signed off. - Creation of Azure DevOps backlog with technical requirements and acceptance criteria to be refined and estimated when new supplier development/test team when onboarded. Dependencies Timelines for delivery of the UI for generic screens dependent on Supplier team onboarding and estimations. Serious Incident Data Development Team – CSINS Data and Reporting: Alpha RAG is amber-green. The project has just started, and we have made good progress, but we need to gather more information on the scope and problem area before determining likely outcomes of the Alpha project. The project started on Tuesday with the team now moving their focus to the CSINS Form and Ministerial Reporting process in the CSIRT Team. We need to rapidly learn more about the Reporting process in the CSIRT team as this has not been investigated before. We have met with Laura Bailey, who leads the CSIRT team, to have a short teach-in on the process. We are continuing these discussions next week when we will start to investigate the more detail processes and data being used in this report. We had an inception session on Wednesday to review the project scope/deliverables. We have shared the outcome of this meeting with DDT and the Child Safeguarding Deputy Director for views. Deliverables/scope may change depending on the outcome of continuing conversations with the CSIRT team. Additionally, the Dot Net team have refined several tickets covering minor improvements to the existing CSIN form that will be moved into the next sprint to action. | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2026-03-02 12:46
328 | 275 | We conducted a research round with Early Year mainstream settings (private nurseries - big & small, pre-school nursery). We also started conducting a research round with Post-16 settings (colleges) parallelly. Along with the user research, we wrapped our desk research to understand tech and data landscape in both Early Years and Post-16 settings. | 0b3ddd1b-cbab-49b0-ab3f-1cf4f757191a | JINARAL, Tejas | Tejas.JINARAL@EDUCATION.GOV.UK |  | 2026-03-02 13:18
329 | 276 | Peer review service assessment completed, positive feedback given. Suggested improvements noted and planned in as appropriate. DAC audit is underway. Final sprints ahead of Go/No planned for later in March addressing key feedback from private BETA. | 53b409ec-10a3-4b05-ad6d-d7ff8d9946f1 | DUNNE, Alison | Alison.Dunne@EDUCATION.GOV.UK |  | 2026-03-02 13:45
331 | 277 | We’re working with Data Science to automate key processes using AI. An AI call summary tool is now live for the National Helpline and Data Operations. We’ve agreed next steps to use AI for Enquiry Queue Management, generating enquiry themes, and creating responses. We’re also addressing a CRM API access issue and exploring alternative ways to obtain backend data. | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  | 2026-03-02 13:52
332 | 278 | Key Team Highlights MSI team: Delivery remains on track, with research activity supported by the RISE advisor, key API issues resolved, and continued progress on metrics and business benefits mapping. Innovation team: Continued strong momentum on AI initiatives, with clear epic ownership agreed, SLT agreed to continue, and early technical foundations progressing well. CAT team: Tech Ops and data enablement work progressed steadily, including Azure consolidation, supporting of CI work, and preparatory work for Ofsted report changes. Service Support (SS) team: BAU performance remains strong with service stability maintained, major incidents effectively managed, and optimisation and data quality automation delivering measurable benefits. EAT: Discovery activity remains on track, with design work completed, automated testing in place, and technical foundations laid ahead of MVP build activity. LSRP: Work has started and backlog of work created. School complaints: Discovery progressed well with extensive user research completed, early analysis underway, and concepts iterating based on insights from parents, schools and sector bodies Performance Analytics (PA) team: Maintained delivery against OKRs despite reduced capacity, progressing business benefits mapping and embedding the Continuous Improvement Framework. CI team: Strong delivery momentum with 40+ development tickets completed, including accessibility statements, DevOps unblocking, and early progress on Ofsted Report Cards and SEND Reform mapping. Delivery challenges & Mitigations Resource Constraints: Short‑term capacity gaps (notably Service Support and enabling roles) are being mitigated through interim cover, phased onboarding of new joiners, and prioritisation of critical BAU activity. Dependency on External Data & Policy Change: Delivery risks linked to Ofsted data availability and evolving policy are being managed through early technical preparation, mock data usage, and close engagement with policy teams. | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-03-02 14:19
333 | 279 | Tendering Process has begun. Quotes received and will be reviewed in the next week. | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  | 2026-03-02 14:27
334 | 280 | New instance of CXone went live in January 2026, discovery sessions held with new supplier. Follow up workshops to be arranged. | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  | 2026-03-02 14:29
335 | 281 | Tech OPs Eleventy – POC in progress to look at whether APIs can move content and what a front end would look like Amended Power BI reports to new Ofsted report card format Supported set up of PENTEST to be completed end March Supported MSI with memory database for Cypress Supported EAT setting up Test/Prod environments Analysed data from first Survey to devs for AI increase of awareness and shared recommendations Data Built form for the Onboarding process Built EATs data requirements for reporting Set up DAU RISE more frequent transfer | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-03-02 14:31
336 | 282 | National Helpline moved successfully and has gone live on 2nd March 2026. We are currently working towards go live for Free Breakfast Clubs on 23rd March 2026. Work continues to remove the LRS tier 2 backlog for completion before end of March 2026 and this is on track. | b72dad8f-5fe7-4823-af91-f73e849cdff6 | TAVERNER, Helen | Helen.TAVERNER@EDUCATION.GOV.UK |  | 2026-03-02 14:31
337 | 281 | CI: VCC Engagement Monitoring and Design Update Completed SEND Risk Framework Mapping 50% Ofsted Tickets completed Text Editors/ DDM Decision made and can move forward Accessibility tickets | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-03-02 14:33
338 | 91 | Consistent progress with large numbers of new joiners coming in January, February and March 2026. Data Architects have now been assessed and allowances begun. Business case for Test Engineering is in the later stages with this expected to be the next profession to go live. Strong outcomes from the first round of Software Developer recruitment. Current net savings (committed only) are £1.75m in 25-26 and over £5m in 26-27. | aba43bb4-6f1f-401b-959d-d4ecf70bf792 | WILSON, Catherine | Catherine.WILSON@EDUCATION.GOV.UK |  | 2026-03-02 14:38
339 | 283 | Good progress on the skills and expertise objective this month. Planning for the L&D and profession time/leadership agenda item at March's SLB continues. CDTO has approved the outline of the SCS training day. Planning for that continues. First event is scheduled to run in May 26. DDT demystification project is also now underway - case studies to showcase DDT collaboration and value added are being drafted. | 32908ea6-3e40-4e69-9cff-3fa3c6aab41f | RYE, Samantha | Samantha.RYE@EDUCATION.GOV.UK |  | 2026-03-02 14:40
340 | 284 | Completed service design iteration Continued build activities Finalised multitenancy API work PM created a final product plan and shared with the Team Continued user research with LA's | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-03-02 14:47
341 | 285 | No update provided this month |  | Rhiannon.BARNES@EDUCATION.GOV.UK | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-03-02 14:48
342 | 286 | No update provided this month |  | Rhiannon.BARNES@EDUCATION.GOV.UK | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-03-02 14:49
343 | 287 | No update provided this month |  | Rhiannon.BARNES@EDUCATION.GOV.UK | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-03-02 14:50
344 | 288 | No update provided this month |  | Rhiannon.BARNES@EDUCATION.GOV.UK | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-03-02 14:51
345 | 289 | No update provided this month |  | Rhiannon.BARNES@EDUCATION.GOV.UK | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-03-02 14:52
346 | 290 | No update provided this month |  | Rhiannon.BARNES@EDUCATION.GOV.UK | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-03-02 14:53
347 | 291 | PA VCC Dashboard successfully developed and published, providing improved visibility and reporting capability. EAT Dashboard delivered and released, enhancing performance tracking and stakeholder insight. Tech Stack Report completed, establishing a clear view of current systems and dependencies. Unified Intake and Routing model produced, defining a structured entry point and clearer ownership framework to improve ticket triage and reduce ambiguity. SS Designed and implemented a structured communications plan to enable effective rollout and stakeholder alignment for Ofsted Report Cards. | ebfd9ec2-e03d-42c3-9ec4-bd00de9b9ccc | BARNES, Rhiannon | Rhiannon.BARNES@EDUCATION.GOV.UK |  | 2026-03-02 14:56
348 | 292 | DfE Connect has now been successfully released in line with the newly rebranded design system components. The product is now fully aligned with the refreshed visual identity, improving consistency and preparing the platform for wider adoption across the department. The Alpha team has identified three priority user journeys to take forward into discovery mapping for the Alpha phase. These journeys will be developed in more detail to validate assumptions, test feasibility, and inform the Alpha prototypes. | 847721d6-8a9e-4a7a-8170-76096b429a8d | BRIGGS, Shelley | Shelley.BRIGGS@EDUCATION.GOV.UK |  | 2026-03-02 15:13
350 | 293 | N/A This is a duplicate entry | 847721d6-8a9e-4a7a-8170-76096b429a8d | BRIGGS, Shelley | Shelley.BRIGGS@EDUCATION.GOV.UK |  | 2026-03-02 15:16
351 | 294 | Multi-school management design concepts tested with users. Prototype development and research planning for usability testing is now underway. Schools Readiness Insights squad are preparing final discovery report and preparing for next phase of work (building the dashboard for prioritising schools furthest away from meeting standards by 2030). | f7abf0c1-9598-41e9-957a-3d7638a74856 | MURPHY, Carmel | Carmel.MURPHY@EDUCATION.GOV.UK |  | 2026-03-02 16:22
352 | 295 | Key design documentation is under review and the team have been focussing on engagements with the Cyber Security team. As well, a proposal for the future governance of the project has been created and will be presented to the necessary stakeholders for agreement. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-03-02 16:59
353 | 296 | We have completed our workshops with STA leads and are using this to support the findings from the Digital Maturity Assessment in putting our recommendations forward. We are completing our gap analysis and mapping (process, organisation, and systems). which will also feed into the Options paper, identifying areas for improvement, productivity gains, and ways to maintain or enhance the quality of service. We will then be validating our Options and recommendations with HoPS, colleagues from DDT and STA leads before presenting back our findings. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-03-02 17:03
354 | 297 | This review is currently waiting for other reviews to finish in order for the resource to be reallocated. Some desk research has been complete but engagement with the area won't resume until BA resource is made available. Until then the project is on hold. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-03-02 17:05
355 | 298 | Business Analyst now onboarded and interviews/workshops being done with stakeholders to establish and map the as-is processes. Analysis also being done to identify potential improvements. Plan created and high levels costing being provided to business area as requested. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-03-02 17:06
356 | 299 | The new Internal Productivity & AI Forum successfully launched on 20 February, expanding on the previous AI Steerco to include productivity, automation and AI. As we roll out the programme across the department this forum will be key in maintaining alignment across portfolios and delivering the right change programmes. We are starting to build out stronger oversight of delivery across the deaprtment accompanied by extensive work on cost-benefits analysis, which will be one of the foundations of future prioritisation and reporting for the programme. Continuing with capabilty review pilots. STA is sharing findings with stakeholders for review, Post-16 Awarding has progressed to the mapping stage and providing early costings to support bids and FEO is paused until one of the other reviews conclude. We completed a teach-in for the GAP division in Strategy Group and are looking to progress a fuller review next. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-03-02 17:08
357 | 300 | Documents being reviewed by GIAA Interviews with teams being established | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-03-02 17:14
358 | 301 | Development of DfE AI Principles with continued engagement/alignment with AI teams across the department Implications and implementation scoping underway Show and tell of redrafted principles w/c 2/3 SCS engagement w/c2/3 to discuss work and plan for DDT committee | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-03-02 17:15
359 | 302 | No update provided this month |  | Sharon.THOMPSON@education.gov.uk | Sharon.THOMPSON@education.gov.uk |  | 2026-03-02 17:16
360 | 303 | Drafting the 12‑month comms plan, outlining key activities, channels and target audiences. I have already walked this through with the G6 and will make a small number of tweaks based on feedback | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-03-02 17:22
361 | 304 | Committee agreed with the framework and looking forward to seeing how it can be used to support prioritisation. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-03-02 17:25
362 | 305 | "SEND Data - Work kicked off on mapping all SEND projects accross DFE to identify where DDT is/should be supporting. Information gathering complete, moving onto mapping - outputs expected mid March. Work kicked off on benefits for data spine. Digital performance review responded to & key metrics supplied" | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-03-02 17:27
364 | 306 | The team have begun engagement with the wider project team and catching up on latest progress. Following some initial conversations, the team have been able to map a first draft of some processes using resources available in SharePoint. Workshops with those areas identified as falling within scope have been booked in from the first week of March. Further conversations with the programme delivery leads are going to be required to define the exact scope of this project however this isn't currently delaying progress as some areas have already been identified as core to the scope. Preparation is also being made to take this through DDT triage in order for the programme to receive wider support. | d4968443-887a-4dcb-a13e-475357639ee2 | THOMPSON, Sharon | Sharon.THOMPSON@education.gov.uk |  | 2026-03-02 17:34
365 | 307 | The scheduled Go/No Go decision call has been moved to 23rd March, this has been pushed back (from 2nd March) as it was determined to be too early to have this call as the data migration process had not begun. Phase 1 Go Live remains on schedule for 31st March. We carried out a Phase 2 scope document review with senior management and are updating the feedback. The Phase 2 plan is being progressed. | 8bb35da2-e794-49d1-b8b6-f9ddd6d12dd2 | KUMAR, Daniel | Daniel.KUMAR@EDUCATION.GOV.UK |  | 2026-03-02 18:23
366 | 308 | Analysis and moderation of ALB self-assessment data (CAR tool) is complete. Insights and key risks are being prepared to share with DfE CISO, senior colleagues and ALB stakeholders. We have secured short term cyber SME resource to support work to articulate expectations and accountabilities of the government cyber action plan on the department in relation to our ALBs. We are also undertaking a short discovery into governance arrangements that need to be in place to deliver the government cyber plan and wider government cyber security strategies. | 53b409ec-10a3-4b05-ad6d-d7ff8d9946f1 | DUNNE, Alison | Alison.Dunne@EDUCATION.GOV.UK |  | 2026-03-02 22:35
367 | 309 | All portfolio self-assessments are complete. Data analysis and validation is nearing completion. Security incident and vulnerability management data analysis is underway and on track. Red-teaming has been completed. Code reviews and targeted penetration testing are on-going. Initial portfolio ranking has been completed and initial key insights identified. Reporting of overall DfE portfolio security posture and insights by 31 March is on track. | 53b409ec-10a3-4b05-ad6d-d7ff8d9946f1 | DUNNE, Alison | Alison.Dunne@EDUCATION.GOV.UK |  | 2026-03-02 23:09
370 | 311 | • Project is Green as project is on-track • Data lookups finalising • Data stores being created as local copies of the data • UKRLP Applicant journey UI being built • UKRLP Admin journey being finalised in prototype • Decision point to remain on ASE (as per SLD configuration) • Extra data tables received from IDP and being analysed • New data schema in place for UKRLP application • Data fields in progress for UKRLP administration • UR: UKRLP Reports survey out with 4 reminders each week in Feb • UR: PIMS UI Survey out with 4 reminders each week in Feb • UR: UKRLP API users down to 7 parties outstanding to tie up • Operational Readiness Review checkpoint and observed to be making good progress • Test URL in place https://tst.ukrlp.education.gov.uk/ • First contractual Exit/TUPE discussion with IDP, fortnightly catchups, setup a session for 24th Feb • Working with DSI to setup the onboarding of 40,000 logins & creating the service integration • Decision point to work in ASE, not Kubernetes • Agreed cost forecast vs. funding (through LRS modernisation split budgets) for UKPIMS • UR leaving, filling the role with existing individual that will be doing a broader UCD role | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-03-03 08:55
371 | 312 | R07 for 25/26 opened on time over 99% of files process successfully at first attempt failures are re-submitted either by the provider or SLD team | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-03-03 08:58
372 | 313 | No progress on the AI team leader role recruitment, and reduced capacity because of paternity leave, staff leaving next year | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-03-03 08:59
373 | 314 | Our next show and tell is planned for 27 February 2026. We have run further webinars for schools to provide additional information, support and guidance, and we have run the first webinars for MI Suppliers to provide information on the integration approaches that are available. We have visited a school to observe the issuing process and conduct user research, we have also spoken to a number of schools who have signed up for UR so that we can plan further online sessions and visits. We have recruited UR participants for a round of UR with independent schools based on the queries we received following the announcement. We have released new versions of both apps to support MI Suppliers with testing their integration, these also included some minor bug fixes and updates to content. We have implemented a solution for DSI MFA in pre-production, as the current exemption runs out at the end of February. On the guidance website, we have gone live with some additional content (the video and posters to support schools) and some updates to ensure consistency across the pages. Our designers are working on some further updates in this area (e.g. to host our webinar recordings) and are working on the share history and updates to the qualifications display in the app which will be going out for research. | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-03-03 09:00
374 | 315 | Our next show and tell is planned for 27 February 2026. We have delivered a training session to the helpdesk to support them with managing ELD queries at first line. We have completed a round of user research focused on the manage learners information and export, this has identified some design changes to meet user needs and the design work is progressing. We have gone live with some improvements/enhancements based on user feedback, this includes generating the software supplier aim ID, simplification of export business rules and breaks in learning for individual aims. We have also implemented a solution for DSI MFA in pre-production, as the current exemption runs out at the end of February. The design and business analysis work is continuing for the ILR changes for 26/27. The development work on Study Programmes is continuing, we are also addressing some technical debt and making some updates that are required before the 26/27 development work starts. | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-03-03 09:00
375 | 316 | The work is progressing against the project plan and Service teams within DDT are being engaged to allow us to map the first 5 services as outlined in the work proposal. | 73fa79c3-5d67-4a7a-bf30-12fa7da710d2 | RAE, Angus | Angus.RAE@EDUCATION.GOV.UK |  | 2026-03-03 09:01
376 | 317 | The collection closed on 9 Jan and the data has been transferred to MI teams | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-03-03 09:01
377 | 318 | Green - all projects adequately resourced and running to time, although capacity is stretched. Risk Protection Arrangement (BAU rollover) - all work complete, deployment scheduled for 2 March. Risk Protection Arrangement (RPA) - CI project has been reviewed and deemed a larger piece of work that we will resource appropriately later in the year. Submit Financial Data (SFD) - We have successfully established a reliable data collection process for the ITPs’ contact email addresses using DfE Sign‑in. In addition, the team has completed and released all required ITHC and accessibility actions. Work is ongoing to define the email reminders. We have agreed the changes to the borrowings section of the form and work is starting to reflect those improvements in the form. Children’s Social Care Financial Oversight Project - The project is successfully continuing through the Beta phase, the team are continuing to engaged in detailed planning of the Minimum Viable Service (MVS) scope and completing technical spikes to understand feasibility of some requirements. | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-03-03 09:02
378 | 319 | The teams remain fully committed with very little scope to additional work without support. The new NEET work is starting to be onboarded and will form a major project for two of my teams this year. | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-03-03 09:03
379 | 320 | This project was paused in January - will need to be archived. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-03-03 12:37
380 | 321 | Site MVP soft launch complete – working on content additions and technical handover. Some translation issues found; short-term mitigations in-progress, longer-term fixes still being scoped. Analytics update needed to ensure comparability of insights. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-03-03 13:06
381 | 322 | Show and tells held on MAIS programme continue to receive positive feedback. Meeting of DGs from DfE, DHSC and NHSE to agree way forward for use of NHS number. DHSC putting advice up to Ministers to seek way forward. Strategy to engage CMS providers being developed. Commercial support being sought for advice on contractors post Hippo contract ending and to bring on board CMS vendors for Alpha. Application made for mid phase peer review with the service assessment team – planned for end of March 2026. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-03-03 13:11
382 | 323 | Have started Private Beta phase of work and onboarded new colleagues. User research round 1 has started. Development work has started. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-03-03 13:12
383 | 324 | Discovery completed, project is now paused so will need to be archived. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-03-03 13:14
384 | 325 | Delivery Plan is 'On Track'. Continuing to improve the EYQL Web-view service, reduce help queries, promote clarity, increase feedback engagement & user confidence with a view to start scaling our service in order to reduce costs and increase value. Generally, delivery is steady. We continue to iterate on our Product Map & Delivery Plan. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-03-03 13:15
385 | 326 | This project is now live (not discovery) - DfE site has been formally launched, and the team are on track to meet the timescales for the next iteration of changes however future funding needed. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-03-03 13:19
387 | 328 | Project paused in December - please archive. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-03-03 13:24
388 | 329 | Project paused in December 2025, please archive. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-03-03 13:24
389 | 330 | The team are moving at pace and progressing well with scoping for scale activities to and while market engagement is progressing well, we are Amber due to ongoing work with Commercial to ensure 1-2-1 supplier sessions provide sufficient technical depth whilst ensuring parity of discussion | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-03-03 13:35
390 | 331 | Project has just started and are on track against delivery plan milestones, and entering ideation phase as planned. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-03-03 13:43
391 | 332 | HfEYP remains live and stable. The EYFSP support package is on track for publication on HfEYP during the week commencing 9 March (agreed with policy). The policy team for EYCDT has made good progress in clearing and approving changes and providing the required images to be added to the training. As a result, the status has improved to amber‑green. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-03-03 14:13
392 | 327 | Delivery confidence has dipped slightly, as progress on core Phase 1a Alpha activities has slowed due to some team members being diverted to urgent CSON form improvements required for 1 April. While the Alpha remains mobilised with a clear, ministerially‑aligned scope, reduced capacity has impacted momentum on defining the minimum day‑5 SIN dataset and progressing other deliverables. Regular sprint governance and ongoing tactical improvements to the live service (CSON/SIN updates and dashboard stabilisation) continue to manage operational risks, but this short‑term shift in focus has created pressure on Alpha timelines. Work to extend the NCVPP/College of Policing cooperation agreement is still underway to maintain analytical continuity and support a stable pathway toward the Alpha decision gate and transition to Phase 1b. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-03-03 16:50
393 | 333 | Following a BSiL digital workshop in w/c 23 Feb, key next steps are as follows: Create MVP landing pages for school readiness and screen time; audit parent email journeys and identify gaps; explore tactical user research options. Share BSiL Discovery recommendations; confirm available capacity for ongoing work; schedule follow‑up discussions to resolve key content decisions and long‑term ownership. Engage WPP early on relevant tools and support; provide GCS with a readout at the next monthly meeting to ensure alignment across comms. | 6cabce7a-d8ad-4303-91f8-f9cd9f12c56b | MOLYNEUX, Sue | Sue.MOLYNEUX@EDUCATION.GOV.UK |  | 2026-03-03 17:15
394 | 310 | Primary focus is engagement with Data Owners and Stewards to establish single asset register. Continuing to deliver against milestones outlined. | c010c450-1cef-4ad2-8ac2-96870b5b3dd8 | WRIGHT, Jo | Jo.WRIGHT@EDUCATION.GOV.UK |  | 2026-03-04 10:30
395 | 334 | No update provided this month |  | Kuldip.OSBORNE@EDUCATION.GOV.UK | Kuldip.OSBORNE@EDUCATION.GOV.UK |  | 2026-03-04 10:49
396 | 335 | NEET Data Programme Board took place on 02.03. Discussed inhousing governance and contract extension procurement alongside stakeholder engagement. Clarification that completed Discovery work will be handed over to Tom to integrate with ongoing FE attendance and real-time data projects. | c010c450-1cef-4ad2-8ac2-96870b5b3dd8 | WRIGHT, Jo | Jo.WRIGHT@EDUCATION.GOV.UK |  | 2026-03-04 10:52
397 | 336 | No update provided this month |  | Jo.WRIGHT@EDUCATION.GOV.UK | Jo.WRIGHT@EDUCATION.GOV.UK |  | 2026-03-04 11:02
398 | 335 | Programme manager has been assigned and a small team assembled to review existing artefacts and knowledge for each strand to allow planning for the next phases. NEETs NCCIS In-housing and modernisation: We are looking at the technical aspect of what the current website does and starting to gather the MVP that we would need for a new inhouse service, looking at the ingestion of .XML files that are produced by LA's on NEET, also scoping the resources that we are likely to need to deliver the front end website and back end data models. Risk of NEET Indicator AI developments: We are undertaking pre-discovery for the Risk of NEETs Indicator (RONI), with a focus on confirming the problem statement, intended users/decisions, and data feasibility. We are engaging stakeholders through workshops to understand drivers, existing interventions, and the data needed. Pre-discovery will conclude with a recommended option and a proposed approach for progressing into discovery. FE timeliness of data improvements: Discussing need for business cases, planning resource requirements and speaking to managed service suppliers on our possible requirements from Aptil onwards. Product Manager identified. | 817ce0dd-c08b-435c-8a1e-8f592028eade | MEDLOCK, Ruth | Ruth.MEDLOCK@EDUCATION.GOV.UK |  | 2026-03-04 13:48
399 | 337 | Deployed Access Manager to AI platform to enable tracking of AI token usage, costs and recharging to business units. Comms on how users access the Sandbox environment via FaUAPI issued and technical guide published on hub. Survey to understand views and usage of AI tools and where potential opportunities could exist completed. Records Management proof of concept – user research around frontend design and prototypes completed. Ed chat – Private Beta launch currently blocked due to token limits/availability in UK South with embeddings model. | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-03-04 15:48
400 | 338 | Continued to model business capabilities for Regions group & CPD programmes Continued to assure the Enterprise Data Model (EDM) domain-level structures with broader portfolio engagement Initiated and led on glossary alignment across EDM, DfE Subject Taxonomy, CMDB, FIPS and Data Governance Continued to provide EA input and alignment between DDT 2030 (Service Delivery Revolution) work and Target Architecture / op model Initial meetings with identified ALBs to understand architecture service opportunities. Supporting corporate services options discussions with DfE CI team. Agreed updates to data/security architecture frameworks. Launched re-assessment of CBP for Enterprise Architects. Delivered xGov ‘Architect Elevator’ training for 8 DfE architects. Secured training credits for 3 day deep-dive next FY for 15+ DfE architects. | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-03-04 15:49
401 | 339 | Ifate/Skills England CRM – handover complete and in BAU support, ITHC scheduling in progress Turing Application window for AY26/27 opened Student and adult data spreadsheet download functionality Payment requests – status reason updates, payment request page updates, Final reporting pages updates Provider BAU EED user journeys completed Customer insights improvements SLA updates AI chatbot work | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-03-04 15:50
402 | 340 | Reviewed and update IE Standards governance processes. Encourage more collaboration to propose and develop standards throughout the community. Review sources to feed IE standards backlog - eg CIS policies & dashboards, Azure policies. Seek additional resource (Tech Arch) to work on standards. | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-03-04 15:51
403 | 341 | FSM basic frontend single and batch check built. Removed reliance on legacy system which was a cross-check of the results from the two systems so we could assess mismatches between them - but we have completed that analysis and are happy the rule in ECE are correct. Finalize and roll out support model with Service Delivery & 1st Line teams. IT Healthcheck, Welsh Translation, & Accessibility Audit process started. Working families checks now available in beta. | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-03-04 15:53
404 | 342 | API analytics phase 1 (service scope) MVP complete Migrate environments to feature flagged customisable environments WIP Migrations and onboarding ongoing | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-03-04 15:53
405 | 343 | Ongoing work on CAAS Stage 1 engagements – a productive workshop was held with the Apprenticeship Service on 24th Feb, which has resulted in some possible new requirements for the CAAS calculation tool enable it to capture savings from this Service Line. CAAS Stage 2 – On Hold. A switch in suppliers means resources will not be available to work on CAAS Stage 2 until 9th March. The next phase will consider the findings from the recent Discovery, which may lead to re-scoping the CAAS Stage 2 service offer. A 3-year 3,000,000 DBCU Databricks reserved capacity was purchased on 2nd March at a cost of £1.59m which will deliver a 31% saving on the 'on-demand' price. 51 Azure reservations have been renewed for either 3-year or 1-year plans (depending on business intelligence) ensuring that the Department continues to optimise the rate for Azure cloud hosting. The business case for financial year 26/27 has been submitted to assurance/approval and the SoWs have been drafted ready to issue to suppliers once the business case is approved. A new 3-year tech strategy cost avoidance target of 5% (£1m) is proposed within the new business case; in the context of having already delivered £2.5m in the previous strategy period, with much of the quick win work already completed. The remaining opportunities to avoid costs will be harder to identify / implement. | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-03-04 15:54
406 | 344 | Continue with Strategy engagement and comms with communities of practice to ensure awareness. Continue work to develop a plan for single tenancy options to share with stakeholders. Began engagement with Microsoft to review and understand single tenancy implementation. Workshop with key stakeholders planned and scheduled to discuss the single tenancy options paper. | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-03-04 15:56
407 | 345 | Service Status and Capacity GREEN Network availability GREEN Hosting availability GREEN Recruitment and Retention GREEN | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-03-04 15:58
408 | 346 | No update provided this month |  | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-03-04 16:00
409 | 347 | No update provided this month |  | Louise.HAGUE@EDUCATION.GOV.UK | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-03-04 16:01
410 | 348 | No update provided this month |  | Chris.KIRBY@EDUCATION.GOV.UK | Chris.KIRBY@EDUCATION.GOV.UK |  | 2026-03-05 09:03
411 | 349 | Project remains on hold | e57d3845-6188-48e7-963e-d46363500207 | DALE, Tracey | Tracey.DALE@EDUCATION.GOV.UK |  | 2026-03-05 09:48
412 | 246 | Catalyst Fund (known externally as the AI Tools for Education Competition): 4 suppliers are all on all on track. 1 project is looking to reprioritise deliverables in the face of delays however we are assured that this will not impact delivery. | 0f9f7777-e6eb-4bd9-99af-fa0b883c2a83 | LANGLEY, Georgina | Georgina.LANGLEY@education.gov.uk |  | 2026-03-05 14:09
413 | 246 | AI Big bets work - AI Benchmarking: New work with DSIT launched in October 2025 to assess and evaluate the current pedagogical and safety standards of AI models for developing personalised AI learning tools. Rubric development with teachers started with a small-scale proof of concept in mid-January and is due to finish at the end of February, before a second, larger-scale proof of concept launches for three weeks in March. We will continue to work with DSIT by helping to review the results of the first proof of concept and to shape the rubric development work from the DfE policy side for the second iteration, and we will also continue to help set up procurement routes to aid delivery for the work too. | 0f9f7777-e6eb-4bd9-99af-fa0b883c2a83 | LANGLEY, Georgina | Georgina.LANGLEY@education.gov.uk |  | 2026-03-05 14:10
414 | 350 | Delivery has been going well - CGI are implementing changes and enhancements into the system on an adhoc basis. The current SoW is due to complete on 31st March, and all is on schedule to complete agreed milestones. | f3e1f612-d430-4f14-b918-df815d949249 | MARSDEN, Daniel | Daniel.MARSDEN@EDUCATION.GOV.UK |  | 2026-03-05 14:27
415 | 351 | No update provided this month |  | Daniel.MARSDEN@EDUCATION.GOV.UK | Daniel.MARSDEN@EDUCATION.GOV.UK |  | 2026-03-05 14:29
416 | 352 | The service remains stable and on track with the service in steady state and no significant development in progress or planned. Final preparations for the Autumn results issue in March 2026 are completed, ahead of receipt of results from AOs on 9th March. We continue to progress plans for a longer-term delegation of the functions delivered by this service to AOs, with Ministerial agreement received on 5 March to the direction of travel. We are working towards a transition from the 2027 cohort, following which there would be a period of dual running of whilst earlier cohorts continue to final certification by DfE. On this basis, the DfE service would be decommissioned in 2029/30. | f7f31ca6-8502-4d63-93e2-bac025095fa3 | SCOTT, David | David.SCOTT@EDUCATION.GOV.UK |  | 2026-03-05 17:30
417 | 224 | Completing handover from CXandD team | c010c450-1cef-4ad2-8ac2-96870b5b3dd8 | WRIGHT, Jo | Jo.WRIGHT@EDUCATION.GOV.UK |  | 2026-03-06 08:27
419 | 353 | Everything remains on track. Good progress made on the Data Bricks migration. | e83f7a5b-59b4-4ac0-bf4a-a87587a40d7d | YOUNG, Joe | Joe.YOUNG@EDUCATION.GOV.UK |  | 2026-03-10 09:11
420 | 354 | No update provided this month |  | Joe.YOUNG@EDUCATION.GOV.UK | Joe.YOUNG@EDUCATION.GOV.UK |  | 2026-03-10 09:12
421 | 355 | MVP approach defined and agreed. Two track solution to cover 4 main pain points we are seeing for users: Service Improvements (general, in definition), creation of an Operational Data Layer (definition underway, due to be delivered w/c 16th March). Validation of evidence underway, assumptions collated, and delivery plan set out to and signed off by SMT. | f16be3e8-8523-460d-af95-7d6290fbf32b | HALIM, Amna | Amna.HALIM@EDUCATION.GOV.UK |  | 2026-03-10 10:03
422 | 356 | PI 15 planning progresses well | 9cdea143-507b-4b33-831b-9e2ddeae99c5 | MYERSCOUGH, Jennifer | Jennifer.MYERSCOUGH@EDUCATION.GOV.UK |  | 2026-03-10 15:33
423 | 357 | No update provided this month |  | Jennifer.MYERSCOUGH@EDUCATION.GOV.UK | Jennifer.MYERSCOUGH@EDUCATION.GOV.UK |  | 2026-03-10 15:34
424 | 358 | Breakfast Clubs is currently being reported under CRM. No specific update further to last month. | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-03-11 08:33
425 | 359 | Metadata and Data Quality is not currently being reported because this is not a live project at the moment. No further update from last month. | e7b9a911-e1f2-4ba4-972f-63d5ca0fc0e0 | HAGUE, Louise | Louise.HAGUE@EDUCATION.GOV.UK |  | 2026-03-11 08:35

## WeeklySuccess
Id | ProjectId | Year | WeekNumber | WeekStartDate | WeekEndDate | SuccessDescription | CreatedByEntraId | CreatedByName | CreatedByEmail | CreatedByUserId | UpdatedByUserId | IsReportedToSlt | SltResponse | SltRespondedByEmail | SltRespondedByName | SltRespondedAt | CreatedAt | UpdatedAt

## SROs
Id | ProjectId | UserId | CreatedAt
2 | 123 | 36 | 2025-11-22 11:15
3 | 130 | 11 | 2025-11-22 11:19
4 | 179 | 10 | 2025-11-22 11:21
5 | 72 | 15 | 2025-11-22 11:23
6 | 172 | 10 | 2025-11-22 11:35
8 | 124 | 36 | 2025-11-22 18:52
10 | 51 | 44 | 2025-11-22 19:26
11 | 126 | 9 | 2025-11-22 19:26
12 | 71 | 15 | 2025-11-22 19:27
13 | 26 | 45 | 2025-11-22 19:27
14 | 41 | 11 | 2025-11-22 19:27
16 | 190 | 47 | 2025-11-22 19:33
17 | 90 | 14 | 2025-11-22 19:40
18 | 193 | 47 | 2025-11-22 19:41
19 | 81 | 10 | 2025-11-22 19:41
20 | 152 | 12 | 2025-11-22 19:42
21 | 25 | 48 | 2025-11-22 19:42
23 | 50 | 11 | 2025-11-22 19:43
24 | 171 | 10 | 2025-11-22 19:44
25 | 118 | 11 | 2025-11-22 19:45
26 | 18 | 50 | 2025-11-22 19:46
27 | 75 | 51 | 2025-11-22 19:46
28 | 73 | 52 | 2025-11-22 19:47
29 | 69 | 15 | 2025-11-22 19:47
32 | 19 | 10 | 2025-11-22 19:49
33 | 160 | 51 | 2025-11-22 20:02
35 | 161 | 51 | 2025-11-22 20:02
37 | 166 | 17 | 2025-11-22 20:04
38 | 27 | 53 | 2025-11-22 20:06
39 | 80 | 10 | 2025-11-22 20:07
40 | 74 | 51 | 2025-11-22 20:07
41 | 79 | 51 | 2025-11-22 20:07
42 | 169 | 10 | 2025-11-22 20:08
43 | 170 | 10 | 2025-11-22 20:08
44 | 150 | 12 | 2025-11-22 20:08
46 | 56 | 14 | 2025-11-22 20:09
47 | 174 | 10 | 2025-11-22 20:09
48 | 65 | 15 | 2025-11-22 20:10
49 | 154 | 9 | 2025-11-22 20:10
50 | 91 | 14 | 2025-11-22 20:10
53 | 191 | 47 | 2025-11-22 20:11
54 | 192 | 47 | 2025-11-22 20:11
55 | 53 | 56 | 2025-11-22 20:12
58 | 194 | 47 | 2025-11-22 20:13
59 | 68 | 15 | 2025-11-22 20:13
61 | 186 | 58 | 2025-11-22 20:14
63 | 151 | 12 | 2025-11-22 20:15
64 | 67 | 15 | 2025-11-22 20:15
65 | 137 | 10 | 2025-11-22 20:16
66 | 32 | 12 | 2025-11-22 20:16
69 | 66 | 15 | 2025-11-22 20:19
70 | 92 | 14 | 2025-11-22 20:32
71 | 89 | 14 | 2025-11-22 20:32
72 | 173 | 10 | 2025-11-22 20:32
73 | 44 | 59 | 2025-11-22 20:33
75 | 38 | 11 | 2025-11-22 20:33
76 | 40 | 60 | 2025-11-22 20:33
77 | 188 | 58 | 2025-11-22 20:34
78 | 78 | 3 | 2025-11-22 20:34
79 | 62 | 52 | 2025-11-22 20:34
80 | 146 | 9 | 2025-11-22 20:35
82 | 138 | 10 | 2025-11-22 20:35
83 | 147 | 9 | 2025-11-22 20:36
84 | 57 | 15 | 2025-11-22 20:36
85 | 85 | 62 | 2025-11-22 20:36
87 | 63 | 63 | 2025-11-22 20:39
88 | 181 | 64 | 2025-11-22 20:39
89 | 196 | 65 | 2025-11-22 20:39
90 | 187 | 58 | 2025-11-22 20:40
92 | 125 | 65 | 2025-11-22 20:40
93 | 70 | 15 | 2025-11-22 20:41
94 | 180 | 1 | 2025-11-22 20:41
95 | 128 | 9 | 2025-11-22 20:42
96 | 86 | 12 | 2025-11-22 20:42
97 | 168 | 10 | 2025-11-22 20:42
103 | 77 | 51 | 2025-11-22 20:44
104 | 116 | 9 | 2025-11-22 20:45
105 | 31 | 12 | 2025-11-22 20:45
106 | 29 | 11 | 2025-11-22 20:45
110 | 121 | 15 | 2025-11-22 20:46
112 | 28 | 15 | 2025-11-22 20:47
113 | 144 | 67 | 2025-11-22 20:48
114 | 117 | 58 | 2025-11-22 20:48
115 | 16 | 68 | 2025-11-22 20:48
118 | 54 | 65 | 2025-11-22 21:38
119 | 55 | 65 | 2025-11-22 21:39
120 | 34 | 12 | 2025-11-22 21:40
121 | 33 | 12 | 2025-11-22 21:40
122 | 36 | 12 | 2025-11-22 21:40
123 | 35 | 12 | 2025-11-22 21:40
124 | 37 | 12 | 2025-11-22 21:41
125 | 127 | 9 | 2025-11-22 21:41
126 | 87 | 14 | 2025-11-22 21:41
127 | 148 | 69 | 2025-11-22 21:41
128 | 115 | 68 | 2025-11-22 21:42
129 | 176 | 10 | 2025-11-22 21:42
130 | 140 | 16 | 2025-11-22 21:43
134 | 163 | 51 | 2025-11-22 21:44
135 | 88 | 12 | 2025-11-22 21:45
136 | 22 | 65 | 2025-11-22 21:45
137 | 132 | 65 | 2025-11-22 21:45
138 | 24 | 70 | 2025-11-22 21:45
139 | 58 | 71 | 2025-11-22 21:46
140 | 48 | 70 | 2025-11-22 21:46
142 | 47 | 11 | 2025-11-22 21:47
143 | 49 | 11 | 2025-11-22 21:47
144 | 30 | 73 | 2025-11-22 21:48
145 | 142 | 67 | 2025-11-22 21:48
146 | 143 | 67 | 2025-11-22 21:48
147 | 20 | 74 | 2025-11-22 21:49
148 | 21 | 74 | 2025-11-22 21:49
150 | 177 | 10 | 2025-11-22 21:50
151 | 178 | 10 | 2025-11-22 21:51
152 | 76 | 51 | 2025-11-22 21:52
153 | 7 | 3 | 2025-11-24 09:49
154 | 1 | 3 | 2025-11-24 21:15
155 | 198 | 77 | 2025-11-25 21:58
156 | 15 | 10 | 2025-11-25 22:01
157 | 96 | 8 | 2025-11-26 07:50
158 | 111 | 8 | 2025-11-26 07:50
159 | 109 | 8 | 2025-11-27 08:18
160 | 113 | 8 | 2025-11-27 08:19
161 | 199 | 10 | 2025-11-27 08:50
162 | 114 | 14 | 2025-11-27 12:17
164 | 195 | 88 | 2025-12-03 15:51
166 | 204 | 17 | 2025-12-15 15:37
172 | 200 | 17 | 2025-12-18 11:36
173 | 203 | 10 | 2025-12-18 12:52
174 | 210 | 17 | 2025-12-18 12:59
176 | 202 | 17 | 2026-01-05 16:02
177 | 209 | 17 | 2026-01-05 16:06
180 | 4 | 141 | 2026-01-15 16:02
182 | 213 | 14 | 2026-01-20 13:52
183 | 214 | 14 | 2026-01-20 13:52
184 | 215 | 14 | 2026-01-20 13:52
185 | 216 | 14 | 2026-01-20 13:52
189 | 64 | 13 | 2026-01-21 13:16
190 | 217 | 9 | 2026-01-26 07:43
191 | 84 | 9 | 2026-01-26 07:55
192 | 82 | 9 | 2026-01-26 07:58
193 | 83 | 9 | 2026-01-26 08:01
194 | 3 | 141 | 2026-01-26 13:40
195 | 2 | 141 | 2026-01-26 13:42
196 | 5 | 141 | 2026-01-26 13:44
197 | 212 | 15 | 2026-01-26 17:03
198 | 218 | 10 | 2026-01-27 13:30
199 | 167 | 10 | 2026-01-28 10:05
200 | 219 | 3 | 2026-01-28 12:01
201 | 6 | 10 | 2026-01-29 11:28
202 | 220 | 17 | 2026-01-30 10:52
203 | 221 | 17 | 2026-01-30 11:16
204 | 222 | 17 | 2026-01-30 15:42
205 | 223 | 17 | 2026-01-30 15:50
206 | 224 | 17 | 2026-01-30 15:53
207 | 225 | 17 | 2026-01-30 16:00
208 | 226 | 17 | 2026-01-30 16:08
209 | 227 | 17 | 2026-01-30 17:26
210 | 228 | 17 | 2026-01-30 17:30
211 | 229 | 17 | 2026-01-30 17:32
212 | 230 | 17 | 2026-01-30 17:35
213 | 158 | 15 | 2026-02-02 08:35
214 | 99 | 11 | 2026-02-02 08:52
215 | 182 | 58 | 2026-02-02 14:04
216 | 185 | 58 | 2026-02-02 16:50
217 | 184 | 58 | 2026-02-03 15:36
219 | 232 | 58 | 2026-02-04 21:19
220 | 81 | 8 | 2026-02-05 10:24
222 | 233 | 67 | 2026-02-10 10:31
223 | 234 | 11 | 2026-02-13 12:36
224 | 235 | 11 | 2026-02-13 16:15
226 | 237 | 11 | 2026-02-13 16:25
227 | 239 | 11 | 2026-02-19 11:52
228 | 145 | 11 | 2026-02-19 11:54
229 | 240 | 11 | 2026-02-19 11:55
230 | 119 | 11 | 2026-02-19 11:56
231 | 241 | 51 | 2026-02-19 15:28
237 | 243 | 51 | 2026-02-23 13:24
242 | 254 | 51 | 2026-02-23 14:27
243 | 255 | 51 | 2026-02-23 14:29
244 | 164 | 51 | 2026-02-25 13:42
245 | 244 | 51 | 2026-02-25 13:44
246 | 242 | 51 | 2026-02-25 13:48
247 | 159 | 51 | 2026-02-25 13:49
250 | 245 | 51 | 2026-02-26 08:54
251 | 17 | 472 | 2026-02-26 12:16
252 | 45 | 472 | 2026-02-26 12:16
253 | 46 | 472 | 2026-02-26 12:16
255 | 133 | 472 | 2026-02-26 12:16
256 | 134 | 472 | 2026-02-26 12:16
257 | 135 | 472 | 2026-02-26 12:16
258 | 136 | 472 | 2026-02-26 12:16
259 | 153 | 472 | 2026-02-26 12:16
260 | 205 | 472 | 2026-02-26 12:16
261 | 206 | 472 | 2026-02-26 12:16
262 | 207 | 472 | 2026-02-26 12:16
263 | 208 | 472 | 2026-02-26 12:16
264 | 238 | 472 | 2026-02-26 12:16
265 | 246 | 51 | 2026-03-02 13:50
266 | 252 | 51 | 2026-03-02 14:40
267 | 248 | 51 | 2026-03-02 14:42
268 | 250 | 51 | 2026-03-02 14:44
269 | 39 | 9 | 2026-03-05 14:05
271 | 120 | 58 | 2026-03-11 14:16
272 | 259 | 8 | 2026-03-16 13:27
273 | 258 | 8 | 2026-03-16 13:29

## ServiceOwners
Id | ProjectId | UserId | CreatedAt
1 | 1 | 1 | 2025-11-24 21:15
2 | 6 | 1 | 2025-11-25 08:47
3 | 179 | 1 | 2025-11-25 12:01
4 | 176 | 30 | 2025-11-25 20:45
5 | 198 | 1 | 2025-11-25 21:58
6 | 15 | 1 | 2025-11-25 22:00
7 | 7 | 5 | 2025-11-26 09:43
8 | 199 | 1 | 2025-11-27 08:50
10 | 122 | 109 | 2026-01-05 15:20
11 | 211 | 109 | 2026-01-05 15:45
18 | 167 | 29 | 2026-01-14 16:04
19 | 213 | 14 | 2026-01-20 13:33
20 | 214 | 14 | 2026-01-20 13:37
21 | 215 | 14 | 2026-01-20 13:42
22 | 216 | 14 | 2026-01-20 13:44
23 | 18 | 63 | 2026-01-20 14:47
24 | 141 | 109 | 2026-01-20 15:56
26 | 3 | 189 | 2026-01-26 13:38
28 | 163 | 140 | 2026-01-27 14:35
29 | 219 | 4 | 2026-01-28 12:01
30 | 169 | 1 | 2026-01-28 17:11
31 | 44 | 227 | 2026-02-02 13:55
32 | 72 | 232 | 2026-02-03 14:03
33 | 72 | 233 | 2026-02-03 14:03
34 | 71 | 32 | 2026-02-04 11:07
35 | 71 | 234 | 2026-02-04 11:07
36 | 69 | 88 | 2026-02-04 11:08
37 | 69 | 240 | 2026-02-04 11:08
38 | 69 | 241 | 2026-02-04 11:09
39 | 65 | 235 | 2026-02-04 11:09
40 | 67 | 88 | 2026-02-04 11:10
41 | 67 | 228 | 2026-02-04 11:10
42 | 67 | 242 | 2026-02-04 11:10
43 | 66 | 237 | 2026-02-04 11:12
44 | 66 | 243 | 2026-02-04 11:12
45 | 66 | 244 | 2026-02-04 11:12
46 | 66 | 245 | 2026-02-04 11:12
47 | 57 | 238 | 2026-02-04 11:13
48 | 57 | 246 | 2026-02-04 11:13
49 | 57 | 233 | 2026-02-04 11:13
50 | 70 | 237 | 2026-02-04 11:13
51 | 70 | 247 | 2026-02-04 11:13
54 | 23 | 88 | 2026-02-05 12:37
56 | 212 | 88 | 2026-02-09 11:35
57 | 212 | 258 | 2026-02-09 11:35
58 | 212 | 224 | 2026-02-09 11:38
59 | 234 | 177 | 2026-02-13 12:36
60 | 235 | 177 | 2026-02-13 16:15
62 | 237 | 177 | 2026-02-13 16:25
63 | 239 | 443 | 2026-02-19 11:52
64 | 145 | 43 | 2026-02-19 11:54
65 | 240 | 443 | 2026-02-19 11:55
66 | 119 | 43 | 2026-02-19 11:56
68 | 241 | 140 | 2026-02-19 15:28
69 | 161 | 140 | 2026-02-19 16:29
74 | 160 | 140 | 2026-02-19 16:44
79 | 243 | 140 | 2026-02-23 13:24
84 | 254 | 140 | 2026-02-23 14:27
85 | 255 | 140 | 2026-02-23 14:29
86 | 236 | 177 | 2026-02-24 14:35
88 | 164 | 452 | 2026-02-25 13:41
89 | 244 | 140 | 2026-02-25 13:44
90 | 242 | 140 | 2026-02-25 13:48
91 | 159 | 51 | 2026-02-25 13:50
94 | 245 | 140 | 2026-02-26 08:54
95 | 246 | 452 | 2026-03-02 13:50
96 | 182 | 61 | 2026-03-02 13:52
97 | 182 | 382 | 2026-03-02 13:52
98 | 252 | 452 | 2026-03-02 14:40
99 | 248 | 452 | 2026-03-02 14:42
100 | 250 | 452 | 2026-03-02 14:44

## Directorates
Id | ProjectId | DivisionId | CreatedAt
124 | 1 | 2 | 2025-11-21 16:48
132 | 72 | 2 | 2025-11-22 11:23
140 | 7 | 2 | 2025-11-24 09:14
149 | 71 | 2 | 2025-11-24 12:13
152 | 46 | 2 | 2025-11-24 12:15
171 | 18 | 2 | 2025-11-24 12:19
172 | 75 | 2 | 2025-11-24 12:20
180 | 159 | 2 | 2025-11-24 12:23
201 | 65 | 2 | 2025-11-24 12:56
204 | 122 | 2 | 2025-11-24 12:57
205 | 141 | 2 | 2025-11-24 12:57
221 | 67 | 2 | 2025-11-24 16:56
224 | 66 | 2 | 2025-11-24 16:57
235 | 78 | 2 | 2025-11-24 17:00
236 | 62 | 2 | 2025-11-24 17:00
243 | 63 | 2 | 2025-11-24 17:01
244 | 52 | 2 | 2025-11-24 17:02
245 | 85 | 2 | 2025-11-24 17:02
246 | 57 | 2 | 2025-11-24 17:02
247 | 196 | 2 | 2025-11-24 17:02
250 | 125 | 2 | 2025-11-24 17:03
251 | 70 | 2 | 2025-11-24 17:04
258 | 136 | 2 | 2025-11-24 17:06
259 | 134 | 2 | 2025-11-24 17:07
260 | 153 | 2 | 2025-11-24 17:08
261 | 45 | 2 | 2025-11-24 17:08
262 | 77 | 2 | 2025-11-24 17:08
264 | 133 | 2 | 2025-11-24 17:11
268 | 120 | 2 | 2025-11-24 17:12
274 | 121 | 2 | 2025-11-24 17:13
275 | 23 | 2 | 2025-11-24 17:13
276 | 28 | 2 | 2025-11-24 17:13
277 | 144 | 2 | 2025-11-24 17:13
284 | 54 | 2 | 2025-11-24 17:15
285 | 55 | 2 | 2025-11-24 17:16
320 | 198 | 2 | 2025-11-25 21:58
323 | 199 | 2 | 2025-11-27 08:50
331 | 206 | 2 | 2025-12-16 11:24
333 | 207 | 2 | 2025-12-17 14:30
335 | 200 | 2 | 2025-12-18 11:37
336 | 209 | 2 | 2025-12-18 12:22
338 | 210 | 2 | 2025-12-18 12:59
339 | 156 | 2 | 2025-12-18 15:29
340 | 205 | 2 | 2026-01-05 12:58
343 | 204 | 2 | 2026-01-05 16:07
344 | 208 | 2 | 2026-01-07 15:16
349 | 4 | 2 | 2026-01-15 16:03
359 | 3 | 2 | 2026-01-26 13:41
360 | 2 | 2 | 2026-01-26 13:45
361 | 5 | 2 | 2026-01-26 13:46
364 | 219 | 2 | 2026-01-28 12:01
366 | 220 | 2 | 2026-01-30 10:52
367 | 221 | 2 | 2026-01-30 11:16
369 | 222 | 2 | 2026-01-30 15:42
372 | 223 | 2 | 2026-01-30 15:50
375 | 224 | 2 | 2026-01-30 15:53
381 | 226 | 2 | 2026-01-30 16:08
384 | 227 | 2 | 2026-01-30 17:26
387 | 228 | 2 | 2026-01-30 17:30
390 | 229 | 2 | 2026-01-30 17:32
393 | 230 | 2 | 2026-01-30 17:35
401 | 186 | 2 | 2026-02-02 20:49
405 | 185 | 2 | 2026-02-02 21:47
408 | 184 | 2 | 2026-02-03 15:38
410 | 117 | 2 | 2026-02-04 11:45
414 | 232 | 2 | 2026-02-04 21:19
417 | 233 | 2 | 2026-02-09 10:55
418 | 1 | 1 | 2026-02-11 18:25
419 | 234 | 1 | 2026-02-13 12:36
420 | 235 | 1 | 2026-02-13 16:15
421 | 236 | 1 | 2026-02-13 16:20
422 | 237 | 1 | 2026-02-13 16:25
423 | 239 | 1 | 2026-02-19 11:52
424 | 240 | 1 | 2026-02-19 11:55
425 | 16 | 1 | 2026-02-19 12:36
426 | 241 | 1 | 2026-02-19 15:28
427 | 161 | 1 | 2026-02-19 16:29
430 | 160 | 1 | 2026-02-19 16:44
433 | 164 | 1 | 2026-02-19 16:56
434 | 163 | 1 | 2026-02-19 16:58
435 | 15 | 1 | 2026-02-21 15:48
436 | 15 | 2 | 2026-02-21 15:48
437 | 26 | 1 | 2026-02-23 07:34
438 | 243 | 1 | 2026-02-23 13:23
447 | 256 | 1 | 2026-02-24 11:34
448 | 245 | 1 | 2026-02-25 15:47
449 | 182 | 1 | 2026-03-02 13:52
450 | 246 | 1 | 2026-03-02 14:58
451 | 258 | 1 | 2026-03-03 13:33
452 | 259 | 1 | 2026-03-03 13:42
453 | 260 | 1 | 2026-03-11 13:11
454 | 225 | 1 | 2026-03-11 14:17

## BudgetOwners
Id | ProjectId | BusinessAreaLookupId | CreatedAt
2 | 17 | 4 | 2025-11-20 13:56
3 | 18 | 10 | 2025-11-20 13:56
4 | 20 | 10 | 2025-11-20 13:56
5 | 21 | 10 | 2025-11-20 13:56
6 | 22 | 9 | 2025-11-20 13:56
7 | 23 | 4 | 2025-11-20 13:56
8 | 24 | 4 | 2025-11-20 13:56
9 | 25 | 4 | 2025-11-20 13:56
10 | 26 | 9 | 2025-11-20 13:56
11 | 27 | 4 | 2025-11-20 13:56
12 | 28 | 4 | 2025-11-20 13:56
13 | 30 | 8 | 2025-11-20 13:56
14 | 31 | 8 | 2025-11-20 13:56
15 | 32 | 8 | 2025-11-20 13:56
16 | 33 | 8 | 2025-11-20 13:56
17 | 34 | 8 | 2025-11-20 13:56
18 | 35 | 8 | 2025-11-20 13:56
19 | 36 | 8 | 2025-11-20 13:56
20 | 37 | 8 | 2025-11-20 13:56
21 | 38 | 10 | 2025-11-20 13:56
22 | 39 | 9 | 2025-11-20 13:56
23 | 40 | 8 | 2025-11-20 13:56
24 | 41 | 8 | 2025-11-20 13:56
25 | 42 | 8 | 2025-11-20 13:56
26 | 43 | 8 | 2025-11-20 13:56
27 | 44 | 8 | 2025-11-20 13:56
28 | 45 | 8 | 2025-11-20 13:56
29 | 46 | 8 | 2025-11-20 13:56
30 | 47 | 8 | 2025-11-20 13:56
31 | 48 | 4 | 2025-11-20 13:56
32 | 49 | 8 | 2025-11-20 13:56
33 | 50 | 8 | 2025-11-20 13:56
34 | 51 | 8 | 2025-11-20 13:56
36 | 53 | 4 | 2025-11-20 13:56
37 | 54 | 10 | 2025-11-20 13:56
38 | 55 | 10 | 2025-11-20 13:56
39 | 56 | 8 | 2025-11-20 13:56
40 | 57 | 10 | 2025-11-20 13:56
42 | 64 | 8 | 2025-11-20 13:56
43 | 65 | 10 | 2025-11-20 13:56
44 | 66 | 10 | 2025-11-20 13:56
45 | 67 | 10 | 2025-11-20 13:56
46 | 68 | 4 | 2025-11-20 13:56
47 | 69 | 10 | 2025-11-20 13:56
48 | 74 | 10 | 2025-11-20 13:56
49 | 75 | 10 | 2025-11-20 13:56
50 | 76 | 10 | 2025-11-20 13:56
51 | 77 | 10 | 2025-11-20 13:56
52 | 78 | 10 | 2025-11-20 13:56
53 | 81 | 4 | 2025-11-20 13:56
54 | 82 | 9 | 2025-11-20 13:56
55 | 83 | 9 | 2025-11-20 13:56
56 | 84 | 9 | 2025-11-20 13:56
57 | 85 | 9 | 2025-11-20 13:56
58 | 87 | 8 | 2025-11-20 13:56
59 | 88 | 7 | 2025-11-20 13:56
60 | 89 | 8 | 2025-11-20 13:56
62 | 91 | 8 | 2025-11-20 13:56
63 | 92 | 8 | 2025-11-20 13:56
64 | 93 | 4 | 2025-11-20 13:56
65 | 94 | 4 | 2025-11-20 13:56
66 | 95 | 4 | 2025-11-20 13:56
67 | 96 | 4 | 2025-11-20 13:56
68 | 97 | 4 | 2025-11-20 13:56
69 | 98 | 4 | 2025-11-20 13:56
71 | 100 | 4 | 2025-11-20 13:56
72 | 101 | 4 | 2025-11-20 13:56
73 | 102 | 4 | 2025-11-20 13:56
74 | 103 | 4 | 2025-11-20 13:56
75 | 104 | 4 | 2025-11-20 13:56
76 | 105 | 4 | 2025-11-20 13:56
77 | 106 | 4 | 2025-11-20 13:56
78 | 107 | 4 | 2025-11-20 13:56
79 | 108 | 4 | 2025-11-20 13:56
80 | 109 | 4 | 2025-11-20 13:56
81 | 110 | 4 | 2025-11-20 13:56
82 | 111 | 4 | 2025-11-20 13:56
83 | 112 | 4 | 2025-11-20 13:56
84 | 113 | 4 | 2025-11-20 13:56
85 | 114 | 8 | 2025-11-20 13:56
86 | 115 | 8 | 2025-11-20 13:56
87 | 116 | 9 | 2025-11-20 13:56
88 | 119 | 8 | 2025-11-20 13:56
89 | 120 | 10 | 2025-11-20 13:56
90 | 121 | 10 | 2025-11-20 13:56
91 | 122 | 10 | 2025-11-20 13:56
92 | 123 | 10 | 2025-11-20 13:56
93 | 124 | 10 | 2025-11-20 13:56
94 | 126 | 9 | 2025-11-20 13:56
95 | 127 | 9 | 2025-11-20 13:56
96 | 128 | 9 | 2025-11-20 13:56
97 | 129 | 9 | 2025-11-20 13:56
98 | 130 | 8 | 2025-11-20 13:56
99 | 131 | 8 | 2025-11-20 13:56
100 | 133 | 8 | 2025-11-20 13:56
101 | 134 | 8 | 2025-11-20 13:56
102 | 135 | 8 | 2025-11-20 13:56
103 | 136 | 8 | 2025-11-20 13:56
104 | 137 | 9 | 2025-11-20 13:56
105 | 138 | 10 | 2025-11-20 13:56
106 | 139 | 10 | 2025-11-20 13:56
107 | 140 | 10 | 2025-11-20 13:56
108 | 141 | 8 | 2025-11-20 13:56
109 | 145 | 8 | 2025-11-20 13:56
110 | 146 | 9 | 2025-11-20 13:56
111 | 147 | 9 | 2025-11-20 13:56
112 | 148 | 8 | 2025-11-20 13:56
113 | 149 | 9 | 2025-11-20 13:56
114 | 154 | 9 | 2025-11-20 13:56
115 | 155 | 4 | 2025-11-20 13:56
116 | 156 | 4 | 2025-11-20 13:56
117 | 157 | 4 | 2025-11-20 13:56
120 | 181 | 4 | 2025-11-20 13:56
121 | 189 | 4 | 2025-11-20 13:56
123 | 1 | 6 | 2025-11-20 15:17
124 | 72 | 6 | 2025-11-22 11:24
125 | 172 | 6 | 2025-11-22 11:35
126 | 6 | 2 | 2025-11-25 08:46
127 | 179 | 2 | 2025-11-25 12:01
128 | 197 | 6 | 2025-11-25 17:11
129 | 176 | 2 | 2025-11-25 20:45
130 | 198 | 13 | 2025-11-25 21:58
131 | 15 | 2 | 2025-11-25 22:00
132 | 7 | 13 | 2025-11-26 09:43
133 | 199 | 2 | 2025-11-27 08:50
134 | 202 | 9 | 2025-12-15 15:11
135 | 210 | 13 | 2025-12-18 12:59
136 | 205 | 13 | 2026-01-05 12:58
137 | 208 | 13 | 2026-01-13 17:06
138 | 213 | 5 | 2026-01-20 13:33
139 | 214 | 5 | 2026-01-20 13:37
140 | 215 | 5 | 2026-01-20 13:42
141 | 216 | 5 | 2026-01-20 13:44
142 | 60 | 20 | 2026-01-20 15:13
143 | 59 | 20 | 2026-01-20 15:16
144 | 61 | 20 | 2026-01-20 15:18
145 | 52 | 6 | 2026-01-21 16:50
146 | 217 | 9 | 2026-01-26 07:43
147 | 90 | 5 | 2026-01-27 07:22
148 | 218 | 2 | 2026-01-27 13:30
149 | 167 | 2 | 2026-01-28 10:06
151 | 219 | 13 | 2026-01-28 12:01
152 | 221 | 10 | 2026-01-30 11:16
153 | 222 | 10 | 2026-01-30 15:42
154 | 223 | 10 | 2026-01-30 15:50
155 | 224 | 10 | 2026-01-30 15:53
156 | 225 | 10 | 2026-01-30 16:00
157 | 226 | 10 | 2026-01-30 16:08
158 | 227 | 10 | 2026-01-30 17:26
159 | 228 | 10 | 2026-01-30 17:30
160 | 229 | 10 | 2026-01-30 17:32
161 | 230 | 10 | 2026-01-30 17:35
162 | 158 | 14 | 2026-02-02 08:36
163 | 99 | 8 | 2026-02-02 08:53
164 | 232 | 16 | 2026-02-04 21:19
165 | 234 | 8 | 2026-02-13 12:36
166 | 235 | 8 | 2026-02-13 16:15
167 | 236 | 8 | 2026-02-13 16:20
168 | 237 | 8 | 2026-02-13 16:25
169 | 239 | 8 | 2026-02-19 11:52
170 | 240 | 8 | 2026-02-19 11:55
171 | 241 | 15 | 2026-02-19 15:28
172 | 161 | 15 | 2026-02-19 16:29
175 | 243 | 15 | 2026-02-23 13:24
180 | 256 | 9 | 2026-02-24 11:34
181 | 245 | 15 | 2026-02-25 15:47
182 | 182 | 16 | 2026-03-02 13:53
183 | 258 | 4 | 2026-03-03 13:33
184 | 259 | 4 | 2026-03-03 13:42
185 | 260 | 9 | 2026-03-11 13:11

## PMOContacts
Id | ProjectId | UserId | CreatedAt
1 | 1 | 4 | 2025-11-21 18:31
2 | 123 | 37 | 2025-11-22 11:16
3 | 130 | 39 | 2025-11-22 11:20
4 | 179 | 1 | 2025-11-22 11:21
5 | 172 | 41 | 2025-11-22 11:35
7 | 6 | 1 | 2025-11-22 20:17
8 | 175 | 30 | 2025-11-22 21:50
9 | 7 | 5 | 2025-11-24 09:14
11 | 176 | 76 | 2025-11-25 20:45
12 | 15 | 31 | 2025-11-25 22:01
13 | 15 | 30 | 2025-11-25 22:01
14 | 15 | 32 | 2025-11-25 22:01
15 | 15 | 29 | 2025-11-25 22:01
16 | 15 | 1 | 2025-11-25 22:01
17 | 124 | 37 | 2025-11-27 08:29
18 | 199 | 1 | 2025-11-27 08:50
19 | 198 | 78 | 2025-11-27 09:02
20 | 1 | 2 | 2025-11-27 09:31
21 | 1 | 25 | 2025-11-27 09:31
22 | 1 | 7 | 2025-11-27 09:31
23 | 54 | 82 | 2025-11-27 10:16
24 | 54 | 84 | 2025-11-27 10:16
25 | 55 | 82 | 2025-11-27 10:30
26 | 55 | 84 | 2025-11-27 10:30
27 | 125 | 82 | 2025-11-27 10:31
28 | 125 | 84 | 2025-11-27 10:31
29 | 132 | 82 | 2025-11-27 10:34
30 | 132 | 84 | 2025-11-27 10:34
31 | 142 | 82 | 2025-11-27 10:43
32 | 142 | 84 | 2025-11-27 10:43
33 | 143 | 82 | 2025-11-27 10:44
34 | 143 | 84 | 2025-11-27 10:44
35 | 144 | 82 | 2025-11-27 10:45
36 | 144 | 84 | 2025-11-27 10:45
37 | 196 | 82 | 2025-11-27 10:46
38 | 196 | 84 | 2025-11-27 10:46
39 | 111 | 47 | 2025-11-27 11:03
40 | 96 | 47 | 2025-11-27 11:04
41 | 97 | 47 | 2025-11-27 11:06
42 | 93 | 47 | 2025-11-27 11:18
43 | 189 | 47 | 2025-11-27 11:19
45 | 121 | 40 | 2025-11-27 12:31
49 | 202 | 42 | 2025-12-15 15:11
51 | 204 | 42 | 2025-12-15 15:37
56 | 200 | 42 | 2025-12-18 11:36
57 | 209 | 42 | 2025-12-18 12:22
58 | 210 | 42 | 2025-12-18 12:59
59 | 156 | 94 | 2025-12-18 15:31
60 | 156 | 92 | 2025-12-18 15:31
61 | 156 | 93 | 2025-12-18 15:31
63 | 122 | 108 | 2026-01-05 15:20
64 | 62 | 37 | 2026-01-06 11:27
65 | 205 | 113 | 2026-01-06 14:19
66 | 46 | 113 | 2026-01-06 14:22
68 | 136 | 113 | 2026-01-06 14:40
69 | 134 | 113 | 2026-01-06 14:40
70 | 135 | 113 | 2026-01-06 14:41
71 | 153 | 113 | 2026-01-06 14:42
72 | 45 | 113 | 2026-01-06 14:42
73 | 133 | 113 | 2026-01-06 14:43
75 | 206 | 113 | 2026-01-07 15:13
76 | 207 | 113 | 2026-01-07 15:14
77 | 208 | 113 | 2026-01-07 15:15
78 | 203 | 41 | 2026-01-08 12:56
80 | 179 | 41 | 2026-01-08 12:56
81 | 179 | 125 | 2026-01-08 12:56
85 | 171 | 41 | 2026-01-08 13:11
87 | 19 | 41 | 2026-01-08 13:11
88 | 19 | 125 | 2026-01-08 13:11
89 | 80 | 41 | 2026-01-08 13:17
91 | 169 | 41 | 2026-01-08 13:17
93 | 170 | 41 | 2026-01-08 13:18
95 | 199 | 41 | 2026-01-08 13:19
96 | 199 | 125 | 2026-01-08 13:19
97 | 174 | 41 | 2026-01-08 13:19
98 | 174 | 125 | 2026-01-08 13:19
99 | 137 | 41 | 2026-01-08 13:20
101 | 173 | 41 | 2026-01-08 13:21
102 | 173 | 125 | 2026-01-08 13:21
103 | 138 | 41 | 2026-01-08 13:26
104 | 138 | 125 | 2026-01-08 13:26
105 | 180 | 41 | 2026-01-08 13:27
106 | 180 | 125 | 2026-01-08 13:27
107 | 168 | 41 | 2026-01-08 13:28
108 | 168 | 125 | 2026-01-08 13:28
109 | 176 | 41 | 2026-01-08 13:30
110 | 176 | 125 | 2026-01-08 13:30
111 | 15 | 41 | 2026-01-08 13:30
112 | 15 | 125 | 2026-01-08 13:30
113 | 177 | 41 | 2026-01-08 13:31
114 | 177 | 125 | 2026-01-08 13:31
115 | 175 | 41 | 2026-01-08 13:31
116 | 175 | 125 | 2026-01-08 13:31
117 | 178 | 125 | 2026-01-08 13:32
119 | 178 | 41 | 2026-01-08 13:32
121 | 160 | 134 | 2026-01-13 15:05
122 | 161 | 134 | 2026-01-13 15:06
125 | 163 | 134 | 2026-01-13 15:07
126 | 205 | 138 | 2026-01-13 17:03
127 | 205 | 114 | 2026-01-13 17:04
128 | 206 | 138 | 2026-01-13 17:05
129 | 206 | 114 | 2026-01-13 17:05
130 | 207 | 138 | 2026-01-13 17:05
131 | 207 | 114 | 2026-01-13 17:05
132 | 208 | 138 | 2026-01-13 17:06
133 | 208 | 114 | 2026-01-13 17:06
134 | 160 | 139 | 2026-01-15 14:44
136 | 161 | 139 | 2026-01-15 14:47
139 | 163 | 139 | 2026-01-15 14:50
140 | 4 | 92 | 2026-01-15 16:03
141 | 4 | 93 | 2026-01-15 16:03
142 | 205 | 101 | 2026-01-15 16:13
143 | 206 | 101 | 2026-01-15 16:13
144 | 207 | 101 | 2026-01-15 16:14
145 | 208 | 101 | 2026-01-15 16:14
146 | 213 | 166 | 2026-01-20 13:33
147 | 213 | 167 | 2026-01-20 13:33
148 | 214 | 166 | 2026-01-20 13:37
149 | 214 | 167 | 2026-01-20 13:37
150 | 90 | 166 | 2026-01-20 13:37
151 | 90 | 167 | 2026-01-20 13:37
152 | 91 | 166 | 2026-01-20 13:38
153 | 91 | 167 | 2026-01-20 13:38
154 | 92 | 166 | 2026-01-20 13:39
155 | 92 | 167 | 2026-01-20 13:39
156 | 89 | 166 | 2026-01-20 13:39
157 | 89 | 167 | 2026-01-20 13:39
160 | 215 | 166 | 2026-01-20 13:42
161 | 215 | 167 | 2026-01-20 13:42
162 | 216 | 166 | 2026-01-20 13:44
163 | 216 | 167 | 2026-01-20 13:44
169 | 64 | 169 | 2026-01-22 18:30
170 | 64 | 83 | 2026-01-22 18:30
172 | 44 | 83 | 2026-01-22 18:31
173 | 16 | 171 | 2026-01-22 18:33
174 | 16 | 83 | 2026-01-22 18:33
175 | 126 | 164 | 2026-01-26 07:12
176 | 126 | 181 | 2026-01-26 07:12
177 | 26 | 181 | 2026-01-26 07:12
179 | 154 | 164 | 2026-01-26 07:13
180 | 154 | 181 | 2026-01-26 07:13
181 | 146 | 164 | 2026-01-26 07:14
182 | 146 | 181 | 2026-01-26 07:14
183 | 147 | 181 | 2026-01-26 07:14
184 | 147 | 164 | 2026-01-26 07:14
185 | 116 | 164 | 2026-01-26 07:15
186 | 116 | 181 | 2026-01-26 07:15
191 | 128 | 183 | 2026-01-26 07:33
192 | 128 | 182 | 2026-01-26 07:33
193 | 127 | 182 | 2026-01-26 07:34
194 | 127 | 183 | 2026-01-26 07:34
195 | 217 | 182 | 2026-01-26 07:43
196 | 84 | 184 | 2026-01-26 07:56
197 | 82 | 185 | 2026-01-26 07:58
199 | 83 | 187 | 2026-01-26 08:01
200 | 3 | 92 | 2026-01-26 13:38
201 | 3 | 93 | 2026-01-26 13:38
202 | 2 | 92 | 2026-01-26 13:42
203 | 2 | 93 | 2026-01-26 13:43
204 | 5 | 93 | 2026-01-26 13:46
205 | 5 | 92 | 2026-01-26 13:46
206 | 152 | 192 | 2026-01-26 16:51
207 | 152 | 193 | 2026-01-26 16:51
208 | 150 | 193 | 2026-01-26 16:52
209 | 150 | 192 | 2026-01-26 16:52
210 | 151 | 192 | 2026-01-26 16:53
211 | 151 | 193 | 2026-01-26 16:53
212 | 32 | 192 | 2026-01-26 16:53
213 | 32 | 193 | 2026-01-26 16:53
214 | 86 | 193 | 2026-01-26 16:54
215 | 86 | 192 | 2026-01-26 16:54
216 | 31 | 192 | 2026-01-26 16:54
217 | 31 | 193 | 2026-01-26 16:54
218 | 33 | 192 | 2026-01-26 16:55
219 | 33 | 193 | 2026-01-26 16:55
220 | 34 | 193 | 2026-01-26 16:56
221 | 34 | 192 | 2026-01-26 16:56
222 | 36 | 192 | 2026-01-26 16:56
223 | 36 | 193 | 2026-01-26 16:56
224 | 35 | 193 | 2026-01-26 16:57
225 | 35 | 192 | 2026-01-26 16:57
226 | 37 | 192 | 2026-01-26 16:58
227 | 37 | 193 | 2026-01-26 16:58
228 | 115 | 193 | 2026-01-26 16:59
229 | 115 | 192 | 2026-01-26 16:59
230 | 88 | 193 | 2026-01-26 16:59
231 | 88 | 192 | 2026-01-26 16:59
233 | 218 | 41 | 2026-01-27 13:30
234 | 219 | 21 | 2026-01-28 12:04
235 | 6 | 23 | 2026-01-29 11:28
236 | 87 | 212 | 2026-01-29 13:17
237 | 87 | 216 | 2026-01-29 13:17
238 | 56 | 212 | 2026-01-29 13:19
239 | 56 | 216 | 2026-01-29 13:19
240 | 220 | 42 | 2026-01-30 10:52
241 | 221 | 42 | 2026-01-30 11:16
242 | 222 | 42 | 2026-01-30 15:42
243 | 223 | 42 | 2026-01-30 15:50
244 | 224 | 42 | 2026-01-30 15:53
245 | 225 | 42 | 2026-01-30 16:00
246 | 226 | 42 | 2026-01-30 16:08
247 | 227 | 42 | 2026-01-30 17:26
248 | 228 | 42 | 2026-01-30 17:30
249 | 229 | 42 | 2026-01-30 17:32
250 | 230 | 42 | 2026-01-30 17:35
251 | 158 | 40 | 2026-02-02 08:36
252 | 99 | 39 | 2026-02-02 08:53
253 | 153 | 115 | 2026-02-02 15:58
254 | 133 | 115 | 2026-02-02 15:59
255 | 45 | 115 | 2026-02-02 16:37
256 | 136 | 115 | 2026-02-02 16:57
257 | 134 | 115 | 2026-02-02 17:03
258 | 135 | 115 | 2026-02-02 17:09
259 | 46 | 115 | 2026-02-02 17:16
268 | 117 | 57 | 2026-02-04 15:10
269 | 182 | 57 | 2026-02-04 15:11
270 | 188 | 57 | 2026-02-04 15:12
271 | 185 | 57 | 2026-02-04 15:13
272 | 232 | 57 | 2026-02-05 09:27
273 | 43 | 167 | 2026-02-05 11:41
275 | 233 | 82 | 2026-02-10 09:33
276 | 233 | 84 | 2026-02-10 14:05
277 | 167 | 41 | 2026-02-10 16:28
278 | 234 | 386 | 2026-02-13 12:36
279 | 235 | 390 | 2026-02-13 16:15
281 | 237 | 392 | 2026-02-13 16:25
282 | 141 | 108 | 2026-02-17 10:38
284 | 238 | 113 | 2026-02-18 13:56
285 | 238 | 115 | 2026-02-18 13:56
286 | 239 | 249 | 2026-02-19 11:52
287 | 239 | 444 | 2026-02-19 11:52
288 | 240 | 447 | 2026-02-19 11:55
289 | 240 | 249 | 2026-02-19 11:55
290 | 241 | 134 | 2026-02-19 15:28
291 | 241 | 139 | 2026-02-19 15:28
300 | 243 | 134 | 2026-02-23 13:23
301 | 243 | 139 | 2026-02-23 13:23
310 | 254 | 134 | 2026-02-23 14:27
311 | 254 | 139 | 2026-02-23 14:27
312 | 255 | 134 | 2026-02-23 14:29
313 | 255 | 139 | 2026-02-23 14:29
314 | 236 | 249 | 2026-02-24 14:36
315 | 236 | 390 | 2026-02-24 14:36
316 | 237 | 249 | 2026-02-24 14:37
317 | 234 | 249 | 2026-02-24 14:38
318 | 164 | 134 | 2026-02-25 13:41
319 | 164 | 139 | 2026-02-25 13:41
320 | 244 | 134 | 2026-02-25 13:44
321 | 244 | 139 | 2026-02-25 13:44
322 | 162 | 134 | 2026-02-25 13:46
323 | 162 | 139 | 2026-02-25 13:46
324 | 242 | 134 | 2026-02-25 13:48
325 | 242 | 139 | 2026-02-25 13:48
326 | 159 | 134 | 2026-02-25 13:50
327 | 159 | 139 | 2026-02-25 13:50
332 | 245 | 134 | 2026-02-26 08:55
333 | 245 | 139 | 2026-02-26 08:55
334 | 246 | 134 | 2026-03-02 13:50
335 | 246 | 139 | 2026-03-02 13:50
336 | 252 | 134 | 2026-03-02 14:40
337 | 252 | 139 | 2026-03-02 14:40
338 | 248 | 134 | 2026-03-02 14:43
339 | 248 | 139 | 2026-03-02 14:43
340 | 250 | 134 | 2026-03-02 14:44
341 | 250 | 139 | 2026-03-02 14:44
342 | 186 | 57 | 2026-03-02 15:57
343 | 257 | 42 | 2026-03-02 17:33
344 | 18 | 37 | 2026-03-05 07:49
345 | 122 | 487 | 2026-03-05 13:39
346 | 211 | 108 | 2026-03-05 13:39
347 | 211 | 487 | 2026-03-05 13:40
348 | 141 | 487 | 2026-03-05 13:40
349 | 149 | 183 | 2026-03-05 14:11
350 | 149 | 182 | 2026-03-05 14:11
351 | 256 | 183 | 2026-03-05 14:12
352 | 256 | 182 | 2026-03-05 14:12
353 | 43 | 166 | 2026-03-10 08:41
354 | 39 | 490 | 2026-03-10 15:37
357 | 52 | 113 | 2026-03-11 15:09

## Milestones
Id | ObjectiveId | ProjectId | FipsId | ProductDocumentId | Name | Description | BusinessArea | OwnerUserId | OwnerEmail | BaselineDueDate | DueDate | ActualDate | Status | ProgressPercent | ExternalRef | Notes | IsDeleted | CreatedAt | UpdatedAt
3 |  | 1 |  |  | Migrate BuRT | Migrate and decommission the BuRT |  |  |  |  | 2025-11-24 | 2025-11-27 | complete | 100 |  | Migration of core information completed and phased rollout with Funding, Data, and Families group. | False | 2025-10-31 11:12 | 2025-11-28 09:13
4 |  | 1 |  |  | Complete pilot with Families group, EDFO and EDS | Run a pilot through November for delivery and operational reporting. |  |  |  |  | 2025-12-31 |  | complete | 100 |  |  | False | 2025-11-04 09:46 | 2026-01-05 14:51
5 |  | 6 |  |  | MVP Phase 1 - Central Operations Beta | Beta phase with the Central Operations team and diary study. |  |  |  |  | 2025-12-05 | 2025-12-04 | complete | 100 |  |  | False | 2025-11-12 15:10 | 2025-12-04 13:00
6 | 11 | 197 |  |  | Service Manual | Phase 1 to include DDT standards and guidance for service assessments and applying the Service Standard to be migrated into the Service Manual. |  |  |  |  | 2026-06-30 |  | in_progress | 5 |  |  | False | 2025-11-25 21:11 | 2025-12-02 11:09
7 |  | 15 |  |  | Standards migration | Migrate all the guidance and content around standards, including: - Apply the Service Standard - Find and use standards |  |  |  |  | 2026-03-13 |  | in_progress | 75 |  | 2 Dec 2025 - Standards migrated to COMPASS from CMS | False | 2025-12-02 09:24 | 2026-02-21 16:39
8 |  | 72 |  |  | FEAT Beta Launch | Ed chat – Private Beta launch planned with circa 200 DfE colleagues for 4 – 6 weeks planned – Beta focus is on colleagues in policy, strategy, legislation, grants, and finance profession but trial open to all. |  |  |  |  | 2026-02-28 |  | in_progress |  |  |  | False | 2025-12-09 14:08 | 2026-02-03 13:45
9 |  | 72 |  |  | Ed chat – user research with Private Beta users | [5 empty] | 2026-02-28 | 2026-02-28 | in_progress |  |  |  | False | 2025-12-09 14:08 | 2026-02-03 13:56
10 |  | 209 |  |  | Provide MVP | OFFICIAL SENSITIVE - details redacted |  |  |  |  | 2026-03-31 |  | in_progress |  |  | As this is an OFFSEN project we are unable to detail everything on the project and it's aims on this card - if further details are needed please contact Sharon Thompson | False | 2025-12-18 12:25 | 2026-01-07 16:40
11 |  | 1 |  |  | January reporting to be commissioned to be delivered on COMPASS | Provide training and complete next reporting phase on COMPASS. As part of this process Divisional Worklists will be confirmed with DDs. |  |  |  |  | 2026-01-23 | 2026-01-26 | complete | 100 |  |  | False | 2026-01-05 14:57 | 2026-02-05 08:05
12 |  | 205 |  |  | Submission of DSIT business case for initial funding (FY25/26) | DSIT have provided 3m up front to get the programme through discovery and PoC. We need to provide a short form DSIT business case process to formalise this. |  |  |  |  | 2025-12-01 | 2025-12-12 | complete | 100 |  |  | False | 2026-01-05 15:32 | 2026-01-05 15:32
13 |  | 205 |  |  | Submission of DfE business case | Business case needed to support the programme through FY26/27 |  |  |  |  | 2026-03-31 |  | in_progress | 20 |  |  | False | 2026-01-05 15:34 | 2026-03-02 11:31
14 |  | 205 |  |  | Comms strategy & plan - sign-off and publish | Work being completed on the comms action plan for the programme. This is a key piece of work as the programme will need well planned and informative comms to convince stakeholders of the aims and benefits of the Data Spine. |  |  |  |  | 2026-03-27 |  | in_progress | 10 |  |  | False | 2026-01-07 14:42 | 2026-03-02 11:32
15 |  | 205 |  |  | Programme plan preparation and agreement | The high-level programme planning phase has been successfully completed. Detailed workstream planning remains in progress due to the inherent complexity of individual workstreams. Each workstream requires careful consideration to ensure alignment with overall programme objectives and to address specific dependencies and risks. |  |  |  |  | 2026-03-31 |  | on_track | 95 |  |  | False | 2026-01-07 14:53 | 2026-03-02 16:04
16 |  | 206 |  |  | Architecture & Data Principles Agreed | "1) Architecture principles are enduring rules and guidelines that govern how systems, processes, and technologies are designed and implemented. 2) Data principles are basic rules for handling data. They guide how data is collected, managed, shared, and used responsibly, and provide a foundation for data governance and strategy." |  |  |  |  | 2026-03-31 |  | on_track | 65 |  | The initial milestone is complete but will be continually re-iterated throughout the discovery and PoC phase | False | 2026-01-07 15:24 | 2026-01-07 15:30
17 |  | 206 |  |  | Review existing data collection and analysis | AS IS data domain and data flows mapped. |  |  |  |  | 2026-03-31 |  | on_track | 65 |  | The initial milestone is complete but will be continually re-iterated throughout the discovery and PoC phase | False | 2026-01-07 15:26 | 2026-01-07 15:26
18 |  | 206 |  |  | Conceptual data model | A blueprint for aligning data structure and flow with business objectives, ensuring stakeholder alignment before transitioning to a logical data model. |  |  |  |  | 2026-03-31 |  | on_track | 65 |  | The initial milestone is complete but will be continually re-iterated throughout the discovery and PoC phase | False | 2026-01-07 15:27 | 2026-01-07 15:29
19 |  | 206 |  |  | Data flow analysis and design | Showing the future-state data domains and how data flows between them |  |  |  |  | 2026-03-31 |  | on_track | 65 |  | The initial milestone is complete but will be continually re-iterated throughout the discovery and PoC phase | False | 2026-01-07 15:31 | 2026-01-07 15:33
20 |  | 206 |  |  | High level design (and LLD) | Provides a broad overview of a system's architecture, components, and their interactions. |  |  |  |  | 2026-02-20 |  | complete | 75 |  | The initial milestone is complete but will be continually re-iterated throughout the discovery and PoC phase | False | 2026-01-07 15:32 | 2026-03-02 11:38
21 |  | 206 |  |  | Logical data model | Representation of an organisation's data that focuses on the business concepts and rules |  |  |  |  | 2026-03-31 |  | not_started | 0 |  |  | False | 2026-01-07 15:36 | 2026-01-07 15:36
22 |  | 206 |  |  | Strategic architecture and roadmap | Development of robust strategic and architecture plans beyond March 26 to scale the data spine and playback to perm sec and key stakeholders. |  |  |  |  | 2026-03-31 |  | not_started | 0 |  |  | False | 2026-01-07 15:37 | 2026-01-07 15:37
23 |  | 207 |  |  | Commercial Agreements for WONDE | DPIA/DSAP to be in place for data access MAT sharing agreement Wonde access and costs confirmed |  |  |  |  | 2026-03-30 |  | in_progress | 85 |  |  | False | 2026-01-07 15:49 | 2026-03-02 11:33
24 |  | 207 |  |  | Design approval | Confirms that the data model, data flows and related documentation are complete, reviewed, and approved for the MIS/Wonde workstream. |  |  |  |  | 2026-01-30 |  | complete | 100 |  |  | False | 2026-01-07 15:50 | 2026-02-04 08:32
25 |  | 207 |  |  | Infrastructure built & tested | Infrastructure tested and built for the PoC & VYED |  |  |  |  | 2026-03-16 |  | on_track | 70 |  |  | False | 2026-01-07 15:52 | 2026-03-02 16:04
26 |  | 207 |  |  | Build PoC & Test & Learn | Build data pipeline using existing attendance data infrastructure and leverage current components. Ingest data via MIS /Quality checking / Data model Test & learn approach for Wonde datasets |  |  |  |  | 2026-03-20 |  | on_track | 10 |  |  | False | 2026-01-07 15:53 | 2026-01-07 15:55
27 |  | 207 |  |  | Playback to users | Demonstrating the value outcomes for the Education sector through improved data insights to perm sec and key stakeholders. |  |  |  |  | 2026-03-31 |  | not_started | 0 |  |  | False | 2026-01-07 15:55 | 2026-01-07 15:55
28 |  | 208 |  |  | Commercial agreement | DPIA to be in place for EdTech data access Engagement with industry being worked on with Policy and Commercial |  |  |  |  | 2026-03-31 |  | in_progress |  |  |  | False | 2026-01-07 16:01 | 2026-03-02 11:39
29 |  | 208 |  |  | Data access | Demonstrate data available which is relevant to learning outcomes, and how the data can be collected effectively and compliantly, with indicators of possible analysis with such data |  |  |  |  | 2026-03-31 |  | not_started |  |  |  | False | 2026-01-07 16:02 | 2026-01-07 16:02
30 |  | 208 |  |  | Playback to users | Demonstrating the value outcomes for the Education sector through improved data insights to perm sec and key stakeholders. |  |  |  |  | 2026-03-31 |  | not_started |  |  |  | False | 2026-01-07 16:03 | 2026-01-07 16:03
33 |  | 18 |  |  | Accelerate CMDB continuous improvement | The CMDB programme with FlyForm is focused on maturing DfE’s configuration management by strengthening discovery, improving data quality, aligning services to the Common Service Data Model, and enabling service mapping for 5 top services to build a reliable, value‑driven CMDB foundation that supports wider digital transformation and meets the requirements for Digital Asset status by March 2026 |  |  |  |  | 2026-03-31 |  | on_track | 25 |  |  | False | 2026-01-21 10:36 | 2026-01-21 10:36
34 |  | 1 |  |  | Reports Development. | Develop analytical reports for use by central PMO and divisions. Feedback has been requested from divisions as to what would be helpful. |  |  |  |  | 2026-03-31 |  | in_progress | 50 |  |  | False | 2026-01-27 11:02 | 2026-02-23 10:49
35 |  | 219 |  |  | First pass at tool - excel based | First draft of tool in excel to be tested and used, once its stable and the questions / priorities / weighting are stable will look to migrate into COMPASS |  |  |  |  | 2026-02-02 |  | complete | 100 |  |  | False | 2026-01-28 12:02 | 2026-03-02 07:36
36 |  | 219 |  |  | Prioritsation tool built in COMPASS after initital testing | migrate from excel based tool into COMPASS once tested and stabalised |  |  |  |  | 2026-06-01 |  | not_started | 0 |  |  | False | 2026-01-28 12:03 | 2026-01-28 12:03
37 |  | 213 |  |  | FDS Go Live | FDS Go Live date has been pushed back by Opex to April end. |  |  |  |  | 2026-04-30 |  | in_progress | 80 |  |  | False | 2026-01-28 16:45 | 2026-01-28 16:51
38 |  | 213 |  |  | CFS Go LIVE | CFS Go LIVE is planned to be in mid of May |  |  |  |  | 2026-05-15 |  | in_progress | 20 |  |  | False | 2026-01-28 16:46 | 2026-01-28 16:51
39 |  | 213 |  |  | FCS Tenancy Migration | FCS Tenancy migration has been planned to end of May |  |  |  |  | 2026-05-31 |  | in_progress | 10 |  | FCS migration slowly progressing. AT env migration has been given to the dev team to test. Still a couple of issues needed to be resolved. Started FCS - CI ENV Pipeline Migration. | False | 2026-01-28 16:48 | 2026-01-28 16:51
40 |  | 213 |  |  | MYESF Tenancy Migration | MYESF Tenancy Migration planned at the end of May |  |  |  |  | 2026-05-31 |  | in_progress | 10 |  | Listing down the Gap/Issues in Current MYESF Infra. Started on DocEx Data API - Pipeline Migration (Build / Platform / Deployment). Started on DocEx Func File Processor - Pipeline Migration (Build / Platform / Deployment) | False | 2026-01-28 16:50 | 2026-01-28 16:50
41 |  | 137 |  |  | Service Assessment | Private Beta assessment |  |  |  |  | 2026-02-10 |  | in_progress | 20 |  |  | False | 2026-01-29 16:11 | 2026-03-04 10:54
42 |  | 137 |  |  | Transition to NCS complete | [5 empty] | 2026-03-27 |  | in_progress | 80 |  |  | False | 2026-01-29 16:12 | 2026-03-04 11:14
43 |  | 171 |  |  | DSIT Campaign Live | [5 empty] | 2026-02-16 |  | complete | 100 |  |  | False | 2026-01-29 16:20 | 2026-02-25 13:10
44 |  | 218 |  |  | UR complete | [5 empty] | 2026-01-29 | 2026-01-29 | complete | 99 |  |  | False | 2026-01-29 16:33 | 2026-01-29 16:33
45 |  | 218 |  |  | UR analysis | Analysis session including the Devolved Union team and EPIC |  |  |  |  | 2026-02-03 |  | complete | 100 |  |  | False | 2026-01-29 16:33 | 2026-02-25 13:00
46 |  | 218 |  |  | Analysis written up and presented | Presentation to Devolved Union and wider team or UR findings and recommendations for pilot |  |  |  |  | 2026-02-12 |  | complete | 100 |  |  | False | 2026-01-29 16:34 | 2026-02-25 13:01
47 |  | 92 |  |  | Apprenticeship Agreement variations | Produce the annual Variation letters and Terms & Conditions for Apps Levy on or before 31st January 2026, so that the documents can be issues to providers on time. |  |  |  |  | 2026-01-31 | 2026-01-30 | complete | 100 |  |  | False | 2026-01-29 17:13 | 2026-03-10 09:03
48 |  | 92 |  |  | FCS application migration from .NET framework 4.8 to .NET 8.0 | Systematic update of FCS application which uses both .NET 4.8 and .NET 6.0 components. This milestone is for migrating the .NET 4.8 to .NET 8.0, by upgrading packages to versions that support .NET 8.0, resolving dependency conflicts, and validating that the solution builds and functions correctly after the updates. This work would include development, end to end testing and integration testing with upstream and downstream systems. |  |  |  |  | 2026-08-31 |  | in_progress |  |  | Dev in progress | False | 2026-01-29 17:47 | 2026-01-29 17:47
49 |  | 89 |  |  | Databricks to SQL Data Connectivity | Currently we are fetching provider data from GIAS, UKRLP and PIMS via AnM server. FDS has its own modeling area MA_FDPS_S_DATA in AnM server which use below views under RA_Datasets to fetch provider data. Now it has been discussed that all datasets in AnM server getting migrated to new ADA platform which is based in Azure Databricks Data Lake. FDS need to create connection to databricks so theat provider data can be pulled to FDS |  |  |  |  | 2026-04-04 |  | in_progress | 30 |  |  | False | 2026-01-30 13:22 | 2026-01-30 13:22
50 |  | 89 |  |  | Azure Tenancy Migration | FDS will be migrated to new S25 tenant. Opex has given a sign off for the migration at the end of April. FDS has already completed the migration in lower env . |  |  |  |  | 2026-05-08 |  | not_started | 70 |  |  | False | 2026-01-30 13:24 | 2026-01-30 13:24
51 |  | 89 |  |  | MAS and PIT data journey update | MAS and PIT will be onboarded into FDS |  |  |  |  | 2026-03-28 |  | not_started | 30 |  |  | False | 2026-01-30 13:25 | 2026-01-30 13:25
52 |  | 89 |  |  | Angular Version upgrade V19 to V21 | [5 empty] | 2026-02-16 | 2026-02-17 | complete | 100 |  |  | False | 2026-01-30 13:26 | 2026-03-06 10:34
53 |  | 89 |  |  | .Net Version upgrade from V8 to V10 | [5 empty] | 2026-02-16 | 2026-02-17 | complete | 100 |  |  | False | 2026-01-30 13:26 | 2026-03-06 10:35
54 |  | 91 |  |  | Multi Process memory optimization | [5 empty] | 2026-01-06 | 2026-01-06 | complete | 100 |  |  | False | 2026-01-30 13:30 | 2026-01-30 13:30
55 |  | 91 |  |  | Data Science Report Optimization | [5 empty] | 2026-01-06 | 2026-01-06 | complete | 100 |  |  | False | 2026-01-30 13:31 | 2026-01-30 13:31
56 |  | 91 |  |  | Barracuda WAF migration to UK South | [5 empty] | 2026-02-03 | 2026-02-03 | complete | 100 |  |  | False | 2026-01-30 13:31 | 2026-02-18 10:29
57 |  | 91 |  |  | Calculation Builder and Result Component Release | [5 empty] | 2026-02-17 | 2026-03-17 | complete | 100 |  |  | False | 2026-01-30 13:32 | 2026-02-18 10:28
58 |  | 133 |  |  | Migrate QRD data from EDAP SQL Server into Databricks | - Migrate QRD data from EDAP SQL Server into Databricks - Migrate and improve QRD "release" process, by removing R elements - Refactoring existing code into Databricks - Automating processes where possible - Standardising and documenting any manual steps still required (e.g discount code assignment) - Improve documentation and widen understanding |  |  |  |  | 2026-03-12 |  | not_started |  |  |  | False | 2026-02-02 14:47 | 2026-03-02 11:55
59 |  | 133 |  |  | Matching 2.0 - Incremental enhancements to components existing in preprod | - Enables CLDS 2.0 to go live - Incremental enhancements to Matching 2.0 components existing in preprod - Preparation for cutover activities - UI features to the Stewardship App 2.0 |  |  |  |  | 2026-02-27 |  | not_started |  |  |  | False | 2026-02-02 14:49 | 2026-02-02 14:49
60 |  | 133 |  |  | Run and Maintain | - KS2/KS4/16-18 Final - HESA |  |  |  |  | 2026-02-27 | 2026-02-26 | complete | 100 |  |  | False | 2026-02-02 14:50 | 2026-03-02 11:35
61 |  | 182 |  |  | Private Beta launched | [5 empty] | 2026-01-30 | 2026-01-30 | complete |  |  |  | False | 2026-02-02 15:41 | 2026-02-02 15:43
62 |  | 182 |  |  | Public Beta launch | [5 empty] | 2026-04-30 |  | in_progress | 60 |  |  | False | 2026-02-02 15:43 | 2026-03-02 13:46
63 |  | 153 |  |  | Go or Not Go Decision | 19th Feb we have a go/no go meeting with stakeholders to decide whether or not to proceed into the cutover to Databricks. Expecting that to go well based on where we are today. |  |  |  |  | 2026-02-19 |  | complete | 100 |  | Cutover to Databricks for first 3 datasets (SC Spring / ILR / APC) on track for end of March/start of April | False | 2026-02-02 16:08 | 2026-03-02 11:40
64 |  | 153 |  |  | Datasets ready for cutover | Build of other datasets ready for cutover |  |  |  |  | 2026-06-30 |  | in_progress |  |  |  | False | 2026-02-02 16:10 | 2026-02-02 16:10
65 |  | 153 |  |  | 50% Migration to Databricks | Next tranche of 7/8 datasets migrated over to Databricks (meaning around 50% complete in migration of CLDS 1.0 to CLDS 2.0) |  |  |  |  | 2026-06-30 |  | in_progress |  |  |  | False | 2026-02-02 16:17 | 2026-02-02 16:17
66 |  | 45 |  |  | Go/No Go Migration Decision | Go/No Go Migration Decision |  |  |  |  | 2026-03-23 |  | planned | 100 |  |  | False | 2026-02-02 16:40 | 2026-03-02 15:31
67 |  | 45 |  |  | Phase 1 Completion | [5 empty] | 2026-03-31 |  | in_progress |  |  |  | False | 2026-02-02 16:41 | 2026-02-02 16:42
68 |  | 188 |  |  | WebCAF self-assessment completed | [5 empty] | 2026-03-31 |  | in_progress |  |  |  | False | 2026-02-02 16:57 | 2026-02-02 16:57
69 |  | 136 |  |  | Feedback cut off date to MDP | Feedback cut-off date to MDP for late data amendments |  |  |  |  | 2026-02-27 |  | complete | 100 |  |  | False | 2026-02-02 16:58 | 2026-03-02 09:55
70 |  | 134 |  |  | KS2 Final ADU Sign Off | From ADU KS2 to AAD KS2 |  |  |  |  | 2026-03-24 |  | in_progress |  |  |  | False | 2026-02-02 17:04 | 2026-03-02 10:13
71 |  | 135 |  |  | Finish final delivery cycle | [5 empty] | 2026-03-31 |  | in_progress |  |  |  | False | 2026-02-02 17:10 | 2026-02-02 17:10
72 |  | 135 |  |  | Plan for new academic year | [5 empty] | 2026-03-31 |  | not_started |  |  |  | False | 2026-02-02 17:11 | 2026-02-02 17:11
73 |  | 135 |  |  | AAD 2.0 Migrations to Databricks | AAD 2.0 migrations over to data bricks including EDAP |  |  |  |  | 2026-03-31 |  | in_progress |  |  |  | False | 2026-02-02 17:12 | 2026-02-02 17:12
74 |  | 135 |  |  | New Academic Year’s dry run (June Unamended) | New Academic Year’s dry run (June Unamended) |  |  |  |  | 2026-04-30 |  | in_progress |  |  |  | False | 2026-02-02 17:12 | 2026-02-02 17:12
75 |  | 135 |  |  | Conclude June Unamended delivery cycle | Conclude June Unamended delivery cycle (May) |  |  |  |  | 2026-05-31 |  | in_progress |  |  |  | False | 2026-02-02 17:13 | 2026-02-02 17:13
76 |  | 46 |  |  | Upload revised 16-18 data onto portal | Upload revised 16-18 data onto portal |  |  |  |  | 2026-02-05 | 2026-02-05 | complete | 100 |  |  | False | 2026-02-02 17:18 | 2026-02-19 12:04
77 |  | 46 |  |  | Required: CYPMD Data Files (Summary Data) | From AAD 16-18 to DCI |  |  |  |  | 2026-03-09 |  | not_started |  |  |  | False | 2026-02-02 17:19 | 2026-03-02 10:46
78 |  | 52 |  |  | Breakfast Clubs | Automate daily collection of breakfast club data to replace manual forms and provide high-quality data for funding decisions. |  |  |  |  | 2026-09-30 |  | in_progress |  |  |  | False | 2026-02-02 17:35 | 2026-02-25 21:14
79 |  | 52 |  |  | Inclusion Dashboard | Users can monitor individual pupils for attendance, including vulnerability characteristics like movement, inclusion, and attending school in a different LA |  |  |  |  | 2026-09-30 |  | in_progress |  |  |  | False | 2026-02-02 17:37 | 2026-02-02 17:37
80 |  | 52 |  |  | Methodology Alignment - Discovery | Support and implement including improved similar schools methodology |  |  |  |  | 2026-03-31 |  | in_progress |  |  |  | False | 2026-02-02 17:37 | 2026-02-24 14:53
81 |  | 52 |  |  | Similar Schools - User Research | User research on the needs for similar schools reports |  |  |  |  | 2026-02-27 | 2026-02-23 | complete | 100 |  |  | False | 2026-02-02 17:38 | 2026-02-26 09:51
82 |  | 52 |  |  | Independent Schools | Give independent schools the option to participate in the attendance daily data submission with MVP data quality and reporting. LA users can see learners who moved into the independent sector |  |  |  |  | 2026-07-31 |  | not_started |  |  |  | False | 2026-02-02 17:39 | 2026-02-25 13:10
83 |  | 52 |  |  | Transition Reports | Use daily Attendance Data, to improve attendance for pupils who need additional focus/support during their transition from primary to secondary school. |  |  |  |  | 2026-03-25 |  | in_progress | 80 |  |  | False | 2026-02-02 17:40 | 2026-02-26 09:52
84 |  | 186 |  |  | First iteration of Data Standards published | [5 empty] | 2026-03-31 |  | in_progress |  |  |  | False | 2026-02-02 20:52 | 2026-02-02 20:52
85 |  | 186 |  |  | Data Contacts for Data Governance appointed | [5 empty] | 2026-03-31 |  | in_progress |  |  |  | False | 2026-02-02 20:56 | 2026-02-02 20:56
86 |  | 186 |  |  | Single Data Asset Register delivered | [5 empty] | 2026-03-31 |  | in_progress |  |  |  | False | 2026-02-02 21:00 | 2026-02-02 21:00
87 |  | 17 |  |  | LA Single view dashboard go live | [5 empty] | 2026-02-28 | 2026-02-23 | complete | 100 |  |  | False | 2026-02-03 12:47 | 2026-02-25 15:10
88 |  | 17 |  |  | Data to Insight (Merton) Ingest | [5 empty] | 2026-03-31 |  | in_progress |  |  |  | False | 2026-02-03 12:48 | 2026-02-25 15:11
89 |  | 17 |  |  | Benchmarking Dashboard go live | [5 empty] | 2026-04-13 |  | in_progress |  |  |  | False | 2026-02-03 12:49 | 2026-02-25 15:12
90 |  | 17 |  |  | Build your Own (Newcastle & Central Bedfordshire & Bath) Ingest | [5 empty] | 2026-03-31 |  | in_progress |  |  |  | False | 2026-02-03 12:49 | 2026-02-25 15:13
91 |  | 17 |  |  | Phase 2 LAs | [5 empty] | 2026-06-30 |  | in_progress |  |  |  | False | 2026-02-03 12:50 | 2026-02-25 15:15
92 |  | 17 |  |  | Azeus LA (East Riding) | [5 empty] | 2026-03-31 |  | in_progress |  |  |  | False | 2026-02-03 12:51 | 2026-02-25 15:14
93 |  | 17 |  |  | System C LAs | [5 empty] | 2026-07-31 |  | in_progress |  |  |  | False | 2026-02-03 12:52 | 2026-02-25 15:16
94 |  | 72 |  |  | Agree and publish standard and first wave of technical guidance | [5 empty] | 2026-03-31 |  | not_started |  |  |  | False | 2026-02-03 13:58 | 2026-02-03 13:58
95 |  | 72 |  |  | Discovery for AI service offer | [5 empty] | 2026-03-31 |  | not_started |  |  |  | False | 2026-02-03 13:58 | 2026-02-03 13:58
96 |  | 71 |  |  | Target Architecture widely communicated | [5 empty] | 2026-03-20 |  | not_started |  |  |  | False | 2026-02-03 14:16 | 2026-03-02 09:16
97 |  | 71 |  |  | Tech Strategy published | [5 empty] | 2026-03-31 |  | not_started |  |  |  | False | 2026-02-03 14:16 | 2026-02-03 14:16
98 |  | 71 |  |  | Tech Strategy published (Cancelled - duplicated in error) | [5 empty] | 2026-03-31 |  | not_started |  |  |  | False | 2026-02-03 14:16 | 2026-02-04 11:06
99 |  | 71 |  |  | Tech Strategy published (Cancelled - duplicated in error) | [5 empty] | 2026-03-31 |  | not_started |  |  |  | False | 2026-02-03 14:16 | 2026-02-04 11:06
100 |  | 65 |  |  | Continue to develop and publish standards. | [5 empty] | 2026-03-31 |  | not_started |  |  |  | False | 2026-02-03 14:54 | 2026-02-03 14:54
101 |  | 65 |  |  | Embed and socialize the development of standards into BAU. | [5 empty] | 2026-03-31 |  | not_started |  |  |  | False | 2026-02-03 14:55 | 2026-02-03 14:55
102 |  | 57 |  |  | Strategy engagement and comms with DDT SLT, DDT All Staff and communities of practice to ensure awareness. | [5 empty] | 2026-01-30 |  | not_started |  |  |  | False | 2026-02-03 15:10 | 2026-02-03 15:10
103 |  | 57 |  |  | Continue Strategy engagement | [5 empty] | 2026-02-27 |  | not_started |  |  |  | False | 2026-02-03 15:10 | 2026-02-03 15:10
104 |  | 57 |  |  | Workshop with key stakeholders to discuss the single tenancy options paper. | [5 empty] | 2026-03-31 |  | not_started |  |  |  | False | 2026-02-03 15:11 | 2026-02-03 15:11
105 |  | 207 |  |  | Commercial Agreements for MIS | DPIA/DSAP to be in place for data access MAT sharing agreement MIS access and costs confirmed |  |  |  |  | 2026-03-27 |  | in_progress | 10 |  |  | False | 2026-02-04 14:26 | 2026-03-02 16:04
107 |  | 64 |  |  | Complete GDS Peer Review (incl. Tech Assessment)​ | A GDS peer review is a lightweight assurance activity used in UK government digital delivery. It comes from the Government Digital Service (GDS) framework and is designed to check how well a team is progressing against the Service Standard, but without the formality of a full service assessment. |  |  |  |  | 2026-01-19 | 2026-01-19 | complete | 100 |  | Delivered as planned. Detailed and constructive feedback received to support Public Beta readiness.​ | False | 2026-02-05 12:25 | 2026-02-05 12:25
108 |  | 64 |  |  | Conduct Accessibility Audit & Update Plan​ | An accessibility audit is a formal evaluation of a digital product—such as a website, mobile app, document, or software—to determine how well it meets the needs of people with disabilities and complies with established accessibility standards. |  |  |  |  | 2026-02-06 | 2026-02-24 | complete | 100 |  | Audit must complete prior to Public Beta to meet service standard point 5. ‘Make sure everyone can use the service’​ | False | 2026-02-05 12:27 | 2026-02-27 16:58
109 |  | 64 |  |  | Private Beta Service Assessment​ | A Private Beta Service Assessment is a formal GOV.UK Service Standard assessment that takes place at the end of the private beta phase of a digital service. |  |  |  |  | 2026-02-11 | 2026-02-24 | complete | 100 |  | The MyEE Team actively preparing and responding to Peer Review actions.​ | False | 2026-02-05 12:30 | 2026-02-27 16:59
110 |  | 64 |  |  | MyEE Public Beta Release​ | The public beta release is the stage in the service lifecycle where MyEE will become open to anyone who needs it, after being tested and refined during private beta. |  |  |  |  | 2026-02-25 | 2026-02-25 | complete | 100 |  | New features will be deployed to production and the service made available to all responsible bodies.​ | False | 2026-02-05 12:32 | 2026-02-27 16:58
111 |  | 16 |  |  | New feature delivery, enabling users to track their progress and update the status of recommendations through the service | Number of recommendations for users to meet have been significantly reduced to a core set of recommendations. Each recommendation provided to users have a status against it, which users can update as improvements are made against recommendations. These pages can be printed for reporting purposes. |  |  |  |  | 2025-11-12 | 2025-11-12 | complete | 100 |  |  | False | 2026-02-16 09:36 | 2026-02-16 09:36
112 |  | 16 |  |  | MATs can access and update status of recommendations for schools in their Trust | Feature to extend access to MATs to begin or continue self-assessments for schools within their Trust, and view progress updates for schools in their Trust. |  |  |  |  | 2025-11-12 | 2025-11-12 | complete | 100 |  |  | False | 2026-02-16 09:59 | 2026-02-16 09:59
113 |  | 16 |  |  | Publication of new IT Support Standards | Development and publication of a new set of standards for schools and colleges on what good IT support looks like. This supports the sector to have effective IT support, supporting schools and colleges to have secure, reliable and up-dated technology. |  |  |  |  | 2025-11-17 | 2025-11-17 | complete | 100 |  |  | False | 2026-02-16 10:03 | 2026-02-16 10:03
114 |  | 167 |  |  | FUI product build complete for provate beta | [5 empty] | 2026-02-20 | 2026-02-20 | complete | 100 |  |  | False | 2026-02-24 12:48 | 2026-02-24 12:48
115 |  | 167 |  |  | Start User Acceptance testing for FUI | [5 empty] | 2026-03-11 | 2026-03-11 | in_progress |  |  |  | False | 2026-02-24 12:49 | 2026-03-11 14:55
116 |  | 167 |  |  | Start FUI pilot with selected portfolios | [5 empty] | 2026-04-02 |  | not_started |  |  |  | False | 2026-02-24 12:51 | 2026-03-11 14:57
117 |  | 167 |  |  | End FUI pilot with selected portfolios | [5 empty] | 2026-05-12 |  | not_started |  |  |  | False | 2026-02-24 12:52 | 2026-02-24 12:52
118 |  | 167 |  |  | Private Beta Service Assessment | [5 empty] | 2026-06-02 |  | not_started |  |  |  | False | 2026-02-24 14:00 | 2026-03-11 14:56
119 |  | 52 |  |  | Ofsted | Implementing a data share protocol every half-term for Daily Attendance Data. Will convert into BAU report after Similar Schools Report is issued. |  |  |  |  | 2026-03-03 |  | in_progress | 99 |  |  | False | 2026-02-24 14:52 | 2026-02-25 13:04
120 |  | 52 |  |  | Heatmaps - Discovery | Validate the usefulness, feasibility and scope of a school level attendance heatmap by understanding user needs, defining the MVP, and mapping technical requirements to deliver. |  |  |  |  | 2026-03-03 |  | in_progress | 50 |  |  | False | 2026-02-24 16:03 | 2026-02-25 13:00
121 |  | 239 |  |  | Finalised build for MVP Phase 1 - secondary schools | [5 empty] | 2026-04-24 |  | in_progress | 60 |  |  | False | 2026-02-25 13:17 | 2026-02-25 13:18
122 |  | 239 |  |  | Rolled out MVP Phase 1 to a controlled group of pilot users (group 1) | [5 empty] | 2026-03-16 |  | not_started |  |  |  | False | 2026-02-25 13:19 | 2026-02-25 13:19
123 |  | 239 |  |  | Rolled out MVP Phase 1 to the next set of controlled group of pilot users (group 2) | [5 empty] | 2026-05-25 |  | not_started |  |  |  | False | 2026-02-25 13:21 | 2026-02-25 13:21
124 |  | 239 |  |  | Finalised build for MVP phase 1 - primary schools | [5 empty] | 2026-05-11 |  | not_started |  |  |  | False | 2026-02-25 13:21 | 2026-02-25 13:21
125 |  | 122 |  |  | Launch of Content Store Public Beta | [5 empty] | 2026-03-31 |  | in_progress |  |  | Aim to launch public of content store service by end of March 2026 to coincide with AI Tutors market engagement activities | False | 2026-02-25 20:52 | 2026-02-25 20:54
126 |  | 122 |  |  | Launch of Public Beta | [5 empty] | 2026-03-31 |  | not_started |  |  | Aim to launch public of content store service by end of March 2026 to coincide with AI Tutors market engagement activities | False | 2026-02-25 20:52 | 2026-02-25 20:52
127 |  | 46 |  |  | KS4 Dynamic Form Live on Zendesk | [5 empty] | 2025-06-06 | 2025-06-06 | complete | 100 |  |  | False | 2026-02-26 09:58 | 2026-02-26 10:21
128 |  | 46 |  |  | KS2 Dynamic Form Updates live on Zendesk | [5 empty] | 2025-08-26 | 2025-08-26 | complete | 100 |  |  | False | 2026-02-26 09:58 | 2026-02-26 10:22
129 |  | 46 |  |  | KS4 Aut & 16-18 Dynamic Form live on Zendesk | [5 empty] | 2025-09-30 | 2025-09-30 | complete | 100 |  |  | False | 2026-02-26 09:59 | 2026-02-26 10:22
130 |  | 46 |  |  | KS4 Aut & 16-18 Dynamic Form live on Zendesk | [5 empty] | 2025-09-30 | 2025-09-30 | complete | 100 |  |  | False | 2026-02-26 09:59 | 2026-02-26 10:22
131 |  | 46 |  |  | KS4 Comms and Guidance Launch | [5 empty] | 2025-04-28 | 2025-04-28 | complete | 100 |  |  | False | 2026-02-26 10:00 | 2026-02-26 10:21
132 |  | 46 |  |  | DCI - KS4 Live | [5 empty] | 2025-06-16 | 2025-06-16 | complete | 100 |  |  | False | 2026-02-26 10:02 | 2026-02-26 10:21
133 |  | 46 |  |  | DCI - KS2 Live | [5 empty] | 2025-09-08 | 2025-09-08 | complete | 100 |  |  | False | 2026-02-26 10:02 | 2026-02-26 10:22
134 |  | 46 |  |  | DCI - KS4 & 16-18 Live | [5 empty] | 2025-10-06 | 2025-10-06 | complete | 100 |  |  | False | 2026-02-26 10:03 | 2026-02-26 10:23
135 |  | 136 |  |  | Required: KS4 Final Data Files (using Final Data) | [5 empty] | 2026-03-03 |  | in_progress |  |  |  | False | 2026-03-02 09:51 | 2026-03-02 09:51
136 |  | 136 |  |  | CYPMD Data Files (Data TBC) | Fro0m AAD 16-18 to CYPMD |  |  |  |  | 2026-03-10 |  | in_progress |  |  |  | False | 2026-03-02 09:52 | 2026-03-02 09:52
137 |  | 136 |  |  | Delivery of final data to ADU | Pupil Allocations, KS4 Prior Attainment, Pupil Indicators, Exam, Pub, Raw Data Files, Inst flags + pupil aims |  |  |  |  | 2026-03-11 |  | in_progress |  |  |  | False | 2026-03-02 09:55 | 2026-03-02 09:55
138 |  | 136 |  |  | 16-18 Final data files signed off by ADU | [5 empty] | 2026-03-25 |  | in_progress |  |  |  | False | 2026-03-02 09:58 | 2026-03-02 09:58
139 |  | 136 |  |  | NPD 16-18 Final Data Files | From AAD 16-18 to NPD |  |  |  |  | 2026-03-20 |  | in_progress |  |  |  | False | 2026-03-02 09:59 | 2026-03-02 09:59
140 |  | 136 |  |  | Retain version of 24/25 source data | From AAD 16-18 to AAD 16-18 |  |  |  |  | 2026-03-20 |  | in_progress |  |  |  | False | 2026-03-02 10:00 | 2026-03-02 10:00
141 |  | 136 |  |  | CSCP Publication Day | Live |  |  |  |  | 2026-03-26 |  | in_progress |  |  |  | False | 2026-03-02 10:01 | 2026-03-02 10:02
142 |  | 136 |  |  | NPD 16-18 Final Data Files to add to spine | From AAD 16-18 to MDP |  |  |  |  | 2026-03-27 |  | not_started |  |  |  | False | 2026-03-02 10:01 | 2026-03-02 10:01
143 |  | 136 |  |  | CSCP Publication Day | Live |  |  |  |  | 2026-04-23 |  | in_progress |  |  |  | False | 2026-03-02 10:02 | 2026-03-02 10:02
144 |  | 134 |  |  | KS2 Final outputs (pupil, results, raw, pub, scdb) | From AAD KS2 to ADU KS2 |  |  |  |  | 2026-03-17 |  | in_progress |  |  |  | False | 2026-03-02 10:07 | 2026-03-02 10:07
145 |  | 134 |  |  | KS2 Final LA CSVs | From AAD KS2 to ADU KS2 |  |  |  |  | 2026-03-17 |  | in_progress |  |  |  | False | 2026-03-02 10:08 | 2026-03-02 10:08
146 |  | 134 |  |  | NPD KS2 Final Data Files | From AAD KS2 to NPD |  |  |  |  | 2026-03-25 |  | in_progress |  |  |  | False | 2026-03-02 10:08 | 2026-03-02 10:08
147 |  | 134 |  |  | NPD KS2 Final Data Files to add to spine | From AAD KS2 to MDP |  |  |  |  | 2026-03-25 |  | in_progress |  |  |  | False | 2026-03-02 10:09 | 2026-03-02 10:09
148 |  | 134 |  |  | Retain version of 24/25 source data | From AAD KS2 to AAD KS2 |  |  |  |  | 2026-03-25 |  | in_progress |  |  |  | False | 2026-03-02 10:13 | 2026-03-02 10:13
149 |  | 134 |  |  | GIAP/ASP KS2 Final Data Files | From ADU KS2 to ASP |  |  |  |  | 2026-03-25 |  | in_progress |  |  |  | False | 2026-03-02 10:14 | 2026-03-02 10:14
150 |  | 134 |  |  | CSCP Final Data Files | From ADU KS2 to CSCP |  |  |  |  | 2026-03-25 |  | in_progress |  |  |  | False | 2026-03-02 10:14 | 2026-03-02 10:14
151 |  | 134 |  |  | KS2 Ofsted Final Data Files | From ADU KS2 to Ofsted |  |  |  |  | 2026-04-01 |  | in_progress |  |  |  | False | 2026-03-02 10:15 | 2026-03-02 10:15
152 |  | 46 |  |  | Go Live: 16-18 Retention Data available on Website | From CYPMD to Schools/Colleges |  |  |  |  | 2026-03-16 |  | not_started |  |  |  | False | 2026-03-02 10:47 | 2026-03-02 10:47
153 |  | 133 |  |  | HESA Final - NPD | From MDP to NPD |  |  |  |  | 2026-02-27 | 2026-02-26 | complete | 100 |  |  | False | 2026-03-02 10:52 | 2026-03-02 11:33
154 |  | 133 |  |  | HESA Final (Current & Historic) - YPMAD | From MDP to YPMAD |  |  |  |  | 2026-02-27 |  | complete | 100 |  |  | False | 2026-03-02 10:55 | 2026-03-02 11:29
155 |  | 133 |  |  | Load SCDB 1 | From Reference Data Team to AODC |  |  |  |  | 2026-03-06 |  | not_started |  |  |  | False | 2026-03-02 10:56 | 2026-03-02 10:56
156 |  | 133 |  |  | KS4 June Additions/Mergers/Removals finalised specs required | [5 empty] | 2026-03-02 |  | not_started |  |  |  | False | 2026-03-02 10:57 | 2026-03-02 10:57
157 |  | 117 |  |  | SME governance and cyber action plan discovery | [5 empty] | 2026-04-30 |  | not_started |  |  |  | False | 2026-03-02 22:44 | 2026-03-02 22:44
158 |  | 117 |  |  | SME governance and cyber action plan discovery | [5 empty] | 2026-04-30 |  | not_started |  |  |  | False | 2026-03-02 22:44 | 2026-03-02 22:44
159 |  | 232 |  |  | Portfolio Self Assessment completed | Portfolios to complete and return self assessments |  |  |  |  | 2026-01-31 | 2026-01-31 | complete | 100 |  |  | False | 2026-03-02 23:30 | 2026-03-02 23:30
160 |  | 232 |  |  | Red teaming | Red teaming exercise undertaken |  |  |  |  | 2025-12-31 | 2025-12-31 | complete | 100 |  |  | False | 2026-03-02 23:31 | 2026-03-02 23:31
161 |  | 232 |  |  | Red teaming | Red teaming exercise undertaken |  |  |  |  | 2025-12-31 | 2025-12-31 | complete | 100 |  |  | False | 2026-03-02 23:31 | 2026-03-02 23:31
162 |  | 232 |  |  | Department consolidated Security Assessment Report | An final over report detailing the departments consolidated security assessment position as a result of the portfolio assessment work |  |  |  |  | 2026-03-31 |  | in_progress | 40 |  |  | False | 2026-03-02 23:34 | 2026-03-02 23:34
163 |  | 232 |  |  | Portfolio Security Assessment Reports | A report for each portfolio detailing the outcome of the assessment work, highlighting strengths and good practice and identifying area for improvement and non-compliance with expected security standards |  |  |  |  | 2026-03-31 |  | in_progress | 40 |  |  | False | 2026-03-02 23:37 | 2026-03-02 23:37
164 |  | 117 |  |  | Cyber Assurance Return (CAR) output shared with stakeholders | Annual assurance exercise to establish the cyber maturity and posture of out ALBs. The return is a light version of Gov Assure based on the 5 CAF domains. The first return was completed in late 2025 and we have analysed and evaluated the returns. |  |  |  |  | 2026-04-30 |  | in_progress | 75 |  |  | False | 2026-03-03 14:10 | 2026-03-03 14:10
165 |  | 117 |  |  | Cyber Assurance Return (CAR) output shared with stakeholders | Annual assurance exercise to establish the cyber maturity and posture of out ALBs. The return is a light version of Gov Assure based on the 5 CAF domains. The first return was completed in late 2025 and we have analysed and evaluated the returns. |  |  |  |  | 2026-04-30 |  | in_progress | 75 |  |  | False | 2026-03-03 14:10 | 2026-03-03 14:10
166 |  | 117 |  |  | Cyber Assurance Return (CAR) output shared with stakeholders | Annual assurance exercise to establish the cyber maturity and posture of out ALBs. The return is a light version of Gov Assure based on the 5 CAF domains. The first return was completed in late 2025 and we have analysed and evaluated the returns. |  |  |  |  | 2026-04-30 |  | in_progress | 75 |  |  | False | 2026-03-03 14:10 | 2026-03-03 14:10
167 | 10 | 229 |  |  | GIAA team interviews | GIAA auditors will be interviewing colleagues as part of the overall review |  |  |  |  | 2026-03-20 |  | in_progress |  |  |  | False | 2026-03-09 16:07 | 2026-03-09 16:07
168 |  | 229 |  |  | Final Report Date | [5 empty] | 2026-03-20 |  | on_track |  |  |  | False | 2026-03-09 16:38 | 2026-03-09 16:38
169 |  | 228 |  |  | Draft AI principles presented to DDT committee for review | [5 empty] | 2026-03-23 |  | in_progress |  |  |  | False | 2026-03-09 16:43 | 2026-03-09 16:43
170 |  | 224 |  |  | Co-ordinate cross government engagement | [5 empty] | 2026-03-27 |  | on_track |  |  |  | False | 2026-03-09 16:48 | 2026-03-09 16:48
171 |  | 224 |  |  | Co-ordinate development of measurable plans and monitor delivery | [5 empty] | 2026-04-27 |  | in_progress |  |  |  | False | 2026-03-09 16:49 | 2026-03-09 16:49
172 |  | 224 |  |  | Establish cross departmental AI working group | [5 empty] | 2026-04-27 |  | not_started |  |  |  | False | 2026-03-09 16:50 | 2026-03-09 16:50
173 |  | 223 |  |  | John Kelly takes over as CDO | - |  |  |  |  | 2026-05-04 |  | in_progress |  |  |  | False | 2026-03-11 11:33 | 2026-03-11 11:33
174 |  | 223 |  |  | Data Spine Delivery Responsibility Moves to EDI | Responsibility for delivery of data spine moving over to EDI under Pragya and Corrine. |  |  |  |  | 2026-03-30 |  | on_track |  |  |  | False | 2026-03-11 11:37 | 2026-03-11 11:37
175 |  | 223 |  |  | Strategy & Transformation takes over responsibility for the Data Spine Steering Group | [5 empty] | 2026-04-24 |  | in_progress |  |  |  | False | 2026-03-11 11:38 | 2026-03-11 11:38
176 |  | 223 |  |  | SEND DDT Project Mapping Deliverables shared with SLT | Share of project register and project map |  |  |  |  | 2026-03-27 |  | in_progress |  |  |  | False | 2026-03-11 11:41 | 2026-03-11 11:41
177 |  | 223 |  |  | Prep for New CDO | Align on Data Strategy Approach Identify Priorities Gap analysis on capabilities Identify possible role needs |  |  |  |  | 2026-05-04 |  | not_started |  |  |  | False | 2026-03-11 11:42 | 2026-03-11 11:42
178 |  | 223 |  |  | Deliver Data R&D Updates | Maintain a regular update to Ian K on the data R&D projects being funded |  |  |  |  | 2026-06-01 |  | in_progress |  |  |  | False | 2026-03-11 11:50 | 2026-03-11 11:50
179 |  | 167 |  |  | End pilot | Pilot period ends |  |  |  |  | 2026-05-12 |  | not_started |  |  |  | False | 2026-03-11 14:59 | 2026-03-11 15:01
180 |  | 230 |  |  | Introductory Launch | Make sure everyone understands what DfE’s DDaT Strategy is and why it matters |  |  |  |  | 2026-04-30 |  | not_started |  |  |  | False | 2026-03-12 08:09 | 2026-03-12 08:13
181 |  | 230 |  |  | Phase 1 – Build early engagement | Encourage people to interact, ask questions and relate the strategy to their work |  |  |  |  | 2026-06-30 |  | not_started |  |  |  | False | 2026-03-12 08:10 | 2026-03-12 08:10
182 |  | 230 |  |  | Phase 2 – Participation and momentum | Show real examples, increase contributions, build champions |  |  |  |  | 2026-09-30 |  | not_started |  |  |  | False | 2026-03-12 08:11 | 2026-03-12 08:11
183 |  | 230 |  |  | Phase 3 – Embedding and normalising | Make the strategy part of everyday work and decision‑making |  |  |  |  | 2026-12-31 |  | not_started |  |  |  | False | 2026-03-12 08:12 | 2026-03-12 08:12
184 |  | 230 |  |  | Phase 4 – Sustain, celebrate and improve | Strengthen long‑term adoption and celebrate success |  |  |  |  | 2027-03-31 |  | not_started |  |  |  | False | 2026-03-12 08:12 | 2026-03-12 08:12
185 |  | 230 |  |  | Phase 4 – Sustain, celebrate and improve | Strengthen long‑term adoption and celebrate success |  |  |  |  | 2027-03-31 |  | not_started |  |  |  | False | 2026-03-12 08:12 | 2026-03-12 08:12

## MilestoneUpdates
Id | MilestoneId | UpdateDetails | PreviousStatus | NewStatus | PreviousProgress | NewProgress | UpdatedByEmail | UpdatedByName | UpdatedAt
1 | 3 | Progress changed from 0% to 80% |  |  |  | 80 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-21 14:32
2 | 3 | Due date changed from 01 Dec 2025 to 24 Nov 2025 |  |  |  |  | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-21 14:32
3 | 3 | Actual date set to 27 Nov 2025 |  |  |  |  | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-28 09:11
4 | 3 | Progress changed from 80% to 100% |  |  | 80 | 100 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-28 09:11
5 | 3 | Notes updated |  |  |  |  | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-28 09:12
6 | 3 | Status changed from 'in progress' to 'complete' | in_progress | complete |  |  | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-28 09:13
7 | 7 | Notes updated |  |  |  |  | Andy.JONES@education.gov.uk | JONES, Andy | 2025-12-02 09:25
8 | 7 | Standards migrated to COMPASS from CMS and worked through designing the view of standard information. | in_progress |  | 30 |  | Andy.JONES@education.gov.uk | JONES, Andy | 2025-12-02 09:41
9 | 6 | Name changed from 'Phase 1 - Standards and Assessments' to 'Service Manual' |  |  |  |  | Andy.JONES@education.gov.uk | JONES, Andy | 2025-12-02 11:09
10 | 6 | Due date changed from 31 Jan 2026 to 30 Jun 2026 |  |  |  |  | Andy.JONES@education.gov.uk | JONES, Andy | 2025-12-02 11:09
11 | 5 | Actual date set to 04 Dec 2025 |  |  |  |  | Andy.JONES@education.gov.uk | JONES, Andy | 2025-12-04 13:00
12 | 5 | Due date changed from 05 Nov 2025 to 05 Dec 2025 |  |  |  |  | Andy.JONES@education.gov.uk | JONES, Andy | 2025-12-04 13:00
13 | 5 | Progress changed from 90% to 100% |  |  | 90 | 100 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-12-04 13:00
14 | 5 | Status changed from 'in progress' to 'complete' | in_progress | complete |  |  | Andy.JONES@education.gov.uk | JONES, Andy | 2025-12-04 13:00
15 | 5 | Pilot and diary study completed with the DesignOps team. | complete |  | 100 |  | Andy.JONES@education.gov.uk | JONES, Andy | 2025-12-04 13:00
16 | 4 | Due date changed from 05 Dec 2025 to 31 Dec 2025 |  |  |  |  | Andy.JONES@education.gov.uk | JONES, Andy | 2025-12-06 18:55
17 | 4 | Progress changed from 0% to 50% |  |  |  | 50 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-12-06 18:55
18 | 8 | Status changed from 'not started' to 'in progress' | not_started | in_progress |  |  | Tracey.DALE@EDUCATION.GOV.UK | DALE, Tracey | 2025-12-09 14:09
19 | 4 | Name changed from 'Complete pilot with Families group' to 'Complete pilot with Families group, EDFO and EDS' |  |  |  |  | Tracey.DALE@EDUCATION.GOV.UK | DALE, Tracey | 2025-12-10 11:06
20 | 4 | Progress changed from 50% to 75% |  |  | 50 | 75 | Tracey.DALE@EDUCATION.GOV.UK | DALE, Tracey | 2025-12-10 11:06
21 | 4 | Description updated |  |  |  |  | Tracey.DALE@EDUCATION.GOV.UK | DALE, Tracey | 2025-12-10 11:07
22 | 4 | Progress changed from 75% to 100% |  |  | 75 | 100 | Tracey.DALE@EDUCATION.GOV.UK | DALE, Tracey | 2026-01-05 14:50
23 | 4 | Status changed from 'in progress' to 'complete' | in_progress | complete |  |  | Tracey.DALE@EDUCATION.GOV.UK | DALE, Tracey | 2026-01-05 14:50
24 | 4 | Families and EDFO completed updates in November. Due to leave, EDS completed later in December but all done. There are some updates to be made in the families area in terms of deliverables lists, but feedback on the process and system was positive. | complete | complete | 100 |  | Tracey.DALE@EDUCATION.GOV.UK | DALE, Tracey | 2026-01-05 14:51
25 | 11 | Due date changed from 05 Jan 2026 to 23 Jan 2026 |  |  |  |  | Tracey.DALE@EDUCATION.GOV.UK | DALE, Tracey | 2026-01-05 14:57
26 | 14 | Status changed from 'in progress' to 'in progress' | in_progress | in_progress |  |  | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-01-07 14:43
27 | 18 | Due date changed from 31 Mar 0026 to 31 Mar 2026 |  |  |  |  | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-01-07 15:27
28 | 18 | Progress changed from 0% to 65% |  |  |  | 65 | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-01-07 15:27
29 | 18 | Notes updated |  |  |  |  | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-01-07 15:29
30 | 16 | Notes updated |  |  |  |  | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-01-07 15:30
31 | 19 | Description updated |  |  |  |  | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-01-07 15:33
32 | 20 | Description updated |  |  |  |  | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-01-07 15:34
33 | 23 | Due date changed from 07 Jan 2026 to 30 Jan 2026 |  |  |  |  | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-01-07 15:50
34 | 23 | Progress changed from 0% to 85% |  |  |  | 85 | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-01-07 15:50
35 | 26 | Due date changed from 07 Jan 2026 to 20 Mar 2026 |  |  |  |  | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-01-07 15:54
36 | 26 | Progress changed from 50% to 10% |  |  | 50 | 10 | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-01-07 15:55
37 | 27 | Status changed from 'on track' to 'not started' | on_track | not_started |  |  | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-01-07 15:55
38 | 10 | Status changed from 'in progress' to 'in progress' | in_progress | in_progress |  |  | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-01-07 16:40
39 | 7 | Due date changed from 16 Jan 2026 to 28 Feb 2026 |  |  |  |  | Andy.JONES@education.gov.uk | JONES, Andy | 2026-01-13 12:13
40 | 7 | Progress changed from 30% to 0% |  |  | 30 | 0 | Andy.JONES@education.gov.uk | JONES, Andy | 2026-01-13 12:13
41 | 7 | Status changed from 'in progress' to 'not started' | in_progress | not_started |  |  | Andy.JONES@education.gov.uk | JONES, Andy | 2026-01-13 12:13
42 | 14 | Status changed from 'in progress' to 'at risk' | in_progress | at_risk |  |  | Sharon.THOMPSON@education.gov.uk | THOMPSON, Sharon | 2026-01-15 16:52
43 | 11 | Progress changed from 10% to 80% |  |  | 10 | 80 | Tracey.DALE@EDUCATION.GOV.UK | DALE, Tracey | 2026-01-21 14:21
44 | 11 | Milestone completed. Commission was issued as planned on Monday 26th January. | on_track | complete | 80 | 100 | Tracey.DALE@EDUCATION.GOV.UK | DALE, Tracey | 2026-01-27 10:59
45 | 39 | Status changed from 'not started' to 'in progress' | not_started | in_progress |  |  | Lavanya.GANESULA@EDUCATION.GOV.UK | GANESULA, Lavanya | 2026-01-28 16:51
46 | 38 | Status changed from 'not started' to 'in progress' | not_started | in_progress |  |  | Lavanya.GANESULA@EDUCATION.GOV.UK | GANESULA, Lavanya | 2026-01-28 16:51
47 | 37 | Status changed from 'not started' to 'in progress' | not_started | in_progress |  |  | Lavanya.GANESULA@EDUCATION.GOV.UK | GANESULA, Lavanya | 2026-01-28 16:51
48 | 47 | Progress changed from 0% to 90% |  |  |  | 90 | Ravi.THIPPESWAMY@EDUCATION.GOV.UK | THIPPESWAMY, Ravi | 2026-01-29 17:14
49 | 15 | Due date changed from 12 Jan 2026 to 28 Feb 2026 |  |  |  |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-02-02 12:53
50 | 15 | 02-FEb: Planning progressing for the current activities as well as future state and way forward after the Proof of Concept. | on_track |  | 95 |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-02-02 12:54
51 | 61 | Actual date set to 30 Jan 2026 |  |  |  |  | Angela.SCALE@EDUCATION.GOV.UK | SCALE, Angela | 2026-02-02 15:43
52 | 67 | Name changed from 'Phase 1 Go Live' to 'Phase 1 Completion' |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-02-02 16:42
53 | 82 | Due date changed from 02 Feb 2026 to 31 Jul 2026 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-02 17:39
54 | 86 | Status changed from 'not started' to 'in progress' | not_started | in_progress |  |  | Angela.SCALE@EDUCATION.GOV.UK | SCALE, Angela | 2026-02-02 21:00
55 | 8 | Description updated |  |  |  |  | Louise.HAGUE@EDUCATION.GOV.UK | HAGUE, Louise | 2026-02-03 13:44
56 | 8 | Due date changed from 31 Jan 2026 to 28 Feb 2026 |  |  |  |  | Louise.HAGUE@EDUCATION.GOV.UK | HAGUE, Louise | 2026-02-03 13:45
57 | 9 | Due date changed from 09 Dec 2025 to 28 Feb 2026 |  |  |  |  | Louise.HAGUE@EDUCATION.GOV.UK | HAGUE, Louise | 2026-02-03 13:55
58 | 9 | Actual date set to 28 Feb 2026 |  |  |  |  | Louise.HAGUE@EDUCATION.GOV.UK | HAGUE, Louise | 2026-02-03 13:56
59 | 9 | Description updated |  |  |  |  | Louise.HAGUE@EDUCATION.GOV.UK | HAGUE, Louise | 2026-02-03 13:56
60 | 24 | COmpleted | on_track | complete | 85 | 100 | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-02-04 08:32
61 | 14 | Our new communications team is currently working on the re-planning, and we expect to have an updated timeline shortly this is due to a delay in the transition period when the former comms lead moved on. New team no in place and re-planning underway. Target completion is currently revised from 16 Jan to 28 Feb and remains at Risk as may move again due to re-planning efforts | at_risk |  | 80 | 10 | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-02-04 08:48
62 | 14 | Due date changed from 16 Jan 2026 to 27 Feb 2026 |  |  |  |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-02-04 08:48
63 | 98 | Name changed from 'Tech Strategy published' to 'Tech Strategy published (Cancelled - duplicated in error)' |  |  |  |  | Louise.HAGUE@EDUCATION.GOV.UK | HAGUE, Louise | 2026-02-04 10:36
64 | 98 | Name changed from 'Tech Strategy published (Cancelled - duplicated in error)' to 'Tech Strategy published (Cancelled - duplicated in error)' |  |  |  |  | Louise.HAGUE@EDUCATION.GOV.UK | HAGUE, Louise | 2026-02-04 11:06
65 | 99 | Name changed from 'Tech Strategy published' to 'Tech Strategy published (Cancelled - duplicated in error)' |  |  |  |  | Louise.HAGUE@EDUCATION.GOV.UK | HAGUE, Louise | 2026-02-04 11:06
66 | 99 | Due date changed from 31 Mar 2026 to 31 Mar 2026 |  |  |  |  | Louise.HAGUE@EDUCATION.GOV.UK | HAGUE, Louise | 2026-02-04 11:06
67 | 23 | Name changed from 'Commercial (MIS/Wonde) Agreements' to 'Commercial Agreements for WONDE' |  |  |  |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-02-04 14:24
68 | 23 | Description updated |  |  |  |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-02-04 14:24
69 | 23 | Due date changed from 30 Jan 2026 to 28 Feb 2026 |  |  |  |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-02-04 14:24
70 | 23 | WONDE DPIA currently in progress which a requirement for the Commercial agreement, | on_track | in_progress | 85 | 85 | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-02-04 14:25
71 | 105 | There are ongoing challenges with completing the MIS DPIA which may impact completing the Commercial Agreement by the end of Feb, therefore meaning this milestone is at risk of competing on time, | in_progress | at_risk | 10 | 10 | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-02-04 14:27
72 | 11 | Actual date set to 26 Jan 2026 |  |  |  |  | Jo.WRIGHT@EDUCATION.GOV.UK | WRIGHT, Jo | 2026-02-05 08:05
73 | 56 | Progress changed from 70% to 100% |  |  | 70 | 100 | Joe.YOUNG@EDUCATION.GOV.UK | YOUNG, Joe | 2026-02-11 14:08
74 | 56 | Name changed from 'Barracuda WAF migration to UK South' to 'Barracuda WAF migration to UK South' |  |  |  |  | Joe.YOUNG@EDUCATION.GOV.UK | YOUNG, Joe | 2026-02-18 10:27
75 | 56 | Status changed from 'in progress' to 'complete' | in_progress | complete |  |  | Joe.YOUNG@EDUCATION.GOV.UK | YOUNG, Joe | 2026-02-18 10:27
76 | 57 | Status changed from 'in progress' to 'complete' | in_progress | complete |  |  | Joe.YOUNG@EDUCATION.GOV.UK | YOUNG, Joe | 2026-02-18 10:28
77 | 57 | Progress changed from 60% to 100% |  |  | 60 | 100 | Joe.YOUNG@EDUCATION.GOV.UK | YOUNG, Joe | 2026-02-18 10:28
78 | 57 | Actual date set to 17 Mar 2026 |  |  |  |  | Joe.YOUNG@EDUCATION.GOV.UK | YOUNG, Joe | 2026-02-18 10:28
79 | 56 | Actual date set to 03 Feb 2026 |  |  |  |  | Joe.YOUNG@EDUCATION.GOV.UK | YOUNG, Joe | 2026-02-18 10:29
80 | 76 | Status changed from 'in progress' to 'complete' | in_progress | complete |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-02-19 12:03
81 | 76 | Actual date set to 05 Feb 2026 |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-02-19 12:03
82 | 76 | Progress changed from 0% to 100% |  |  |  | 100 | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-02-19 12:04
83 | 7 | Due date changed from 28 Feb 2026 to 13 Mar 2026 |  |  |  |  | Andy.JONES@education.gov.uk | JONES, Andy | 2026-02-21 16:38
84 | 7 | Progress changed from 0% to 75% |  |  | 0 | 75 | Andy.JONES@education.gov.uk | JONES, Andy | 2026-02-21 16:39
85 | 7 | Status changed from 'not started' to 'in progress' | not_started | in_progress |  |  | Andy.JONES@education.gov.uk | JONES, Andy | 2026-02-21 16:39
86 | 34 | Due date changed from 02 Mar 2026 to 31 Mar 2026 |  |  |  |  | Tracey.DALE@EDUCATION.GOV.UK | DALE, Tracey | 2026-02-23 10:48
87 | 34 | Due date changed from 31 Mar 2026 to 31 Mar 2026 |  |  |  |  | Tracey.DALE@EDUCATION.GOV.UK | DALE, Tracey | 2026-02-23 10:48
88 | 34 | Progress changed from 0% to 50% |  |  |  | 50 | Tracey.DALE@EDUCATION.GOV.UK | DALE, Tracey | 2026-02-23 10:48
89 | 34 | There are reports available, but this will be a continued area of development based on user feedback. | in_progress |  | 50 | 50 | Tracey.DALE@EDUCATION.GOV.UK | DALE, Tracey | 2026-02-23 10:49
90 | 115 | Name changed from 'STart User Acceptance testing' to 'Start User Acceptance testing for FUI' |  |  |  |  | Julie.JENKINS@EDUCATION.GOV.UK | JENKINS, Julie | 2026-02-24 12:49
91 | 83 | Description updated |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-24 14:52
92 | 80 | Description updated |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-24 14:53
93 | 81 | Description updated |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-24 14:54
94 | 82 | Description updated |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-24 14:54
95 | 119 | Description updated |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-24 16:39
96 | 119 | Due date changed from 24 Feb 2026 to 17 Mar 2026 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-24 16:39
97 | 119 | Progress changed from 0% to 90% |  |  |  | 90 | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-24 16:39
98 | 41 | Status changed from 'on track' to 'in progress' | on_track | in_progress |  |  | Kuldip.OSBORNE@EDUCATION.GOV.UK | OSBORNE, Kuldip | 2026-02-25 12:58
99 | 120 | Due date changed from 17 Mar 2026 to 03 Mar 2026 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 12:58
100 | 120 | Progress changed from 0% to 50% |  |  |  | 50 | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 12:58
101 | 41 | Service Assessment report has Ambers and a Red so will complete once those have been addressed. | in_progress | in_progress | 75 | 20 | Kuldip.OSBORNE@EDUCATION.GOV.UK | OSBORNE, Kuldip | 2026-02-25 12:59
102 | 120 | Notes updated |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 12:59
103 | 120 | Notes updated |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 13:00
104 | 120 | Team currently working on sizing, planning to playback at end of sprint (03.03.26), with intention of moving into next steps/agreed phase. | in_progress |  | 50 |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 13:00
105 | 45 | Analysis completed | on_track | complete | 20 | 100 | Kuldip.OSBORNE@EDUCATION.GOV.UK | OSBORNE, Kuldip | 2026-02-25 13:00
106 | 46 | Completed. | on_track | complete |  | 100 | Kuldip.OSBORNE@EDUCATION.GOV.UK | OSBORNE, Kuldip | 2026-02-25 13:01
107 | 119 | Due date changed from 17 Mar 2026 to 03 Mar 2026 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 13:03
108 | 119 | Progress changed from 90% to 99% |  |  | 90 | 99 | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 13:03
109 | 119 | Ofsted have latest DfE data but need to organise data on their side. | in_progress |  | 99 |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 13:04
110 | 41 | Status changed from 'in progress' to 'in progress' | in_progress | in_progress |  |  | Kuldip.OSBORNE@EDUCATION.GOV.UK | OSBORNE, Kuldip | 2026-02-25 13:05
111 | 41 | Progress changed from 20% to 90% |  |  | 20 | 90 | Kuldip.OSBORNE@EDUCATION.GOV.UK | OSBORNE, Kuldip | 2026-02-25 13:05
112 | 41 | One Amber for NCS to rectify | in_progress | in_progress | 90 | 80 | Kuldip.OSBORNE@EDUCATION.GOV.UK | OSBORNE, Kuldip | 2026-02-25 13:05
113 | 41 | Over-riding previous one as intended for a different project! Service Assessment report has Ambers and a Red so will complete once those have been addressed | in_progress | in_progress | 80 | 20 | Kuldip.OSBORNE@EDUCATION.GOV.UK | OSBORNE, Kuldip | 2026-02-25 13:08
114 | 43 | Status changed from 'not started' to 'in progress' | not_started | in_progress |  |  | Kuldip.OSBORNE@EDUCATION.GOV.UK | OSBORNE, Kuldip | 2026-02-25 13:09
115 | 43 | Progress changed from 75% to 100% |  |  | 75 | 100 | Kuldip.OSBORNE@EDUCATION.GOV.UK | OSBORNE, Kuldip | 2026-02-25 13:09
116 | 43 | DSIT campaign is now live and driving users to the campaign site. | in_progress | complete | 100 | 100 | Kuldip.OSBORNE@EDUCATION.GOV.UK | OSBORNE, Kuldip | 2026-02-25 13:10
117 | 82 | Currently on roadmap for later mid-year. | not_started |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 13:10
118 | 83 | Due date changed from 13 Mar 2026 to 25 Mar 2026 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 13:12
119 | 83 | Data Analyst planning QA process and awaiting capacity to test current process. Guidance update in draft. | in_progress |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 13:12
120 | 78 | Working with Comms & Engagement team to shape and invite for UR. Tech spec has been given to tech team to be able to start work. | in_progress |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 13:15
121 | 78 | Prep-work kicked off 23/02/26. Working with Comms & Engagement team to shape and invite for UR. Tech spec has been given to tech team to be able to start work. | in_progress |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 13:16
122 | 121 | Status changed from 'not started' to 'in progress' | not_started | in_progress |  |  | Lea.ALIPERTA@EDUCATION.GOV.UK | ALIPERTA, Lea | 2026-02-25 13:17
123 | 121 | Name changed from 'Completed development for MVP Phase 1 – Secondary schools' to 'Finalised build for MVP Phase 1 - secondary schools' |  |  |  |  | Lea.ALIPERTA@EDUCATION.GOV.UK | ALIPERTA, Lea | 2026-02-25 13:17
124 | 121 | Status changed from 'in progress' to 'in progress' | in_progress | in_progress |  |  | Lea.ALIPERTA@EDUCATION.GOV.UK | ALIPERTA, Lea | 2026-02-25 13:18
125 | 90 | Name changed from '• Build your Own (Newcastle & Central Bedfordshire & Bath) Ingest' to 'Build your Own (Newcastle & Central Bedfordshire & Bath) Ingest' |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 14:49
126 | 87 | Actual date set to 23 Feb 2026 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 15:10
127 | 87 | Progress changed from 0% to 100% |  |  |  | 100 | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 15:10
128 | 87 | Dashboard is now live. | in_progress | complete | 100 |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 15:10
129 | 88 | Waiting on data from Merton. | in_progress |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 15:11
130 | 89 | Due date changed from 31 Mar 2026 to 13 Apr 2026 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 15:11
131 | 89 | Resource capacity has shifted work - hoping to complete in April. | in_progress |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 15:12
132 | 90 | Policy has issued comms to all on 25/02/26. | in_progress |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 15:13
133 | 92 | Currently in pre-production, hoping it will be in production by mid-March. | in_progress |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 15:14
134 | 91 | Status changed from 'not started' to 'in progress' | not_started | in_progress |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 15:14
135 | 91 | Kick-off mtgs with 13 Phase 2 early adopters complete. | in_progress |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 15:15
136 | 93 | Status changed from 'not started' to 'in progress' | not_started | in_progress |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 15:16
137 | 93 | System C has started development work. | in_progress |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 15:16
138 | 125 | Status changed from 'not started' to 'in progress' | not_started | in_progress |  |  | Georgina.LANGLEY@education.gov.uk | LANGLEY, Georgina | 2026-02-25 20:53
139 | 125 | Name changed from 'Launch of Public Beta' to 'Launch of Content Store Public Beta' |  |  |  |  | Georgina.LANGLEY@education.gov.uk | LANGLEY, Georgina | 2026-02-25 20:54
140 | 78 | We may have additional avenues for recruiting user‑research participants. Local Authorities will need to be incorporated into our user‑research plan, and we are engaging with the Census team wherever possible for effective cross‑team collaboration. | in_progress |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-25 21:14
141 | 81 | Name changed from 'Similar Schools' to 'Similar Schools - User Research' |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 09:40
142 | 81 | Actual date set to 23 Feb 2026 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 09:40
143 | 81 | Due date changed from 30 Jun 2026 to 27 Feb 2026 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 09:40
144 | 81 | Progress changed from 0% to 100% |  |  |  | 100 | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 09:41
145 | 81 | User Research complete. Similar schools comparison report release (half termly and ongoing managed by Comms and Engagement). | not_started |  | 100 | 100 | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 09:48
146 | 83 | Progress changed from 0% to 60% |  |  |  | 60 | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 09:50
147 | 81 | Status changed from 'not started' to 'complete' | not_started | complete |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 09:51
148 | 83 | Progress changed from 60% to 80% |  |  | 60 | 80 | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 09:52
149 | 131 | Due date changed from 28 Apr 2026 to 28 Apr 2025 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:14
150 | 131 | Status changed from 'not started' to 'complete' | not_started | complete |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:14
151 | 131 | Actual date set to 28 Apr 2025 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:15
152 | 127 | Status changed from 'not started' to 'complete' | not_started | complete |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:15
153 | 127 | Due date changed from 06 Jun 2026 to 06 Jun 2025 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:15
154 | 127 | Actual date set to 06 Jun 2025 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:15
155 | 132 | Status changed from 'not started' to 'complete' | not_started | complete |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:16
156 | 132 | Due date changed from 16 Jun 2026 to 16 Jun 2025 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:16
157 | 132 | Actual date set to 16 Jun 2025 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:16
158 | 128 | Status changed from 'not started' to 'complete' | not_started | complete |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:16
159 | 128 | Due date changed from 26 Aug 2026 to 26 Aug 2025 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:16
160 | 128 | Actual date set to 26 Aug 2025 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:17
161 | 133 | Status changed from 'not started' to 'complete' | not_started | complete |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:17
162 | 133 | Due date changed from 08 Sep 2026 to 08 Sep 2025 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:17
163 | 133 | Actual date set to 08 Sep 2025 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:17
164 | 129 | Status changed from 'not started' to 'complete' | not_started | complete |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:18
165 | 129 | Due date changed from 30 Sep 2026 to 30 Sep 2025 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:18
166 | 129 | Actual date set to 30 Sep 2025 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:18
167 | 130 | Status changed from 'not started' to 'complete' | not_started | complete |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:18
168 | 130 | Due date changed from 30 Sep 2026 to 30 Sep 2025 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:18
169 | 130 | Actual date set to 30 Sep 2025 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:20
170 | 134 | Status changed from 'not started' to 'complete' | not_started | complete |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:20
171 | 134 | Due date changed from 06 Oct 2026 to 06 Oct 2025 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:20
172 | 134 | Actual date set to 06 Oct 2025 |  |  |  |  | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:20
173 | 131 | Progress changed from 0% to 100% |  |  |  | 100 | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:21
174 | 127 | Progress changed from 0% to 100% |  |  |  | 100 | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:21
175 | 127 | Progress changed from 100% to 100% |  |  | 100 | 100 | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:21
176 | 132 | Progress changed from 0% to 100% |  |  |  | 100 | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:21
177 | 128 | Progress changed from 0% to 100% |  |  |  | 100 | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:22
178 | 133 | Progress changed from 0% to 100% |  |  |  | 100 | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:22
179 | 129 | Progress changed from 0% to 100% |  |  |  | 100 | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:22
180 | 130 | Progress changed from 0% to 100% |  |  |  | 100 | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:22
181 | 134 | Progress changed from 0% to 100% |  |  |  | 100 | Amanda.STRINE@EDUCATION.GOV.UK | STRINE, Amanda | 2026-02-26 10:23
182 | 110 | Status changed from 'on track' to 'complete' | on_track | complete |  |  | Kathryn.KING@EDUCATION.GOV.UK | KING, Kathryn | 2026-02-27 16:56
183 | 108 | Audit completed ahead of Public Beta. Findings reviewed and prioritised, with remediation plan underway. | on_track | complete | 50 |  | Kathryn.KING@EDUCATION.GOV.UK | KING, Kathryn | 2026-02-27 16:57
184 | 108 | Progress changed from 50% to 100% |  |  | 50 | 100 | Kathryn.KING@EDUCATION.GOV.UK | KING, Kathryn | 2026-02-27 16:57
185 | 108 | Actual date set to 24 Feb 2026 |  |  |  |  | Kathryn.KING@EDUCATION.GOV.UK | KING, Kathryn | 2026-02-27 16:58
186 | 110 | Actual date set to 25 Feb 2026 |  |  |  |  | Kathryn.KING@EDUCATION.GOV.UK | KING, Kathryn | 2026-02-27 16:58
187 | 110 | Progress changed from 75% to 100% |  |  | 75 | 100 | Kathryn.KING@EDUCATION.GOV.UK | KING, Kathryn | 2026-02-27 16:58
188 | 109 | Status changed from 'on track' to 'complete' | on_track | complete |  |  | Kathryn.KING@EDUCATION.GOV.UK | KING, Kathryn | 2026-02-27 16:58
189 | 109 | Actual date set to 24 Feb 2026 |  |  |  |  | Kathryn.KING@EDUCATION.GOV.UK | KING, Kathryn | 2026-02-27 16:59
190 | 109 | Progress changed from 70% to 100% |  |  | 70 | 100 | Kathryn.KING@EDUCATION.GOV.UK | KING, Kathryn | 2026-02-27 16:59
191 | 35 | Status changed from 'in progress' to 'complete' | in_progress | complete |  |  | Jo.WRIGHT@EDUCATION.GOV.UK | WRIGHT, Jo | 2026-03-02 07:35
192 | 35 | Progress changed from 50% to 100% |  |  | 50 | 100 | Jo.WRIGHT@EDUCATION.GOV.UK | WRIGHT, Jo | 2026-03-02 07:36
193 | 96 | Due date changed from 27 Feb 2026 to 20 Mar 2026 |  |  |  |  | Luke.SLOWEN@EDUCATION.GOV.UK | SLOWEN, Luke | 2026-03-02 09:16
194 | 69 | Name changed from 'Delivery of final data' to 'Delivery of final data to ADU' |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 09:31
195 | 69 | Description updated |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 09:47
196 | 69 | Status changed from 'in progress' to 'complete' | in_progress | complete |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 09:47
197 | 69 | Progress changed from 0% to 100% |  |  |  | 100 | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 09:47
198 | 69 | Complete | complete |  | 100 |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 09:48
199 | 69 | Name changed from 'Delivery of final data to ADU' to 'Feedback cut off date to MDP' |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 09:55
200 | 141 | Description updated |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 10:02
201 | 70 | Description updated |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 10:10
202 | 70 | Due date changed from 27 Feb 2026 to 24 Mar 2026 |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 10:12
203 | 70 | Name changed from 'Delivery of Final Data' to 'KS2 Final ADU Sign Off' |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 10:13
204 | 77 | Name changed from 'Upload 16-18 Retention data' to 'Required: CYPMD Data Files (Summary Data)' |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 10:45
205 | 77 | Description updated |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 10:45
206 | 77 | Due date changed from 31 Mar 2026 to 09 Mar 2026 |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 10:46
207 | 153 | Due date changed from 27 Mar 2026 to 27 Feb 2026 |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 10:52
208 | 154 | Data is available for self serve | not_started | complete |  | 100 | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 11:29
209 | 13 | Due date changed from 27 Feb 2026 to 31 Mar 2026 |  |  |  |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-03-02 11:30
210 | 13 | Status changed from 'not started' to 'in progress' | not_started | in_progress |  |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-03-02 11:30
211 | 13 | Business case in progress. expected to go for submission late march/early April | in_progress | in_progress | 0 | 20 | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-03-02 11:31
212 | 14 | Due date changed from 27 Feb 2026 to 27 Mar 2026 |  |  |  |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-03-02 11:31
213 | 14 | Status changed from 'at risk' to 'in progress' | at_risk | in_progress |  |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-03-02 11:32
214 | 14 | To be presetned and signed off mid-March | in_progress |  | 10 |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-03-02 11:32
215 | 153 | Delivered | not_started | complete |  | 100 | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 11:33
216 | 23 | Due date changed from 28 Feb 2026 to 30 Mar 2026 |  |  |  |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-03-02 11:33
217 | 153 | Actual date set to 26 Feb 2026 |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 11:33
218 | 23 | T&Cs under review with Commercial, estimated 4 weeks to completion | in_progress |  | 85 |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-03-02 11:33
219 | 60 | Actual date set to 26 Feb 2026 |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 11:34
220 | 60 | KS2 - Delivered 13th Feb KS4 - Delivered 20th Feb 16-18 Final - Delivered 20th Feb | not_started | complete |  | 100 | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 11:35
221 | 66 | Go decision received | in_progress | complete |  | 100 | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 11:35
222 | 20 | Status changed from 'on track' to 'complete' | on_track | complete |  |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-03-02 11:38
223 | 28 | Status changed from 'not started' to 'in progress' | not_started | in_progress |  |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-03-02 11:39
224 | 28 | Due date changed from 27 Feb 2026 to 31 Mar 2026 |  |  |  |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-03-02 11:39
225 | 28 | delayed due to delayed engagement from EdTech providers | in_progress |  |  |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-03-02 11:39
226 | 63 | Go confirmation received | in_progress | complete |  | 100 | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 11:40
227 | 58 | Due date changed from 27 Feb 2026 to 10 Mar 2026 |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 11:40
228 | 58 | Due date changed from 10 Mar 2026 to 12 Mar 2026 |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 11:55
229 | 62 | Progress changed from 0% to 60% |  |  |  | 60 | Alison.Dunne@EDUCATION.GOV.UK | DUNNE, Alison | 2026-03-02 13:46
230 | 66 | Description updated |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 15:30
231 | 66 | Name changed from 'Go/No Go Migration Cutover' to 'Go/No Go Migration Decision' |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 15:30
232 | 66 | Status changed from 'complete' to 'planned' | complete | planned |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 15:31
233 | 66 | Due date changed from 27 Feb 2026 to 23 Feb 2026 |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 15:31
234 | 66 | Due date changed from 23 Feb 2026 to 23 Mar 2026 |  |  |  |  | Daniel.KUMAR@EDUCATION.GOV.UK | KUMAR, Daniel | 2026-03-02 15:31
235 | 105 | Due date changed from 27 Feb 2026 to 27 Mar 2026 |  |  |  |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-03-02 16:04
236 | 105 | Status changed from 'at risk' to 'in progress' | at_risk | in_progress |  |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-03-02 16:04
237 | 25 | Due date changed from 16 Feb 2026 to 16 Mar 2026 |  |  |  |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-03-02 16:04
238 | 15 | Due date changed from 28 Feb 2026 to 31 Mar 2026 |  |  |  |  | Lorraine.COLEY@EDUCATION.GOV.UK | COLEY, Lorraine | 2026-03-02 16:04
239 | 41 | Ambers for NCS to rectify | in_progress |  | 20 |  | Kuldip.OSBORNE@EDUCATION.GOV.UK | OSBORNE, Kuldip | 2026-03-04 10:54
240 | 42 | Progress changed from 20% to 80% |  |  | 20 | 80 | Kuldip.OSBORNE@EDUCATION.GOV.UK | OSBORNE, Kuldip | 2026-03-04 11:14
241 | 52 | Progress changed from 80% to 100% |  |  | 80 | 100 | Joe.YOUNG@EDUCATION.GOV.UK | YOUNG, Joe | 2026-03-06 10:33
242 | 52 | Status changed from 'not started' to 'complete' | not_started | complete |  |  | Joe.YOUNG@EDUCATION.GOV.UK | YOUNG, Joe | 2026-03-06 10:34
243 | 52 | Actual date set to 17 Feb 2026 |  |  |  |  | Joe.YOUNG@EDUCATION.GOV.UK | YOUNG, Joe | 2026-03-06 10:34
244 | 53 | Progress changed from 80% to 100% |  |  | 80 | 100 | Joe.YOUNG@EDUCATION.GOV.UK | YOUNG, Joe | 2026-03-06 10:35
245 | 53 | Status changed from 'not started' to 'complete' | not_started | complete |  |  | Joe.YOUNG@EDUCATION.GOV.UK | YOUNG, Joe | 2026-03-06 10:35
246 | 53 | Actual date set to 17 Feb 2026 |  |  |  |  | Joe.YOUNG@EDUCATION.GOV.UK | YOUNG, Joe | 2026-03-06 10:35
247 | 47 | Progress changed from 90% to 100% |  |  | 90 | 100 | Ravi.THIPPESWAMY@EDUCATION.GOV.UK | THIPPESWAMY, Ravi | 2026-03-10 09:03
248 | 47 | Status changed from 'in progress' to 'complete' | in_progress | complete |  |  | Ravi.THIPPESWAMY@EDUCATION.GOV.UK | THIPPESWAMY, Ravi | 2026-03-10 09:03
249 | 115 | Due date changed from 04 Mar 2026 to 11 Mar 2026 |  |  |  |  | Julie.JENKINS@EDUCATION.GOV.UK | JENKINS, Julie | 2026-03-11 14:54
250 | 115 | Actual date set to 11 Mar 2026 |  |  |  |  | Julie.JENKINS@EDUCATION.GOV.UK | JENKINS, Julie | 2026-03-11 14:55
251 | 115 | Status changed from 'not started' to 'in progress' | not_started | in_progress |  |  | Julie.JENKINS@EDUCATION.GOV.UK | JENKINS, Julie | 2026-03-11 14:55
252 | 118 | Due date changed from 24 Jun 2026 to 02 Jun 2026 |  |  |  |  | Julie.JENKINS@EDUCATION.GOV.UK | JENKINS, Julie | 2026-03-11 14:56
253 | 116 | Due date changed from 01 Apr 2026 to 02 Apr 2026 |  |  |  |  | Julie.JENKINS@EDUCATION.GOV.UK | JENKINS, Julie | 2026-03-11 14:57
254 | 179 | Actual date cleared |  |  |  |  | Julie.JENKINS@EDUCATION.GOV.UK | JENKINS, Julie | 2026-03-11 15:01
255 | 180 | Due date changed from 31 Mar 2026 to 30 Apr 2026 |  |  |  |  | Kiranjit.GILL@EDUCATION.GOV.UK | GILL, Kiranjit | 2026-03-12 08:13

## Risks
Id | ObjectiveId | ProjectId | FipsId | ProductDocumentId | Title | Description | Category | BusinessArea | RiskTierId | OwnerEmail | ImpactRating | LikelihoodRating | RiskScore | ProximityDate | Response | ResidualImpact | ResidualLikelihood | TargetDate | Status | ClosedDate | Notes | Source | SourceId | OwnerUserId | RiskStatusId | RiskPriorityId | RiskLikelihoodId | RiskImpactLevelId | RiskProximityId | RiskCategoryId | InherentScore | ResidualScore | IdentifiedDate | NextReviewDate | LastReviewDate | GovernanceBoardId | PrimaryProductId | ResponseStrategy | HowIdentified | CreatedByUserId | UpdatedByUserId | ClosedByUserId | IsDeleted | CreatedAt | UpdatedAt
1 |  |  | NEQ-753 |  | Products not onboarded to the accessibility issues and statement service | We have 400 products and we are legally required to provide accessibility statements on all web browser based products and services. While statements are in place for the majority, not all teams may choose to onboard to the product which will result in continued inaccurate, out of date and statements with wrong information on. This could result in legal action or users not being able to use DfE's products or services properly. |  | CXD | 4 | Andy.JONES@education.gov.uk | 5 | 5 | 25 | 2026-03-31 | avoid | 3 | 3 |  | open | [23 empty] | False | 2025-10-18 14:45 | 2025-10-21 21:25

## Issues
Id | ObjectiveId | ProjectId | FipsId | ProductDocumentId | Title | Description | Category | BusinessArea | OwnerUserId | Severity | Priority | DetectedDate | TargetResolutionDate | Status | ResolutionSummary | Workaround | SourceType | SourceReference | SourceRecordUrl | SourceRiskId | BlockedFlag | ClosedDate | Source | SourceId | MilestoneId | RiskId | PrimaryProductId | UserImpactSummary | ServiceImpactSummary | BlocksRelease | StatusId | PriorityId | SeverityId | IssueCategoryId | ResolvedDate | CreatedByUserId | UpdatedByUserId | ClosedByUserId | IsDeleted | CreatedAt | UpdatedAt

## Actions
Id | ObjectiveId | ProjectId | DecisionId | FipsId | ProductDocumentId | Title | Description | BusinessArea | SourceType | SourceReference | SourceRecordUrl | ActionSourceId | AssignedToEmail | Priority | Status | StartDate | DueDate | CompletedDate | ParentActionId | EvidenceUrl | Notes | Source | SourceId | AssignedToUserId | AccountablePersonUserId | TeamName | ClosedDate | LastProgressUpdate | ProgressPercent | Blocked | BlockedReason | ClosureNotes | Rag | Evidence | EvidenceTypeId | VerificationRequired | VerifiedByUserId | VerifiedDate | VerificationNotes | ActionTypeId | CategoryId | ImpactLevelId | PriorityId | StatusId | RiskId | IssueId | MilestoneId | ReminderFrequencyId | EscalationThresholdId | EscalationTriggered | ServiceId | PrimaryProductId | LifecyclePhase | CreatedByUserId | UpdatedByUserId | ClosedByUserId | IsDeleted | CreatedAt | UpdatedAt

## Decisions
Id | ObjectiveId | ProjectId | FipsId | ProductDocumentId | Title | Status | DecisionType | DecisionDate | Summary | BusinessArea | OwnerEmail | Outcome | Notes | SourceType | SourceReference | SourceRecordUrl | StatusId | PriorityId | OutcomeId | EffectiveDate | ExpiresDate | GovernanceBoardId | OwnerUserId | AgendaItemReference | DecisionMakerUserId | ProposedByUserId | SponsorUserId | ResponsibleTeam | ImplementationOwnerUserId | ImplementationStatusId | ImplementationDeadline | VerificationRequired | VerifiedByUserId | VerifiedDate | VerificationNotes | Evidence | EvidenceTypeId | AdditionalDocuments | PrimaryProductId | MilestoneId | Source | SourceId | CreatedByUserId | UpdatedByUserId | ClosedByUserId | IsDeleted | CreatedAt | UpdatedAt

## Comments
Id | EntityType | EntityId | CommentText | CreatedByUserId | CreatedAt | UpdatedAt | IsDeleted

## Dependencies
Id | SourceEntityType | SourceEntityId | TargetEntityType | TargetEntityId | DependencyType | Description | Status | ResolvedDate | ResolvedByEmail | ResolvedByName | CreatedAt | UpdatedAt
1 | Project | 1 | Project | 6 | Prerequisite | The FIPS product provides API data for the products and services for operational reporting feature. | Active |  |  |  | 2025-11-24 21:22 | 2025-11-24 21:22
3 | Project | 15 | Project | 197 | Related | HoPs delivering this work | Active |  |  |  | 2025-11-25 17:19 | 2025-11-25 17:19
6 | Project | 15 | Project | 199 | Prerequisite |  | Active |  |  |  | 2025-11-27 08:55 | 2025-11-27 08:55
7 | Project | 46 | Project | 45 | Prerequisite |  | Active |  |  |  | 2026-01-06 14:25 | 2026-01-06 14:25
8 | Project | 207 | Project | 206 | Related |  | Active |  |  |  | 2026-01-07 15:57 | 2026-01-07 15:57
9 | Project | 208 | Project | 206 | Related |  | Active |  |  |  | 2026-01-07 16:04 | 2026-01-07 16:04
10 | Project | 219 | Project | 1 | Successor |  | Active |  |  |  | 2026-01-28 12:05 | 2026-01-28 12:05
11 | Project | 159 | Project | 160 | Related |  | Active |  |  |  | 2026-01-28 14:08 | 2026-01-28 14:08
12 | Project | 159 | Project | 56 | Related |  | Active |  |  |  | 2026-01-28 14:41 | 2026-01-28 14:41
13 | Project | 133 | Project | 153 | Prerequisite | - QRD - Dependency on CLDS 2.0 as QRD will consume the qualification details view from catalog_10_gold.central_learner_data_store_views - Matching - Go live of CLDS 2.0 | Active |  |  |  | 2026-02-02 14:55 | 2026-02-02 14:58
15 | Project | 45 | Project | 153 | Prerequisite | Dependent on the migration of CLDS 2.0 on 20/03 and being able to move our assurance data and code to the SecTest environment before middle of March when BAU team will need to use pre-prod. | Active |  |  |  | 2026-02-02 16:46 | 2026-02-02 16:46
16 | Project | 136 | Project | 45 | Prerequisite | AAD 2.0 for EDAP migration | Active |  |  |  | 2026-02-02 17:01 | 2026-02-02 17:01
17 | Project | 136 | Project | 133 | Prerequisite | Final Data Delivery | Active |  |  |  | 2026-02-02 17:01 | 2026-02-02 17:01
18 | Project | 134 | Project | 45 | Prerequisite | AAD2.0 for EDAP migration | Active |  |  |  | 2026-02-02 17:05 | 2026-02-02 17:05
19 | Project | 134 | Project | 133 | Prerequisite | MDP for final Data delivery | Active |  |  |  | 2026-02-02 17:05 | 2026-02-02 17:05
20 | Project | 135 | Project | 133 | Prerequisite | Delivery of final data from CLDS | Active |  |  |  | 2026-02-02 17:14 | 2026-02-02 17:14
21 | Project | 135 | Project | 45 | Prerequisite | Continued migration to Databricks including EDAP (dependent on AAD 2.0 team and ADA team) | Active |  |  |  | 2026-02-02 17:15 | 2026-02-02 17:15
22 | Project | 205 | Project | 206 | Related |  | Active |  |  |  | 2026-02-17 10:50 | 2026-02-17 10:50
23 | Project | 205 | Project | 207 | Related |  | Active |  |  |  | 2026-02-17 10:51 | 2026-02-17 10:51
24 | Project | 205 | Project | 208 | Related |  | Active |  |  |  | 2026-02-17 10:51 | 2026-02-17 10:51
25 | Project | 239 | Project | 38 | Prerequisite |  | Active |  |  |  | 2026-02-25 13:22 | 2026-02-25 13:22
26 | Project | 239 | Project | 46 | Related |  | Active |  |  |  | 2026-02-25 13:23 | 2026-02-25 13:23
27 | Project | 239 | Project | 240 | Related |  | Active |  |  |  | 2026-02-25 13:23 | 2026-02-25 13:23
28 | Project | 239 | Project | 227 | Related |  | Active |  |  |  | 2026-02-25 13:24 | 2026-02-25 13:24
29 | Project | 230 | Project | 225 | Related |  | Active |  |  |  | 2026-03-05 14:28 | 2026-03-05 14:28

## RiskActions
RiskId | ActionId

## RiskRiskTypes
RiskId | RiskTypeId | CreatedAt

## IssueActions
IssueId | ActionId

## RiskDecisions
RiskId | DecisionId

## IssueDecisions
IssueId | DecisionId

## IssueRisks
IssueId | RiskId

## ActionDecisions
ActionId | DecisionId

## MilestoneActions
MilestoneId | ActionId

## MilestoneRisks
MilestoneId | RiskId

## MilestoneIssues
MilestoneId | IssueId

## Summary
Sheet | Rows
Projects | 253
Users | 492
BusinessAreas | 20
Phases | 16
ActivityTypes | 5
DirectoratesLookup | 4
RiskAppetite | 5
RagStatuses | 5
DeliveryPriorities | 4
RiskTiers | 5
RiskTypes | 13
ActionSources | 4
Divisions | 2
Missions | 4
Objectives | 20
RagHistory | 174
Successes | 79
Outcomes | 0
Needs | 14
ProblemStatements | 39
ProblemStatementHist | 18
ProjectMissions | 32
ResourceFunding | 4
ResourceFundingHist | 4
ProjectContacts | 224
ProjectObjectives | 101
ProjectProducts | 17
StatusUpdates | 150
MonthlyUpdates | 359
MonthlyNarratives | 375
WeeklySuccess | 0
SROs | 205
ServiceOwners | 71
Directorates | 92
BudgetOwners | 170
PMOContacts | 279
Milestones | 180
MilestoneUpdates | 255
Risks | 1
Issues | 0
Actions | 0
Decisions | 0
Comments | 0
Dependencies | 25
RiskActions | 0
RiskRiskTypes | 0
IssueActions | 0
RiskDecisions | 0
IssueDecisions | 0
IssueRisks | 0
ActionDecisions | 0
MilestoneActions | 0
MilestoneRisks | 0
MilestoneIssues | 0