## ReadMe
Area | Guidance
Export type | Raw source extract from the legacy Compass database.
Environment | Development
Output file | /Users/andyjones/Source/code-digital-ops/FIPS/compass/exports/compass-migration-workbook.xlsx
Legacy IDs | The `Id` column in each sheet is the source identifier to carry into the migration mapping.
Parent links | Child sheets keep their original foreign keys such as `ProjectId`, `RiskId`, `IssueId`, and `MilestoneId`.
Lookup sheets | Use lookup sheets like `BusinessAreas`, `Phases`, `RagStatuses`, `RiskTiers`, and `Users` to resolve IDs and names.
Migration hint | Use `Projects` as the parent work-item source and then attach related sheets in a second pass.
Deleted rows | This export is a full raw dump of the source tables, so soft-deleted rows are retained if they exist.

## Projects
Id | ProjectCode | Title | Aim | StrategicObjectives | MissionPillars | StartDate | TargetDeliveryDate | ActualDeliveryDate | IsFlagship | IsAiInitiative | RagStatusLookupId | RagStatus | RagJustification | PathToGreen | PhaseId | BusinessAreaId | HistoricBuRTId | PrimaryContactUserId | DeliveryPriorityId | DeliveryPriorityChangeReason | PrimaryOrganizationalGroupId | IsMultiDepartmentProject | OtherDepartments | BusinessCaseApproval | TotalPermFte | TotalMspFte | Status | StatusChangeReason | IsDeleted | CreatedAt | UpdatedAt | CreationMethod | ActivityTypeLookupId | RiskAppetiteLookupId | ServiceUsers | IsInternal | IsExternal | IsSubjectToSpendControl | DiscoveryStartDatePlanned | DiscoveryStartDateActual | DiscoveryEndDatePlanned | DiscoveryEndDateActual | AlphaStartDatePlanned | AlphaStartDateActual | AlphaEndDatePlanned | AlphaEndDateActual | PrivateBetaStartDatePlanned | PrivateBetaStartDateActual | PrivateBetaEndDatePlanned | PrivateBetaEndDateActual | PublicBetaStartDatePlanned | PublicBetaStartDateActual | PublicBetaEndDatePlanned | PublicBetaEndDateActual
1 | PRJ-0001 |  |  |  |  | 2025-10-22 21:07 | 2026-04-22 21:07 |  | False | False |  | Green | [9 empty] | False |  |  |  |  | Active |  | True | 2025-10-22 21:07 | 2025-10-23 08:05 |  |  |  |  | False | False
2 | PRJ-0002 |  |  |  |  | 2025-10-22 21:19 | 2026-04-22 21:19 |  | False | False |  | Green | [9 empty] | False |  |  | 1.00 |  | Active |  | True | 2025-10-22 21:19 | 2025-10-23 08:05 |  |  |  |  | False | False
3 | PRJ-0003 |  |  |  |  | 2025-10-22 21:49 | 2026-04-22 21:49 |  | False | False |  | Green | [9 empty] | False |  |  |  |  | Active |  | True | 2025-10-22 21:49 | 2025-10-23 08:05 |  |  |  |  | False | False
4 | PRJ-0004 |  |  |  |  | 2025-10-23 07:50 | 2026-04-23 07:50 |  | False | False |  | Green | [9 empty] | False |  |  |  |  | Active |  | True | 2025-10-23 07:50 | 2025-10-23 08:05 |  |  |  |  | False | False
5 | PRJ-0005 | COMPASS |  |  |  | -1 | -1 |  | False | False |  | Green | [9 empty] | False |  |  |  |  | Active |  | True | 2025-10-23 12:19 | 2025-10-23 12:20 |  |  |  |  | False | False
6 | PRJ-0006 | COMPASS Reporting | Deliver centralised reporting for compliance, assurance and governance and management of programme work. |  |  | 2025-10-01 | 2026-12-31 |  | False | False |  | Amber-Green | Design and build - single point of failure in Andy Jones (currently) |  |  |  |  | 1 | 3 | Tetsing |  | False |  |  | 5.00 | 0.00 | Active |  | False | 2025-10-23 12:22 | 2025-11-20 05:40 |  | 4 | 5 | DfE Staff | True | False | False
7 | DEL-0007 | Flagship test | Testing flagship projects |  |  | 2025-01-01 | 2025-01-01 |  | True | False |  | Green | [9 empty] | False |  |  |  |  | Active |  | False | 2025-10-27 17:52 | 2025-10-27 17:52 |  |  |  |  | False | False
11 | DEL-0007 | Test | test | [5 empty] | False | False | [11 empty] | False |  |  |  |  | Active |  | False | 2025-10-31 15:04 | 2025-10-31 15:04 |  |  |  |  | False | False
12 | DDTDEL-0007 | Service Manual | To centralise all manuals, standards, guidance within DDT into one resource. |  |  | 2025-11-05 | 2026-06-01 |  | False | False |  | Amber-Green | Under resourced |  | 1 | [6 empty] | False |  |  |  |  | Active |  | False | 2025-11-05 21:29 | 2025-11-05 21:29 |  |  |  |  | False | False
17 | DDTDEL-0007 | new proj | vw |  |  | 2026-11-11 |  |  | False | False |  | Amber-Green | [6 empty] | 1 |  |  | False |  |  |  |  | Active |  | False | 2025-11-13 12:59 | 2025-11-16 09:43 |  |  |  |  | False | False
18 |  | Plan Technology for Your School/ Digital Standards | The service currently has two main products: -Plan Technology for our School - a self-assessment tool gives schools a better understanding of their technology needs. It provides recommendations and actions to support technology planning. - Digital and technology Standards for Schools and Colleges- guidelines to support schools and college to use the right digital infrastructure and technology. Hosted on gov.uk The service also provides support content that to compliment the above Current agile teams are working on: - Creation and maintenance of the Digital Standards - New topics added to the Plan Technology for your School to assist schools to meet all Digital Standards - Extra support resources that might be needed by schools and colleges to meet the standards and follow recommendations - Better user journeys for MATs when using the tool - A technology financial planner https://www.gov.uk/guidance/meeting-digital-and-technology-standards-in-schools-and-colleges https://www.gov.uk/guidance/plan-technology-for-your-school | [5 empty] | False | False |  | Amber/Green |  |  |  |  | DDaT_22/23_003a |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 08:16 | 2025-11-20 11:01 |  | 3 |  | Schools, Teachers, School Business Leaders, Policy Areas (Security, Commercial, Schools Group etc), Our teams of Digital professionals | False | True |  | 2022-04-06 |  |  |  | 2022-07-19 |  |  |  | 2023-03-13 |  |  |  | 2024-06-12
2294 |  | CSC: Data Modernisation (daily data) | We want timely [automated], relevant CSC data to be collected and shared, including through published and private dashboards, enabling valuable insights into the policy, delivery and experiences of CSC. Our ambition is for DfE and the sector to be partners, and build trust in working together, using data to learn and improve the lives and outcomes for children and families. The service will allow Local Authorities to see their data in real time, without having to submit a return. ​ More timely data will enable the government and Local Authorities to identify and respond to arising problems quicker, making evidence-based decisions that result in better outcomes for children and families.​ The Department for Education does not have a solid, streamlined oversight of children’s social care (CSC) at national or local authority (LA) level due to the lack of frequency, consistency and quality of the data flowing in and out of the department. The department’s ability to understand, improve and support the needs of LAs and frontline workers most effectively is therefore inhibited. SoS has expressed a desire for DfE to make better use of modern data techniques (including developing dashboards and apps) to support Ministers and the department in making evidence-informed decisions around key priorities.​ | [5 empty] | False | False |  | Amber |  |  |  |  | DDaT_22/23_004 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 08:37 | 2025-11-20 11:01 |  | 4 |  | Local Authorities Public Families Group | False | True |  | 2022-06-20 |  |  |  | 2022-07-30 |  |  |  | 2022-12-01
2295 |  | Configuration Management Database on ServiceNow | Understanding what services we deliver and how our existing IT estate supports these is a critical foundation to enable the delivery of DfE missions, helping to ensure that we can minimise duplication and complexity of services and supporting technology, enabling a more responsive approach to delivery demands and quickly identifying and addressing potential security threats and vulnerabilities. In the simplest terms, if we don’t know clearly what services we have and what technologies they depend on then we cannot effectively exploit, support, manage or improve our services. | [5 empty] | False | False |  | Green |  |  |  |  | DDaT_22/23_005 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 08:37 | 2025-11-20 11:01 |  | 1 |  |  | True | False |  | 2022-02-01
2296 |  | Customer Experience Phase 2 | The Customer Experience team is supporting digital portfolios and wider policy teams to drive an enhanced focus on user-centred design and customer experience. The team is driving efficiency and culture change through its focus on solving complex user problems and improving user journeys across DfE products and services. This is a significant business change to the Customer Experience digital Transformation programme which was delivered in 2022. This includes substantial improvements, such as: developing an organic way of driving traffic towards our landing pages that doesn’t rely on the existence of a campaign. adding further features and tools to the landing pages, as well as new and more digestible content that links from them, such as a comparison tool for employers that will enable them to benchmark themselves against similar employers. further consolidation of content. investigating the potential for new offline resources to provide support to online developments. | [5 empty] | False | False |  | De-prioritised |  |  |  |  | DDaT_22/23_007 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 08:37 | 2025-11-20 11:01 |  | 1 |  | Multiple internal and external users. External users include: young people, adult learners, parents, teachers, careers advisers, educational settings, local authorities, employers, OGDs Internal users include: policy teams across Skills, Families, Schools and Operations & Infrastructure Groups, comms campaign teams, data teams, DfE DDT professionals and DDT leadership. | False | True
2297 |  | Turing Scheme Year 4 - Application phase | The overall objective of the proposal is to change how the Turing Scheme is delivered from academic year 2024/2025 onwards changing the existing delivery model and bringing the administration of the Scheme in house. There are two distinct elements to this proposal: the development of a digital service to support the administration of the Scheme; and the administration of the Scheme itself. The in-house service will be delivered in phases according to the need of users to complete a series of transactions throughout the year. Applying for funding is the first of these transactions. | [5 empty] | False | False |  | Green |  |  |  |  | DDaT_22/23_012 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 08:37 | 2025-11-20 11:01 |  | 1 | 3 | User in schools, colleges and universities across the UK and British Overseas Territories apply for funding on behalf of their students so that they can undertake work ans study placements across the world. | False | True |  | 2023-03-28 |  |  |  | 2023-07-10 |  |  |  | 2023-10-02 |  |  |  | 2024-02-06
2298 |  | Turing Scheme Year 4 - Payments and Reporting | The overall objective of the proposal is to change how the Turing Scheme is delivered from academic year 2024/2025 onwards changing the existing delivery model and bringing the administration of the Scheme in house. The service is being developed iteratively to meet user need and delivery milestones. Following the development and launch of the application form and assessment functionality, the team is now developing processes to support the process by which funds will be allocated to and managed by organisations. We wish to re-design the existing payment process so that it is less burdensome for users while ensuring that it continues to meet DfE and HMG rules on grant payments. The first payments must be made no later than 1 September 2024 | [5 empty] | False | False |  | Amber/Red |  |  |  |  | DDaT_22/23_012_A |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 08:37 | 2025-11-20 11:01 |  | 1 | 3 | User in schools, colleges and universities across the UK and British Overseas Territories apply for funding on behalf of their students so that they can undertake work ans study placements across the world. | False | True | [5 empty] | 2023-07-10 |  |  |  | 2023-10-02 |  |  |  | 2024-02-06
2299 |  | Skills Bootcamps Data Modernisation Project | Utilise digital technologises to fundamentally how the Skills Bootcamps can operate and deliver value to customers. It will involve a wide range of activities, including adoption of new technologies, the redisgn of business processes, and development of new organisational structures and ways of working. They are requesting assistance from the Submit Learner Data team to help build auxiliary data collection tools that produce datasets that can be merged with the dataset produced through the ILR. The Skills Bootcamps Data team has received feedback from multiple subject matter experts who have highlighted critical risks to the programme based on the lack of a &amp;quot;Single Source of the Truth&amp;quot; on programme performance. Currently, 3+ tools are used to collect data from Suppliers, resulting in duplication (even triplication) of data. This is because we have a number of data fields that existing fields in the ILR cannot accommodate. We collect these supplementary fields using excel-based collection tools with fragile validation that leads to challenges for suppliers (when submitting data) and the programme&amp;#39;s data team (when cleaning and consolidating the data). Submit Learner Data has recruited a Business Analyst and User Reearcher to deliver the work. The UR commenced work on 07/01/24 and the BA starts on 16/01/24. Scoping and other ceremonies will begin immeadiately. | [5 empty] | False | False |  | De-prioritised |  |  |  |  | DDaT_23/24_003 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 08:37 | 2025-11-20 11:01 |  | 1 |  |  | False | True |  | 2023-06-05 |  |  |  | 2024-04-08 |  |  |  | 2024-07-04
2300 |  | NOT ON I&P PERF REPORT - Eligibility Checking Engine & Free School Meals service (ECS replacement stage 1) | The ECS enables local authorities (LAs) to check eligibility for: Free School Meals (FSMs), Early Years Pupil Premium (EYPP), Free education and childcare for 2-year-olds and 30 hours free childcare. The ECS is a legacy system and work is currently underway to build a replacement for the Free School Meals element of legacy ECS and also the checking engine which will be called by all ECS entitlements which move from the legacy system toa new service. . The Beta phase commenced in January 2024 and will build a service for use with selected Local Authorities and Schools over 2024. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | DDaT_23/24_004 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 08:37 | 2025-11-20 11:01 |  | 4 | 4 | LAs, Schools, Parents/Carers/Guardians | False | True |  | 2023-07-01 |  |  |  | 2023-09-18 |  |  |  | 2024-01-03 |  |  |  | 2025-08-01
2301 |  | Social Work Practice Development Programme (SWPDP) (formerly Social Work Induction Programme (SWIP) and Early Career Framework (ECF) - Private Beta)) | To develop a strong pipeline of social workers, improved levels of retention of experienced social workers and improved quality of practice by launching a new programme of training, support and assessment for social workers: the Early Career Framework | [5 empty] | False | False |  | Amber/Green |  |  |  |  | DDaT_23/24_005 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 08:37 | 2025-11-20 11:01 |  | 1 |  | Children and Families Social Workers | False | True |  | 2023-02-06 |  |  |  | 2023-09-18 |  |  |  | 2024-04-01 |  |  |  | 2027-09-01
2302 |  | Check an early years qualification and EY workforce register | The vision of the project is for an Early Years workforce that has clarity around, and confidence in their qualifications from day one of their career journey. The service aim is to be the definitive and trusted source of information about Early Years qualifications. | [5 empty] | False | False |  | Green |  |  |  |  | DDaT_23/24_006 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 08:37 | 2025-11-20 11:01 |  | 1 |  | Nursery managers, early years practitioners and, in the future, those looking to enter the early years sector | False | True | [5 empty] | 2023-10-10 |  |  |  | 2024-02-01 |  |  |  | 2025-03-20
2303 |  | Awarding Organisation Digital Portal (AODP) | Following the Government review of post-16 qualifications at level 3 and below in England, DfE needed to simplify the funding qualifications approval process. Awarding Bodies (AOs) need to be able to submit academic qualifications/submissions for 16-19 years olds/or adult offers to DfE for funding approval, 5-10 windows throughout the year that enables AOs to to submit applications. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | DDaT_23/24_007 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 08:37 | 2025-11-20 11:01 |  | 1 |  | Awarding Organisations | False | True |  | 2023-11-13 |  |  |  | 2024-04-15 |  |  |  | 2024-12-09
2304 |  | Data sharing on vulnerable children between public sector bodies/Single Unique Identifier (Discovery+) | To improve the use of technology to share information between agencies working with children and families (schools, police, health and children's social care) and to explore the use of a consistent child identifier (CCI) to enable this. | [5 empty] | False | False |  | Amber/Red |  |  |  |  | DDaT_23/24_011 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 08:37 | 2025-11-20 11:01 |  | 4 |  |  | False | True |  | 2024-07-01 |  |  |  | 2024-11-01
2305 |  | NOT ON I&P PERF REPORT - Eligibility Checking Service (ECS) 30 hours and Early Years Pupil Premium (EYPP) eligibility expansion | By September 2025, working parents will be able to claim 30 hours of free childcare a week, over 38 weeks of the year, for children from nine months up to their child starting school. The expansion of 30 hours entitlement will also expand eligibility for EYPP. The existing ECS system will need to be updated in phases to support the expansion of entitlements | [5 empty] | False | False |  | Amber/Green |  |  |  |  | DDaT_23/24_013 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 08:37 | 2025-11-20 11:01 |  | 1 |  | LAs, parents | False | True
2475 |  | Master Education Provider System | We have a legal requirement for a register of schools and governors within the DfE, this data underpins a number of critical systems within the DfE and across wider government. The current system GIAS is currently running on a legacy database and dated code making it unsustainable moving forward. The new system will allow the retirement of several existing systems, GIAS, Provider Profile and UKRLP bringing in an estimated saving of £1.75m a year. | [5 empty] | False | False |  | ON HOLD |  |  |  |  | DDaT_23/24_016 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 1 |  | Being a public service, consumers of provider data can range from private and public sector organisations or anyone who can connect via an API. The main consumer of GIAS are internal DfE users including and not limited to Schools Checking Service, ESFA and DSI. External consumers tend to be local authorities and several commercial or voluntary organisations such as software houses across the education sector and private companies with an interest in or need for official school attribute data such as Zoopla and Rightmove | False | False |  | 2023-10-09 |  |  |  | 2024-09-01
2476 |  | Teaching Vacancies Service | Purpose - A free, online, national search and listing service for teaching roles in schools, for schools to list their vacancies free of any charge and for teachers to search these vacancies. Benefits - Saving schools money on recruitment costs by offering a free national job listing service | [5 empty] | False | False |  | Green |  |  |  |  | IT_TA8 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 4 |  |  | False | True |  | 2017-04-03 |  |  |  | 2017-07-03 |  |  |  | 2018-02-19 |  |  |  | 2018-07-13
2477 |  | Live Regions Services | We make it more efficient for academies to belong to a strong trust, so that regional colleagues and schools can focus on improving education. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | IT243 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 3 |  |  | False | True
2478 |  | Find information about academies and trusts (FIAT) | Design and development of a tool that collates information from multiple sources about academies and trusts (replacing legacy tech - TRAMS) BETA: FIAT will be the go-to-place for DfE and ESFA colleagues to get the information they need to inform decision making and assessments about trusts and to provide better support to trusts. Brings together data from different services to give users a single source of information about trusts and academies​ | [5 empty] | False | False |  | Green |  |  |  |  | IT243a |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 3 |  | Regions Group, Capital directorate | False | True | [9 empty] | 2024-03-25 |  |  |  | 2024-10-01
2479 |  | Record Concerns and Support for Trusts | ReCast enables Regions Group and ESFA colleagues to record and manage concerns about schools and trusts. These include financial, governance, safeguarding and whistleblowing concerns. It enables DfE to make effective decisions about support and action that may be taken in relation to a trust. Product is currently being used by users. Allows Regions Group and SFSO (Schools Financial Support and Oversight) colleagues to record concerns and support related to trusts​ | [5 empty] | False | False |  | Green |  |  |  |  | IT243c |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 3 |  | Regions Group, SFSO (ESFA) | False | True |  | 2020-03-31 |  |  |  | 2020-09-21 |  |  |  | 2022-09-30 |  |  |  | 2023-02-20
2480 |  | Regional Services Division: Make changes to an Academy | Detailed understanding of school needs on significant change procedures to help schools and internal staff to manage significant changes such as school expansions and academy mergers. | [5 empty] | False | False |  | ON HOLD |  |  |  |  | IT243e |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 3 |  |  | False | True |  | 2020-07-27 |  |  |  | 2020-11-19
2481 |  | Regional Services Division: Manage free school projects | Make opening free schools easier and more efficient by capturing reliable data to manage projects, track progress and make informed decisions. | [5 empty] | False | False |  | Green |  |  |  |  | IT243f |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 3 |  | Regions Group, Capital directorate | False | True |  | 2022-12-19 |  |  |  | 2023-04-10 |  |  |  | 2024-01-18 |  |  |  | 2024-07-01
2482 |  | Regional Services Division: Manage Academy Projects | Enable regional colleagues to process applications from schools to become an academy and to prepare papers for approval by the Advisory Board. Improve the end-to-end process for completing academy conversions and transferring academies from one trust to another, following Advisory Board approval. | [5 empty] | False | False |  | Green |  |  |  |  | IT243g |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 3 |  | Schools and academy trusts, Regions Group | False | True | [9 empty] | 2022-07-01 |  |  |  | 2023-01-17
2483 |  | Regional Services Division: TRAMs | For staff to use one system with one version of the truth. This will reduce time taken to do their jobs and provide schools and trusts with consistent and joined up experience. To enable schools to apply to become an academy. | [5 empty] | False | False |  | Green |  |  |  |  | IT243h |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 3 |  |  | False | True |  | 2017-09-04 |  |  |  | 2018-02-01 |  |  |  | 2019-02-12 |  |  |  | 2019-11-25
2484 |  | Get Information About Schools | GIAS is a register of schools and colleges in England, and can be used to find and compare the performance of schools as well as the type, status and phase of each school or centre. GIAS displays information about governors, trustees and headteachers. Schools, local authorities and academy trusts can also update details by signing in to their DfE Sign-in account GIAS is the Department’s official register of state-funded and independent schools and online providers in England. It also contain vital information about and academy trusts in accordance with the Education (Supply of Information about the School Workforce) (No.2) (England) Regulations 2007). GIAS is also the national database of school governance in accordance with S538 of the Education 1996 and the Academy Trust Handbook. | [5 empty] | False | False |  | Amber |  |  |  |  | IT255 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 3 |  | Schools Children's Centres Colleges Universities Local Authorities Academy trusts Dioceses Governors and Governing Bodies OGDs ALBs Rightmove UKRLP China, Ghana, Cayman Islands not for profit organisations | False | True |  | 2016-06-01 |  |  |  | 2016-07-01 |  |  |  | 2016-11-30 |  |  |  | 2017-09-18
2485 |  | T Levels: Results and Certification | Design and delivery of the Manage T Level Results including digital systems and customer support, to enable T Level students receive accurate confirmation of achievement and attainment to specified deadlines. | [5 empty] | False | False |  | Green |  |  |  |  | IT316a |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 4 |  | Awarding organisations (currently 3 AOs, c. 40 registered users) Providers (c.250 schools and colleges for 25/26) | False | True |  | 2019-04-09 |  |  |  | 2019-09-01 |  |  |  | 2020-04-27 |  |  |  | 2024-02-01
2486 |  | Get Into Teaching | The Get Into Teaching website aims to support potential candidates on their journey to becoming a teacher by offering inspiration, information and reassurance. The CRM enables support services including email journeys, events, advisers and the contact centre. Get school experience supports potential teachers to request unpaid placements so they can decide if teaching is for them and gain valuable experience for their ITT application, and enable providers to meet potential candidates. | [5 empty] | False | False |  | Green |  |  |  |  | IT322 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 4 |  |  | False | True |  | 2018-01-02 |  |  |  | 2018-02-01 |  |  |  | 2018-09-03 |  |  |  | 2021-04-08
2487 |  | Becoming A Teacher | Our services are aiming to facilitate all postgraduate teacher training applications between candidates and training providers. With the inclusion of Find and Publish, this now includes searches for ITT courses by candidates and publishing courses by training providers. Includes; Apply For Teacher Training Find Postgraduate Teacher Training Publish Teacher Training Courses Register Trainee Teachers Manage School Placements Claim Funding For Mentor Training (was Track & Pay) | [5 empty] | False | False |  | Amber/Green |  |  |  |  | IT323a |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 4 |  | Teachers, trainers, trainees | False | True |  | 2017-07-03 |  |  |  | 2017-08-19 | [7 empty] | 2020-06-01
2488 |  | Claim Additional Payments for Teaching | The Claim Additional Payments for Teaching service (Claim) aims to increase teacher recruitment and retention by enabling early-career teachers to claim financial incentives. The service currently delivers the following retention policies: Teachers’ Student Loan Reimbursement (TSLR), Early-Career Payments (ECP) and Levelling Up Premium Payments (LUP). Claim will host the International Relocation Payments (IRP) service from September 2024. We are currently in the beta phase for two new services to be delivered through Claim – Further Education (FE) LUP payments and Early Years Recruitment Payments. | [5 empty] | False | False |  | Amber |  |  |  |  | IT453 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 4 |  |  | False | True |  | 2018-06-12 |  |  |  | 2018-10-01 |  |  |  | 2019-08-21 |  |  |  | 2019-10-31
2489 |  | MYESF View Your Funding | The aim of the project is to develop a pre-16 data integration pattern that will enable MYESF to integrate with Calculate Funding Service in order to provide easy to use, simple user interfaces that will aggregate and display pre-16 allocation statements. The key objectives of the project are: To improve the external user experience To improve the internal user experience To enable complex data flows between CFS and MYESF To have the basis for single funding allocation views that can scale to include further allocation types | [5 empty] | False | False |  | Green |  |  |  |  | IT484d |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 3 |  | Schools, academies & local authorities | False | True |  | 2019-04-01 | [7 empty] | 2019-08-01 |  |  |  | 2024-09-23
2490 |  | Get help buying for Schools | Get Help Buying supports schools to enter better value commercial deals, saving them money Get Help Buying for Schools makes schools feel better equipped to deliver future procurements Get Help Buying meets School Business Professionals’ changing needs and they are satisfied with the service they receive | [5 empty] | False | False |  | Amber |  |  |  |  | IT575b |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 3 | 3 | School business buying professionals Commercial operations staff | False | True | [5 empty] | 2020-07-03 |  |  |  | 2021-11-01 |  |  |  | 2023-03-20
2491 |  | Learner Data Service (LDS - NPDAAT Replacement) programme | To simplify and improve the process of managing learner data | [5 empty] | False | False |  | Amber/Green |  |  |  |  | IT594 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 1 |  | Public Ofsted Ofqual STA ESFA Families Group Skills Group Schools Group | False | True |  | 2017-07-03 |  |  |  | 2017-08-19 |  |  |  | 2023-03-27 |  |  |  | 2024-10-01
2492 |  | Check Your Performance Measures Data (CYPMD) | To deliver the Schools Checking Service previously provided externally by RM Education. The intial cycle delivered in house was in 2024. This was via the Oracle IA system, a tactical solution, until a strategic solution is developed. A digital service which shares school and pupil performance measures data back with schools and colleges ahead of publication of data. Users have the opportunity to requests pupils are included or removed from the performance measures calculations. They can also request amendments to their results data. These requests and any supporting evidence are scrutinised to inform a final decision. | [5 empty] | False | False |  | Green |  |  |  |  | IT594b |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 3 |  | Schools LAs DfE - DISD and Policy teams | False | True |  | 2023-07-17 |  |  |  | 2023-10-02 | [7 empty] | 2024-06-24
2493 |  | Teacher Continuing Professional Development | The ECF will provide teachers with high quality induction materials and support schools to set up and manage statutory induction requirements for teachers who are newly qualified and in the first two years of their profession and gain access to a funded programme of support to improve teacher retention and teaching quality. NPQ will provide high quality professional development to teachers later in their career. Includes: Continuing Professional Development Information Continuing Professional Development Service Manual Find A Teaching School Hub Manage Training For Early Career Teachers Register For A National Professional Qualification | [5 empty] | False | False |  | Amber/Green |  |  |  |  | IT627d |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 4 |  |  | False | True | [5 empty] | 2020-11-09 | [7 empty] | 2021-09-06
2494 |  | Support for Social Workers (Public Beta) | Giving child and family social workers access to the right opportunities and encourage them to proactive manage their learning and development so that they can provide quality services while continuing to advance their careers within the profession. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | IT631 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 1 |  | Children and Families Social Workers | False | True |  | 2021-05-04 |  |  |  | 2022-05-05 |  |  |  | 2022-08-15 |  |  |  | 2023-09-22
2495 |  | Teaching Records Service | Creating the modern and reliable services, data and infrastructure needed to enable DfE to meet the needs of teachers, and confidently inform future strategy and policy decisions Data: - The data that Teacher Services stores is high quality, safe, secure and relevant - Removal of duplicate data flows; increase of data automation via secure APIs - Removal of legacy technology, components and implement full continuous integration and continuous deployment Digital services: - We understand how we can add more value to our users through the teaching record services - We understand how the teaching record services can better serve other Teacher Services Includes: Access Your Teaching Qualifications Check A Teacher's Record Find a lost Teacher Record Number Teacher Services Portals (part of DQT) Teaching Identity Teaching Record System (replacement for legacy database - DQT) | [5 empty] | False | False |  | Amber/Green |  |  |  |  | IT636 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 4 |  |  | True | False |  | 2021-04-26 |  |  |  | 2021-09-06
2496 |  | Children's Barred List | The service allows authorised users to conduct checks in the following circumstances, in line with Keeping Children Safe in Education: ** newly appointed staff who are engaging in regulated activity, pending the receipt of an Enhanced Certificate with Barred List information from the Disclosure and Barring Service (DBS) ** where an individual has worked in a post in a school or college that brought them into regular contact with children or young persons which ended not more than three months prior to that person’s appointment to the organisation | [5 empty] | False | False |  | Green |  |  |  |  | IT636e |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 4 |  |  | False | True |  | 2021-11-30 |  |  |  | 2023-06-21 |  |  |  | 2024-01-25 |  |  |  | 2024-08-01
2497 |  | Apply for Qualified Teacher Status (QTS) | Purpose - Development and delivery of a new service for the award of QTS to overseas qualified teachers, including a new policy approach and underpinning legistlation Benefits - Opportunity to increase the number of international teachers being awarded QTS and working in English schools ​ Opportunity to improve the user journey for applicants | [5 empty] | False | False |  | Amber/Green |  |  |  |  | IT638b |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 4 |  |  | False | True |  | 2021-11-01 |  |  |  | 2022-01-31 |  |  |  | 2022-05-23 |  |  |  | 2023-06-01
2498 |  | Improving Daily Attendance Data | Accelerating improvements in attendance data benchmarking functionality for schools, trusts and LAs, and explore matching with other data sets to support improvements in attendance through targeted interventions Background The project aims to enhance attendance data benchmarking and self-review in schools and local authorities, helping identify areas for improvement and assess intervention effectiveness. Reducing student absences could significantly boost lifetime earnings, with a 1% reduction potentially adding £282 million. Integrating attendance data with Children’s Social Care data will inform better interventions for vulnerable children. | [5 empty] | False | False |  | Green |  |  |  |  | IT642 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 3 |  | External reporting via View Your Education Data (VYED) to the Sector: Schools, SATs, MATs, and LAs. Internal use of the data by the Analytical Function Fortnightly publications via gov.uk | False | True |  | 2021-10-21 |  |  |  | 2022-04-01 |  |  |  | 2022-07-01 |  |  |  | 2023-11-01
2499 |  | Early years child development training & Help for early years providers | Provide information and guidance needed to successfully implement the EYFS in an early years setting, and upskill the early years workforce on child development, empowering them to enable each child in their care to thrive. Early years child development training- A universally accessible, trusted training service for the early years workforce to provide skills and tools in child development so that they can improve outcomes for every child in their care. . Help for early years providers- Providing the trusted information and guidance you need to successfully implement the EYFS in your Early Years setting. | [5 empty] | False | False |  | Green |  |  |  |  | IT650 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  |  | 3 | Early Years Practitioners and managers. Reception school staff. | False | True |  | 2021-10-04 |  |  |  | 2021-11-24 |  |  |  | 2022-06-30 |  |  |  | 2022-11-24
2500 |  | Project Titan: Education Record | Develop a decentralised student ID system for citizens, build data automation tools and build a single post-14 education data store that this student data feeds into . | [5 empty] | False | False |  | Green |  |  |  |  | IT652 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 4 |  |  | False | True |  | 2022-04-01 |  |  |  | 2022-08-01 |  |  |  | 2024-06-04 |  |  |  | 2025-07-01
2501 |  | Project Titan: Enter Learning Data | To develop a new MI System for training providers to record their learner data and support Individual Learner Record (ILR) data generation, also to provide real time BI reporting through links to View Your Education Data (VYED) | [5 empty] | False | False |  | Green |  |  |  |  | IT652a |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 4 |  |  | False | True |  | 2021-06-09 |  |  |  | 2022-12-18 |  |  |  | 2024-08-01 |  |  |  | 2025-04-01
2502 |  | DfE Connect (School Account) | To improve discoverability, findability, and navigation of DfE services. To provide better personalisation of content and experience for users and consider how data join up might be progressed between different services. | [5 empty] | False | False |  | Amber |  |  |  |  | IT663 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 2 |  | Current users: School Business Managers /School Leaders for all Pre-16 Academies. | False | True |  | 2022-01-01 |  |  |  | 2022-08-01 |  |  |  | 2023-09-28
2503 |  | Identity Strategy | To improve user experience around identity management and authentication, and reduce the burden of fragmentation of identity management solutions for the sector and department. To reduce security risk around identity and access management for the department. | [5 empty] | False | False |  | Amber |  |  |  |  | IT663b |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 2 |  |  | False | True |  | 2022-01-01 |  |  |  | 2022-09-01 |  |  |  | 2023-04-03 |  |  |  | 2023-10-02
2504 |  | Standards Testing Agency (STA) Transformation Programme | STA will be a modern, diverse, inclusive world leader in developing and delivering accessible, valid and reliable digital assessments that support the delivery of excellent standards for education. Our services will be user centred to support schools effectively and efficiently to carry out these assessments. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | DDaT_22/23_013 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 1 |  |  | False | True |  | 2025-09-01
2505 |  | EUC: Core Service run and improvements | Improving the colleague experience and delivering exceptional workplace technology by maintaining, assuring and upgrading core technology services including: Videoconferencing refresh; headset refresh; mobile refresh, print refresh (aligned to the DfE Technology Strategy themes). Incl Unified Comms (Fixed and Mobile Telephony, Teams, AV/VC, Contact Centres); Desktop; Productivity (O365); Digital Tools, Accounts & Access, headset refresh, mobile refresh, CCTS). | [5 empty] | False | False |  | Green |  |  |  |  | BuRT006 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 2 |  | Department | True | False |  | 2024-04-01
2506 |  | Desktop Improvement | Delivering high performing secure end user compute through technical upgrades (Win 10 – Win 11), EUC service review assessing org wide strategy needs and reshaping the core device and virtual service. Multiple projects incl. print estate refresh and device refresh. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT007 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 2 |  | Department | True | False |  | 2024-04-01
2507 |  | Productivity Improvement and Enhancements | Development of a Power Platform Centre of Excellence, consideration and deployment of products across corporate tools (e.g. O365 Copilot) . Multiple projects incl. powerplatform expansion | [5 empty] | False | False |  | Green |  |  |  |  | BuRT008 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 1 |  | Department | True | False |  | 2024-04-01
2508 |  | GPA Technology Partnership | Developing and implementing the Shared Service Tech Offer in GPA buildings to deliver economies of scale whilst ensuring autonomy of DfE services. Phase 1 Coventry North, Phase 2 Sanctuary Buildings). | [5 empty] | False | False |  | Green |  |  |  |  | BuRT009 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 3 |  | Department | True | False |  | 2024-09-30
2509 |  | Improving the Colleague Experience | Developing and integrating strategic tools to improve the colleague experience (E.g. Teams integration with Service Now) | [5 empty] | False | False |  | Green |  |  |  |  | BuRT010 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 1 |  | Department | True | False |  | 2024-04-01
2510 |  | Education Estates | Provide BAU support to ensure sector facing services are maintained and live for users | [5 empty] | False | False |  | Amber/Red |  |  |  |  | BuRT011 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 09:07 | 2025-11-20 11:01 |  | 3 |  |  | False | True
11403 |  | DfE PAS (DfE Platform Architechture Standards) | To provide standards and reusable artefacts for infrastructure deployment. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT022 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | Department | True | False |  | 2023-03-01
11404 |  | FinOps Services | Making every pound count by improving financial and commercial accountability and planning for cloud computing services; implement devolved budgeting and cost avoidance. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT023 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | Department | True | False |  | 2023-03-01
11405 |  | Find and use APIs | To drive improvements to the FaUAPI platform in order to ensure it is the central tool that all development teams use for API management. To ensure all DfE APIs are in one place, discoverable and easy to interact with. | [5 empty] | False | False |  | Amber |  |  |  |  | BuRT024 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  | Department | True | False |  | 2023-03-01
11406 |  | Eligibility Checking Service (ECS) Replacement | Replacement of ECS legacy system in 2025. The Replacement project has reviewed the end-to-end process for eligibility checking and determined what the overall process and technology should look like in the post-ECS environment. Now in Beta we are building two products as an MVP: a hub – the Entitlements Checking Engine (ECE), and replacement spokes for both School Meals and Childcare. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT025 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  | LAs, department | True | False |  | 2023-03-01
11407 |  | CRM - Delivery Team | Programme of work to deliver standardised products across the business using the Dynamics 365 CRM platform. The CRM applications used across DfE include: Provider; Employer; Capital; ICA; EDD; IEBT and SISL. | [5 empty] | False | False |  | Amber |  |  |  |  | BuRT026 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  |  | True | False |  | 2023-03-01
11408 |  | Infrastructure Services BAU | BAU activity | [5 empty] | False | False |  | Green |  |  |  |  | BuRT028 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 2 |  |  | True | False |  | 2021-04-01
11409 |  | Architecture | BAU activity | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT030 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 2 |  |  | True | False |  | 2023-04-01
11410 |  | AI Adoption | Support DfE to implement AI | [5 empty] | False | False |  | Green |  |  |  |  | BuRT031 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 2 |  |  | True | False |  | 2023-04-01
11411 |  | Criticality Classification | Harmonisation of criticality classifications to ensure a consistent taxonomy so that services apply the appropriate criteria relevant to their service – to ensure appropriate support and assurance is in place. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT032 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | Department | True | False |  | 2024-10-07
11412 |  | DDT Finance | Oversight and planning of DDT finances providing insight to DDT directors and governance forums. Includes spending review work and other finance business planning. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT037 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 2 |  | All divisions in Tech and CXD Directorates, plus Data, CXD and Tech directors for information and insight on DDT workforce as a whole and related reporting to Cabinet Office, DDT Committee and others. | True | False |  | 2024-04-01
11413 |  | Contract Management | Management of contracts and suppliers through which CXD (participating divisions), Tech and other part of DfE budgets. Provide insights to support decision making. Contract management is an essential activity to ensure public money is spent compliantly and achieved vfm. This is a shared service for Tech and most of CXD which achieves economies of scale and continuity of service and expertise for the areas supported. | [5 empty] | False | False |  | Amber |  |  |  |  | BuRT042 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  | All divisions in Tech Directorate plus six Divisions in CXD. Five divisions in CXD who partner with: - Families Group - Regions Group (primarily academies service lines) - Commercial (e.g. Get Help Buying for Schools) - Ops &amp; Infra Group (e.g. Schools Technology). - Skills Group (e.g. Turing Scheme). Plus other users who have nowhere to go or need support in a hurry - e.g. Data Directorate to support management of a critical risk to DfE, we have only User Research participant contract in DfE. | True | False
11414 |  | Workforce management | Managing the workforce in two large Directorates (MI, analysis, reward and recognition) plus insight on DDT workforce as a whole and related reporting to Cabinet Office, DDT Committee and others. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT043 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  | All divisions in Tech and CXD Directorates, plus Data, CXD and Tech directors for information and insight on DDT workforce as a whole and related reporting to Cabinet Office, DDT Committee and others. | True | False
11415 |  | Learning & Development / Early Talent | Leading on key aspects of DDT capability across DfE - early talent schemes, L&D budget and capability-based pay. These are critical to solving recruitment and retention issues that have been longstanding. Driving up Apprenticeship numbers within our Directorates (6%), delivery of £335,000 L&D budget and increasing access to L&D through internal enhancements, implement capability based pay across DDT. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT044 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  | DfE LT, DDT committee, Design and Delivery Board, Cabinet Office, DDT Directors and DDs, Finance colleagues, Commercial colleagues. HR colleagues, all DDT professionals. | True | False
11416 |  | Governance, Performance & Insight | Effective and proporiate governance and assurance including board secretariat, planning, performance, risk and audit. Underpinned by tools and automation to support efficiencies and maintain one version of the truth across the Directorate(s). Shared service across CXDT &amp; DDT for Governance, Performance &amp; Insight. Automation service (PowerPlatform tools Apps and BI) to support effiencies across other SSO teams and provide effective live, self serve tools to DDT customer and leadership. Governance (DDT wide SLT, Design and Delivery Board &amp; DDT Committee) Planning, Performance &amp; Insight - PAD (CXDT &amp; DDT) Insights &amp; associated PowerApps to collect and manage data RMT, Contracts App, BuRT, IYA and IR Apps &amp; DDT Portfolio App Risk management, Audit Management, Performance/KPI and Objective tracking and monitoring &amp; DDT Correspondence | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT045 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 | 2 | DfE LT, DDT committee, Design and Delivery Board, Cabinet Office, DDT Directors and DDs, Finance colleagues, all DDT professionals. | True | False |  | 2024-04-01
11417 |  | DDT Spend Controls & Service Assessments | Ensure compliance with GDS/CDDO service standards and spend controls. | [5 empty] | False | False |  | Amber |  |  |  |  | BuRT046 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  | DfE, GDS, HMT, CDDO | True | False
11418 |  | DDT Capability based pay | Implement DDT Capability Based Pay for Group 1 professions in DfE within three years of business case approval (which was January 2024). We have DfE LT and Baroness Barran's approval for the overall proposition, which is to save significant taxpayers' money by paying certain DDT professionals more and reducing reliance on managed services. DfE has approval from the Government Chief People Offier for its business case to implement CBP for Group 1 professions. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT047 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 2 |  | DDT Directors, DDs plus HoPs and SEO to Grade 6 staff in Group 1 professions. Recruiting Line Managers for eligible posts. Strategic Finance will collect the savings in a single cost centre and allocate as needed across DfE. Will work in conjunction with HR pay team on approving payments. | True | False
11419 |  | Care leavers information / support | Create a service that aims to ensure that young people know all the options and support that are available to them across the journey of leaving care (approaching leaving and having left care) | [5 empty] | False | False |  | Green |  |  |  |  | BuRT050 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | Children approaching leaving care, care leavers and those who support them | False | True
11420 |  | FE Performance Dashboard - Provider & MCA | The FE Performance Dashboard project aims to deliver a dashboard tracking high level outcomes for FE providers and seperately for MCAs. Both products will initially go live on VYED in 2024. By July 25 both products are expected to be launched as public versions on GOV.UK. They are two measure in the FE provider dashboard which we currently have no method of collecting the data to populate the dashboard. We are currently looking at short term solution and longer term options to address this. Expect any longer term version will be a major project. | [5 empty] | False | False | [6 empty] | BuRT066 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | True | False
11421 |  | Lifelong Loan Entitlement | The Lifelong Learning Entitlement (LLE) is a transformation of the student finance system that will replace the current HE Student Finance system from 2025. | [5 empty] | False | False | [6 empty] | BuRT067 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | Higher Education/Students | True | False
11422 |  | Contact Centre Procurement | The re-procurement activity of a business as usual Contact Centre Service provision for the operational areas of Apply to Pay (A2P) and Repayment Customer Services (RCS) within SLC | [5 empty] | False | False | [6 empty] | BuRT068 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  | Higher Education/Students | True | False
11423 |  | iFATE CRM | IFATE is an ALB hosted on DfE’s IT infrastructure. As part if its wider IT transformation programme, IfATE will be introduce a CRM system to support its front line delivery to stakeholder who include Employers and other organisations. | [5 empty] | False | False | [6 empty] | BuRT069 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | True | False
11424 |  | Interventions to harness generative AI in our sectors | Ambitious interventions to harness the opportunities for generative AI in our sectors, on critical path for SoS priorities in 24/25 (unlocking the potential of tech in education). 1) improve evidence base; 2) hackathons and 3) sandbox | [5 empty] | False | False |  | Amber |  |  |  |  | BuRT070 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  | Schools, colleges, edtech providers | False | True |  | 2023-01-03
11425 |  | School Account Programme | Developing an external website that targets personalised support to School Leaders and School Business Professionals; Implementing an internal change programme inc setting out tasks and support to ensure the right services in place (Task and Service Index); Developing a Digital Services Strategy for Schools to co-ordinate service improvement. The programme seeks to improve the way that school leaders and school business professionals intetract with the department and seeks to be a single version of the truth. By standardising the creation & publishing of content, products & services and providing a digital platform that aims to eliminate the fragmentation in both the user’s journey and the underlying digital infrastructure, the DfE can give schools what they need in one place whilst reducing cost, increasing speed of delivery, and transforming and improving our current digital estate. Work in 25/26 will focus on: - developing the underlying source/database of DfE products, services and content that drives the school account experience - developing an onboarding strategy &amp; plan to expand the number and type of DfE products and services that are part of the School Account - developing &amp; scaling the School Account platform and programme delivery approach to deliver the service to a larger group of settings and users at scale, including the internal user experience - transforming the collective approach that the department takes to prioritising, funding, delivering and evaluating the delivery of services to schools. | [5 empty] | False | False |  | Amber |  |  |  |  | BuRT072 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 | 4 | School leaders, School business professionals, internal users from service teams and teams who publish and/or share information & comms with the sector | False | True |  | 2022-01-03
11426 |  | Service Support & Performance Analysis | Provision of frontline support to schools and trusts and to users within Regions Group and SFSO (ESFA). Maintaining legacy systems and services in public beta, including bug fixes. Continously improving the services, based on user feedback and programme priorities. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT073 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 2 |  | Schools and academy trusts, Regions Group, SFSO (ESFA) | False | True
11427 |  | Funding Data Service (FDS) | Funding operations are heavily data dependant. FDS enables operators to make sure that the provider and funding data used in the Funding Service is correct. Work underway to enhance aspects of funding data managed out of CFS into FDS. Future work to integrate into the wider service to centrally serve data. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT074 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  | Department | False | True
11428 |  | Calculation Funding Service (CFS) | Onboarding of outstanding grants. Allows the Allocations team to calculate complex allocations for thousands of schools and providers efficiently and accurately. Profiles the allocations for payment. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT075 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  | Department | False | True
11429 |  | Digital Forms Builder (DFB) | Product being moved to SQL to allow for more complex forms and integration. Allows the user to quickly stand up professional, GDS compliant micro-services to make small collections and transactions better and more efficient. There is an opportunity to improve the efficiency and effectiveness of data collection. The team can then focus on the wider process around the forms to make sure accurate data is collected and that users are aware of what they can apply for, when and how. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT076 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  | Department | False | True
11430 |  | Funding and Contracting Service (FCS) | Automates the generation of hundreds of further education funding agreements and controls the FE payments from data supplied by the provider.​ | [5 empty] | False | False |  | Green |  |  |  |  | BuRT078 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  |  | False | True
11431 |  | Attendance mentoring | This intervention seeks to support better attendance for persistently or severely absent pupils (those who miss 10% or 50% or more of their education). | [5 empty] | False | False | [6 empty] | BuRT079 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | True | False
11432 |  | DCS (Director Childrens Services) Leadership Program (UPON FutureLeaders Programme) | The Upon programme is an important part of the Children’s Social Care (CSC) workforce strategy. The programme has two strands: one for newly recruited Directors of Children’s Services (DCS) and a second strand focussing on those aspiring to the role. | [5 empty] | False | False | [6 empty] | BuRT081 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | DCS/ADCS | True | False
11433 |  | Child Minder Grants | launching a grant scheme for childminders, which is likely to be run externally. Expecting the contractor to build a website / portal to receive applications and with information about the scheme, and commercial have informed us that we need to let you know about any govt business not hosted on gov.uk | [5 empty] | False | False | [6 empty] | BuRT082 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | EY Workforce | True | False
11434 |  | Always Heard Helpline | Provision of a national advocacy advice and ‘safety net’ service (currently known as the “Always Heard” service). The service ensures looked-after children are aware of and understand their rights and entitlements to advocacy; signposts them to local advocacy services; and provides direct ‘safety net’ advocacy for those who have been denied or cannot access local services. | [5 empty] | False | False | [6 empty] | BuRT083 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | looked-after children | True | False
11435 |  | Assessed & Supported Year in Employment | funds employers to provide bespoke support to their newly qualified social workers (NQSWs) which is fundamental to raising the quality of frontline practice and improving social worker retention. The funding enables further professional development to take place and requires employers to meet expectations around induction and support for newly qualified staff. | [5 empty] | False | False | [6 empty] | BuRT084 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | NQSWs | True | False
11436 |  | LA Early Implementers | Sub programme of Early Years Childcare reforms Programme - plan to extend rollout to LAs ahead of the national rollout to understand the labour market impacts and to understand the barriers/impacts of the extension to the EY entitlements. | [5 empty] | False | False | [6 empty] | BuRT085 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | LAs | True | False
11437 |  | National School Breakfast Programme | The National School Breakfast Programme (NSBP) is funded by the Department for Education and delivered by Family Action to support schools in England to provide children with a healthy breakfast at the start of the school day. +1 - final year of contract. | [5 empty] | False | False | [6 empty] | BuRT086 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | Schools, pupils | True | False
11438 |  | NELI (Nuffield Early Language Intervention) | to improve language outcomes for disadvantage children in Reception Class. Training being delivered to TAs to implement with children. This was to reduce the progress impact as a result of Covid. | [5 empty] | False | False | [6 empty] | BuRT087 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | Settings, reception learners | True | False
11439 |  | Loving Relationships Programme | Funding of £30.1m in the next two years (£11.7m in 2023-24 and £18.4m in 2024-25) to significantly increase the number of LAs with family finding, mentoring and befriending programmes, including Lifelong Links. | [5 empty] | False | False | [6 empty] | BuRT088 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | LAs | True | False
11440 |  | SEND Supported Internships | SIs are a type of study programme aimed at 16-24 year olds who have an Education Health and Care (EHC) plan, who want to move into employment and who need extra support to do so. | [5 empty] | False | False | [6 empty] | BuRT089 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | LAs (learners) | True | False
11441 |  | Fostering recruitment and retention | Working with local authorities across the North East region to introduce a new regional hub to support individuals interested in applying to foster, facilitate regional targeted communications and improve retention. | [5 empty] | False | False | [6 empty] | BuRT090 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | LAs | True | False
11442 |  | New data solution for tracking and analysing Serious Incident Notifications (SINs), Rapid Reviews and Local Child Safeguarding Practice Reviews (LCSPRs) | data management for the Safeguarding Review Panels, including analysis and reporting. | [5 empty] | False | False |  | Amber |  |  |  |  | BuRT091 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | DfE, | True | False
11443 |  | Care Leavers Covenant | CLC is designed to enable national and local private, public and voluntary sector organisations across wider society to make a public commitment to support care leavers by providing specific practical things that help them to live independently | [5 empty] | False | False | [6 empty] | BuRT092 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | national and local private, public and voluntary sector organisations | True | False
11444 |  | Fosterlink | To support local authorities (LAs) to increase the numbers of foster carers they successfully recruit, increase placement stability, and deliver cost savings for the LA | [5 empty] | False | False | [6 empty] | BuRT093 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | LAs | True | False
11445 |  | Designated Family Judge - Trailblazer Pilot | Trailblazer pilot aims to tackle the drivers of delay across the FJ system therefore reducing costs across the FJ system and improving children’s outcomes. | [5 empty] | False | False | [6 empty] | BuRT094 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | LAs | True | False
11446 |  | Fosterline | Reprocurement of a free, confidential, impartial advice/support service | [5 empty] | False | False | [6 empty] | BuRT095 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | Existing and potential foster carers | True | False
11447 |  | Wraparound Childcare - Start-up Programme | pump prime pilot, help test and further understand what support and funding is needed at a national level to support all schools to ensure availability of wraparound childcare for all families who need it, so we can support parents to work/get into work. | [5 empty] | False | False | [6 empty] | BuRT096 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | schools | True | False
11448 |  | CYP Advisory Board | The team are setting up a Children and Young Person’s Board. They want to set up a website to provide updates on the activities of this CYP Board. Also looking to procure secretariat function (contract). | [5 empty] | False | False | [6 empty] | BuRT097 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | DfE, Board members | True | False
11449 |  | Always Heard (Advocacy) helpline | Provision of a national advocacy advice and ‘safety net’ service (currently known as the “Always Heard” service). | [5 empty] | False | False | [6 empty] | BuRT098 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | CYP | True | False
11450 |  | Educational Psychology Training | Programme aims to continue the supply of Educational Psychologists (EPs) into the local authority (LA) workforce, by seeking approval to continue part -funding the three-year EP Doctorate training course. | [5 empty] | False | False | [6 empty] | BuRT099 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | Universities | True | False
11451 |  | What Works Centre Foundations | Learning and evaluation from the IP and PIP is currently available on different websites and is not well utilised by the sector. This programme would see the body of work hosted in one place and communicated to the sector as part of WWCSC’s impact strategy, therefore increasing the use and impact of the learning in practice settings. | [5 empty] | False | False | [6 empty] | BuRT101 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | CSC and SEND worksforces | True | False
11452 |  | Complete end-to-end grant management system | MAPs initial overall aim is to be a complete end-to-end grant management system from data to payment approval for all funding. | [5 empty] | False | False | [6 empty] | BuRT104 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | True | False
11453 |  | Schools Tech Policy (Strategy for schools to gain digital maturity) | Policy interventions to make sure all schools have secure, effective and efficient techology infrastructure, meet basic technology standards, have the capability and capacity to use tech effectively and set a sustainable digital strategy for the future, including use of emerging technologies and assistive technology. Responsible for dept relationship with the edtech market including new activity on kitemarking products for safety and outcomes. Aims of programme: to improve outcomes, reduce workload and make efficiencies in schools. Set the strategy and policy interventions so that all schools can achieve a good level of digital maturity and use technology effectively. This is on the critical path for SoS priorities (digital/AI - ensure broadband and basic infrastructure in sectors). Aims of programme: to improve pupil outcomes, reduce staff workload and make efficiencies in schools. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT107 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  | Schools, colleges, edtech providers | False | True
11454 |  | Live Apprenticeship Service | Build/test/run an end to end Digital Service for Apprentices, Employers, Providers and End Point Assessment Organisations. The Apprenticeship Service is an end-to-end Digital service that builds, tests and runs Digital systems for Apprentices, Employers, Providers and End Point Assessment Organisations. It comprises of 11 transactions (0.7bn transactions a year) that drives efficiencies through a Digital first approach of self-serve. Apprentices are inspired to apply for an Apprenticeship through Apprenticeships.gov. Find an apprenticeship has 2.8million accounts. 30,000 vacancies are added by employers and providers a month. Employers manage apprentices and their Levy funds online through 253,000 employer accounts, and providers apply through the Register of Training Providers to qualify for Government Funding. We pay £2.4bn yearly to providers and employers through digital payments systems. The functionality is supported by a Service Support desk which gets 500 calls per week and through user research and testing (3,000 face to face UR sessions, 4,500 surveys). | [5 empty] | False | False |  | Green |  |  |  |  | Z00ERF0012/13 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  | Apprentices (and Potential Apprentices), Employers (Levy Payers) and SMEs, Approved Training Providers, End Point Assessment Organisations | False | True
11455 |  | OVERSIGHT ACROSS OUR ALBs TO INCREASE CYBER RESILIENCE - [current focus area to report on is - ALB cyber assurance return) | [6 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT132 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | False | True |  | 2024-09-01
11456 |  | Compare School and College Performance | A digital service provided by DfE to help the public access and compare school or college performance. CSCP is mainly used by school and college staff, leaders and governing bodies, parents and other stakeholders interested in educational outcomes. It is a Public facing service that provides information on school and college performance to parents, schools, Ofsted, LA’s, researchers and governors. The service is designed to support parental choice, increase school accountability and support improvement. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT136 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  | Parents; Schools; Ofsted; Local Authoriteis; Researchers; Governors. | False | True |  | 2021-03-01
11457 |  | Analyse School Performance | A web-based interactive that allows schools to review their performance data to support self-evaluation, and is the main source of data for School Improvement Advisers and OFSTED Inspectors. ASP is accessed through DfE Sign in that gives school leaders, governors, LAs, MATs, dioceses, DfE and Ofsted access to official detailed pupil level performance data. The service is designed to support accountability policy and helps schools improve by providing accurate attainment data. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT137 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  | Schools; Local Autorities; MATs; Dioceses; Ofsted; Traning Providers; DfE regional & policy teams. | False | True | [13 empty] | 2022-03-04
11458 |  | Metadata & Data Quality - Education and Awareness | [6 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT138 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 5 |  |  | True | False |  | 2023-04-03
11459 |  | NOT ON I&P PERF REPORT - Critical Data / ESDA (Data Quality Capability Development) | An Essential Shared Data Asset (ESDA) is data provided or acquired by a government department or agency to provide an essential process or purpose. To provide CDDO with information required to support their Roadmap 2022-2025, xpecifically "better data to power decision making", of which 2 specifically relate to critical data assets. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT140 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 5 |  |  | True | False |  | 2023-04-03
11460 |  | Driving effectiveness of AI tools for education | To develop the departments AI capability we are bringing together a store of education content which has been optimised for AI use. This content is a vital ingredient for high quality AI education tools which are tailored to our system and curriculum. Working with DSIT, no10 colleagues and an external contractor, we will run hackathons where edtech developers can access this content to develop new AI education tools. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT143 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  | For the content store: Schools, colleges, providers for uploading content to the content store. Developers/edtech providers accessing content store content via API. | False | True |  | 2024-09-09
11461 |  | Get Help with Data Protection in Schools | Providing advice and guidance on the use of personal data to DfE and ESFA staff, ensuring policies and practices meet with data protection legislation and codes of practice. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT147 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 13:09 |  | 3 |  |  | True | False
11462 |  | AI Tools for Appraisal | Advice and guidance on access to and collection of paper records (using offsite archive providers), on management of digital knowledge and information content in shared areas in DfE and anywhere else that DfE records are held | [5 empty] | False | False |  | Amber |  |  |  |  | BuRT149 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | True | False |  | 2024-09-01
11463 |  | Individualised Learner Record (ILR) | We will collect, assure, analyse, manage and share key data on learners and the sector for processing as part of the end-to-end funding service. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT151 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  |  | False | True
11464 |  | Approvals Simplification and Earnings Calc | The Service are implementing a new payments system that pays providers using primarily Service data, reducing reliance on ILR data. This work will provide more flexibility for the programme to adapt payment models, improve the management of change of circumstances through provider accounts, and release funding more readily to providers as a result of reduced data locks. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT155 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | False | True |  | 2024-12-02 | [7 empty] | 2024-10-04 |  |  |  | 2025-09-01
11465 |  | Run and maintain live service National Careers Service and Skills for Careers | To support the triage (1st line) Service Management Services and provide 2nd line resolution (where relevant), using the Buyer’s Tooling, including: Incident Management; Problem Management; Change Management; Release Management; Risks and Issues and Knowledge Management. Provide support during the development lifecycle to include the development and testing of environment configuration, including Technical Spikes; assist with debugging and troubleshooting of platform level problems. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT156 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  |  | False | True
11466 |  | Interactive Careers and Skills | The Beta phase was approved at the Portfolio Review Meeting on 2 July 2024 with the following agreed recommendations: The high-level recommendations that were presented for Beta are: Understanding Skills User needs, this includes a continuing with User Research and the retirement of Skills Health check, Improving the Signposting of service features and Navigation of the product Improvements to the Triage Tool – including personalisation of content to mindsets, 2 stage selection of articles and filtering. Improvements to DYSAC – includes changes to content to improve on users understanding of the intent of using DYSAC, improvement of users understanding of the summary and the results shown. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT157 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  |  | False | True |  | 2024-02-01
11467 |  | Data Insights | Design, develop, and maintain the technical infrastructure, data models, and visualisations that enable the Digital scorecard and Power Bi to deliver insights Supporting the identifying of additional KPI’s and data points which work to demonstrate performance of the digital service in line with user, policy and business needs.Developing additional visualisations within PowerBi or improving existing ones. Development or support with any Digital Scorecard and data insights team backlog items | [5 empty] | False | False |  | Green |  |  |  |  | BuRT160 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  |  | False | True |  | 2023-07-03
11468 |  | Access Your Teaching Qualifications | [6 empty] | False | False |  | NOT STARTED |  |  |  |  | IT636b |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  |  |  |  | False | False
11469 |  | Find a lost Teacher Record Number | [6 empty] | False | False |  | NOT STARTED |  |  |  |  | IT636a |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | False | False
11470 |  | SLD - FE workforce collection roll forward for 24/25 | Roll forward the FE Workforce collection for 24/25 and delivery any required policy updates. Will open in Oct 25 and close in Jan 26. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT164 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | False | True
11471 |  | Matched Data Production | To provide Operational Matched Data Production for Learner Data. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT166 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  | End users - The key users are the National Funding Formula, Pupil Premium and Accountability & Skills Policy and Statistics Teams. However, the data under NPDAAT is used across the department, sector and public citizen to inform research, analysis and decision making. | False | True
11472 |  | LDS - NPDAAT - KS2 | To enable the department to provide KS2 data to fulfil education and department needs. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT168 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  | Public Ofsted Ofqual STA | False | True
11473 |  | LDS - NPDAAT - KS4 | To enable the department to provide KS4 data to fulfil education and department needs. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT167 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  | Public Ofsted Ofqual STA | False | True
11474 |  | LDS - NPDAAT - 16-18 | To enable the department to provide 16-18 data to fulfil education and department needs. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT169 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  | Public Ofsted Ofqual STA | False | True
11475 |  | Find education and training | Creation of a single tool that:​​ empowers young people to explore all their education and training options in their area; helps those facing additional barriers; assists parents, teachers and careers advisors to support these decisions; maintains relevance regardless of the direction of future policy and organisational delivery | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT177 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | False | True |  | 2024-04-01
11476 |  | Heads of Profession Framework | Embed the Heads of Profession Framework including weekly profession time | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT186 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | True | False |  | 2024-04-01
11477 |  | Culture & behaviours (wave 2) | [6 empty] | False | False |  | Green |  |  |  |  | BuRT190 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | True | False |  | 2024-06-03
11478 |  | Service and delivery lifecycle (wave 2) | [6 empty] | False | False |  | ON HOLD |  |  |  |  | BuRT193 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | True | False
11479 |  | Driving safety of AI tools for education | Lay the groundwork to ensure the safe and compliant use and monitoring of generative AI in education. Background The program aims to optimise generative AI tools to benefit the English education system, reducing teacher workload and closing the attainment gap. It ensures safe governance of UK education data for AI training, improving tool quality and benefits. It enhances the DfE’s ability to develop AI/ML tools and insights, informing better interventions, support, and policy. These are the projects: Content Store and Catalyst Fund: Make funding and pre-processed education content/data available to AI developers to drive creation of high-quality, evidence-based AI educational products (£3m DSIT funding, £1m DfE funding). Safety expectations and safety interface piloting: Setting expectations for the safety of AI products used in education; small scale testing of safety mechanisms in school | [5 empty] | False | False |  | Green |  |  |  |  | BuRT197 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | False | True |  | 2025-04-30
11480 |  | To provide a digital service to collect organisation level data from the sector to support Funding and Oversight | To collect and process that data to inform funding, assurance and provide business intelligence to the organisation. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT199 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 2 |  |  | False | False
11481 |  | To provide data collections and modelling services within EDFO for funding and assurance purposes | To provide collections, data management, business intelligence and visualisation services across ESFA and DfE where we are required. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT200 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  |  | False | False
11482 |  | Operational Data Science Service | Deliver the analysis and modeling requests from the ESFA Directorates, prioritised and agreed upon for the financial year, within the specified timeframe and quality standards. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT201 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  |  | False | False
11483 |  | Get Information about Pupils (GIAP) | GIAP allows schools, Local Authorities and Further Education establishments to search for and download pupils’ end-of-Key Stage results data and their contextual indicators, including Pupil Premium information, from a DfE National Database The service allows users to access selected pupil level census and attainment data from the national pupil database, to create and monitor the progress of virtual cohorts of pupils and access pupil premium information It is used by schools, further education colleges and Local Authorities to access matched National Pupil Database (NPD) datasets for their pupils and download important Pupil Premium data. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT202 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  | Schools (c20,000)​ Local authorities (c150) Academy trusts (c5,000) Further Education colleges (c300) | False | True
11484 |  | Growth & Skills Offer (phase 2) | [6 empty] | False | False |  | Amber |  |  |  |  | BuRT206 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | False | True |  | 2025-04-01
11485 |  | HMRC validation | Automated checking of whether an apprentice is employed. Reduce fraud. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT207 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | False | True |  | 2024-06-03
11486 |  | School Accountability and Performance Discovery | By providing parents with comprehensive, accessible and transparent data/info on school performance, schools will be motivated to maintain or improve their standards to remain competitive and attract pupils to secure revenue. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT209 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  | Discovery: Policy team; parents, school leaders | True | False |  | 2025-01-20
11487 |  | Find a Course | [6 empty] | False | False |  | Green |  |  |  |  | BuRT210 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | False | True |  | 2025-01-14
11488 |  | Define Team (Paused) | [6 empty] | False | False |  | Green |  |  |  |  | BuRT211 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | False | False
11489 |  | External Applications | [6 empty] | False | False |  | Green |  |  |  |  | BuRT212 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | False | False
11490 |  | CAT/CI | [6 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT214 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 2 |  |  | True | False
11491 |  | LDS 2.0 (improve, re-platform and transform LDS) (DD028h) | Re-platfrom the recently in-housed LDS service from DEI to Databricks to be delivered by 26/27. Discovery completed May 25 and development commenced. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT216 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  | The key users are the National Funding Formula, Pupil Premium and Accountability & Skills Policy and Statistics Teams. However, the data under NPDAAT is used across the department, sector and public citizen to inform research, analysis and decision making. | False | False |  | 2024-11-01
11492 |  | Digital Certification | Switch apprenticeship certificates to digital by default. This project is essential for gaining efficiencies and programme value for money. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT218 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | False | True |  | 2024-08-01
11493 |  | Ministerial Commission - Online Safety (Discovery) | 12-week research project to conduct one-to-one interviews with parents from a range of backgrounds, to understand their views around online safety and extreme misogyny in more depth, along with ideas for the role of DfE in supporting them. The project will also link with DfE policy colleagues and other Government Departments. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRt220 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | False | False
11494 |  | Early Years Census: termly collection | Move to collect the EYC data termly rather than annually. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT221 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  |  | False | False
11495 |  | Existing data collection | Ongoing collection of BAU data used by Families Group including School Census | [5 empty] | False | False |  | Green |  |  |  |  | BuRT222 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 2 |  |  | False | False
11496 |  | Breakfast Clubs | There are four data elements required to support the introduction of breakfast clubs: 1. Expression of Interest form for schools to sign-up to the pilot [now live] 2. Sharing of the blueprint toolkit with pilot schools 3. Medium term data required for funding and analysis of the pilot starting in April 2025. 4. Longer term data needed for live running. | [5 empty] | False | False |  | Amber/Red |  |  |  |  | BuRT223 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | False | False
11497 |  | Customer Service Digital Strategy | [6 empty] | False | False |  | Amber |  |  |  |  | BuRT224 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | False | False |  | 2025-06-02
11498 |  | Customer Service Centralisation and Transition. | Centralise OIG teams into CSEO division. DfE teams to follow in 2026/27. Migration of services roadmap - refresh, transition plan and timelines and updated MOUs required, (with learns from migrations undertaken in 2025). Outsource partnership management Service resilience, efficiency, scalability & flexibility | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT225 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | False | False |  | 2025-01-02
11499 |  | Customer Service Technology and Transformation | [6 empty] | False | False |  | Green |  |  |  |  | BuRT226 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  |  | False | False |  | 2025-04-01
11500 |  | Service Engagement | [6 empty] | False | False |  | Amber |  |  |  |  | BuRT227 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  |  | False | False |  | 2025-04-01
11501 |  | Service recovery | Complaint improvement delivery program and complaint policy review. (Includes process and policy review customer concerns about whistleblowing and safeguarding.) Options / recommendations on opportunity to create central team, governed by one policy and using one CRM to enhance insight and reporting. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT228 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  |  | False | False |  | 2024-11-01
11502 |  | Service Insight | Insight into why customers are behaving (making contact) in the way they do and identify policy, process and communication failures and reduce / automate future contact. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT229 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  |  | False | False |  | 2025-04-01
11503 |  | AI Statement of Work Assessment: Part 2 | To investigate uncover user experiences and needs relating to SOW To identify business requirements for SOW within DfE To establish and align with external workflow for using external SOW tool | [5 empty] | False | False |  | Green |  |  |  |  | DDTi-17 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | False | False |  | 2025-06-16
11504 |  | Data Insights project | Short Term: Deliver an interim tactical solution which enables sharing of mapped information and drawing of insights. Long Term: Deliver a solution which enables maps to be shared, insights to be created, and maps to be maintained as live. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | DDTi-18 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | True | False |  | 2025-03-16
11505 |  | Find User Insights Alpha | [6 empty] | False | False |  | Green |  |  |  |  | DDTi-24 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 2 |  |  | True | False |  | 2025-06-16
11506 |  | Keeping children safe online (responsible adults) digital information project | "Comissioned by Minister Morgan Project goal is: To understand issues around online safety and extreme misogyny among a range of parents and experts alongside mapping out the policy interventions by DfE and other government departments. This will enable a gap analysis and assessment of potential for further interventions by DfE or government to better support parents to understand and educate their children, alongside interventions through schools." | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT230 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | False | True |  | 2025-07-09
11507 |  | DDT Strategic Objective 1 | "Register of Serices Information Problem statementWe don’t have a consistent understanding of our users and services.As a result we don't efficiently deliver joined up, high-quality outcomes or fully understand the current value, innovation opportunities and potential savings." | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT231 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 2 |  |  | True | False |  | 2025-04-25
11508 |  | DDT Strategic Objective 8 | [6 empty] | False | False |  | Green | [9 empty] | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | False | False
11509 |  | Comms campaign help: Information to parents | "Best Start in Life Collaboration between Strat Comms, family policy and DHSC colleagues to create a landing page for NHS site Best start for life and DFEs Childcare Choices. " | [5 empty] | False | False |  | Green |  |  |  |  | BuRT233 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 2 |  |  | False | True |  | 2025-05-25
11510 |  | AI Comms Hub | Ensures that all employees have access to the most current updates, policies, and details in the I space. This hub helps maintain consistency in messaging and ensures that everyone is on the same page. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT324 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 2 |  |  | True | False |  | 2025-05-25
11511 |  | Gen AI Champions Network | The Champions network enhances communication, engagement, and the successful implementation of AI initiatives. It will help foster a positive mindset within the organisation. Champions have been setup to engage early and continuously with stakeholders, facilitating understanding and trust, and mitigating challenges. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT235 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  |  |  |  | True | False |  | 2025-05-25
11512 |  | DfE Ethics for Gen AI | The Ethics policy is being set up to enhance the work in the AI space, protect our organisational reputation, and ensure effectiveness. It will ensure consistency, understanding and governance within DfE and provide clear guidance to staff on when and how to implement ethical considerations. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT326 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | True | False |  | 2025-05-25
11513 |  | User research manual guidance improvements | Redesign and rewrite the content in the Guidance and User Insights to make it more usable, findable and specific to DfE user research contexts, enabling better efficiency and lower risk user research across DfE. Delivered in two phases: 1. design content strategy and patterns, and redesign information architecture, and 2. rewrite all existing content into the new design. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT327 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  |  |  |  | True | False |  | 2024-12-24
11514 |  | Schools users research participant panel | Creation of a CRM of opted-in research participants from school leadership and school business professional user groups, plus processes for URs across DfE to access it, and comms strategy to drive sign-ups into it. Technical build of the platform (into DfE Microsoft CRM) is being delivered by the Solution Delivery Team in Infrastructure and Platforms. | [5 empty] | False | False |  | Red |  |  |  |  | BuRT328 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  |  |  |  | True | False |  | 2025-06-24
11515 |  | User research incentives service and policy | Procurement of specialist supplier of user research incentives, to enable teams to access incentives in an efficient, cost effective way. Also an incentives policy to ensure proper, ethical and value for money use of incentives (policy being developed in collaboration with DfE Social Research) | [5 empty] | False | False |  | Amber |  |  |  |  | BuRT329 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  |  |  |  | True | False |  | 2025-06-25
11516 |  | User research participant supplier re-procurement | Procurement to replace incumbent supplier at end of contract, to ensure all teams across DfE have access to a high quality commercial recruitment capability (nb, this re-procurement will happen earlier than initially planned, due to burn rate in current contract) | [5 empty] | False | False |  | Amber |  |  |  |  | BuRT330 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  |  |  |  | True | False |  | 2025-06-25
11517 |  | Accessibility audit process improvement | [6 empty] | False | False |  | NOT STARTED |  |  |  |  | BuRT331 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  |  |  |  | False | False
11518 |  | Interaction design and ux training programme development for people looking to move into, or develop their technical design skills | [6 empty] | False | False |  | NOT STARTED |  |  |  |  | BuRT332 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  |  |  |  | False | False
11519 |  | Improving user journeys in early education and childcare | [6 empty] | False | False |  | Green |  |  |  |  | BuRT333 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 | 3 | Parents and carers accessing government funded childcare. | False | True | [5 empty] | 2025-10-13
11520 |  | INCREASING CYBER RESILIENCE IN SCHOOLS [Current focus area to report on is - Sector Operational Hub for Schools] | [6 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT334 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | False | True
11521 |  | EMBEDDING SECURE DESIGN AND ARCHITETURE THROUGHOUT THE OUR DELIVERY LIFECYCLES [Current areas to focus on are SSDLC and CA for digital services] | [6 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT335 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | True | False
11522 |  | HARDEN DFE'S SYSTEMS [current focus area to report on is - Continuous Assurance CA platform to increase the security posture of our foundation systems] | [6 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT336 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | True | False |  | 2025-07-01
11523 |  | PROACTIVE CYBER SECURITY RISK MANAGEMENT [Current focus area to report on is - single view of departmental cyber risks and effective risk management processes embedded throughout the organisation] | [6 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT337 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | True | False
11524 |  | ESTABLISH DFE'S TARGET DATA GOVERNANCE FUNCTION | [6 empty] | False | False |  | NOT STARTED |  |  |  |  | BuRT338 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 2 |  |  | False | False
11525 |  | INCREASING CYBER RESILIENCE IN FURTHER EDUCATION [Current focus area to report on is FENCCSS - Further Education Network Connectivity, Cyber Security Services] | [6 empty] | False | False |  | Amber |  |  |  |  | BuRT339 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | False | False
11526 |  | GOVASSURE ASSESSMENTS ENABLE TARGETED HARDENING OF ESSENTIAL SERVICES | [6 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT340 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | False | False
11527 |  | Best Start Digital Service | Exploring how we can maximise the impact of the BSIL website through improving parent/carer cross-government user journeys and developing new products to support parents. In the discovery phase, we will explore what support around parenting and the home learning environment parents/carers need for their children to get the outcomes they need and the opportunities to deliver the biggest impact. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT341 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 | 3 | Parents/carers of 0-5 year old children | False | True |  | 2025-10-06 |  |  |  | 2026-01-05
11528 |  | Best Start in Life Campaign Site (Live) | Use user centred design (UCD to design a Government Communications Service (GCS) campaign landing page for the Best Start in Life comms campaign to parents of 0 - 5-year-olds ready for the campaign launch in September. The campaign needs to strongly signpost to both the NHS "Start in Life" campaign and the Childcare Choices as well any other priority government information needed by parents of 0 - 5-year-olds. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT342 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  |  | False | False
11529 |  | Early Years – Childcare Access (Discovery) | The purpose of the discovery is to strengthen our understanding of parents' and carers' user journeys to access cross-government funded early education and childcare, so that we can identify changes that would improve the user journey of government funded early education and childcare entitlements and offers. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT343 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | False | False
11530 |  | Early Years – Workforce Register (Discovery) | To introduce a professional register of EY practitioners to gain a better view of those who work in EY including the qualifications they hold. This is called out in the BSIL publication. The register will support DfE to make targeted interventions, improve workforce management and sufficiency, and reduce safeguarding risks. The belief is that it would also lead to the workforce feeling more valued through providing them professionalisation and recognition, with a hope that any future workforce register might improve relationships with the sector. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT346 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 1 |  |  | False | False
11531 |  | Care Leavers (Beta) | To bring together and simplify relevant information for young people leaving care and their intermediaries to make them aware of, and help them understand, the services and support available to them so they can navigate independent life to meet their diverse needs. Support for care leavers | [5 empty] | False | False |  | Green |  |  |  |  | BuRT347 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | False | False
11532 |  | Eligibility Checking Service (ECS) – Eligibility Expansion (Change Project) | By September 2025, working parents will be able to claim 30 hours of free childcare a week, over 38 weeks of the year, for children from nine months up to their child starting school. The ECS needs to be updated and changes made to ensure the entitlement expansion is built in. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT348 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 3 |  |  | False | False
11533 |  | Eligibility Checking Engine (Private Beta) | Replacement of ECS legacy system in 2025. The Replacement project has reviewed the end-to-end process for eligibility checking and determined what the overall process and technology should look like in the post-ECS environment. Now in Beta we are building two products as an MVP: a hub – the Entitlements Checking Engine (ECE), and replacement spokes for both School Meals and Childcare. | [5 empty] | False | False |  | Amber/Green |  |  |  |  | BuRT349 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | False | False
11534 |  | In house UKRLP and incorporate PIMS into a single Provider Management service | In housing UKRLP and incorporating PIMS into a single service. The solution will be a fit-for-purpose, DfE design that fulfils all of the operational and technical requirements through one service. | [5 empty] | False | False |  | Green |  |  |  |  | BuRT355 |  |  |  |  | False |  |  |  |  | Active |  | False | 2025-11-20 11:01 | 2025-11-20 11:01 |  | 4 |  |  | False | False |  | 2025-04-30

## Users
Id | AzureObjectId | Email | Name | FirstName | LastName | UserPrincipalName | JobTitle | PhotoUpdatedAt | Role | CreatedAt | UpdatedAt
1 | 02f70415-5d66-4b88-af44-e21d0879808a | Andy.JONES@education.gov.uk | JONES, Andy | Andy | JONES | Andy.JONES@education.gov.uk |  | 2025-11-28 19:30 | SuperAdmin | 2025-10-17 21:30 | 2025-11-28 19:30
2 |  | kerry.lyons@education.gov.uk | Kerry LYONS | [5 empty] | Visitor | 2025-10-27 12:59 | 2025-10-27 12:59
3 | c010c450-1cef-4ad2-8ac2-96870b5b3dd8 | Jo.WRIGHT@education.gov.uk | WRIGHT, Jo | Jo | WRIGHT | Jo.WRIGHT@EDUCATION.GOV.UK |  | 2025-11-15 11:51 | Visitor | 2025-11-03 18:36 | 2025-11-15 11:51
4 |  | jake.lloyd@education.gov.uk | Jake Lloyd | [5 empty] | Visitor | 2025-11-03 18:44 | 2025-11-03 18:44
5 | faaca2ab-4904-4f18-8228-4a011f6e4faf | Louise.CLARK@education.gov.uk | CLARK, Louise | Louise | CLARK | Louise.CLARK@EDUCATION.GOV.UK |  | 2025-11-15 11:54 | Visitor | 2025-11-14 12:57 | 2025-11-15 11:54
8 | a2330846-1fe5-49c2-8931-c72db41db0df | Juliet.KAMPASI@education.gov.uk | KAMPASI, Juliet | Juliet | KAMPASI | Juliet.KAMPASI@EDUCATION.GOV.UK |  | 2025-11-14 21:49 | Visitor | 2025-11-14 21:49 | 2025-11-14 21:49
12 | e57d3845-6188-48e7-963e-d46363500207 | Tracey.DALE@education.gov.uk | DALE, Tracey | Tracey | DALE | Tracey.DALE@EDUCATION.GOV.UK |  | 2025-11-15 11:55 | Visitor | 2025-11-15 11:55 | 2025-11-15 11:55
13 | ef58175c-38bb-4aa4-b081-c5f0e49b2e10 | Prina.PATEL@education.gov.uk | PATEL, Prina | Prina | PATEL | Prina.PATEL@EDUCATION.GOV.UK |  | 2025-11-15 11:55 | Visitor | 2025-11-15 11:55 | 2025-11-15 11:55
14 | 9556c339-cdf8-4b2a-ad3f-00fed5f97ec1 | Sherene.MORRIS@education.gov.uk | MORRIS, Sherene | Sherene | MORRIS | Sherene.MORRIS@EDUCATION.GOV.UK |  |  | Visitor | 2025-11-15 12:43 | 2025-11-15 12:43
15 | 652744d9-9a6b-401b-a970-64e3073e2ee0 | Rachel.SHOOTER@education.gov.uk | SHOOTER, Rachel | Rachel | SHOOTER | Rachel.SHOOTER@EDUCATION.GOV.UK |  | 2025-11-15 13:56 | Visitor | 2025-11-15 13:27 | 2025-11-15 13:56
16 | 2d8cb4a5-98e4-4adb-847c-b3b9a4ea3639 | Sammi.CLARKE@EDUCATION.GOV.UK | CLARKE, Sammi | Sammi | CLARKE | Sammi.CLARKE@EDUCATION.GOV.UK |  | 2025-11-19 20:04 | Visitor | 2025-11-19 20:04 | 2025-11-19 20:04
17 | fbcf800a-b91a-48bb-93d1-d4d27e67e97b | Shafiqa.DAWOOD@education.gov.uk | DAWOOD, Shafiqa | Shafiqa | DAWOOD | Shafiqa.DAWOOD@EDUCATION.GOV.UK |  | 2025-11-19 20:04 | Visitor | 2025-11-19 20:04 | 2025-11-19 20:04
18 | 5d29ea54-aacd-4209-b91f-afb191e97cd8 | Adam.DUMBELL@education.gov.uk | DUMBELL, Adam | Adam | DUMBELL | Adam.DUMBELL@EDUCATION.GOV.UK |  | 2025-11-19 20:05 | Visitor | 2025-11-19 20:05 | 2025-11-19 20:05
19 | ae9d166e-7a5b-44a2-acfa-ee02c3c2ea24 | Kuldip.OSBORNE@education.gov.uk | OSBORNE, Kuldip | Kuldip | OSBORNE | Kuldip.OSBORNE@EDUCATION.GOV.UK |  | 2025-11-19 20:05 | Visitor | 2025-11-19 20:05 | 2025-11-19 20:05
20 | fa01b414-9e39-4740-ab85-0ef228e3f7e7 | Luke.SLOWEN@education.gov.uk | SLOWEN, Luke | Luke | SLOWEN | Luke.SLOWEN@EDUCATION.GOV.UK |  | 2025-11-28 19:30 | Visitor | 2025-11-28 19:30 | 2025-11-28 19:30

## BusinessAreas
Id | Name | Description | SortOrder | IsActive | CreatedAt | UpdatedAt
1 | Commercial |  | 10 | True | 2025-10-27 18:07 | 2025-10-27 18:07

## Phases
Id | Name | Description | SortOrder | IsActive | CreatedAt | UpdatedAt
1 | Explore |  | 0 | True | 2025-10-27 18:08 | 2025-10-27 18:08

## ActivityTypes
Id | Name | Description | SortOrder | IsActive | CreatedAt | UpdatedAt
1 | Change/Improve project |  | 10 | True | 2025-11-19 19:28 | 2025-11-19 19:28
2 | Cross-cutting function |  | 20 | True | 2025-11-19 19:28 | 2025-11-19 19:28
3 | Live service |  | 30 | True | 2025-11-19 19:28 | 2025-11-19 19:28
4 | New service in development |  | 40 | True | 2025-11-19 19:28 | 2025-11-19 19:28
5 | Wishlist |  | 50 | True | 2025-11-19 19:29 | 2025-11-19 19:29

## DirectoratesLookup
Id | Name | Description | SortOrder | IsActive | CreatedAt | UpdatedAt

## RiskAppetite
Id | Name | Description | SortOrder | IsActive | CreatedAt | UpdatedAt
1 | Averse | Avoidance of risk and uncertainty in achievement of key deliverables or initiatives is key objective. Activities undertaken will only be those considered to carry virtually no inherent risk. | 10 | True | 2025-11-19 19:22 | 2025-11-19 19:22
2 | Minimal | Preference for very safe business delivery options that have a low degree of inherent risk with the potential for benefit/return not a key driver. Activities will only be undertaken where they have a low degree of inherent risk. | 20 | True | 2025-11-19 19:23 | 2025-11-19 19:23
3 | Cautious | Preference for safe options that have low degree of inherent risk and only limited potential for benefit. Willing to tolerate a degree of risk in selecting which activities to undertake to achieve key deliverables or initiatives, where we have identified scope to achieve significant benefit and/or realise an opportunity. Activities undertaken my carry a high degree of inherent risk that is deemed controllable to a large extent. | 30 | True | 2025-11-19 19:23 | 2025-11-19 19:23
4 | Open | Willing to consider all options and choose one most likely to result in successful delivery while providing an acceptable level of benefit. Seek to achieve a balance between a high likelihood of successful delivery and a high degree of benefit and value for money. Activities themselves may potentially carry, or contribute to, a high degree of residual risk. | 40 | True | 2025-11-19 19:23 | 2025-11-19 19:23
5 | Eager | Eager to be innovative and to choose options based on maximising opportunities and potential higher benefit even if those activities carry a very high residual risk. | 50 | True | 2025-11-19 19:24 | 2025-11-19 19:24

## RagStatuses
Id | Name | Description | SortOrder | IsActive | CssClass | CreatedAt | UpdatedAt
1 | Green | On track, no issues | 1 | True | badge badge-green | 2026-01-15 | 2026-01-15
2 | Amber-Green | Minor issues, corrective action in place | 2 | True | badge badge-amber-green | 2026-01-15 | 2026-01-15
3 | Amber | Some issues, may impact delivery | 3 | True | badge badge-amber | 2026-01-15 | 2026-01-15
4 | Amber-Red | Significant issues, likely to impact delivery | 4 | True | badge badge-amber-red | 2026-01-15 | 2026-01-15
5 | Red | Critical issues, will impact delivery | 5 | True | badge badge-red | 2026-01-15 | 2026-01-15

## DeliveryPriorities
Id | Name | Summary | Description | SortOrder | IsActive | CssClass | CreatedAt | UpdatedAt
1 | High | Critical delivery focus | Reserved for urgent projects with significant ministerial or statutory drivers. | 1 | True | badge badge-high | 2025-11-14 | 2025-11-14
2 | Medium | Important delivery focus | Projects with clear departmental value that may tolerate minor delay. | 2 | True | badge badge-medium | 2025-11-14 | 2025-11-14
3 | Low | Routine delivery focus | Foundational or exploratory work that can flex if higher priorities emerge. | 3 | True | badge badge-low | 2025-11-14 | 2025-11-14

## RiskTiers
Id | Code | Name | Description | Summary | SortOrder | IsActive | CreatedAt | UpdatedAt
1 | PROJECT | Project-level risk | Tactical risks that directly affect the delivery of a single project, product, or service. Managed day-to-day by delivery teams. Examples: Supplier delays, resource gaps, accessibility issues, technology bugs, dependency on another service. | Within a discrete project or service | 1 | True | 2025-10-17 20:25 | 2025-10-17 20:25
2 | PROGRAMME | Programme-level risk | Strategic and operational risks that threaten delivery across multiple projects in a programme. Managed by programme boards and senior responsible owners (SROs). Examples: Conflicting priorities across projects, funding shortfalls, interdependencies, benefits not realised. | Across a set of related projects | 2 | True | 2025-10-17 20:25 | 2025-10-17 20:25
3 | PORTFOLIO | Portfolio-level risk | Risks affecting the achievement of strategic objectives within a portfolio (e.g. Digital Portfolio, Transformation Portfolio). Examples: Competing resource demand, cross-programme technology dependencies, change fatigue. | Across multiple programmes or a business area | 3 | True | 2025-10-17 20:25 | 2025-10-17 20:25
4 | DEPARTMENT | Department-level risk | High-level or strategic risks that could impact departmental objectives or public reputation. Usually captured in the Departmental Risk Register. Examples: Failure to deliver strategic outcomes, budgetary control, workforce capability, cyber security, major policy change. | Across the entire department (e.g. DfE) | 4 | True | 2025-10-17 20:25 | 2025-10-17 20:25
5 | CROSS_GOVERNMENT | Cross-government / systemic risk | Risks that transcend departmental boundaries and could impact public sector capability, continuity, or reputation. Managed by Cabinet Office / HMT via Government Risk Register. Examples: Major data breach across departments, shared platform failure (e.g. Notify, GOV.UK), policy shifts, economic shocks. | Across multiple departments or sectors | 5 | True | 2025-10-17 20:25 | 2025-10-17 20:25

## RiskTypes
Id | Code | Name | Description | Summary | IsActive | Severity | CreatedAt | UpdatedAt
1 | STRATEGY | Strategy risk | Risks arising from identifying and pursuing a strategy that is poorly defined, based on flawed or inaccurate data, or fails to support the delivery of commitments, plans, or objectives due to a changing macro-environment (political, economic, social, technological, environmental, or legislative change). | Poorly defined or outdated strategic direction. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
2 | GOVERNANCE | Governance risk | Risks arising from unclear plans, priorities, authorities, and accountabilities, and/or ineffective or disproportionate oversight of decision-making or performance. | Weak oversight, unclear accountability, or poor governance. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
3 | OPERATIONS | Operations risk | Risks arising from inadequate, poorly designed, ineffective, or inefficient internal processes resulting in fraud, error, impaired customer service, non-compliance, or poor value for money. | Failures in internal processes or delivery operations. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
4 | LEGAL | Legal risk | Risks arising from a defective transaction, a claim being made, or other legal events that result in liability or loss, or from a failure to meet legal or regulatory requirements or to protect assets (e.g. intellectual property). | Exposure to legal, regulatory, or contractual liabilities. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
5 | PROPERTY | Property risk | Risks arising from property deficiencies or poorly designed or ineffective safety management leading to non-compliance, harm, or injury to employees, contractors, service users, or the public. | Property, estate, or safety management deficiencies. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
6 | FINANCIAL | Financial risk | Risks arising from failure to manage finances in line with requirements, leading to poor returns, unmanaged assets or liabilities, lack of value for money, or non-compliant reporting. | Ineffective financial control or value-for-money failure. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
7 | COMMERCIAL | Commercial risk | Risks arising from weaknesses in the management of commercial partnerships, supply chains, or contracts, resulting in poor performance, inefficiency, fraud, or unmet business objectives. | Failures in contracts, suppliers, or commercial management. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
8 | PEOPLE | People risk | Risks arising from ineffective leadership, poor culture, lack of capability or capacity, inappropriate behaviours, industrial action, or breaches of employment law or HR policy. | Leadership, culture, or workforce capacity/capability issues. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
9 | TECHNOLOGY | Technology risk | Risks arising from technology not delivering the expected services due to inadequate or deficient system design, development, performance, or resilience. | Technology failures or insufficient system resilience. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
10 | INFORMATION | Information risk | Risks arising from a failure to produce or use robust, suitable, and appropriate data and information, or to exploit data to its full potential. | Data quality, availability, or misuse issues. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
11 | SECURITY | Security risk | Risks arising from a failure to prevent unauthorised or inappropriate access to information or assets, including cyber security breaches or GDPR non-compliance. | Cyber, data, or physical security breaches. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
12 | PROJECT | Project/Programme risk | Risks that programmes and projects are not aligned with strategic priorities, or fail to deliver intended benefits to time, cost, or quality. | Programme or project delivery failures. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13
13 | REPUTATIONAL | Reputational risk | Risks arising from adverse events, ethical breaches, sustainability failures, or poor quality or innovation leading to loss of reputation or trust. | Loss of stakeholder trust or public confidence. | True | Medium | 2025-10-17 20:13 | 2025-10-17 20:13

## ActionSources
Id | Code | Name | Description | Summary | SortOrder | IsActive | CreatedAt | UpdatedAt
1 | RISK | Risk | Action created to mitigate, treat, or manage a risk. These actions are typically focused on reducing impact or likelihood of risk materialisation. | Action arising from a risk | 1 | True | 2025-10-17 20:35 | 2025-10-17 20:35
2 | ISSUE | Issue | Action created to resolve, workaround, or close an issue. These actions address problems that have already materialised and require remediation. | Action arising from an issue | 2 | True | 2025-10-17 20:35 | 2025-10-17 20:35
3 | MILESTONE | Milestone | Action created to deliver a milestone or track progress towards milestone completion. These actions are typically project or programme delivery activities. | Action arising from a milestone | 3 | True | 2025-10-17 20:35 | 2025-10-17 20:35
4 | SERVICE_ASSESSMENT | Service Assessment | Action created as a result of a service assessment review. These actions may be created by external assessment teams or third-party reviewers and typically address recommendations or compliance requirements. | Action from service assessment | 4 | True | 2025-10-17 20:35 | 2025-10-17 20:35

## Divisions
Id | Name | Description | SortOrder | IsActive | CreatedAt | UpdatedAt

## Missions
Id | Title | Description | Theme | OwnerUserId | StartDate | EndDate | Status | IsDeleted | CreatedAt | UpdatedAt
1 | Best start in life |  | Break Down Barriers to Opportunity |  |  |  | Active | False | 2025-10-22 18:46 | 2025-10-22 18:46
2 | Every child achieving and thriving |  | Break Down Barriers to Opportunity |  |  |  | Active | False | 2025-10-22 18:46 | 2025-10-22 18:46
3 | Skills for opportunity and growth |  | Break Down Barriers to Opportunity |  |  |  | Active | False | 2025-10-22 18:46 | 2025-10-22 18:46
4 | Family Security (tackling child poverty, keeping children safe) |  | Break Down Barriers to Opportunity |  |  |  | Active | False | 2025-10-22 18:47 | 2025-10-22 18:47

## Objectives
Id | Title | Theme | Description | OwnerUserId | ThemeSroUserId | OutcomeSroUserId | MissionId | StartDate | EndDate | Status | RagStatus | SuccessMeasures | ProgressPercent | IsDeleted | CreatedAt | UpdatedAt
1 | Joined-Up services that empower Parents and Carers | Delivering Digitally | [7 empty] | active |  |  |  | False | 2025-10-20 11:48 | 2025-10-20 12:39
2 | Services that help learners progress between education stages | Delivering Digitally | [7 empty] | active |  |  |  | False | 2025-10-20 12:39 | 2025-10-20 13:24
3 | Joined-up school services that support improvement & productivity | Delivering Digitally | [7 empty] | active |  |  |  | False | 2025-10-20 12:40 | 2025-10-20 12:40
4 | Workforce services that address quality and sufficiency gaps | Delivering Digitally | [7 empty] | active |  |  |  | False | 2025-10-20 12:40 | 2025-10-20 12:40
5 | Services that deliver accurate and timely funding to DfE sectors | Delivering Digitally | [7 empty] | active |  |  |  | False | 2025-10-20 12:40 | 2025-10-20 12:40
6 | Trusted data from end to end | Powered by Data | [7 empty] | active |  |  |  | False | 2025-10-20 12:40 | 2025-10-20 12:40
7 | Ready for any question | Powered by Data | [7 empty] | active |  |  |  | False | 2025-10-20 12:41 | 2025-10-20 12:41
8 | Data-driven school system | Powered by Data | [7 empty] | active |  |  |  | False | 2025-10-20 12:41 | 2025-10-20 12:41
9 | Efficient multi-agency information sharing | Powered by Data | [7 empty] | active |  |  |  | False | 2025-10-20 12:41 | 2025-10-20 12:41
10 | AI-enabled business operations | The Right Technology | [7 empty] | active |  |  |  | False | 2025-10-20 12:42 | 2025-10-20 12:42
11 | Unified platforms for scale, efficiency and resilience | The Right Technology | [7 empty] | active |  |  |  | False | 2025-10-20 12:42 | 2025-10-20 12:42
12 | Exceptional workplace technology | The Right Technology | [7 empty] | active |  |  |  | False | 2025-10-20 12:42 | 2025-10-20 12:42
13 | Secure by design | The Right Technology | [7 empty] | active |  |  |  | False | 2025-10-20 12:42 | 2025-10-20 12:42
14 | The right people are in the right roles, with skills matched to organisation needs | DDaT Skills and Expertise | [7 empty] | active |  |  |  | False | 2025-10-20 12:42 | 2025-10-20 12:42
15 | DfE workforce upskilling | DDaT Skills and Expertise | [7 empty] | active |  |  |  | False | 2025-10-20 12:43 | 2025-10-20 12:43
16 | Safe and effective digital and AI tools for teaching and learning | Sector Capability | [7 empty] | active |  |  |  | False | 2025-10-20 12:43 | 2025-10-20 12:43
17 | Safe and effective case management systems in CSC | Sector Capability | [7 empty] | active |  |  |  | False | 2025-10-20 12:43 | 2025-10-20 12:43
18 | All schools to safe and reliable tech baseline | Sector Capability | [7 empty] | active |  |  |  | False | 2025-10-20 12:43 | 2025-10-20 12:43
19 | School workforce digital and data capability building | Sector Capability | [7 empty] | active |  |  |  | False | 2025-10-20 12:44 | 2025-10-20 12:44
20 | Local authority digital and data capability building | Sector Capability | [7 empty] | active |  |  |  | False | 2025-10-20 12:44 | 2025-10-20 12:44

## RagHistory
Id | ProjectId | RagStatusLookupId | RagStatus | Justification | PathToGreen | ChangedByEmail | ChangedByName | ChangedAt
1 | 1 |  | Green |  |  | unknown@example.com | Unknown User | 2025-10-22 21:07
2 | 2 |  | Green |  |  | unknown@example.com | Unknown User | 2025-10-22 21:19
3 | 3 |  | Green |  |  | unknown@example.com | Unknown User | 2025-10-22 21:49
4 | 4 |  | Green |  |  | unknown@example.com | Unknown User | 2025-10-23 07:50
17 | 6 |  | Green | Design and build - single point of failure in Andy Jones (currently) |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk | 2025-10-29 10:56
18 | 6 |  | Red | Design and build - single point of failure in Andy Jones (currently) |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk | 2025-10-29 10:56
19 | 6 |  | Amber-Green | Design and build - single point of failure in Andy Jones (currently) |  | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk | 2025-11-15 13:31

## Successes
Id | ProjectId | SuccessDescription | RecordedByEmail | RecordedByName | RecordedAt | IsReportedToSlt | SltResponse | SltRespondedByEmail | SltRespondedByName | SltRespondedAt
5 | 6 | Something | unknown@example.com | Unknown User | 2025-11-14 13:01 | True

## Outcomes
Id | ProjectId | Outcome | MeasureOfSuccess | ConfidenceLevel | ConfidenceExplanation | AchievementStatus | AchievementNotes | SortOrder | CreatedByEmail | CreatedByName | CreatedAt | UpdatedAt
2 | 6 | Test outcome | something | Medium |  |  |  | 1 |  |  | 2025-10-29 19:03 | 2025-10-29 19:03

## Needs
Id | ProjectId | Title | Need | Source | Validated | ValidationNotes | ValidatedAt | SortOrder | CreatedByEmail | CreatedByName | CreatedAt | UpdatedAt
1 | 6 | asd | asd | 2 | Yes |  | 2025-11-17 17:14 | 1 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-17 17:13 | 2025-11-17 17:14
2 | 6 | dsvf | dsfdsf | ewgewr | Yes | dju | 2025-11-17 17:42 | 2 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-17 17:23 | 2025-11-17 17:42

## ProblemStatements
Id | ProjectId | ProblemStatement | CreatedByEmail | CreatedByName | CreatedAt | UpdatedAt
1 | 6 | The Department for Education delivers a large and varied portfolio of digital services, products, programmes, and operational activities. Information about performance, risks, issues, decisions, actions, compliance, strategic objectives, and service health is currently fragmented across multiple tools, spreadsheets, bespoke processes, and disconnected reporting cycles. This creates duplicated work, inconsistent data quality, opaque governance, and an inability to form a reliable, real-time view of departmental delivery and operational risk. Teams cannot easily trace how risks link to milestones, or how actions connect to issues, decisions, objectives, service assessments, and standards compliance. Strategic reporting relies heavily on manual consolidation, which delays insight and weakens decision-making. Assurance functions lack a single mechanism to monitor compliance across the lifecycle, while delivery teams face repeated evidence requests and inconsistent expectations from governance bodies. As demand increases and services become more interdependent, the department requires a unified, authoritative platform that provides visibility, reduces duplication, improves confidence in data, and supports consistent governance across delivery and live operations. | Andy.JONES@education.gov.uk | JONES, Andy | 2025-11-17 10:34 | 2025-11-17 10:34

## ProblemStatementHist
Id | ProjectProblemStatementId | ProblemStatement | ChangedByEmail | ChangedByName | ChangedAt

## ProjectMissions
Id | ProjectId | MissionId | CreatedAt

## ResourceFunding
Id | ProjectId | ResourceType | ProgrammeFundedPercentage | AdminFundedPercentage | Notes | CreatedAt | UpdatedAt
1 | 6 | MSP | 0.00 | 0.00 |  | 2025-10-25 11:42 | 2025-10-27 14:45
2 | 6 | Permanent | 0.00 | 100.00 |  | 2025-10-25 11:42 | 2025-10-27 14:45

## ResourceFundingHist
Id | ProjectId | ResourceType | Count | ProgrammeFundedPercentage | AdminFundedPercentage | Notes | ChangedAt | ChangedByEmail | ChangedByName
1 | 6 | Permanent | 12.00 | 90.00 | 10.00 |  | 2025-10-25 12:06 | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk
2 | 6 | MSP | 4.00 | 100.00 | 0.00 |  | 2025-10-25 12:06 | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk
3 | 6 | Permanent | 11.00 | 90.00 | 10.00 |  | 2025-10-25 12:18 | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk
4 | 6 | MSP | 6.00 | 90.00 | 10.00 |  | 2025-10-25 12:19 | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk
5 | 6 | Permanent | 11.00 | 0.00 | 10.00 |  | 2025-10-27 14:45 | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk
6 | 6 | MSP | 0.00 | 0.00 | 0.00 |  | 2025-10-27 14:45 | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk
7 | 6 | Permanent | 5.00 | 0.00 | 100.00 |  | 2025-10-27 14:45 | Andy.JONES@education.gov.uk | Andy.JONES@education.gov.uk

## ProjectContacts
Id | ProjectId | UserId | Role | Name | Email | RoleDescription | SortOrder | FundingArrangement | TimeAllocation | EmploymentType | TeamStatus | LeaveReason | LeftAt | CreatedAt | UpdatedAt
4 | 6 | 1 | Head of Design | JONES, Andy | Andy.JONES@education.gov.uk | Design and build | 1 | Not specified |  | Permanent | current |  |  | 2025-10-25 14:18 | 2025-11-15 11:50
5 | 6 | 3 | Head of PMO | WRIGHT, Jo | Jo.WRIGHT@education.gov.uk |  | 1 | Not specified |  | Permanent | current |  |  | 2025-10-27 14:41 | 2025-11-20 05:40
6 | 6 | 5 | Not specified | CLARK, Louise | Louise.CLARK@education.gov.uk |  | 1 | Not specified |  | Permanent | current |  |  | 2025-10-27 14:42 | 2025-11-15 11:54
7 | 6 | 12 | Not specified | DALE, Tracey | Tracey.DALE@education.gov.uk |  | 1 | Not specified |  | Permanent | current |  |  | 2025-10-27 14:43 | 2025-11-15 11:55
8 | 6 | 13 | Not specified | PATEL, Prina | Prina.PATEL@education.gov.uk |  | 1 | Not specified |  | Permanent | current |  |  | 2025-10-27 14:43 | 2025-11-15 11:55
9 | 6 | 8 | Service Designer | KAMPASI, Juliet | Juliet.KAMPASI@education.gov.uk |  | 6 | Programme |  | Permanent | current |  |  | 2025-11-14 21:49 | 2025-11-14 21:49

## ProjectObjectives
Id | ProjectId | ObjectiveId | CreatedAt
1 | 1 | 12 | 2025-10-22 21:07
2 | 1 | 11 | 2025-10-22 21:07
3 | 2 | 11 | 2025-10-22 21:19
4 | 3 | 11 | 2025-10-22 21:49
5 | 4 | 14 | 2025-10-23 07:50
6 | 4 | 11 | 2025-10-23 07:50
9 | 12 | 11 | 2025-11-05 21:29
12 | 6 | 14 | 2025-11-06 11:04
13 | 6 | 7 | 2025-11-06 11:04
14 | 6 | 6 | 2025-11-06 11:04
15 | 6 | 12 | 2025-11-06 11:04
16 | 6 | 11 | 2025-11-06 11:04

## ProjectProducts
Id | ProjectId | ProductDocumentId | ProductFipsId | ProductTitle | ProductDescription | ProductUrl | CreatedAt | UpdatedAt
7 | 6 |  | OTU-077 | COMPASS Reporting |  |  | 2025-11-04 10:16 | 2025-11-04 10:16
8 | 12 |  | ACY-747 | DDT Service Manual | To centralise all manuals, standards, guidance within DDT into one resource. |  | 2025-11-05 21:30 | 2025-11-05 21:30

## StatusUpdates
Id | ProjectId | Narrative | CreatedByEntraId | CreatedByName | CreatedByEmail | CreatedByUserId | UpdatedByUserId | CreatedAt | UpdatedAt | IsBulkImport
183 | 18 | 24/10/25 Standards: - IT support standard being prepared for launch on 17 November in time for the Schools and Academies Show - new gov.uk landing page with policy stakeholders for review. The changes will reflect the "core standards" ahead of launch Plan tech: - MVP build almost all at testing phase or release ready. - Core recommendations have all been signed off by stakeholders and being 2id in contentful. - Mapping of old questions to new recommendations complete to support existing users to understand the changes we've made - Set up gov.notify and prepared comms to let users know about the service changes. Banner is ready to be implemented. Comms will go out a week before launch. - Minor accessibility issues resolved - Aiming to launch MVP by 12 November in time for the Schools and Academies Show on 19 November. Service downtime for release is expected to last for 3 hours. |  |  |  | 1 |  | 2025-11-20 08:37 | 2025-11-20 08:37 | False
184 | 2294 | The API and Lakehouse are being refactored and due to being held up with issues with commercials with system C impacting schedule - refactoring sliver and gold layers. Improvement work continues on improving the public dashboard - working on servere absences. Continuing iteration and build of private Dashboard. Will work on Testing API with CMS providers, D2I and or LAs. Progress during this period - -Public Dashboard OFSTED update -UR for Private Dahsboard ongoing -Private Dashboard MVP build underway alongside final QA page (UaT) -Prototyping of Private Dashboard continuing -Severe absence in main -7 LAs connected to SIT environment |  |  |  | 1 |  | 2025-11-20 08:37 | 2025-11-20 08:37 | False
185 | 2295 | 16/10/25 - Work to start in November to map all technical services within the CMDB |  |  |  | 1 |  | 2025-11-20 08:37 | 2025-11-20 08:37 | False
186 | 2296 | 25/06/24: This has been on hold for a long while and not going to go ahead as originally planned. A new deliverable will be added once we have procured a team to do the work. 26/09/24: This has now been overtaken by new deliverables which we are reporting on at a more granular level. |  |  |  | 1 |  | 2025-11-20 08:37 | 2025-11-20 08:37 | False
187 | 2297 | The application window closed on 21 March. We received 753 applications for Turing Scheme funding in academic year 2024/25. This represents an 21.6% increase from the 619 applications received in year 3 (note - this information has not yet been shared publicly). This represents the conclusion of the application process for AY24/25 and the design and development focus now shifts to the development of functionality to support the assessment, appeals, payment and grant management processes. Longer term, and subject to SR approval, the team will launch the application process for the fifth year of the scheme (academic year 2025/26). The application window is expected to open in early 2025, although minimal changes are required to the application portal. |  |  |  | 1 |  | 2025-11-20 08:37 | 2025-11-20 08:37 | False
188 | 2298 | Development delays resulted in a transition to a contingency offline solution (spreadsheets) to ensure the payment of funds to organisations taking part in the Turing Scheme. The contingency replicated the design of the digital solution and enabled organisations starting Turing Scheme placements in September 2024 to submit details of payments and payment requests. This solution enabled payments to be made to 81 organisations in August, 83 providers in September and 310 organisations in October. New delivery date planned for 31/01/2025. While the contingency option has enabled participating organisations to receive the funding they need to support students on international placements, it has required significant developer input to prepare for and enable the extraction of placement data into the CRM. This has resulted in developer resource being diverted away frrom the development of the monthly reporting process through which organisations submit details of expenditure, expected expenditure and placements. The monthly reporting functionality is expected to launch in w/c 4 November and the final reporting functionality is expected to go live by the end of January 2025. This will complete the development of the service supporting the fourth year of the scheme. |  |  |  | 1 |  | 2025-11-20 08:37 | 2025-11-20 08:37 | False
189 | 2299 | Due to recent ministerial steers leading to the decision not to do extensions of the DPS1 and DPS2 contracts, and with no plans to undertake a DPS3 at this time, the Skills Bootcamps leadership team have reviewed the value that would be gained from having the supplementary data collection for Grants providers and deemed that the added value isn’t enough to warrant the costs of the project, especially with added pressures to reduce spend within the department. Notification was received on 22nd August and the project will fully close down on 30th August. |  |  |  | 1 |  | 2025-11-20 08:37 | 2025-11-20 08:37 | False
190 | 2300 | Agree non project team owner for accreditation process issues. Continue to work with 3rd parties to ensure all can adopt solution. Replacement of ECS legacy system in 2025. The Replacement project has reviewed the end-to-end process for eligibility checking and determined what the overall process and technology should look like in the post-ECS environment. Now in Beta we are building two products as an MVP: a hub – the Entitlements Checking Engine (ECE), and replacement spokes for both School Meals and Childcare. |  |  |  | 1 |  | 2025-11-20 08:37 | 2025-11-20 08:37 | False
191 | 2301 | The status has been moved to Amber/Green due to the delays to the procurement specification which was due to go out to the sector in October 2025 but will likely fall into the start of the new year now, following the request from the new minister Josh MacAlister to revisit and amend the Post Qualifying Standard (PQS). The digital service, however, is not currently blocked by this decision and are able to proceed as per the current plan, whilst the PQS is being re-drafted. |  |  |  | 1 |  | 2025-11-20 08:37 | 2025-11-20 08:37 | False
192 | 2302 | We've extended the early years workforce register discovery by a sprint due to a slower than anticipated start. Work is continuing on the qualifications side to explore opportunities to improve how we manage qualifications date. |  |  |  | 1 |  | 2025-11-20 08:37 | 2025-11-20 08:37 | False
193 | 2303 | A new team is now in place to work on this product until March 2026. A GDS assessment is planned for after the next round of updates. |  |  |  | 1 |  | 2025-11-20 08:37 | 2025-11-20 08:37 | False
194 | 2304 | Lack of ownership of NHSE of their elements of the work needed to progress with the NHS number as the SUI and the use of their systems to enable the pilots to take place. Amber/red due to lack of progress on resolving issues. Escalation of concerns about NHSE engagement. To improve the use of technology to share information between agencies working with children and families (schools, police, health and children's social care) and to explore the use of a consistent child identifier (CCI), also referred to as a Single Unique Identifier (SUI), to enable this. |  |  |  | 1 |  | 2025-11-20 08:37 | 2025-11-20 08:37 | False
195 | 2305 | All required IT changes have already been made by HMRC, and LA third-party suppliers have all provided roadmaps for delivery. Successful delivery involves handoffs between multiple digital systems – these all need to be assured with no degree of risk for this project to be Green. |  |  |  | 1 |  | 2025-11-20 08:37 | 2025-11-20 08:37 | False
196 | 18 | 24/10/25 Standards: - IT support standard being prepared for launch on 17 November in time for the Schools and Academies Show - new gov.uk landing page with policy stakeholders for review. The changes will reflect the "core standards" ahead of launch Plan tech: - MVP build almost all at testing phase or release ready. - Core recommendations have all been signed off by stakeholders and being 2id in contentful. - Mapping of old questions to new recommendations complete to support existing users to understand the changes we've made - Set up gov.notify and prepared comms to let users know about the service changes. Banner is ready to be implemented. Comms will go out a week before launch. - Minor accessibility issues resolved - Aiming to launch MVP by 12 November in time for the Schools and Academies Show on 19 November. Service downtime for release is expected to last for 3 hours. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
197 | 2294 | The API and Lakehouse are being refactored and due to being held up with issues with commercials with system C impacting schedule - refactoring sliver and gold layers. Improvement work continues on improving the public dashboard - working on servere absences. Continuing iteration and build of private Dashboard. Will work on Testing API with CMS providers, D2I and or LAs. Progress during this period - -Public Dashboard OFSTED update -UR for Private Dahsboard ongoing -Private Dashboard MVP build underway alongside final QA page (UaT) -Prototyping of Private Dashboard continuing -Severe absence in main -7 LAs connected to SIT environment |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
198 | 2295 | 16/10/25 - Work to start in November to map all technical services within the CMDB |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
199 | 2296 | 25/06/24: This has been on hold for a long while and not going to go ahead as originally planned. A new deliverable will be added once we have procured a team to do the work. 26/09/24: This has now been overtaken by new deliverables which we are reporting on at a more granular level. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
200 | 2297 | The application window closed on 21 March. We received 753 applications for Turing Scheme funding in academic year 2024/25. This represents an 21.6% increase from the 619 applications received in year 3 (note - this information has not yet been shared publicly). This represents the conclusion of the application process for AY24/25 and the design and development focus now shifts to the development of functionality to support the assessment, appeals, payment and grant management processes. Longer term, and subject to SR approval, the team will launch the application process for the fifth year of the scheme (academic year 2025/26). The application window is expected to open in early 2025, although minimal changes are required to the application portal. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
201 | 2298 | Development delays resulted in a transition to a contingency offline solution (spreadsheets) to ensure the payment of funds to organisations taking part in the Turing Scheme. The contingency replicated the design of the digital solution and enabled organisations starting Turing Scheme placements in September 2024 to submit details of payments and payment requests. This solution enabled payments to be made to 81 organisations in August, 83 providers in September and 310 organisations in October. New delivery date planned for 31/01/2025. While the contingency option has enabled participating organisations to receive the funding they need to support students on international placements, it has required significant developer input to prepare for and enable the extraction of placement data into the CRM. This has resulted in developer resource being diverted away frrom the development of the monthly reporting process through which organisations submit details of expenditure, expected expenditure and placements. The monthly reporting functionality is expected to launch in w/c 4 November and the final reporting functionality is expected to go live by the end of January 2025. This will complete the development of the service supporting the fourth year of the scheme. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
202 | 2299 | Due to recent ministerial steers leading to the decision not to do extensions of the DPS1 and DPS2 contracts, and with no plans to undertake a DPS3 at this time, the Skills Bootcamps leadership team have reviewed the value that would be gained from having the supplementary data collection for Grants providers and deemed that the added value isn’t enough to warrant the costs of the project, especially with added pressures to reduce spend within the department. Notification was received on 22nd August and the project will fully close down on 30th August. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
203 | 2300 | Agree non project team owner for accreditation process issues. Continue to work with 3rd parties to ensure all can adopt solution. Replacement of ECS legacy system in 2025. The Replacement project has reviewed the end-to-end process for eligibility checking and determined what the overall process and technology should look like in the post-ECS environment. Now in Beta we are building two products as an MVP: a hub – the Entitlements Checking Engine (ECE), and replacement spokes for both School Meals and Childcare. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
204 | 2301 | The status has been moved to Amber/Green due to the delays to the procurement specification which was due to go out to the sector in October 2025 but will likely fall into the start of the new year now, following the request from the new minister Josh MacAlister to revisit and amend the Post Qualifying Standard (PQS). The digital service, however, is not currently blocked by this decision and are able to proceed as per the current plan, whilst the PQS is being re-drafted. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
205 | 2302 | We've extended the early years workforce register discovery by a sprint due to a slower than anticipated start. Work is continuing on the qualifications side to explore opportunities to improve how we manage qualifications date. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
206 | 2303 | A new team is now in place to work on this product until March 2026. A GDS assessment is planned for after the next round of updates. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
207 | 2304 | Lack of ownership of NHSE of their elements of the work needed to progress with the NHS number as the SUI and the use of their systems to enable the pilots to take place. Amber/red due to lack of progress on resolving issues. Escalation of concerns about NHSE engagement. To improve the use of technology to share information between agencies working with children and families (schools, police, health and children's social care) and to explore the use of a consistent child identifier (CCI), also referred to as a Single Unique Identifier (SUI), to enable this. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
208 | 2305 | All required IT changes have already been made by HMRC, and LA third-party suppliers have all provided roadmaps for delivery. Successful delivery involves handoffs between multiple digital systems – these all need to be assured with no degree of risk for this project to be Green. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
209 | 2475 | MEPS currently paused. Transferred to Rob Rodney/Schools digital division who will review the project. Prior to pause, work was focusing only on the first component (Search, Filter and View - Unauthenticated) before moving on to the next component. Progress had been made as follows - * Initial meetings held with assessors for the Alpha assessment. A peer assessent will be undertaken during the coming period. * Fourth Show and Tell took place on 25/02/2025 (approx. 87 attendees). * Teach-in session with Teacher services took place on 13/02/2025. Architecture and Helpdesk parts to be rescheduled (ran out of time). |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
210 | 2476 | 11/09/2025 Reason for delivery confidence rating: We are performing well, with strong engagement from schools and record numbers of jobseekers. We launched the All School Roles MVP in March, which has seen a significant uptick in the number of schools signed up to the service, to over 87% of schools in scope. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
211 | 2477 | Key Highlights: - MSI delivered the monitoring phase and began iteration 2 of mandation, with contact management improvements underway. - FAST completed its final deliverables and transitioned successfully to CI, marking a key milestone in product consolidation. - Innovation launched MPC and shifted focus to AI discovery, aligning with strategic objectives. - CAT progressed .Net migration and achieved infrastructure standardisation, supporting long-term technical resilience. - Service Support (SS) maintained high SLA performance and user satisfaction, despite ongoing resource constraints. Areas Requiring Attention: - EAT remains Amber-Green, with extended timelines and reliance on external accessibility audits. While delivery is progressing, dependencies and testing limitations present risks to future milestones. - CI is managing increased scope due to handovers from FAST and MPC, alongside SEND/CSC delivery challenges. Engagement gaps in user testing and overlapping priorities are impacting delivery pace. Risks to Delivery Confidence: - Contract re-procurement remains a strategic risk due to tight timelines and limited commercial support. - White Paper reforms continue to introduce uncertainty, affecting planning and capacity management for Q4 and beyond. - CI delivery risk due to scope increase and SEND/CSC engagement issues. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
212 | 2478 | FIAT has been handed over to the Continuous Improvement team |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
213 | 2479 | Product is managed by our Performance analysis & service support team (PASS) It is performing well and there are no concerns. Key metrics: - average availability has been 100% in the last 30 days and average response time has been 34ms SFSO & RG colleagues are successfully managing governance concerns within ReCaST. Successful progression of the continuous improvements entered through the new front door process for SFSO. Service reviews are scheduled with SFSO. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
214 | 2480 | 06.06.25 - Continues to be on hold, and probably will be for some time – There is a power app supporting the business processes now so it’s not as important as it was to get of legacy tech. The external application process though does need significant improvement; but that will fall into another one of our projects in the medium term, External Applications. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
215 | 2481 | MFSP continues to receive predominantly positive feedback, only receiving one disatisified response since the start of May. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
216 | 2482 | Product is now managed by our Performance analysis & service support team (PASS) |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
217 | 2483 | Previous update stands as tool is replaced by FIAT. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
218 | 2484 | Work is ongoing on bug fixes with no clear date identifed on when all will be cleared. IEBT put on hold until current identified bugs are cleared. Amber RAG due to schedule delays. PSR resources will be extended on current Data POs and transferred to Teacher Services at a later date to prevent standing Java developers down. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
219 | 2485 | All work is on track with limited large scale development and a focus on minor enhancements, and ongoing service maintenance and operations. The past period has seen a number of enhancements to improve the AO user experience in terms of data visibility and to extend the DfE admin interface to give greater functionality that reduces reliance on technical development support. Testing ahead of summer 2025 results has completed successfully. There are no major concerns/issues to note. Work continues to progress the potential for a future transfer of the results service to AOs. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
220 | 2486 | 11/09/2025 Website: Project is reliable, with planned improvements to improve performance and enhance user experience. CRM: Team moved outside IR35 in October 2023 but is still aligned with the rest of the service, with continuous improvements alongside major development work. GSE: Growth continues organically with the service but there is little active development of the service due to team and budget constraints. We are instead focusing on ‘keeping the lights on’ and ensuring the service complies with governance requirements. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
221 | 2487 | 11/09/2025 Reason for delivery confidence rating: The new recruitment cycle started well, without issue for Find or Apply opening. Offer and acceptance rates in the first 10 weeks have been encouraging however we are noticing lower submission rates of applications (particularly for Primary courses and international candidates; we continue to monitor. Send trainee data direct project delivery is dependent upon SRS vendors AND Providers being ready – this is being mitigated through ongoing engagement with both groups, but remains a delivery risk Summarise actions being undertaken to bring the project back to green: Close collaboration with key external and internal stakeholders to assess and address key concerns. Summarise the business impact, if any: Send trainee data direct risk to 25/26 ITT collection – any vendors/providers who have not successfully integrated with the Register API could still use the CSV bulk upload or the manual entry routes. There is also inclusion of backstop clause in case DfE requires HESA to collect the 25/26 ITT collection if insufficient numbers of providers are ready, |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
222 | 2488 | 11/09/2025 Reason for delivery confidence rating: In the previous claim window we received over 21,315 claims and £73.9m has been paid to teachers across all user journeys to date (over £108m paid by DfE including tax). All claim services have now been closed. With the service now closed we are focusing on improving our existing services, particularly the FE service and the implementation of a permanent alternative IDV route for users who cannot verify their identity using GOV One Login. We also successfully completed the EY service private beta assessment in May, receiving an amber rating, and are preparing for public beta launch in September. We have removed the Early Career Payments service from Claim, now that this policy has ended. We are also making changes to accommodate Year 2 requirements to the IRP user journey. We also supported the DfE's teacher pay announcement with the launch of the Teacher Pay Calculator on GOV.UK. The proposed solution to accessing HE Qualifications from alternative sources once DQT is decommissioned (which was a blocker for checking claims next year) has been progressed and the data has been tested with claim successfully. The main risk for Claim continues to be civil servant resource, with both product managers, delivery manager, and the interaction designer leaving the Claim service. Since then, a new product manager and service designer has joined the team as well as a contractor delivery manager from Version 1. Whilst resource has been replaced, a significant amount of knowledge and experience on claim has been lost. Summarise actions being undertaken to bring the project back to green: Working with SMT regarding resource risk for Claim Handovers are in place to help knowledge transfer with new claim members |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
223 | 2489 | Final pre-production testing and any subsequent remedial development work is almost complete. The plan to meet the target go-live date of 10 November 2025 is on track. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
224 | 2490 | 07/05/25 - PMO discussion with delivcery team. Confirmed that this is a programme of delivery. Will work to confirm high-level milestones within the programme over the coming months. Overall - the service is delivering basic needs with strong user satisfaction. Pain points remain and crucially the service does not have the capacity to scale in line with its FBC requirements. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
225 | 2491 | Overall programme rag remains amber/green, with individual project RAGS, which can be seen below, ranging from Amber/red to Green. Delivery details are recorded on the individual progreamme updates. After delivering the intial data cycle, work is now onoing to iterate the product, with work to replace DEI and moving to Databricks identfied, alongside the current delivery cycle. KS2 - Green. KS4 - Amber/Green. 16-18 - Green LDS 2.0 (improve & re-platform) - Green. (Requirement to be off DEI by September 2027 (Planned for April 2026.) |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
226 | 2492 | School Checking schedule is currently on track, with key milestones outlined below. Following completion of the KS4 & 16-18 Autumn Live Checking Exercise, scrutiny is underway with outcome to be provided to MDP on 03/11. KS4 - 16 June - Complete KS2 - 08 September - Complete KS4 & 16-18 Autumn - Complete KS4 & 16-18 LR2 File - 20 Nov 16-18 L3 VA Data - 20 Nov |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
227 | 2493 | 11/09/2025 Reason for delivery confidence rating: AB portal work not throwing off roadmap as much, amber green as there are still lots of dependencies across teams but delivery momentum is picking up. Combined ECF/NPQ data model which causes bugs, data quality issues and high volumes of support tickets. High civil servant to contractor ratio on the programme. Summarise actions being undertaken to bring the project back to green: New regular meetings on AB portal and NPQ dependencies with TRN to manage considerable dependencies |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
228 | 2494 | A service that supports the career development of child and family social workers by showcasing DfE funded development programmes. There has been a decision to pause work on the service from December. Completing the information architecture restructure work will put the service in a much better place from an accessibility and usability perspective. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
229 | 2495 | 31/10/25 Reason for delivery confidence rating: All teaching record data supporting services across Schools Digital is now soley coming from TRS, not DQT. The Operations and Support team have a console to view and manage queries from users about their Teaching Record. Much is still in MVP but with clear plans for critical improvements. How we're getting to GREEN DQT decommissioning is in progress and being conducted at pace to reduce the risk of the vulnerabilities highlighted on DQT (more valuable to spend resource effort on deommissioning DQT than fixing the vulnerabilities ahead of decommissioning). Roadmap of prioritised development to complete key features e.g. integration with OneLogin |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
230 | 2496 | 31/10/25 Reason for delivery confidence rating: The service is in Public Beta, with all users transitioned from the legacy service. We continue to monitor service metrics for any elements of the service that require attention. The main concerns relate to misunderstandings of when the service is required. Summarise actions being undertaken to bring the project back to green: N/A, although looking at how we can improve guidance and work with the policy team on the longer-term future of the service (ultimately seeking to decommission the service, which requires DBS buy-in). DBS have indicated, for the first time, they are open to discussions now (11 March 2025) Policy team starting to engage with actions needed to progress decommissioning due to other priorites. This was escalated in June 2025 |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
231 | 2497 | 11/09/2025 Reason for delivery confidence rating: When we launched the service in February 2023, we saw much higher than anticipated demand – particularly from teachers who qualified in the newly eligible countries. Whilst demand levels have significantly decreased and we are beginning to see a reduction in the size of the backlog we know that eligible candidates are still facing wait times that are outside the service level agreement and associated correspondence is causing additional burden. We are reviewing the priorities for delivery as there are currently two high priority workstreams (implementing recommendations agree by the minister and further information/decline) Summarise actions being undertaken to bring the project back to green: We have streamlined new functionality to enable the rapid decline of ineligible applicants. We have created a model to assess how surges will impact our backlog and inform future policy change. We have rolled out a new workflow to differentiate between higher and lower skilled tasks to enable support staff to take more burden off assessors. Agreed policy interventions will safeguard the service against future spikes in applications. To reduce the number of offline processes and make the assessment process more efficient and robust we are analysing correspondence data and exploring opportunities to bring more processes within service. Policy are reviewing our approach to global roll out and will provide advice to ministers in the next month. Updates to the way we build our delivery plan should enable foresight into the work that is coming up and better review resourcing requirements to avoid competing prioritise across both workstreams Summarise the business impact, if any: high volume of applicants risks long delays and high workloads for assessors |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
232 | 2498 | Attendance data mandating successfully went live on 21st August 2024. Work is on track to continue to iterate the product during this financial year. 99.57% of schools are sharing their daily attendance data. The team continue to work with Wonde to improve DQ and CBDS data fields. Product live and stable, with iterations happening for additional features/services. AtO sign off received. The following features were released on 1st September for new acamic year. - Removed from Roll (MVP2 Download) - Postcode Functionality - LA Learners Postscode - Attendance Return Reports 10 Days Continuous Unathorised Absence Return & Sickness Return (non-postcode) - Session Level Code Breakdowns - Transitional Years Data Sept released to schools on 09/09/2025 |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
233 | 2499 | There are three work strands, two of which are on track: maintenance of Help for early years providers, and delivering changes to the EY Child Development Training so that it meets the needs of Reception-based staff. We are extending timelines for the third work strand - publishing guidance around EYFS profile assessments for reception teachers on HfEYP - due to delays on content production following EY policy restructure. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
234 | 2500 | Our last show and tell was on 3rd October 2025, our next one is planned for 31st October 2025. We did a demo of the Education Record to the Permanent Secretary during her visit to Coventry, she was impressed by how simple the service was for Schools and how easy it was for pupils to get access to their own data. We had the Education Record Steering Group on 6th October, there were no concerns/objections raised on our next steps and we have some actions to take forward. The submission for the minister has been shared for feedback. We have a SoW in place with People for Research for a round of UR with pupils, we are also planning a round of UR focused on accessibility. We have started working on a video for schools to use to explain the purpose of the Education Record, and we have started on our communications material in preparation of the national roll out. We have released an update to Issue Education Record with a simplified issuing journey for schools, this was developed based on feedback from our pilot schools. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
235 | 2501 | Our last show and tell was on 3rd October 2025, our next one is planned for 31st October 2025. We have updated our user guidance based on user feedback and helpdesk queries, this is going for sign-off and will then be published on gov.uk. We are drafting comms to send out to apprenticeship providers following R14 to encourage them to transfer from LET to ELD. We released new functionality for additional learning aims to be added to a learner who is already enrolled on a course, and we are continuing with the developent work for non-funded apprenticeships. We have just completed a round of UR looking at reporting which covered ELD alongside SLD, VYED etc We have designed some updates to the service (e.g. additional content, inclusion of ILR codes alongside descriptions) based on UR feedback and provider queries. We delivered a webinar at the very end of September to over 70 employer providers, we were able to demo the new service, explain the benefits and answer questions from the participants |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
236 | 2502 | Following the recent strategy refresh, we’ve now structured our operating model around three core priorities. This shift began yesterday and is designed to help us deliver incrementally and at pace. We’ve also started work on deliverables to support resourcing for the “Cool Tool for School” initiative, which will enable us to move forward with delivery in that area. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
237 | 2503 | November: Final draft of strategy document to be shared with stakeholders and a Q&A session. Strategy to be shared with Tech SLT for sign-off – 21/11/25. Strategy published and engagement and comms with communities of practice to ensure awareness. Continue to prepare for implementation phase. October: Options paper developed and shared with Tech SLT on ownership model of the IDAMs space. Strategy reviewed to ensure all stakeholder comments resolved and where applicable addressed in the next version of Strategy document Continue to prepare for implementation phase. Initial engagement with DSiT about digital IDs and implications in the education space. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
238 | 2504 | Programme launched September 2025, goverance launched. Projects will be stood up over the coming months. Phonics project launched Tuesday 16.09.2025. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
239 | 2505 | Headset fresh completed Oct 16th 2024. 4084 headsets issued by the project. Including BAU, 63% of staff now have a noise cancelling headset Multiple projects in train to maintain, assure and improve all core services as listed. Videoconferencing refresh successfully completed (April - May 2024). Mobile refresh commenced (ongoing) from April 2024. Headset refresh commenced April 2024. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
240 | 2506 | Ongoing hardware refresh programme and associated technical upgrades throughout DfE estate. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
241 | 2507 | 23/9/24 CoPilot is underway with the Champions already trained and the community channel set up. Initial workshops for the main cohort started this week, with training and follow-up workshops over the coming weeks. Second tranche of licenses have been issued today. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
242 | 2508 | GPA has confirmed the new target delivery date is Qtr 1 of FY26/27. GPA has confirmed DfE as their tech partner. Governance arrangments now agreed. DfE to assign DM yo the project to work with GPA and DfE Estates to avoid the risk of delays or missing key dates due to BAU pressures. First step is for GPA to share a clear set of requirements for SB. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
243 | 2509 | 16/6/25 working with our 3rd party partners we are progressing the work and updating the LLM and utterances to make the returns for search results and CHAT interaction more DfE specific which will improve the end user experience. |  |  |  | 1 |  | 2025-11-20 09:07 | 2025-11-20 09:07 | True
378 | 18 | 24/10/25 Standards: - IT support standard being prepared for launch on 17 November in time for the Schools and Academies Show - new gov.uk landing page with policy stakeholders for review. The changes will reflect the "core standards" ahead of launch Plan tech: - MVP build almost all at testing phase or release ready. - Core recommendations have all been signed off by stakeholders and being 2id in contentful. - Mapping of old questions to new recommendations complete to support existing users to understand the changes we've made - Set up gov.notify and prepared comms to let users know about the service changes. Banner is ready to be implemented. Comms will go out a week before launch. - Minor accessibility issues resolved - Aiming to launch MVP by 12 November in time for the Schools and Academies Show on 19 November. Service downtime for release is expected to last for 3 hours. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
379 | 2294 | The API and Lakehouse are being refactored and due to being held up with issues with commercials with system C impacting schedule - refactoring sliver and gold layers. Improvement work continues on improving the public dashboard - working on servere absences. Continuing iteration and build of private Dashboard. Will work on Testing API with CMS providers, D2I and or LAs. Progress during this period - -Public Dashboard OFSTED update -UR for Private Dahsboard ongoing -Private Dashboard MVP build underway alongside final QA page (UaT) -Prototyping of Private Dashboard continuing -Severe absence in main -7 LAs connected to SIT environment |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
380 | 2295 | 16/10/25 - Work to start in November to map all technical services within the CMDB |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
381 | 2296 | 25/06/24: This has been on hold for a long while and not going to go ahead as originally planned. A new deliverable will be added once we have procured a team to do the work. 26/09/24: This has now been overtaken by new deliverables which we are reporting on at a more granular level. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
382 | 2297 | The application window closed on 21 March. We received 753 applications for Turing Scheme funding in academic year 2024/25. This represents an 21.6% increase from the 619 applications received in year 3 (note - this information has not yet been shared publicly). This represents the conclusion of the application process for AY24/25 and the design and development focus now shifts to the development of functionality to support the assessment, appeals, payment and grant management processes. Longer term, and subject to SR approval, the team will launch the application process for the fifth year of the scheme (academic year 2025/26). The application window is expected to open in early 2025, although minimal changes are required to the application portal. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
383 | 2298 | Development delays resulted in a transition to a contingency offline solution (spreadsheets) to ensure the payment of funds to organisations taking part in the Turing Scheme. The contingency replicated the design of the digital solution and enabled organisations starting Turing Scheme placements in September 2024 to submit details of payments and payment requests. This solution enabled payments to be made to 81 organisations in August, 83 providers in September and 310 organisations in October. New delivery date planned for 31/01/2025. While the contingency option has enabled participating organisations to receive the funding they need to support students on international placements, it has required significant developer input to prepare for and enable the extraction of placement data into the CRM. This has resulted in developer resource being diverted away frrom the development of the monthly reporting process through which organisations submit details of expenditure, expected expenditure and placements. The monthly reporting functionality is expected to launch in w/c 4 November and the final reporting functionality is expected to go live by the end of January 2025. This will complete the development of the service supporting the fourth year of the scheme. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
384 | 2299 | Due to recent ministerial steers leading to the decision not to do extensions of the DPS1 and DPS2 contracts, and with no plans to undertake a DPS3 at this time, the Skills Bootcamps leadership team have reviewed the value that would be gained from having the supplementary data collection for Grants providers and deemed that the added value isn’t enough to warrant the costs of the project, especially with added pressures to reduce spend within the department. Notification was received on 22nd August and the project will fully close down on 30th August. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
385 | 2300 | Agree non project team owner for accreditation process issues. Continue to work with 3rd parties to ensure all can adopt solution. Replacement of ECS legacy system in 2025. The Replacement project has reviewed the end-to-end process for eligibility checking and determined what the overall process and technology should look like in the post-ECS environment. Now in Beta we are building two products as an MVP: a hub – the Entitlements Checking Engine (ECE), and replacement spokes for both School Meals and Childcare. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
386 | 2301 | The status has been moved to Amber/Green due to the delays to the procurement specification which was due to go out to the sector in October 2025 but will likely fall into the start of the new year now, following the request from the new minister Josh MacAlister to revisit and amend the Post Qualifying Standard (PQS). The digital service, however, is not currently blocked by this decision and are able to proceed as per the current plan, whilst the PQS is being re-drafted. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
387 | 2302 | We've extended the early years workforce register discovery by a sprint due to a slower than anticipated start. Work is continuing on the qualifications side to explore opportunities to improve how we manage qualifications date. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
388 | 2303 | A new team is now in place to work on this product until March 2026. A GDS assessment is planned for after the next round of updates. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
389 | 2304 | Lack of ownership of NHSE of their elements of the work needed to progress with the NHS number as the SUI and the use of their systems to enable the pilots to take place. Amber/red due to lack of progress on resolving issues. Escalation of concerns about NHSE engagement. To improve the use of technology to share information between agencies working with children and families (schools, police, health and children's social care) and to explore the use of a consistent child identifier (CCI), also referred to as a Single Unique Identifier (SUI), to enable this. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
390 | 2305 | All required IT changes have already been made by HMRC, and LA third-party suppliers have all provided roadmaps for delivery. Successful delivery involves handoffs between multiple digital systems – these all need to be assured with no degree of risk for this project to be Green. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
391 | 2475 | MEPS currently paused. Transferred to Rob Rodney/Schools digital division who will review the project. Prior to pause, work was focusing only on the first component (Search, Filter and View - Unauthenticated) before moving on to the next component. Progress had been made as follows - * Initial meetings held with assessors for the Alpha assessment. A peer assessent will be undertaken during the coming period. * Fourth Show and Tell took place on 25/02/2025 (approx. 87 attendees). * Teach-in session with Teacher services took place on 13/02/2025. Architecture and Helpdesk parts to be rescheduled (ran out of time). |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
392 | 2476 | 11/09/2025 Reason for delivery confidence rating: We are performing well, with strong engagement from schools and record numbers of jobseekers. We launched the All School Roles MVP in March, which has seen a significant uptick in the number of schools signed up to the service, to over 87% of schools in scope. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
393 | 2477 | Key Highlights: - MSI delivered the monitoring phase and began iteration 2 of mandation, with contact management improvements underway. - FAST completed its final deliverables and transitioned successfully to CI, marking a key milestone in product consolidation. - Innovation launched MPC and shifted focus to AI discovery, aligning with strategic objectives. - CAT progressed .Net migration and achieved infrastructure standardisation, supporting long-term technical resilience. - Service Support (SS) maintained high SLA performance and user satisfaction, despite ongoing resource constraints. Areas Requiring Attention: - EAT remains Amber-Green, with extended timelines and reliance on external accessibility audits. While delivery is progressing, dependencies and testing limitations present risks to future milestones. - CI is managing increased scope due to handovers from FAST and MPC, alongside SEND/CSC delivery challenges. Engagement gaps in user testing and overlapping priorities are impacting delivery pace. Risks to Delivery Confidence: - Contract re-procurement remains a strategic risk due to tight timelines and limited commercial support. - White Paper reforms continue to introduce uncertainty, affecting planning and capacity management for Q4 and beyond. - CI delivery risk due to scope increase and SEND/CSC engagement issues. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
394 | 2478 | FIAT has been handed over to the Continuous Improvement team |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
395 | 2479 | Product is managed by our Performance analysis & service support team (PASS) It is performing well and there are no concerns. Key metrics: - average availability has been 100% in the last 30 days and average response time has been 34ms SFSO & RG colleagues are successfully managing governance concerns within ReCaST. Successful progression of the continuous improvements entered through the new front door process for SFSO. Service reviews are scheduled with SFSO. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
396 | 2480 | 06.06.25 - Continues to be on hold, and probably will be for some time – There is a power app supporting the business processes now so it’s not as important as it was to get of legacy tech. The external application process though does need significant improvement; but that will fall into another one of our projects in the medium term, External Applications. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
397 | 2481 | MFSP continues to receive predominantly positive feedback, only receiving one disatisified response since the start of May. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
398 | 2482 | Product is now managed by our Performance analysis & service support team (PASS) |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
399 | 2483 | Previous update stands as tool is replaced by FIAT. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
400 | 2484 | Work is ongoing on bug fixes with no clear date identifed on when all will be cleared. IEBT put on hold until current identified bugs are cleared. Amber RAG due to schedule delays. PSR resources will be extended on current Data POs and transferred to Teacher Services at a later date to prevent standing Java developers down. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
401 | 2485 | All work is on track with limited large scale development and a focus on minor enhancements, and ongoing service maintenance and operations. The past period has seen a number of enhancements to improve the AO user experience in terms of data visibility and to extend the DfE admin interface to give greater functionality that reduces reliance on technical development support. Testing ahead of summer 2025 results has completed successfully. There are no major concerns/issues to note. Work continues to progress the potential for a future transfer of the results service to AOs. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
402 | 2486 | 11/09/2025 Website: Project is reliable, with planned improvements to improve performance and enhance user experience. CRM: Team moved outside IR35 in October 2023 but is still aligned with the rest of the service, with continuous improvements alongside major development work. GSE: Growth continues organically with the service but there is little active development of the service due to team and budget constraints. We are instead focusing on ‘keeping the lights on’ and ensuring the service complies with governance requirements. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
403 | 2487 | 11/09/2025 Reason for delivery confidence rating: The new recruitment cycle started well, without issue for Find or Apply opening. Offer and acceptance rates in the first 10 weeks have been encouraging however we are noticing lower submission rates of applications (particularly for Primary courses and international candidates; we continue to monitor. Send trainee data direct project delivery is dependent upon SRS vendors AND Providers being ready – this is being mitigated through ongoing engagement with both groups, but remains a delivery risk Summarise actions being undertaken to bring the project back to green: Close collaboration with key external and internal stakeholders to assess and address key concerns. Summarise the business impact, if any: Send trainee data direct risk to 25/26 ITT collection – any vendors/providers who have not successfully integrated with the Register API could still use the CSV bulk upload or the manual entry routes. There is also inclusion of backstop clause in case DfE requires HESA to collect the 25/26 ITT collection if insufficient numbers of providers are ready, |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
404 | 2488 | 11/09/2025 Reason for delivery confidence rating: In the previous claim window we received over 21,315 claims and £73.9m has been paid to teachers across all user journeys to date (over £108m paid by DfE including tax). All claim services have now been closed. With the service now closed we are focusing on improving our existing services, particularly the FE service and the implementation of a permanent alternative IDV route for users who cannot verify their identity using GOV One Login. We also successfully completed the EY service private beta assessment in May, receiving an amber rating, and are preparing for public beta launch in September. We have removed the Early Career Payments service from Claim, now that this policy has ended. We are also making changes to accommodate Year 2 requirements to the IRP user journey. We also supported the DfE's teacher pay announcement with the launch of the Teacher Pay Calculator on GOV.UK. The proposed solution to accessing HE Qualifications from alternative sources once DQT is decommissioned (which was a blocker for checking claims next year) has been progressed and the data has been tested with claim successfully. The main risk for Claim continues to be civil servant resource, with both product managers, delivery manager, and the interaction designer leaving the Claim service. Since then, a new product manager and service designer has joined the team as well as a contractor delivery manager from Version 1. Whilst resource has been replaced, a significant amount of knowledge and experience on claim has been lost. Summarise actions being undertaken to bring the project back to green: Working with SMT regarding resource risk for Claim Handovers are in place to help knowledge transfer with new claim members |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
405 | 2489 | Final pre-production testing and any subsequent remedial development work is almost complete. The plan to meet the target go-live date of 10 November 2025 is on track. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
406 | 2490 | 07/05/25 - PMO discussion with delivcery team. Confirmed that this is a programme of delivery. Will work to confirm high-level milestones within the programme over the coming months. Overall - the service is delivering basic needs with strong user satisfaction. Pain points remain and crucially the service does not have the capacity to scale in line with its FBC requirements. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
407 | 2491 | Overall programme rag remains amber/green, with individual project RAGS, which can be seen below, ranging from Amber/red to Green. Delivery details are recorded on the individual progreamme updates. After delivering the intial data cycle, work is now onoing to iterate the product, with work to replace DEI and moving to Databricks identfied, alongside the current delivery cycle. KS2 - Green. KS4 - Amber/Green. 16-18 - Green LDS 2.0 (improve & re-platform) - Green. (Requirement to be off DEI by September 2027 (Planned for April 2026.) |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
408 | 2492 | School Checking schedule is currently on track, with key milestones outlined below. Following completion of the KS4 & 16-18 Autumn Live Checking Exercise, scrutiny is underway with outcome to be provided to MDP on 03/11. KS4 - 16 June - Complete KS2 - 08 September - Complete KS4 & 16-18 Autumn - Complete KS4 & 16-18 LR2 File - 20 Nov 16-18 L3 VA Data - 20 Nov |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
409 | 2493 | 11/09/2025 Reason for delivery confidence rating: AB portal work not throwing off roadmap as much, amber green as there are still lots of dependencies across teams but delivery momentum is picking up. Combined ECF/NPQ data model which causes bugs, data quality issues and high volumes of support tickets. High civil servant to contractor ratio on the programme. Summarise actions being undertaken to bring the project back to green: New regular meetings on AB portal and NPQ dependencies with TRN to manage considerable dependencies |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
410 | 2494 | A service that supports the career development of child and family social workers by showcasing DfE funded development programmes. There has been a decision to pause work on the service from December. Completing the information architecture restructure work will put the service in a much better place from an accessibility and usability perspective. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
411 | 2495 | 31/10/25 Reason for delivery confidence rating: All teaching record data supporting services across Schools Digital is now soley coming from TRS, not DQT. The Operations and Support team have a console to view and manage queries from users about their Teaching Record. Much is still in MVP but with clear plans for critical improvements. How we're getting to GREEN DQT decommissioning is in progress and being conducted at pace to reduce the risk of the vulnerabilities highlighted on DQT (more valuable to spend resource effort on deommissioning DQT than fixing the vulnerabilities ahead of decommissioning). Roadmap of prioritised development to complete key features e.g. integration with OneLogin |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
412 | 2496 | 31/10/25 Reason for delivery confidence rating: The service is in Public Beta, with all users transitioned from the legacy service. We continue to monitor service metrics for any elements of the service that require attention. The main concerns relate to misunderstandings of when the service is required. Summarise actions being undertaken to bring the project back to green: N/A, although looking at how we can improve guidance and work with the policy team on the longer-term future of the service (ultimately seeking to decommission the service, which requires DBS buy-in). DBS have indicated, for the first time, they are open to discussions now (11 March 2025) Policy team starting to engage with actions needed to progress decommissioning due to other priorites. This was escalated in June 2025 |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
413 | 2497 | 11/09/2025 Reason for delivery confidence rating: When we launched the service in February 2023, we saw much higher than anticipated demand – particularly from teachers who qualified in the newly eligible countries. Whilst demand levels have significantly decreased and we are beginning to see a reduction in the size of the backlog we know that eligible candidates are still facing wait times that are outside the service level agreement and associated correspondence is causing additional burden. We are reviewing the priorities for delivery as there are currently two high priority workstreams (implementing recommendations agree by the minister and further information/decline) Summarise actions being undertaken to bring the project back to green: We have streamlined new functionality to enable the rapid decline of ineligible applicants. We have created a model to assess how surges will impact our backlog and inform future policy change. We have rolled out a new workflow to differentiate between higher and lower skilled tasks to enable support staff to take more burden off assessors. Agreed policy interventions will safeguard the service against future spikes in applications. To reduce the number of offline processes and make the assessment process more efficient and robust we are analysing correspondence data and exploring opportunities to bring more processes within service. Policy are reviewing our approach to global roll out and will provide advice to ministers in the next month. Updates to the way we build our delivery plan should enable foresight into the work that is coming up and better review resourcing requirements to avoid competing prioritise across both workstreams Summarise the business impact, if any: high volume of applicants risks long delays and high workloads for assessors |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
414 | 2498 | Attendance data mandating successfully went live on 21st August 2024. Work is on track to continue to iterate the product during this financial year. 99.57% of schools are sharing their daily attendance data. The team continue to work with Wonde to improve DQ and CBDS data fields. Product live and stable, with iterations happening for additional features/services. AtO sign off received. The following features were released on 1st September for new acamic year. - Removed from Roll (MVP2 Download) - Postcode Functionality - LA Learners Postscode - Attendance Return Reports 10 Days Continuous Unathorised Absence Return & Sickness Return (non-postcode) - Session Level Code Breakdowns - Transitional Years Data Sept released to schools on 09/09/2025 |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
415 | 2499 | There are three work strands, two of which are on track: maintenance of Help for early years providers, and delivering changes to the EY Child Development Training so that it meets the needs of Reception-based staff. We are extending timelines for the third work strand - publishing guidance around EYFS profile assessments for reception teachers on HfEYP - due to delays on content production following EY policy restructure. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
416 | 2500 | Our last show and tell was on 3rd October 2025, our next one is planned for 31st October 2025. We did a demo of the Education Record to the Permanent Secretary during her visit to Coventry, she was impressed by how simple the service was for Schools and how easy it was for pupils to get access to their own data. We had the Education Record Steering Group on 6th October, there were no concerns/objections raised on our next steps and we have some actions to take forward. The submission for the minister has been shared for feedback. We have a SoW in place with People for Research for a round of UR with pupils, we are also planning a round of UR focused on accessibility. We have started working on a video for schools to use to explain the purpose of the Education Record, and we have started on our communications material in preparation of the national roll out. We have released an update to Issue Education Record with a simplified issuing journey for schools, this was developed based on feedback from our pilot schools. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
417 | 2501 | Our last show and tell was on 3rd October 2025, our next one is planned for 31st October 2025. We have updated our user guidance based on user feedback and helpdesk queries, this is going for sign-off and will then be published on gov.uk. We are drafting comms to send out to apprenticeship providers following R14 to encourage them to transfer from LET to ELD. We released new functionality for additional learning aims to be added to a learner who is already enrolled on a course, and we are continuing with the developent work for non-funded apprenticeships. We have just completed a round of UR looking at reporting which covered ELD alongside SLD, VYED etc We have designed some updates to the service (e.g. additional content, inclusion of ILR codes alongside descriptions) based on UR feedback and provider queries. We delivered a webinar at the very end of September to over 70 employer providers, we were able to demo the new service, explain the benefits and answer questions from the participants |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
418 | 2502 | Following the recent strategy refresh, we’ve now structured our operating model around three core priorities. This shift began yesterday and is designed to help us deliver incrementally and at pace. We’ve also started work on deliverables to support resourcing for the “Cool Tool for School” initiative, which will enable us to move forward with delivery in that area. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
419 | 2503 | November: Final draft of strategy document to be shared with stakeholders and a Q&A session. Strategy to be shared with Tech SLT for sign-off – 21/11/25. Strategy published and engagement and comms with communities of practice to ensure awareness. Continue to prepare for implementation phase. October: Options paper developed and shared with Tech SLT on ownership model of the IDAMs space. Strategy reviewed to ensure all stakeholder comments resolved and where applicable addressed in the next version of Strategy document Continue to prepare for implementation phase. Initial engagement with DSiT about digital IDs and implications in the education space. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
420 | 2504 | Programme launched September 2025, goverance launched. Projects will be stood up over the coming months. Phonics project launched Tuesday 16.09.2025. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
421 | 2505 | Headset fresh completed Oct 16th 2024. 4084 headsets issued by the project. Including BAU, 63% of staff now have a noise cancelling headset Multiple projects in train to maintain, assure and improve all core services as listed. Videoconferencing refresh successfully completed (April - May 2024). Mobile refresh commenced (ongoing) from April 2024. Headset refresh commenced April 2024. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
422 | 2506 | Ongoing hardware refresh programme and associated technical upgrades throughout DfE estate. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
423 | 2507 | 23/9/24 CoPilot is underway with the Champions already trained and the community channel set up. Initial workshops for the main cohort started this week, with training and follow-up workshops over the coming weeks. Second tranche of licenses have been issued today. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
424 | 2508 | GPA has confirmed the new target delivery date is Qtr 1 of FY26/27. GPA has confirmed DfE as their tech partner. Governance arrangments now agreed. DfE to assign DM yo the project to work with GPA and DfE Estates to avoid the risk of delays or missing key dates due to BAU pressures. First step is for GPA to share a clear set of requirements for SB. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
425 | 2509 | 16/6/25 working with our 3rd party partners we are progressing the work and updating the LLM and utterances to make the returns for search results and CHAT interaction more DfE specific which will improve the end user experience. |  |  |  | 1 |  | 2025-11-20 10:53 | 2025-11-20 10:53 | True
560 | 18 | 24/10/25 Standards: - IT support standard being prepared for launch on 17 November in time for the Schools and Academies Show - new gov.uk landing page with policy stakeholders for review. The changes will reflect the "core standards" ahead of launch Plan tech: - MVP build almost all at testing phase or release ready. - Core recommendations have all been signed off by stakeholders and being 2id in contentful. - Mapping of old questions to new recommendations complete to support existing users to understand the changes we've made - Set up gov.notify and prepared comms to let users know about the service changes. Banner is ready to be implemented. Comms will go out a week before launch. - Minor accessibility issues resolved - Aiming to launch MVP by 12 November in time for the Schools and Academies Show on 19 November. Service downtime for release is expected to last for 3 hours. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
561 | 2294 | The API and Lakehouse are being refactored and due to being held up with issues with commercials with system C impacting schedule - refactoring sliver and gold layers. Improvement work continues on improving the public dashboard - working on servere absences. Continuing iteration and build of private Dashboard. Will work on Testing API with CMS providers, D2I and or LAs. Progress during this period - -Public Dashboard OFSTED update -UR for Private Dahsboard ongoing -Private Dashboard MVP build underway alongside final QA page (UaT) -Prototyping of Private Dashboard continuing -Severe absence in main -7 LAs connected to SIT environment |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
562 | 2295 | 16/10/25 - Work to start in November to map all technical services within the CMDB |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
563 | 2296 | 25/06/24: This has been on hold for a long while and not going to go ahead as originally planned. A new deliverable will be added once we have procured a team to do the work. 26/09/24: This has now been overtaken by new deliverables which we are reporting on at a more granular level. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
564 | 2297 | The application window closed on 21 March. We received 753 applications for Turing Scheme funding in academic year 2024/25. This represents an 21.6% increase from the 619 applications received in year 3 (note - this information has not yet been shared publicly). This represents the conclusion of the application process for AY24/25 and the design and development focus now shifts to the development of functionality to support the assessment, appeals, payment and grant management processes. Longer term, and subject to SR approval, the team will launch the application process for the fifth year of the scheme (academic year 2025/26). The application window is expected to open in early 2025, although minimal changes are required to the application portal. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
565 | 2298 | Development delays resulted in a transition to a contingency offline solution (spreadsheets) to ensure the payment of funds to organisations taking part in the Turing Scheme. The contingency replicated the design of the digital solution and enabled organisations starting Turing Scheme placements in September 2024 to submit details of payments and payment requests. This solution enabled payments to be made to 81 organisations in August, 83 providers in September and 310 organisations in October. New delivery date planned for 31/01/2025. While the contingency option has enabled participating organisations to receive the funding they need to support students on international placements, it has required significant developer input to prepare for and enable the extraction of placement data into the CRM. This has resulted in developer resource being diverted away frrom the development of the monthly reporting process through which organisations submit details of expenditure, expected expenditure and placements. The monthly reporting functionality is expected to launch in w/c 4 November and the final reporting functionality is expected to go live by the end of January 2025. This will complete the development of the service supporting the fourth year of the scheme. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
566 | 2299 | Due to recent ministerial steers leading to the decision not to do extensions of the DPS1 and DPS2 contracts, and with no plans to undertake a DPS3 at this time, the Skills Bootcamps leadership team have reviewed the value that would be gained from having the supplementary data collection for Grants providers and deemed that the added value isn’t enough to warrant the costs of the project, especially with added pressures to reduce spend within the department. Notification was received on 22nd August and the project will fully close down on 30th August. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
567 | 2300 | Agree non project team owner for accreditation process issues. Continue to work with 3rd parties to ensure all can adopt solution. Replacement of ECS legacy system in 2025. The Replacement project has reviewed the end-to-end process for eligibility checking and determined what the overall process and technology should look like in the post-ECS environment. Now in Beta we are building two products as an MVP: a hub – the Entitlements Checking Engine (ECE), and replacement spokes for both School Meals and Childcare. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
568 | 2301 | The status has been moved to Amber/Green due to the delays to the procurement specification which was due to go out to the sector in October 2025 but will likely fall into the start of the new year now, following the request from the new minister Josh MacAlister to revisit and amend the Post Qualifying Standard (PQS). The digital service, however, is not currently blocked by this decision and are able to proceed as per the current plan, whilst the PQS is being re-drafted. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
569 | 2302 | We've extended the early years workforce register discovery by a sprint due to a slower than anticipated start. Work is continuing on the qualifications side to explore opportunities to improve how we manage qualifications date. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
570 | 2303 | A new team is now in place to work on this product until March 2026. A GDS assessment is planned for after the next round of updates. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
571 | 2304 | Lack of ownership of NHSE of their elements of the work needed to progress with the NHS number as the SUI and the use of their systems to enable the pilots to take place. Amber/red due to lack of progress on resolving issues. Escalation of concerns about NHSE engagement. To improve the use of technology to share information between agencies working with children and families (schools, police, health and children's social care) and to explore the use of a consistent child identifier (CCI), also referred to as a Single Unique Identifier (SUI), to enable this. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
572 | 2305 | All required IT changes have already been made by HMRC, and LA third-party suppliers have all provided roadmaps for delivery. Successful delivery involves handoffs between multiple digital systems – these all need to be assured with no degree of risk for this project to be Green. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
573 | 2475 | MEPS currently paused. Transferred to Rob Rodney/Schools digital division who will review the project. Prior to pause, work was focusing only on the first component (Search, Filter and View - Unauthenticated) before moving on to the next component. Progress had been made as follows - * Initial meetings held with assessors for the Alpha assessment. A peer assessent will be undertaken during the coming period. * Fourth Show and Tell took place on 25/02/2025 (approx. 87 attendees). * Teach-in session with Teacher services took place on 13/02/2025. Architecture and Helpdesk parts to be rescheduled (ran out of time). |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
574 | 2476 | 11/09/2025 Reason for delivery confidence rating: We are performing well, with strong engagement from schools and record numbers of jobseekers. We launched the All School Roles MVP in March, which has seen a significant uptick in the number of schools signed up to the service, to over 87% of schools in scope. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
575 | 2477 | Key Highlights: - MSI delivered the monitoring phase and began iteration 2 of mandation, with contact management improvements underway. - FAST completed its final deliverables and transitioned successfully to CI, marking a key milestone in product consolidation. - Innovation launched MPC and shifted focus to AI discovery, aligning with strategic objectives. - CAT progressed .Net migration and achieved infrastructure standardisation, supporting long-term technical resilience. - Service Support (SS) maintained high SLA performance and user satisfaction, despite ongoing resource constraints. Areas Requiring Attention: - EAT remains Amber-Green, with extended timelines and reliance on external accessibility audits. While delivery is progressing, dependencies and testing limitations present risks to future milestones. - CI is managing increased scope due to handovers from FAST and MPC, alongside SEND/CSC delivery challenges. Engagement gaps in user testing and overlapping priorities are impacting delivery pace. Risks to Delivery Confidence: - Contract re-procurement remains a strategic risk due to tight timelines and limited commercial support. - White Paper reforms continue to introduce uncertainty, affecting planning and capacity management for Q4 and beyond. - CI delivery risk due to scope increase and SEND/CSC engagement issues. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
576 | 2478 | FIAT has been handed over to the Continuous Improvement team |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
577 | 2479 | Product is managed by our Performance analysis & service support team (PASS) It is performing well and there are no concerns. Key metrics: - average availability has been 100% in the last 30 days and average response time has been 34ms SFSO & RG colleagues are successfully managing governance concerns within ReCaST. Successful progression of the continuous improvements entered through the new front door process for SFSO. Service reviews are scheduled with SFSO. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
578 | 2480 | 06.06.25 - Continues to be on hold, and probably will be for some time – There is a power app supporting the business processes now so it’s not as important as it was to get of legacy tech. The external application process though does need significant improvement; but that will fall into another one of our projects in the medium term, External Applications. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
579 | 2481 | MFSP continues to receive predominantly positive feedback, only receiving one disatisified response since the start of May. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
580 | 2482 | Product is now managed by our Performance analysis & service support team (PASS) |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
581 | 2483 | Previous update stands as tool is replaced by FIAT. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
582 | 2484 | Work is ongoing on bug fixes with no clear date identifed on when all will be cleared. IEBT put on hold until current identified bugs are cleared. Amber RAG due to schedule delays. PSR resources will be extended on current Data POs and transferred to Teacher Services at a later date to prevent standing Java developers down. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
583 | 2485 | All work is on track with limited large scale development and a focus on minor enhancements, and ongoing service maintenance and operations. The past period has seen a number of enhancements to improve the AO user experience in terms of data visibility and to extend the DfE admin interface to give greater functionality that reduces reliance on technical development support. Testing ahead of summer 2025 results has completed successfully. There are no major concerns/issues to note. Work continues to progress the potential for a future transfer of the results service to AOs. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
584 | 2486 | 11/09/2025 Website: Project is reliable, with planned improvements to improve performance and enhance user experience. CRM: Team moved outside IR35 in October 2023 but is still aligned with the rest of the service, with continuous improvements alongside major development work. GSE: Growth continues organically with the service but there is little active development of the service due to team and budget constraints. We are instead focusing on ‘keeping the lights on’ and ensuring the service complies with governance requirements. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
585 | 2487 | 11/09/2025 Reason for delivery confidence rating: The new recruitment cycle started well, without issue for Find or Apply opening. Offer and acceptance rates in the first 10 weeks have been encouraging however we are noticing lower submission rates of applications (particularly for Primary courses and international candidates; we continue to monitor. Send trainee data direct project delivery is dependent upon SRS vendors AND Providers being ready – this is being mitigated through ongoing engagement with both groups, but remains a delivery risk Summarise actions being undertaken to bring the project back to green: Close collaboration with key external and internal stakeholders to assess and address key concerns. Summarise the business impact, if any: Send trainee data direct risk to 25/26 ITT collection – any vendors/providers who have not successfully integrated with the Register API could still use the CSV bulk upload or the manual entry routes. There is also inclusion of backstop clause in case DfE requires HESA to collect the 25/26 ITT collection if insufficient numbers of providers are ready, |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
586 | 2488 | 11/09/2025 Reason for delivery confidence rating: In the previous claim window we received over 21,315 claims and £73.9m has been paid to teachers across all user journeys to date (over £108m paid by DfE including tax). All claim services have now been closed. With the service now closed we are focusing on improving our existing services, particularly the FE service and the implementation of a permanent alternative IDV route for users who cannot verify their identity using GOV One Login. We also successfully completed the EY service private beta assessment in May, receiving an amber rating, and are preparing for public beta launch in September. We have removed the Early Career Payments service from Claim, now that this policy has ended. We are also making changes to accommodate Year 2 requirements to the IRP user journey. We also supported the DfE's teacher pay announcement with the launch of the Teacher Pay Calculator on GOV.UK. The proposed solution to accessing HE Qualifications from alternative sources once DQT is decommissioned (which was a blocker for checking claims next year) has been progressed and the data has been tested with claim successfully. The main risk for Claim continues to be civil servant resource, with both product managers, delivery manager, and the interaction designer leaving the Claim service. Since then, a new product manager and service designer has joined the team as well as a contractor delivery manager from Version 1. Whilst resource has been replaced, a significant amount of knowledge and experience on claim has been lost. Summarise actions being undertaken to bring the project back to green: Working with SMT regarding resource risk for Claim Handovers are in place to help knowledge transfer with new claim members |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
587 | 2489 | Final pre-production testing and any subsequent remedial development work is almost complete. The plan to meet the target go-live date of 10 November 2025 is on track. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
588 | 2490 | 07/05/25 - PMO discussion with delivcery team. Confirmed that this is a programme of delivery. Will work to confirm high-level milestones within the programme over the coming months. Overall - the service is delivering basic needs with strong user satisfaction. Pain points remain and crucially the service does not have the capacity to scale in line with its FBC requirements. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
589 | 2491 | Overall programme rag remains amber/green, with individual project RAGS, which can be seen below, ranging from Amber/red to Green. Delivery details are recorded on the individual progreamme updates. After delivering the intial data cycle, work is now onoing to iterate the product, with work to replace DEI and moving to Databricks identfied, alongside the current delivery cycle. KS2 - Green. KS4 - Amber/Green. 16-18 - Green LDS 2.0 (improve & re-platform) - Green. (Requirement to be off DEI by September 2027 (Planned for April 2026.) |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
590 | 2492 | School Checking schedule is currently on track, with key milestones outlined below. Following completion of the KS4 & 16-18 Autumn Live Checking Exercise, scrutiny is underway with outcome to be provided to MDP on 03/11. KS4 - 16 June - Complete KS2 - 08 September - Complete KS4 & 16-18 Autumn - Complete KS4 & 16-18 LR2 File - 20 Nov 16-18 L3 VA Data - 20 Nov |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
591 | 2493 | 11/09/2025 Reason for delivery confidence rating: AB portal work not throwing off roadmap as much, amber green as there are still lots of dependencies across teams but delivery momentum is picking up. Combined ECF/NPQ data model which causes bugs, data quality issues and high volumes of support tickets. High civil servant to contractor ratio on the programme. Summarise actions being undertaken to bring the project back to green: New regular meetings on AB portal and NPQ dependencies with TRN to manage considerable dependencies |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
592 | 2494 | A service that supports the career development of child and family social workers by showcasing DfE funded development programmes. There has been a decision to pause work on the service from December. Completing the information architecture restructure work will put the service in a much better place from an accessibility and usability perspective. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
593 | 2495 | 31/10/25 Reason for delivery confidence rating: All teaching record data supporting services across Schools Digital is now soley coming from TRS, not DQT. The Operations and Support team have a console to view and manage queries from users about their Teaching Record. Much is still in MVP but with clear plans for critical improvements. How we're getting to GREEN DQT decommissioning is in progress and being conducted at pace to reduce the risk of the vulnerabilities highlighted on DQT (more valuable to spend resource effort on deommissioning DQT than fixing the vulnerabilities ahead of decommissioning). Roadmap of prioritised development to complete key features e.g. integration with OneLogin |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
594 | 2496 | 31/10/25 Reason for delivery confidence rating: The service is in Public Beta, with all users transitioned from the legacy service. We continue to monitor service metrics for any elements of the service that require attention. The main concerns relate to misunderstandings of when the service is required. Summarise actions being undertaken to bring the project back to green: N/A, although looking at how we can improve guidance and work with the policy team on the longer-term future of the service (ultimately seeking to decommission the service, which requires DBS buy-in). DBS have indicated, for the first time, they are open to discussions now (11 March 2025) Policy team starting to engage with actions needed to progress decommissioning due to other priorites. This was escalated in June 2025 |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
595 | 2497 | 11/09/2025 Reason for delivery confidence rating: When we launched the service in February 2023, we saw much higher than anticipated demand – particularly from teachers who qualified in the newly eligible countries. Whilst demand levels have significantly decreased and we are beginning to see a reduction in the size of the backlog we know that eligible candidates are still facing wait times that are outside the service level agreement and associated correspondence is causing additional burden. We are reviewing the priorities for delivery as there are currently two high priority workstreams (implementing recommendations agree by the minister and further information/decline) Summarise actions being undertaken to bring the project back to green: We have streamlined new functionality to enable the rapid decline of ineligible applicants. We have created a model to assess how surges will impact our backlog and inform future policy change. We have rolled out a new workflow to differentiate between higher and lower skilled tasks to enable support staff to take more burden off assessors. Agreed policy interventions will safeguard the service against future spikes in applications. To reduce the number of offline processes and make the assessment process more efficient and robust we are analysing correspondence data and exploring opportunities to bring more processes within service. Policy are reviewing our approach to global roll out and will provide advice to ministers in the next month. Updates to the way we build our delivery plan should enable foresight into the work that is coming up and better review resourcing requirements to avoid competing prioritise across both workstreams Summarise the business impact, if any: high volume of applicants risks long delays and high workloads for assessors |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
596 | 2498 | Attendance data mandating successfully went live on 21st August 2024. Work is on track to continue to iterate the product during this financial year. 99.57% of schools are sharing their daily attendance data. The team continue to work with Wonde to improve DQ and CBDS data fields. Product live and stable, with iterations happening for additional features/services. AtO sign off received. The following features were released on 1st September for new acamic year. - Removed from Roll (MVP2 Download) - Postcode Functionality - LA Learners Postscode - Attendance Return Reports 10 Days Continuous Unathorised Absence Return & Sickness Return (non-postcode) - Session Level Code Breakdowns - Transitional Years Data Sept released to schools on 09/09/2025 |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
597 | 2499 | There are three work strands, two of which are on track: maintenance of Help for early years providers, and delivering changes to the EY Child Development Training so that it meets the needs of Reception-based staff. We are extending timelines for the third work strand - publishing guidance around EYFS profile assessments for reception teachers on HfEYP - due to delays on content production following EY policy restructure. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
598 | 2500 | Our last show and tell was on 3rd October 2025, our next one is planned for 31st October 2025. We did a demo of the Education Record to the Permanent Secretary during her visit to Coventry, she was impressed by how simple the service was for Schools and how easy it was for pupils to get access to their own data. We had the Education Record Steering Group on 6th October, there were no concerns/objections raised on our next steps and we have some actions to take forward. The submission for the minister has been shared for feedback. We have a SoW in place with People for Research for a round of UR with pupils, we are also planning a round of UR focused on accessibility. We have started working on a video for schools to use to explain the purpose of the Education Record, and we have started on our communications material in preparation of the national roll out. We have released an update to Issue Education Record with a simplified issuing journey for schools, this was developed based on feedback from our pilot schools. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
599 | 2501 | Our last show and tell was on 3rd October 2025, our next one is planned for 31st October 2025. We have updated our user guidance based on user feedback and helpdesk queries, this is going for sign-off and will then be published on gov.uk. We are drafting comms to send out to apprenticeship providers following R14 to encourage them to transfer from LET to ELD. We released new functionality for additional learning aims to be added to a learner who is already enrolled on a course, and we are continuing with the developent work for non-funded apprenticeships. We have just completed a round of UR looking at reporting which covered ELD alongside SLD, VYED etc We have designed some updates to the service (e.g. additional content, inclusion of ILR codes alongside descriptions) based on UR feedback and provider queries. We delivered a webinar at the very end of September to over 70 employer providers, we were able to demo the new service, explain the benefits and answer questions from the participants |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
600 | 2502 | Following the recent strategy refresh, we’ve now structured our operating model around three core priorities. This shift began yesterday and is designed to help us deliver incrementally and at pace. We’ve also started work on deliverables to support resourcing for the “Cool Tool for School” initiative, which will enable us to move forward with delivery in that area. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
601 | 2503 | November: Final draft of strategy document to be shared with stakeholders and a Q&A session. Strategy to be shared with Tech SLT for sign-off – 21/11/25. Strategy published and engagement and comms with communities of practice to ensure awareness. Continue to prepare for implementation phase. October: Options paper developed and shared with Tech SLT on ownership model of the IDAMs space. Strategy reviewed to ensure all stakeholder comments resolved and where applicable addressed in the next version of Strategy document Continue to prepare for implementation phase. Initial engagement with DSiT about digital IDs and implications in the education space. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
602 | 2504 | Programme launched September 2025, goverance launched. Projects will be stood up over the coming months. Phonics project launched Tuesday 16.09.2025. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
603 | 2505 | Headset fresh completed Oct 16th 2024. 4084 headsets issued by the project. Including BAU, 63% of staff now have a noise cancelling headset Multiple projects in train to maintain, assure and improve all core services as listed. Videoconferencing refresh successfully completed (April - May 2024). Mobile refresh commenced (ongoing) from April 2024. Headset refresh commenced April 2024. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
604 | 2506 | Ongoing hardware refresh programme and associated technical upgrades throughout DfE estate. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
605 | 2507 | 23/9/24 CoPilot is underway with the Champions already trained and the community channel set up. Initial workshops for the main cohort started this week, with training and follow-up workshops over the coming weeks. Second tranche of licenses have been issued today. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
606 | 2508 | GPA has confirmed the new target delivery date is Qtr 1 of FY26/27. GPA has confirmed DfE as their tech partner. Governance arrangments now agreed. DfE to assign DM yo the project to work with GPA and DfE Estates to avoid the risk of delays or missing key dates due to BAU pressures. First step is for GPA to share a clear set of requirements for SB. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
607 | 2509 | 16/6/25 working with our 3rd party partners we are progressing the work and updating the LLM and utterances to make the returns for search results and CHAT interaction more DfE specific which will improve the end user experience. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
608 | 2510 | Recent finance decisions have led to budget cuts, resulting in lost time on several projects and the offboarding of team members. This has placed key deliverables for the year at further risk, particularly within school-based nurseries. Last year, EDDDT successfully delivered a new CRM system. Although the development process was tumultuous and led to some DDT team burnout, the outcome was positive. However, the post-delivery assessment highlighted that early years policy teams need to provide DDT with more advance notice of upcoming requirements to ensure successful future phases. Currently, the early years policy team has approached DDT with a request to develop a new CRM system, giving less than a month for delivery. This short timeline has caused disruption within the teams. There has been an approach approved that should allow the dealine to be met for the announcement but a lack of clarity on future phase of development. In addition, other teams are facing challenges with development timelines, which may not be achievable within the timeframes set by policy areas in the education sector. Ways of working within teams are also under strain. Delivery plans are not being accurately reflected, which hinders senior decision-making. This issue stems from a combination of contractor quality and evolving policy priorities. We are also experiencing instability across some of our existing systems. Unlocking the necessary resources to implement meaningful fixes within the requested timeframes remains a challenge. Compounding this, we are receiving a number of expedited requests from other policy areas, which we are struggling to meet due to the ongoing financial pressures. Furthermore, there is currently no overarching strategy or roadmap in place. Actions have been taken to address this, including onboarding two lead product managers. However, they require time to consolidate existing DDT information across educational states to enable the creation of a clear vision and roadmap. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
609 | 11403 | November: DM to make final checks on Access to Cloud Resources in ELZ standard then request approval from Standards Forum. Call arranged with HoP to develop a standard drafting process so that this can be shared across Infrastructure Services, socialised at the IE community and then move standards development into BAU. October 2025: Backlog was discussed and left with HoP to review on 20 October. Follow-up calls have been arranged to sign-off backlog. DM had a call with Standards forum admin lead regarding moving the Access to Cloud Resources in ELZ standard into approval as name/publishing issue has been resolved. Updated version (v 1.9) of Azure PIM for Resource roles pattern has been produced. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
610 | 11404 | November: Prepare response to FinOps maturity assessment recommendations for SLT review. Develop approach to recharging Rubriks costs. Product tagging policy review Perform second pilot for CAAS Stage 2. Investigate SQL servers resilience work. October: Completed testing on CAAS tool enhancements.. Progressing CAAS Stage 1 engagements with existing service lines and initiating new ones. Continuing work on Open AI recharging. RD Farm completed. Continuing CAAS Stage 2 engagement, including work identifying a second service line to use in the pilot. Exploring addition of tables to the FinOps Power BI dashboard. Carried out a horizon scanning session to plan the next six months. Investigating unattached Azure recovery vaults. Started development of the FinOps newsletter to be released in November. FinOps Community of Practice, held on 15th October, focussed on workload optimisation. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
611 | 11405 | November: User research workshop Awayday in Manchester Workshop to identify features reporting functionality Make recommendations following results of CMS trial Developing FaUAPI Teams Site beyond front page Fill in Service health check app Continue API migration; workspace notifications; new role types October: Completing ITHC improvements – final issue to be reviewed Developing FaUAPI Teams Site beyond front page. CMS trial of 3 systems recommended in DfE standard Workspace notification groups development New system role types in development |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
612 | 11406 | November: Onboard ~60% of Vendor clients to ECE Launch Private Beta for Multi-Academy Trusts, Academies Launch Private Beta for LAs for EYPP & 2YO offer checks October: Onboard ~60% of Vendor clients to ECE Launch Private Beta for Multi-Academy Trusts, Academies Launch Private Beta for LAs for EYPP & 2YO offer checks |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
613 | 11407 | November: Consolidated ITHC -ITHCs scheduled for all CRMs, EDD, ICA, IEBT, SISL, Employer and Provider completed, Turing and Breakfast Clubs scheduled for Dec. Reports to be received with prioritisation and planning for remediation of findings within our control, Microsoft will need to be contacted for advice on findings which are out of our control due to Dynamics being SAAS Turing - Y6 dev work and further refinements . NCA/SRP - Handover of SRP and NCA to Education Estates support services Qualys scanning - Planning for Provider; Employer; ICA; EDD; IEBT and Turing scans. Provider - Davina chatbot prototype and investigation into AI opportunities for case management completed October: Consolidated ITHC - Demo for Turing ITHC, All CRMs scoped and SoWs sent for approvals. Evergreen – Wave 2 updates to production completed for Turing (all SDT services completed). Provider- Bug fixes and Deployment of GDS framework updates to Prod complete, Removal of unused apps, security role review and updates. In progress - CX One: Create CI from phone call activity, Common ILR errors - journey change, Service Now Integration - Specialist referral Teams, Ofsted/CI&CRM reference changes, Apprenticeship Payment Journey, SCCU reports, new pages, status reasons and fields, Employer CRM into Provider – further requirements gathering. Workshop held on plans for future of Provider CRM – removal of unused fields and improvements that need to be made before other CRMs are migrated in Investigation into chat bot improvements completed and Davina chatbot prototype and investigation into AI opportunities for case management in progress Turing - Monthly reporting updates tested and deployed to Production, Y6 requirements refined and dev work . SISL – Accessibility audit completed with 1 minor finding, Review and prioritisation of Qualys scan results paused awaiting lead dev availability CIF– Handed over to Education Estates services to BAU team. Criticality scorecards - Completed for EDD, ICA, IEBT, SISL, Employer and Provider |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
614 | 11408 | November 2025: Service Status and Capacity GREEN Network availability GREEN Hosting availability AMBER Recruitment and retention: AMBER October 2025: Service Status and Capacity GREEN Network availability GREEN Hosting availability GREEN Recruitment and retention: Amber |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
615 | 11409 | November: Finalise the updated data and technology strategies, generate DG-level support, communicate to Directors, SLT, DDT, then DfE. Provide oversight on STA review, support Skills England (iFATE) with architecture review recommendations. Explore opportunities for corporate services review. Onboard managed service support for the Enterprise Data Model and business capability mapping, accelerate model development. Explore running business process/capability diagnostic with a wider group in DDT Deliver comms for data and technology strategies, Target Architectures, etc with Directors, SLT and portfolios. Publish the EA strategy. Finalise Data/Security Architect updates on the architecture capability framework, begin implementation of CBP for Data Architect. Onboard new architecture services contract, work through new SoWs, support portfolios to transition requirements across. October: Continued refinement of data and technology strategies Implementation plan for ‘first data service’ capital spend drafted Skills England architecture review completed, recommendations delivered Enterprise Data Model development continued, with a SoW for additional support drafted (awaiting new capability contract). Business architecture models continue to evolve, pilot business process diagnostic analysed + updated, exploring options to extend with Info Tech Developing narrative & comms for data and technology strategies, Target Architectures, etc with Directors, SLT and portfolios. EA strategy underway. Security / Data Architect updates drafted in the architecture capability framework, undergoing review before publishing New architecture services contract signed, new SoWs and templates created, supporting portfolios with contingency / transition requirements. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
616 | 11410 | November: AI Adoption CoE roadmap updated. Changes will be implemented on how users access the Sandbox environment to FaUAPI. Engage with Schools Group workshops on potential AI use cases – 17th and 25th November Ed Chat – Service standards peer review scheduled; Private Beta launch with circa 200 DfE colleagues for 2-3 months planned – Beta focus is on colleagues in policy, strategy, legislation, grants, and finance profession but trial open to all. Records Management proof of concept - continue to build the functionality of the product. There is a potential roadblock in that the business rules provided by the KIM team are not robust enough to build an effective and accurate tool. October: Preparations for changes to be implemented on how users access the Sandbox environment to FaUAPI. Follow-up engagement with Schools Group following VCF workshops on potential use cases. One Big Thing communication and engagement – over 20% of all staff have completed the training in the first two weeks New form launched - AI Centre of Excellence Support & Requests - IT Help Centre |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
617 | 11411 | Phase 3 (development and rollout planning in-progress) • Scorecard for new services onboarding Service Now is in testing. Proposed go-live, scheduled for third week of October. • Because Service Now limits user self-service for current offerings, the WG is manually collecting information using the prototype and will separately bulk upload scorecard responses. • There are three groups the project is working on; Enterprise Service Managers, embedded Service Managers and other (contact information is lacking or missing). • The goal is to collate and upload final results into Service Now by end of November 2025. There is circa of 300 plus service offerings requiring scorecards. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
618 | 11412 | Budgets moved to relevant areas in most cases. Continuing to resolve any final areas where budgets need to be moved. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
619 | 11413 | Luc Beer leading on commercial development for the central operations team. Developing commercial pipeline for DDT |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
620 | 11414 | Review of service to take place following development of Central Operations function. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
621 | 11415 | Budgets maximised in 2425. Review taking place on delivery of L&D following development of Central Operations team. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
622 | 11416 | Team established within Central Ops. Vacancies within team being advertised. Appointed Demand Manager from OMS - starts 2nd June. Improved reporting through focused stakeholder engagement Governance review has started, initial data gathering has been completed. Discussion guide compiled ahead of next phase of data gathering reaching out to stakeholders across DDT. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
623 | 11417 | Live service continues to function well. D&T Spend Controls pipeline for Q1 2024-25 authorised by CDDO. All Service Assessment and peer review requests met. RAG reflects ongoing challenge in meeting new CDDO guidance for D&T Spend Controls (v6) & Service Assessments. Continuing to pilot both processes and working with CDDO to develop transition plans. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
624 | 11418 | Current net savings (committed) are £75k in 24-25 (rolling on to deliver £758k in 25-26) and a further £233k of new savings in 25-26. There are a further £331k of likely savings in 25-26 (where jobs have been offered). This is the tip of the iceberg; just from the current and imminent recruitment campaigns there could be a further £1.8m of net savings in 25-26 from only these first five professions. We expect to begin implementation for Security Architecture and Software Development in the next few months, with significant further savings potential. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
625 | 11419 | New content added and content for those in the criminal justice system underway. Reuseable checker ("Get to an answer") being built as reusable component for this project, the FE recruitment site and other uses which have already been identified. Due to complete work by January when site will start to transition over to Families Digital team for continued running |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
626 | 11424 | Ministers have been briefed on the DDT block. Minister Morgan has shown an interest in AI, we have sent several for information context notes requested, and submissions with decisions to be made (e.g. Evidence Board and Sector Fund). Work is beginning to pick up and teams are working on task and finish group projects for the next 100 days. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
627 | 11425 | Following the recent strategy refresh, we’ve now structured our operating model around three core priorities. This shift began yesterday and is designed to help us deliver incrementally and at pace. We’ve also started work on deliverables to support resourcing for the “Cool Tool for School” initiative, which will enable us to move forward with delivery in that area. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
628 | 11426 | PA: MPC report scheduled now live Strong work progress on Inspect and Adapt SS: - A major (P1) incident affecting multiple services was well managed through clear communication and strong coordination across teams, resulting in a swift and controlled resolution. - Delivery of live cases work for Prepare and Complete completed as planned, improving data accuracy and visibility. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
629 | 11427 | Working on gov.uk re-redesign, tech debt and databricks migration |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
630 | 11428 | CFS PI 13 Objectives ( 24/09/2025 to 16/12/25) 1 BAU support and tasks – IN PROGRESS 2 Adults performance management onboarding – IN PROGRESS 3 Complete frontend update for DfE rebrand – IN PROGRESS 4 Cosmos to SQL (work on four containers in PI 13) – IN PROGRESS 5 Tech Debt (Upgrade to TLS 1.3, Fix failing integration tests and upgrade ServiceBus package) – IN PROGRESS 6 Also support communicate funding, tenancy and data projects – IN PROGRESS CFS PI 12 Objectives (02/07/2025 to 23/09/2025) 1 BAU - clones, support, platform maintenance - COMPLETE 2 Adults PMP onboarding - COMPLETE 3 GAG specs to use data from multiple periods - COMPLETE 4 CFS UI Rebrand - Completed for v 4.10 5 Cosmos to SQL - PR, PVM, Calcs, data aggs - COMPLETE 6 Problem releasing big batches of providers - COMPLETE 7 Tenancy move support – Completed for PI 12 and some parts moved to PI 13 8 Test team support - COMPLETE 9 Ensuring zero value allocs are reprofiled for indicative to live providers -COMPLETE 10 Removing v3 grouping – investigation - COMPLETE CFS PI 11 Objectives (26/03/2025 to 01/07/2025) 1 Adults onboarding – COMPLETE 2 Cosmos to SQL - COMPLETE 3 .NET upgrade from version 6 to 8 - COMPLETE 4 Enable rule-based profiles to be applied for new openers in Pupil premium in bulk - COMPLETE 5 Support the refinement squad towards accessibility and compliance for CFS - COMPLETE CFS PI 10 Objectives (01/01/2025 to 25/03/2025) 1 Adults Onboarding - 25/26 Statements, - 25/26 Initial contracts, - Plan for -------- 2 Cosmos to SQL- Specs & DataSets: Deploy - Provider Results: Develop - COMPLETE 3 Platform Maintenance- EAPIM to FAUPI- .Net upgrade from 6 to 8 - COMPLETE 4 Ensure Obsolete Groups have no child providers - COMPLETE 5 Adding MS Clarity to CFS. -> Cookie consent - COMPLETE 6 Decouple CFS V3 COSMOS DBSimpler – Not COMPLETEd Deferred 7 Application of Rule Based Profiles For PP - COMPLETE CFS PI 9 Objectives (02/10/2024 to 24/12/2024) 1 Adult Phase 2 – Carried forward for PI 10 2 Service Enhancements - COMPLETE 3 GAG funding data onboarding 25/26 - COMPLETE 4 Central data discovery - COMPLETE 5 BAU activities - COMPLETE CFS PI 8 Objectives (10/07/2024 to 01/10/2024) 1 Enable Adults allocation team to calculate 25/26 allocations in CFS with data from FDS COMPLETE 2 Design solutions for integrating Adults funding data from CFS to MYESF and FCS to create statements and contracts COMPLETE 3 Complete the Cosmos to SQL for the policy container and develop solution for the datasets container COMPLETE 4 Onboard PSG and ILP Recon 24/25 funding data from FDS into CFS in time for the next allocations round COMPLETE 5 Complete the implementation of the reprofiling previously reprofiled allocations from the open date on refresh funding if there has been an allocation change COMPLETE 6 Set up RU tracking for Cosmos transactions COMPLETE 7 Complete the Disaster Recovery template by the end of September 2024 IN PROGRESS |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
631 | 11429 | RQ delivered. Change summary behaviour work on track. Calculation and result component rebuild beginning. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
632 | 11430 | FCS PI 13 Objectives ( 24/09/2025 to 16/12/25) - Rollover of TTF funding 2526 - Completed - Onboarding of TTF Y2 2526 - Completed - TEC construction Funding 2526 – In progress - CRM Wave-2 2025 upgrade – Completed - .NET Framework update from 6.0 to 8.0 - Completed (except 1 component that being picked up with 4.8 to 8.0 migration) - .NET Framework update from 4.8 to 8.0 - In progress - Angular package updates - In progress - Adult onboarding In year changes - In progress - Apprenticeship Agreement implementation - yet to start - FCS Digitisation – In progress FCS PI 12 Objectives (02/07/2025 to 23/09/2025) - Rollover SBPS 2526 – Completed - SSL certification renewals -Completed - Rollover of TTF funding 2526 - in progress - Onboarding of TTF Y2 2526 - In progress - Apprenticeship Agreement implementation - NA - CRM Wave-2 2025 upgrade – In progress - .NET Framework update from 6.0 to 8.0 - In progress - Angular package updates - In progress - Adult onboarding In year changes - In progress FCS PI 10 Objectives (01/01/2025 to 25/03/2025) - FCS Adult onboarding ASF– In progress - Rollover of Procured Non-Levy Apprenticeship 2526 – Completed - Rollover of EDSK Loans 2526 – Completed - CRM Wave 1 2025 upgrade – In progress - FCS Digitisation – In progress - App Levy Digitisation – Completed - LA and College confirmation report - Completed |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
633 | 11442 | Discovery to complete on time (4 November). Discovery outputs to inform next steps (Alpha phase) towards the future data/digital solution. Continuing to progress the Action Plan for SINs. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
634 | 11453 | Expansion of Plan Tech service Consultation on Standards 2030 vision. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
635 | 11454 | A top 75 service - Services operating at high volumes. We did deal with a P2 in the last month, but that has been resolved. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
636 | 11455 | Milestone - Analysis of returns and identification of risk landscape (end Dec 25) Update October 2025 Initial analysis is considering on maturity levels against the critical domains of the Cyber Assessment Framework (CAF), best practice and improvement opportunities. SEPT 25 UPDATE - All ALBs in scope of the cyber assurance return completed and returned the survey by the end of September. We will now focus on analysing the returns. Agree ALB Gov Assure participants for year 3 (end Oct 25) Targeted conversations are on-going to agree ALB Gov Assure arrangements for Year 3 AUG 25 UPDATE - Developed and launched a cyber assurance return for ALBs in July 2025. The return closes at the end of Sept 2025 and we will analyse the returns to better understand the risk ALB landscape. We will then identify and agree which ALBs will participate in Gov Assure for year 3. Update 20/02/2025 - ALB cyber security forum established, and relationships build across ALB network. Developing a questionnaire for ALBs to complete which will give us a better understanding of the level of cyber security risk across ALBs. Update 28/11/2024 (Alison Dunne) Scoping work is progressing well and inital engagment has been positive. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
637 | 11456 | Work on track. For this financial year this will concentrate on supporting releases through the 23/24 publication cycle, with work to address known stability and security issues, including exploring move from T1 to CIP. A decision has been made to pause the work on the MVP until we have clarification on what a new system should look like. This was discussed as part of the SG2B in August 24. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
638 | 11457 | Work continues to deliver the current release cycle. There are delays in data being provided which has led to the amber/green RAG. Delays have been communicated and impact is minimal. The following work is being completed- 1.Continued working on resolving ASP User Queries 2.Continued working on the BAU Data releases for 2023/24 |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
639 | 11458 | November: Continue - Ed Estates Portfolio -Data activities, Purview adoption / data dictionary embedment. Continue - Data quality assurance working group – data literacy Explore discussions supporting central Data Governance lead – current rational of existing activities. Development of dev ops piece of work. Microsoft costings for Purview post scoping calls Publish Metadata standards. Bi Annual data Asset commission October: Continue - Ed Estates Portfolio -Data activities, Purview adoption / data dictionary embedment. Continue - Data quality assurance working group. Explore discussions supporting central Data Governance lead – current rational of existing activities. Business planning / supplier contract sows. Development of dev ops piece of work. Microsoft costings for Purview. Review Metadata standards. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
640 | 11459 | May 2025: Continue embedding Data Quality Standard education and awareness 1fte - whilst overarching governance model develops. Data Quality standard published first 1/4 25- Cross gov data quality framework in use in some projects. Awaiting finalisation of output from Mapping on central list of important critical data gathered. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
641 | 11460 | Content store: Major deliverables including the main build phase, data science tooling and content discoveries have been completed to a high standard. Slight delays of anonymised teacher and pupil content due to requiring further anonymisation checks. Contract has been extended to September/October 2025 to gather evidence to support the hypothesis agreed by the governance board and for a full cost-benefit analysis of the pilot. We are currently exploring options for moving the pilot into a beta service ready for a key decision point to be taken in Autumn 2025. The content store has been designated one of the Prime Minister’s AI Exemplars. Catalyst Fund (known externally as the AI Tools for Education Competition): 14 out 16 projects are progressing well. 2 contracts have been terminated. 1 contractor was issued with a default notice, but with ongoing support, they have rectified the default and the project is progressing. There have been delays in collation and availability of content via the content store which has meant that some of the suppliers' milestones have been delayed. 12 of the 14 remaining suppliers have agreed to extend contracts until May 2025 to account for this delay and to fully utilise the content store content to train their tools. 2 suppliers will conclude work as agreed in April 2025. Innovate UK awarded us £1m for a closed, second phase of the competition which will be open to successful projects from the first phase. The second phase will launch for applications on 14th July 2025. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
642 | 11461 | 25.07.25 - new round of user research is underway with schools, who again have really stepped up to our ask and fully engaged with the processs. This direct involvement is really shaping our offer and the testing assures us that Users can interact fully with the guidance. Procuremement standards work continues, with the support of internal commercial colleagues and and school staff. This is still in the research phase, which is vital to getting this right for schools as this is such a major area for them when ensuring data prvacy when pricuring EdTech tools. June 2025. Procurement standards work has commenced with Commercial and Procurement colleages and the ICO. First phase is to bring together everthing that schools can rely on to support their procurement of EdTech. This will then be supported with procurement standards which will be developed by the group - ToR - monthly meetings, User Research is phase 2 as the guidance sourced in phase 1 will be the starting point for developing standards for schools, understanding what barriers schools need help to address |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
643 | 11462 | 25.07.25 - structure of the tool has been developed to be interative starting with (redundant, obsolete and trivial) ROT, then phasing up ultimately result in identifying files for appraisal. Testing showed 60% accuracy so the team are currently looking at the business rules and updating the tool to increase the accuracy rate. The testing is against 22k records that have been reviewed by the records team, so we have assurance that we know which records the tool needs to identify. Whilst the rules are relatively straightforward the coding of the tool is complex to reflect human decision making. TNA remain interested in this project, meeting scheduled to update them with progress and involve them in the work as this progresses from ROT |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
644 | 11463 | R03 for 25/26 opened on time over 99% of files process successfully at first attempt failures are re-submitted either by the provider or SLD team |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
645 | 11464 | Sept milestone (removal of manual add option) is delayed while we investigate the slow take up in using the ILR option. Rating also reflects the outstanding questions about short courses policy and unpublished funding rules needed to inform payments work. Work is being prioritised around the most confirmed requirements. Likely rating will go A/R if we don't have critical info by November. Additional resources have now been added to the teams to support delivery of parallel projects. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
646 | 11465 | Last week, the team continued focusing on investigating and detailing work for the next quarter including decommissioning of Skills Health Check and Digital Action Plans, as well as upgrades to the UK.GOV Frontend to ensure the service is aligned with GDS standards, this work has been finalised and project plans and development tickets for the quarter are ready to be implemented. One incident was raised and address for the DSS product which was resolved, and a change in Publish to the Course Directory supported a provider to add new courses, where they had been blocked. In addition, the maintainance backlog was reviewed to prioritise key changes for the National Career Service and Skills for Careers websites. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
647 | 11466 | released 23/01/25 |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
648 | 11467 | Key priorities and any work about to start:DATA Insights this sprint - Chatbot API testing, since inception earlier this year data provided through the API has had errors, we're helping Plianz test this - June monthly tasks, Any tasks which can't be automated such as manual refreshes and are completed monthly - Continued investigation into limiting dates users are able to enter into date selectors e.g no future dates - PowerBI Prime Performance Report Testing - Explore Sector & Landing Page Report Continuation, - Begin work into user tracking between NCS & SFC. Are we able to track our users across both National Careers Service & Skills for Careers Websites, this will lead to better understanding of user journeys and successful journeys These are all on track for this sprint. Key achievements/outcomes and successes (that we can celebrate, both in DDT and the wider department) |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
649 | 11470 | FE workforce collection opened on 29th Sep and is planned to close on 26th November |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
650 | 11471 | Work continues to deliver data, iterate the pipelines and move to Databricks. Delivery is on track. AO Summer results and Late results delivered as planned. Amber/green due to ongoing risks with CLDS 2.0 activity. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
651 | 11472 | RAG remains green, with work progressing to plan. Work continues to iterate, replace DEI and move to Databricks (this will be monitored via the LDS 2.0 workstream (improve, replatform and transform LDS), whilst delivering the current 24/25 delivery cycle. Current progress - Delivery is currently on track. Uanmended data has been successfully delivered and the Checking exercise completed with no major issues.. The team are now working on delivery of the November data and resolving technical debt. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
652 | 11473 | Amber/Green for overall Schedule: Cohort Amended data successfully signed off. This work was completed despite tight deadlines requiring continued monitoring of the delivery plan & robust risk manaagement, ensuring the checking exercise could go ahead as planned on 06/10, thus reducing RAG rating from Amber/Red to Amber/Green. The team continues to work towards future deliverables. Work continues to iterate, replace DEI and move to Databricks. This will be monitored via the LDS 2.0 workstream (improve, replatform and transform LDS) but the K4 team continue to support with this. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
653 | 11474 | Unamended Data was delivered to CYPMD for the checking exercise on 6/10. The team are now working on late results and new developments for 25/26. Work continues to iterate, replace DEI and move to Databricks. This will be monitored via the LDS 2.0 workstream (improve, replatform and transform LDS). |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
654 | 11475 | Find a Course, Find an Apprenticeship and Discover Uni data sets being brought together. Working towards agreement with Data challenges, especially around Find a Course data set, are biggest challenge for the project. Still struggling to get access to NCS GA data to inform our work. Microsoft AI resource lost due to MS reorg so some elements of AI behind, however bid put in for funding 26/27 and 27/28 from central AI funding pot. GDS approved move to Private Beta. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
655 | 11476 | 02/05/25 - DDT PMO confirmed with Sam Rye this will be updated to reflect direction of travel for division. Deliverable to be updated by 31/05/25. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
656 | 11477 | A risk of delivery due to no dedicated resource availability. Long terms plans need to be considered |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
657 | 11478 | This strand was not concluded. There's been no meetings/movement on this for a few months. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
658 | 11479 | Embedding Safety Expectations Through the content store, we have developed safety testing assets based on the safety expectations that developers can use to test the safety of their tools. We plan to test these assets with experts, and explore next steps for delivery. Google have recently confirmed to DfE and Ministers that they now meet the safety expectations. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
659 | 11480 | Service is running well, but we are at capacity having taken on the Technical Excellence College form at short notice. Submit Financial Data progressing to timeline - Form has gone live and webinar with pilot group has been run, 16 participants will be taking part - Links to access form going out on 28/10/25 - Work underway to build email notification system and integration with powerapp RPA - Work underway to make effeciencies in monthly data refresh processes SRMSAC - SRMSAC annual refresh of form is complete, dashboard updates underway TEC - Waiting for final sign-off and go ahead on TEC work CSC - Alpha phase complete, work underway planning reporting side of work while data engineer is being recruited to develop backend College Financials - Prepatory work underway for FR2025 - Issue with expired App ID that prevented sharepoint transfers has been resolved College Financials Reclassification Discovery - Team has been onboarded - BAU processes and protoype have been mapped to inform projects next steps - UR round with colleges in planning |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
660 | 11481 | Currently we have a number of high profile and competing commissions which is stretching our resource and capacity, this has been exacerbated by a priority tech forms commission which is causing delays. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
661 | 11482 | Limited resources due to staff leave and significant risks around talent retention, continuing to deliver on key priorities. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
662 | 11483 | GIAP successfully went through ORB on October 2024. Releases are progressing to schedule. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
663 | 11484 | We are working at risk with lots of assumptions still to be confirmed or updated, and key Ministerial decisions still to be made. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
664 | 11485 | Work now planned in and technical architecture being developed. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
665 | 11486 | The School Accountability and Performance Discovery ended at the start of April – we had a service assessment and have since moved into Alpha. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
666 | 11487 | Status: On Track- Sprint 9 concluded, with the Development of the FaC rebrand progressing as expected.Team have been able to review the changes as part of a new demo session implementedfrom the sprint retrospective.Scoping workshop for Publish to the Course Directory (PttCD) improvements took place with timelines and quick wins being the intial focus in sprint 10 - remaining scopeing work taking place in sprint 10.Key achievements/outcomes and successes (that we can celebrate, both in DDT and the wider department) |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
667 | 11488 | Previous update stands |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
668 | 11489 | Achievements: - Achieved Board Sign off for Public Beta - Almost finished all the ITHC items - Initial feedback form users has been positive |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
669 | 11490 | CAT: * .Net GREEN Completed all goals for the sprint Found a faster way to complete the task list which has now accelerated progress We have replanned the completion of the with a view to being completed early Dec with a medium confidence vote. * Data AMBER due to risks raised re complexity of work. Mitigations in placeand need BA support for Ofsted report cards Completed the Delta live tables MVP and have a way forward on moving the data from silver to gold layer *Tech Ops AMBER due to needing to still plan Containers work Completed EAT environments Moved all alerts from slack to teams Completed the test data lake environments Started the prod data lake environments. Waiting for infra team to do their part before progressing to completion CI: Rebranding Prepare completed Rebranding Complete – work is done but cannot be released until .net rewrite tasklists are done. Rebranding ReCAST – With test. 3 bugs completed Identified recast items to complete Created a data map for prepare |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
670 | 11491 | Phase 1 delivery has been fully planned and Phase 2 delivery plan is making progress. Delivered KS2 unamended assurance, KS4 Build is completed and KS4 June unamended assurance commenced. 16-18 Build is finished and 16-18 testing is ongoing. Modelling is completed for Phase 1. Phase 2 S4 Spike is going ahead with FLAT modelling. Dimensional modelling isn't going ahead. Requirement to be off DEI by September 2027 (contractually) but this is planned for April 2026 to alighn with the data cycle). |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
671 | 11492 | Beta now underway. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
672 | 11493 | Reduced risk now spending approval obtained so content to sit on combination of GCS campaign site and DSIT GOV.UK pages. The campaign site approval is time limited to 1 year so a longer term “parents information hub” still required to host information when this expires. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
673 | 11494 | Agreement with sector reps has been achieved and conversations are ongoing about sector funding which is required. Further agreement between DDT and FG has been secured confirming that resource required to deliver termly collection will be provided by FG. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
674 | 11495 | No live issues but concerns are being expressed that resource in the sector is being reduced at the same time we are asking for more data. Some LAs are already considering whether or not to respond to statutory returns. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
675 | 11496 | 1. EoI form has been delivered by DDT and is now live. 2. The blueprint toolkit will be shared with pilot schools via Azure – solution being implemented by Technology colleagues 3. The requirements for medium term / pilot data will likely now be managed using ‘Achieve’ as school software suppliers were not supportive of our initial, preferred model. 4. Longer term data requirements. -- FG Analysts are being supported by Data colleagues to understand the problem space and consider options. Data Colleagues have given advice on pulling together requirements. This project will likely require significant development time and resources and until more is understood about the requirements and potential solutions this carries a significant risk against eventual delivery. RAG has been changed as ongoing concerns for delivery within the likely required timeframe. Decisions need to be taken very quickly about what the future data needs are to bring this back on track. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
676 | 11497 | Delayed to Mid November in order to deal with recent commissions and the move of work from Skills to DWP. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
677 | 11498 | The LRS CCN for Arvato is nearly complete and should be sent to Arvato by 20 October for an impact assessment. IT are now working on the system upgrade for LRS. Once this is complete we can schedule in testing. We are still waiting for information from DDT to understand the services they provide. We will be chasing this up w/c 20 October. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
678 | 11499 | GDS Upgrade We have successfully deployed the GDS upgrade to the Customer Help Portal into production, marking the completion of a significant piece of work. This upgrade represents a major step forward in improving the user experience for our customers. The portal now features a more modern, intuitive interface that aligns with the design standards used across other government digital services, ensuring consistency and familiarity for users navigating between platforms. The deployment went smoothly, and the updated portal is now live and fully operational. The enhancements not only improve accessibility and usability but also reflect our commitment to delivering high-quality, user-centred digital services. This milestone is the result of collaborative effort across teams and demonstrates our ability to deliver impactful improvements efficiently and effectively. DfE Connect and Digital Consolidation We’re kicking off our first workshop with the DfE Connect team as part of their digital strategy reset. This session will focus on exploring opportunities for alignment across digital services, ensuring that our work supports a cohesive and integrated experience for users. We’re looking forward to contributing to the broader vision and helping shape the future of digital services within the department. Education Estates (Capital) Work continues in close collaboration with the Education Estates Team to migrate the use of 37 individual mailboxes into our Customer Help Portal. This initiative is a key part of our ongoing efforts to consolidate services and streamline communication channels. By centralising these interactions within the portal, we aim to significantly improve operational efficiency, reduce duplication, and provide a more consistent and transparent experience for both internal teams and external users. The migration will also enhance our ability to track and manage enquiries, ensuring quicker response times and better service outcomes. Davina Chatbot We’re currently developing a proof of concept for a generative AI-powered version of our chatbot, Davina, aimed at significantly enhancing customer experience. This new iteration will be capable of handling a broader range of queries with more natural, intelligent responses. Crucially, if Davina is unable to resolve a customer’s issue, it will automatically escalate the case to our CRM system—eliminating the need for the customer to repeat information or take additional steps. This seamless escalation not only reduces effort for the user but also ensures faster resolution and a more joined-up service experience. The proof of concept will help us evaluate the potential of Gen AI to transform how we support our users and deliver smarter, more responsive digital services. AI in Dynamics 365 We’re currently working with an AI developer to explore the feasibility of integrating AI functionality within Dynamics 365 to support case management. The goal is to assess how intelligent automation and natural language processing can assist agents by surfacing relevant information, suggesting next steps, and potentially pre-populating case details based on customer interactions. This could significantly reduce manual effort, improve response times, and enhance the overall quality of service. By embedding AI directly into the case management workflow, we’re aiming to empower agents with smarter tools and deliver a more seamless experience for both staff and customers. Bespoke Journeys We’re making strong progress with the prototype design for Portal 2.0, which will introduce tailored customer journeys based on user type and context. This next-generation portal will ensure that customers only see the options, content, and support relevant to their specific needs, reducing complexity and improving overall usability. By designing with personalisation at the core, we’re aiming to deliver a more efficient and intuitive experience that reflects the diversity of our users and the services they interact with. The prototype is already demonstrating how targeted design can simplify navigation and enhance customer satisfaction. Whistleblowing Project The whistleblowing mapping project is now nearing completion, with the full process successfully mapped across the department. This comprehensive exercise has provided valuable insights into how whistleblowing cases are currently handled, highlighting areas for improvement and greater consistency. A proposed new approach is now taking shape, designed to streamline the process and ensure robust handling of concerns. This proposal will soon be shared with the Complaints Board for review and feedback, marking an important step towards strengthening our overall complaints and safeguarding framework. CRM Next week, the team will be coming together for a full-day workshop focused on re-imagining Provider CRM as a modern, intuitive customer service tool. The session will centre around three key areas: layout and design, functionality, and processes. This collaborative effort will allow us to explore how the CRM can better support users through a cleaner interface, smarter features, and streamlined workflows. By taking a fresh look at how the system is structured and used, we aim to create a solution that not only meets current needs but is also scalable and adaptable for future service delivery. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
679 | 11500 | As of 23rd October we are being told that there is now a formal plan to keep SLACK. This is being explored and we will review next steps once we know who made this decision and how that impacts on this deliverable. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
680 | 11501 | The new whistle blowing process review took place 22/10/2025. Broad agreement except for two divisions that have been commissioned from elsewhere to work in a silo. This has been captured under Risk CSS014. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
681 | 11502 | The team keeps producing, maintaining and enhancing an insight and reporting suite built primarily using Power BI and Microsoft CoPilot. The action-able service insights and management information (MI) are shared with the stakeholders to not only monitor performance of services against agreed SLAs/KPIs but also identify areas of improvements. Some of the highlights for this month are given below: • The team has now fully transitioned its data management processes from a legacy SQL-Server to Databricks platform for National helpline and Data Ops' telephony data. The new platform has enabled the team to automate some aspects of data linkage across various data sources thus helping the team save time and resource. The team will keep exploring and enhancing data management processes through further automation using APIs. • The National helpline (NHL) AI summary tool, to produce an automated summary/insights for each call, has now been fully developed, tested and implemented as BAU. The NHL team has seen an instant improvement in ticket summary quality since the implementation of this tool. The agent call wrap-up time has significantly improved which will help the division save agent time and resource going forward. The team showcased, in collaboration with Operational Data Science colleagues, the savings and improvements using this AI tool to Jane, Saheel and the permanent secretary during their recent visits to Coventry office this month and received good feedback. • The team shared with the senior leadership second iteration of a high-level dashboard containing performance summary for various in-house services that we manage within the division. The team received some positive and encouraging feedback from the senior leadership team. The monthly dashboard will continue to be enhanced based on the feedback in future iterations. • The team also produced monthly insights using external customer satisfaction surveys data. This helps customer service team identify any areas of improvements across the services and implement necessary actions to bring efficiencies and drive improvements. • Despite resource related issues, the team is confident that they will continue to perform their business critical BAU tasks along with dealing with any priority requirements to produce new insights and MI/reporting. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
682 | 11503 | 18/08 Showcase delivered to Emily S and Mark J in prep for stakeholder show and tell. Ownership is required for SOW to move forward. 04/08 - First part of UR complete. Moving onto next phase. BA reviewing current processes and linking in with UR. 01/07 - BA started. Getting to know team and read background information. 17/06 - Both URs now started. Early background research and setting up of work ongoing. Relevant meetings organised. BA to link up and start in July. 04/06 - BA confirmed and one UR confirmed. Awaiting one more UR. 29/05 - Awaiting start date for BA. 2 x URs start first week of June. SOW working group now set up for collaboration on SOW in DfE to avoid duplication.. 13/05 - Awaiting invite for pilot with cabinet office. Resource TBC for exploring needs and requirements within DDT/DfE. Cross team meeting created for transparency and collaboration of this area. 03/04 - Next steps currently in discussion Alex B and awaiting feedback. Provisional plan to be discussed at review board for approval. 20/03 - Awaiting confirmation of direction and funding following meeting on the 19th March but meeting organised with Emily S and Mick R on 21st March to discuss approach to AI projects following wider developments. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
683 | 11504 | 20250902: We are blocked on UR with Data Analysts and that is holding up a getting to a clearer definition of the project. We are addressing the gaps in stakeholder mapping and change management. Work is also underway on the necessary data needed to support the users and technology strategy.20250801: Where are planning fo r show and tells of the dashboard to the Data Analyst community for feedback. At the same time we will be exploring the requirements for requesting access and the updating of the data map. We also need to address the issues around requesting access and updating the data as part of the tactical solution. Cultural changes will be critical to the success to the project. We are looking at a service offering, and potential Service Owners from within the the Business. We are engaging with the DDT communities to understand what tools are available for a tactical solution and how they will interact with this service. We are also exploring great links with other projects within DDTi as a way of generating evidence of the benefits for sharing data across the Dept, and working with DDTi. 20250708: The project is currently completing engagements with linked services (IAR, People Services) to identify possible linkages across business processes and technology. We are working with the data mapping project on engagement with the analyst community (as they are likely to form a key part of the user group) with the aim of completing recruitment for some UR. Development continues on the dashboard with input from the data mapping team. The project is nearing the transition point for Alpha. 20250701: The project has finished it's third sprint and completed planning for sprint four. The project has now completed it's planning and proposals for securing an SRO and activity required prior to Alpha. In the next sprint, the team will be completing the as-is mapping of some linked services and complete UR on the latest version of the dashboard which shows the mapped information. 20250623: Successfully pitched a focussed scope for the project. Key follow up activities have been identified to align with the preferred scoping and a 5 year plan is being developed by the project. The requirements have been reworked and are being reviewed by the Data Architect and Data Analyst. User Research sessions have concluded and are being played back to the team at the end of the week. 20250617: We have now prepared our proposal for scope and priority on DIP. This has been captured in a note ahead of the meeting which has been sent to Emily and Tej. The User Research is finishing now and after the final interview, the analysis will be complete. The BA work will need to continue as requirements must be reframed to capture the change of focus. A DA/SA has been brought on board and is starting to look at the technical side of this project. Our DAn continues to work with the mapping team to get all the mapped information into the tool and is also picking up some analysis of data as it relates to potential capability in the future. 20250610: The main focus of our work currently is to develop a proposal on the scope and priority of this project. In particular, we will be looking to narrow this down and agree a focussed set of requirements and objectives which will aid deliverability. There is also some movement in the resource (loss of a BA and expected gain of a DA/SA) but this is being managed through resource currently onboarded through the Data Mapping project. Work on UR continues with analysis being finalised last week for presentation this week. On the dashboard work, some issues with the data have been resolved and new data loaded on to the tool. 20250603: We successfully delivered the first Show and Tell session which summarised all the work to date on this project (including work that happened as part of the Data Mapping Project). This marked the end of Sprint 1 and the project successfully completed all the usual ceremonies and are reflecting the outputs of our retro. We are now working through Sprint 2 with some of the key outputs to be Hypotheses documentation, UR analysis, and changes to our tactical dashboard. 20250527: We are continuing to complete our UR with additional participants from the data mapping project identified. The team will be delivering a show and tell on the progress to date for the project this week. 20250520: The project is working through Sprint 1 with work focussing on UR work, developing Alpha hypotheses and preparation for a show and tell at the end of the sprint covering all of the work to date on the project. 20250512: The project is conducting sprint planning this week working towards the end of Discovery. Work has been ongoing with the UR Phase 2 and planning for Phase 3. 20250428: We are defining the project's aim and vision statement and are working towards the end of the Discovery phase. A roadmap has been drawn out and it is expected that the Discovery phase will end in May. 20250331: The team delivered an internal review of their UR findings. The team are also linking in with Delivery Directory to understand links between the two projects. 20250324: We are continuing to work on the user research with the final sessions booked in for this week. Our Data Analyst and BA began working on loading more real data into the dashboard but encountered a SharePoint issue. This will be worked through this week with the aim of loading Families and Regions data into the tool. 20250317: A tactical solution has been developed which contains one area of mapped information. The focus is now on loading in the rest of the maps. User research continues and once complete will inform project requirements. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
684 | 11505 | 20250908 Sprit 5 commenced - this will be a 3 week sprint due to DM absence on leave. Sprint details - Overview Strengthen the alpha by improving the search experience and interface design, and by developing and testing a range of concepts to explore alternative user journeys and deepen design insight. Ratify the governance framework approach with service owner and project sponsor. Set us up for success in alpha and beyond by defining OKR targets (alpha) based on baseline metrics, validating the governance framework with stakeholders, and preparing for scaling by understanding how our approach works for other portfolios. Sprint outcomes: Incorporate concept testing feedback into front-end design Refine service blueprint Detailed testing of search result relevance Finalise Test Strategy and plan, create test design for User Stories and Execute test for the delivered User stories Iterate existing concept designs based on user feedback Create alternative concept designs in-line with GDS and DfE standards Continue work on governance framework with service owner and senior stakeholders Set OKR targets for alpha based on baseline metrics Synthesis analysis of other portfolios’ libraries and share with team Service assessment preparation and key messaging Identify priority portfolios for post-alpha focus Sandbox has been accessed along with necessary components. Product has been developed to show successful search. 20250819 -Sprint 3 concluded and Sprint review completed. Sprint 4 started Sprint 4 Goal Progress the alpha by enabling the developer (user perspective) to submit queries and receive basic responses. Begin testing wire frames / early experiences with users to validate key assumptions, gather actionable insights and guide future iterations, finally establish baseline metrics to measure impact. OKR baseline data collection and target setting Continue core build to return a search response in the front end Prepare lo-fi concept designs and gather user feedback High level analyse of other portfolio libraries Continue to test assumptions with UCD roles and URs in wider portfolios Question guide for policy users Validate service design blueprint Continue updating architecture deck Design mechanics and incentives for sharing and reusing insights Create end-to-end user journey maps for Insight Trawler, Strategist, and Networker personas Developing Governance Approach 20250812 - Sprint 3 started. Azure sandbox finally up and running. 20250804 Sprint 2 concluded. Began validating the end-to-end user journey from insight completion to discovery, using sample data. Establish the high-level technical architecture that supports automated ingestion, accept UR teams specified tagging, and automated discovery. Defined the criteria for a "completed" insight. Develop product roadmap and success metrics by 1 Mapped out and validated the ‘To Be’ core user flow completing an insight - tagging - search - summary 2 Developing and test AI summarisation and tagging 3 Defining criteria for a completed insight 4 Documenting core requirements - detailed user stories 5 Architect designs to outline technical flow for automated ingestion and building of RAG pipelines RAID Log updated and issue surfaced 20250723 - Sprint 1 concluded - now in Alpha. Roadmap developed, MVP broken down into deliverable stories or components, Alpha requirements looked at by value and effort, as-is state analysis of schools user insights library, worked with key stakeholders to consider adoption, design requirement and business constraints, core tech spikes completed, developer on boarded and RAID log updated 20250707 - End of Sprint 0 and MVP must haves for Alpha documented. Sprint review concluded, back log refinement completed and goal/planning for Sprint 1 done. 20250623 - Project Kick off held and early planning session. Sprint 0 planning this week along with workshops UR: Problem space, user needs and pain points and defining the product vision and MVP. Additional resource needed - Developer (AI focus) and tester as we move into Alpha. 20250611 - kick off scheduled for 17/6/25 and links made with service mapping (workshop for service mapping an impact projects planned for 18/6/25). Back log and sprint planning scheduled and ways of working meeting planned. Formal start 23/6/25. 20250602- eSourcing Challenges: The Product Manager is scheduled to start on 16/06/25. This is a key role, and their delayed start has been a challenge. We have successfully onboarded the Service Manager, User Researcher (UR), and Solution Architect. Their integration into the team is progressing well. We are still waiting to receive the name of the Business Analyst (BA), which is causing some delays in finalising the team structure. A kick-off session will be organized once all team members are on board. This session is crucial to ensure everyone is aligned and has a shared understanding of the project goals and processes. Harman is working on finding temporary assignments for the SM and UR to keep them engaged and productive. 20250525 - PID timeline agreed with project sponsor. Resourcing in progress to complete discovery and alpha. Preparing 'kick off' sessions. Estimated start is beginning of June 2025. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
685 | 11506 | Working with DSIT to create landing page for Media Literacy campaign for Jan 26 which also acts as the government site for parents information about keeping their child safe online. 4 month project to get from discovery and alpha to a live campaign site. Discovery phase complete and MVP being rapidly prototyped for round 2 testing. Access to GCS campaign site granted. Content process (including sign off) underway. MVP will be small and focused on the top tasks parents want to achieve with signposting to existing (charity) resources where possible. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
686 | 11507 | August update: Alpha assessment completed and Green outcome. Beta has now started with an aim for an MVP and further iterations to be in available internally by End of Nov |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
687 | 11508 | October status: Divisional roadshow almost complete. Staff survey analysed - leadership issues raised escalated to DDT's SLT. Other work will be taken forward by the skills and expertise objective team, including a research project to understand more about L&D needs in DDT and how far they are being met. Discussions underway with alternative supplier about SCS immersion day. BA bootcamp taking place early November. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
688 | 11509 | UR supporting BSIL campaign site now complete. Survey work to support longer term project around parents hub for all ages complete and results shared. Mapping out government parent services and collating research ongoing. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
689 | 11510 | Set up - improvements being made as the AI work develops |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
690 | 11511 | Set up - improvements being made as the AI work develops |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
691 | 11512 | Still being formulated |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
692 | 11513 | On track |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
693 | 11514 | The MVP is ongoing and is currently in UAT, which will include accessibility testing/audit. A revised expected delivery date will be discussed once the UAT is complete and we understand any further work required. Although to note that the SDT team's capacity is taken up by other priorities. Late delivery is impacting on our user researchers needing to continue to find schools research participants via other routes, which are normally chargeable and come with a time lag before the research can take place. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
694 | 11515 | Currently defining internal processes (operational, finance and governance) to ensure viability. If not viable, project will end. Also currently waiting for commercial team resource to be assigned. If major delay in commercial resource, delivery date may slip. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
695 | 11516 | Business case being produced. Waiting for commercial team resource to be assigned. If major delay in commercial resource, delivery date may slip. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
696 | 11519 | The alpha phase has just kicked off and a number of new team members onboarded onto the team. The alpha roadmap and delivery plan are in development. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
698 | 11521 | SEPT 25 SSDLC - Continue with work developer community of practice on source code control and secrets management until December. GITHUB enterprise migration agreed at SLT and being communicated through COPS DCAP - Develop a governance and service wrapper for the Platform, continue with Gold/Silver onboarding and transition DCAP to a BAU team by December. SBD surgeries now established for projects in scope (AUG 25) Threat Modelling service offer established (Aug 25) Deliver pilot for CA for a digital service (end July 25) |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
699 | 11522 | SEPT 25 UPDATE - Meetings have taken place with SRO's and will be held quarterly moving forward. Good progress is being made with the current set of mandated controls. (Aug 25) Agree remediation timeframes for mandated controls. Quarterly reviews with SROs taking place |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
700 | 11523 | UPDATE SEPT 25 - New governance in place - the Cyber Risk Advisory Board (CRAB) has been stood up and the terms of reference will be agreed at the first meeting in October 2025. The CRAB board will feed into the new DDT governance framework. A central risk register has been established. It is currently under review to identify and escalate compound risks (AUG 25) Update intranet content to align with current assurance process (end Aug 25) |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
701 | 11525 | Contract with JISC in place (Oct 25). Update October 25 Minister Smith sought advice from the Permanent Secretary and following definitive advice from legal on the unlawfulness of continuing with grant funding, in further advice to the Minister on 27th October we have again recommended the Minister approves the contract from 1st November; with the condition we aggressively try to drive down costs from day 1. The rating is Amber because on 27th October we still await a decision from the Minister ahead of the end of October deadline. UPDATE - SEPT 25 We have secured an extension to the current grant agreement with Jisc to continue to provide connectivity and cyber security to the FE sector in England until 31st October 2025. The notice period for both Transparency Agreement and Contract Award notices ended without any challenges. A submission is with Minister Smith as the final stage in the approval process to move to a contract from 1st November |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
702 | 11526 | SEPT 25 UPDATE - Gov Assure Year 2 targeted improvement plan is at the final sign-off stage. Once agreed it will be shared with the services and remediation work, alongside Year 1 will continue and be tracked. GOV Assure year 3 - we have agreed Business Central be part of year 3 and another service will be identified shortly. Engagement work has commenced with business central team. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
703 | 11527 | Discovery is on track with the scope and goals agreed and a delivery plan in place. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
704 | 11528 | MVP launched 1 September - work continues to improve and evolve it following user research findings and wider x-gov parent-facing digital projects. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
705 | 11529 | n/a – Discovery complete on 10 October 2025. Alpha business case signed off and Statement of Work being drafted. Anticipated Alpha start date XX. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
706 | 11530 | Team capacity is stretched due to a shared resource pool across two concurrent projects. A two-week extension was agreed with policy and digital leadership, which has relieved the immediate pressure and the project is now rated Green. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
707 | 11532 | No issues have been raised by LAs or third-party suppliers – project is Green. Project closure will be in October 2025. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
708 | 11533 | Agree non project team owner for accreditation process issues (we have learned that some Schools are using checkers without DfE’s Accreditation process trapping or sanctioning this. Presently the legislation does not cover Schools driving an online process).Continue to work with third parties to ensure all can adopt solution. |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True
709 | 11534 | • Project is Green as project has been through both demand triage and Board signoff • Budget lines are being put in to place • Operational Readiness Reviews prepared for the service decommission and commission • SoW's submitted and processing, some candidates coming through Cognizant • SIPOC on PIMS journey carried out + deep dive on Admin functionality carried out 'as is' • Creating the 'to be' process incorporating the UKRLP + PIMS approach • Setup of assumptions and Functional and Non-functional requirements • Drive to create the operational logic map 'to be' to be reviewed to allow technical design to follow |  |  |  | 1 |  | 2025-11-20 11:01 | 2025-11-20 11:01 | True

## MonthlyUpdates
Id | ProjectId | Year | Month | Narrative | CreatedByEntraId | CreatedByName | CreatedByEmail | CreatedByUserId | UpdatedByUserId | CreatedAt | UpdatedAt | SubmittedAt

## MonthlyNarratives
Id | ProjectMonthlyUpdateId | Narrative | CreatedByEntraId | CreatedByName | CreatedByEmail | CreatedByUserId | CreatedAt

## WeeklySuccess
Id | ProjectId | Year | WeekNumber | WeekStartDate | WeekEndDate | SuccessDescription | CreatedByEntraId | CreatedByName | CreatedByEmail | CreatedByUserId | UpdatedByUserId | IsReportedToSlt | SltResponse | SltRespondedByEmail | SltRespondedByName | SltRespondedAt | CreatedAt | UpdatedAt

## SROs
Id | ProjectId | UserId | CreatedAt
1 | 2296 | 16 | 2025-11-20 08:37
538 | 2510 | 17 | 2025-11-20 11:01
539 | 11416 | 5 | 2025-11-20 11:01
540 | 11418 | 16 | 2025-11-20 11:01
541 | 11419 | 16 | 2025-11-20 11:01
542 | 11475 | 16 | 2025-11-20 11:01
543 | 11476 | 16 | 2025-11-20 11:01
544 | 11478 | 17 | 2025-11-20 11:01
545 | 11480 | 16 | 2025-11-20 11:01
546 | 11481 | 16 | 2025-11-20 11:01
547 | 11482 | 16 | 2025-11-20 11:01
548 | 11506 | 16 | 2025-11-20 11:01
549 | 11507 | 16 | 2025-11-20 11:01
550 | 11508 | 16 | 2025-11-20 11:01
551 | 11509 | 16 | 2025-11-20 11:01
552 | 11510 | 16 | 2025-11-20 11:01
553 | 11511 | 16 | 2025-11-20 11:01
554 | 11512 | 16 | 2025-11-20 11:01
555 | 11513 | 16 | 2025-11-20 11:01
556 | 11514 | 16 | 2025-11-20 11:01
557 | 11515 | 16 | 2025-11-20 11:01
558 | 11516 | 16 | 2025-11-20 11:01
559 | 11517 | 16 | 2025-11-20 11:01
560 | 11518 | 16 | 2025-11-20 11:01

## ServiceOwners
Id | ProjectId | UserId | CreatedAt

## Directorates
Id | ProjectId | DivisionId | CreatedAt

## BudgetOwners
Id | ProjectId | BusinessAreaLookupId | CreatedAt

## PMOContacts
Id | ProjectId | UserId | CreatedAt

## Milestones
Id | ObjectiveId | ProjectId | FipsId | ProductDocumentId | Name | Description | BusinessArea | OwnerUserId | OwnerEmail | BaselineDueDate | DueDate | ActualDate | Status | ProgressPercent | ExternalRef | Notes | IsDeleted | CreatedAt | UpdatedAt
1 | 11 |  | VQE-288 |  | Deliver FIPS MVP | Find information about products and services for MVP which is basic product information. | CXD |  | Andy.JONES@education.gov.uk | 2025-11-30 | 2025-11-30 |  | on_track | 80 | [{"text":"GitHub project plan","url":"https://github.com/orgs/DFE-Digital/projects/67"}] | Paul Kelman - Product Kuldip Osborne - Delivery Andy Jones - Owner | False | 2025-10-20 12:47 | 2025-10-20 14:59
2 |  | 6 |  |  | Phase 1 - VC&F and comms pilot | Run a pilot for completing product reports and milestones for VC&F portfolio. |  |  |  |  | 2025-11-17 |  | in_progress | 30 |  | sss | True | 2025-10-24 12:48 | 2025-11-13 11:14
3 |  | 6 |  |  | Implement the demand, triage, and prioritisation process | Design and implement the demand triage process. |  |  |  |  | 2025-12-20 |  | not_started | 0 |  |  | False | 2025-11-20 05:42 | 2025-11-20 05:42
4 |  | 6 |  |  | RAID Management | Design and implement RAID management integration with deliverables and operational, divisional reporting. |  |  |  |  | 2026-01-30 |  | not_started |  |  |  | False | 2025-11-20 05:43 | 2025-11-20 05:43

## MilestoneUpdates
Id | MilestoneId | UpdateDetails | PreviousStatus | NewStatus | PreviousProgress | NewProgress | UpdatedByEmail | UpdatedByName | UpdatedAt
1 | 2 | Something | planned | in_progress |  | 30 | Andy.JONES@education.gov.uk | JONES, Andy | 2025-10-25 17:30
2 | 2 | sss | in_progress |  | 30 |  | Andy.JONES@education.gov.uk | JONES, Andy | 2025-10-25 17:30

## Risks
Id | ObjectiveId | ProjectId | FipsId | ProductDocumentId | Title | Description | Category | BusinessArea | RiskTierId | OwnerEmail | ImpactRating | LikelihoodRating | RiskScore | ProximityDate | Response | ResidualImpact | ResidualLikelihood | TargetDate | Status | ClosedDate | Notes | Source | SourceId | OwnerUserId | RiskStatusId | RiskPriorityId | RiskLikelihoodId | RiskImpactLevelId | RiskProximityId | RiskCategoryId | InherentScore | ResidualScore | IdentifiedDate | NextReviewDate | LastReviewDate | GovernanceBoardId | PrimaryProductId | ResponseStrategy | HowIdentified | CreatedByUserId | UpdatedByUserId | ClosedByUserId | IsDeleted | CreatedAt | UpdatedAt
1 |  |  | NEQ-753 |  | Products not onboarded to the accessibility issues and statement service | We have 400 products and we are legally required to provide accessibility statements on all web browser based products and services. While statements are in place for the majority, not all teams may choose to onboard to the product which will result in continued inaccurate, out of date and statements with wrong information on. This could result in legal action or users not being able to use DfE's products or services properly. |  | CXD | 4 | Andy.JONES@education.gov.uk | 5 | 5 | 25 | 2026-03-31 | avoid | 3 | 3 |  | open | [23 empty] | False | 2025-10-18 14:45 | 2025-10-21 21:25

## Issues
Id | ObjectiveId | ProjectId | FipsId | ProductDocumentId | Title | Description | Category | BusinessArea | OwnerUserId | Severity | Priority | DetectedDate | TargetResolutionDate | Status | ResolutionSummary | Workaround | SourceType | SourceReference | SourceRecordUrl | SourceRiskId | BlockedFlag | ClosedDate | Source | SourceId | MilestoneId | RiskId | PrimaryProductId | UserImpactSummary | ServiceImpactSummary | BlocksRelease | StatusId | PriorityId | SeverityId | IssueCategoryId | ResolvedDate | CreatedByUserId | UpdatedByUserId | ClosedByUserId | IsDeleted | CreatedAt | UpdatedAt
1 |  | 6 |  |  | Issue | cec |  |  |  | medium |  | 2025-11-03 |  | open | [6 empty] | False | [8 empty] | False | [8 empty] | False | 2025-11-03 16:11 | 2025-11-03 16:11
2 |  | 7 |  |  | ewd | wef |  |  |  | high |  | 2025-11-03 |  | open | [6 empty] | False | [8 empty] | False | [8 empty] | False | 2025-11-03 22:40 | 2025-11-03 22:40
3 |  | 6 |  |  | dd | dd |  |  |  | high |  | 2025-11-14 |  | open | [6 empty] | False | [8 empty] | False | [8 empty] | False | 2025-11-14 13:05 | 2025-11-14 13:05

## Actions
Id | ObjectiveId | ProjectId | DecisionId | FipsId | ProductDocumentId | Title | Description | BusinessArea | SourceType | SourceReference | SourceRecordUrl | ActionSourceId | AssignedToEmail | Priority | Status | StartDate | DueDate | CompletedDate | ParentActionId | EvidenceUrl | Notes | Source | SourceId | AssignedToUserId | AccountablePersonUserId | TeamName | ClosedDate | LastProgressUpdate | ProgressPercent | Blocked | BlockedReason | ClosureNotes | Rag | Evidence | EvidenceTypeId | VerificationRequired | VerifiedByUserId | VerifiedDate | VerificationNotes | ActionTypeId | CategoryId | ImpactLevelId | PriorityId | StatusId | RiskId | IssueId | MilestoneId | ReminderFrequencyId | EscalationThresholdId | EscalationTriggered | ServiceId | PrimaryProductId | LifecyclePhase | CreatedByUserId | UpdatedByUserId | ClosedByUserId | IsDeleted | CreatedAt | UpdatedAt
1 |  |  |  | NEQ-753 |  | Onboard services |  | CXD |  |  |  | 1 | Andy.JONES@education.gov.uk | high | in_progress |  | 2026-03-31 | [11 empty] | 0 | False | [5 empty] | False | [13 empty] | False | [6 empty] | False | 2025-10-20 19:09 | 2025-10-20 20:32
2 |  | 6 |  |  |  | Design the risk assurance process | We need to design a risk management process to capture and prioritise risk, escalations and relationships of risk between entities. | [6 empty] | high | in_progress | [13 empty] | 0 | False | [5 empty] | False | [13 empty] | False | [6 empty] | False | 2025-11-13 20:49 | 2025-11-14 21:51

## Decisions
Id | ObjectiveId | ProjectId | FipsId | ProductDocumentId | Title | Status | DecisionType | DecisionDate | Summary | BusinessArea | OwnerEmail | Outcome | Notes | SourceType | SourceReference | SourceRecordUrl | StatusId | PriorityId | OutcomeId | EffectiveDate | ExpiresDate | GovernanceBoardId | OwnerUserId | AgendaItemReference | DecisionMakerUserId | ProposedByUserId | SponsorUserId | ResponsibleTeam | ImplementationOwnerUserId | ImplementationStatusId | ImplementationDeadline | VerificationRequired | VerifiedByUserId | VerifiedDate | VerificationNotes | Evidence | EvidenceTypeId | AdditionalDocuments | PrimaryProductId | MilestoneId | Source | SourceId | CreatedByUserId | UpdatedByUserId | ClosedByUserId | IsDeleted | CreatedAt | UpdatedAt
1 |  | 6 |  |  | We decided something | approved |  | 2025-11-14 | wedf | [22 empty] | False | [13 empty] | False | 2025-11-14 13:05 | 2025-11-14 13:05

## Comments
Id | EntityType | EntityId | CommentText | CreatedByUserId | CreatedAt | UpdatedAt | IsDeleted
1 | Risk | 1 | Something | 1 | 2025-10-20 19:26 |  | False
2 | Risk | 1 | Something else | 1 | 2025-10-20 19:26 |  | False
3 | Action | 1 | A comment on the action | 1 | 2025-10-20 19:27 |  | False

## Dependencies
Id | SourceEntityType | SourceEntityId | TargetEntityType | TargetEntityId | DependencyType | Description | Status | ResolvedDate | ResolvedByEmail | ResolvedByName | CreatedAt | UpdatedAt
2 | Project | 7 | Project | 6 | Deliverable |  | Active |  |  |  | 2025-10-30 10:35 | 2025-10-30 10:35

## RiskActions
RiskId | ActionId
1 | 1

## RiskRiskTypes
RiskId | RiskTypeId | CreatedAt
1 | 4 | 2025-10-21 21:25
1 | 6 | 2025-10-21 21:25
1 | 12 | 2025-10-21 21:25

## IssueActions
IssueId | ActionId

## RiskDecisions
RiskId | DecisionId

## IssueDecisions
IssueId | DecisionId

## IssueRisks
IssueId | RiskId

## ActionDecisions
ActionId | DecisionId

## MilestoneActions
MilestoneId | ActionId

## MilestoneRisks
MilestoneId | RiskId

## MilestoneIssues
MilestoneId | IssueId

## Summary
Sheet | Rows
Projects | 191
Users | 15
BusinessAreas | 1
Phases | 1
ActivityTypes | 5
DirectoratesLookup | 0
RiskAppetite | 5
RagStatuses | 5
DeliveryPriorities | 3
RiskTiers | 5
RiskTypes | 13
ActionSources | 4
Divisions | 0
Missions | 4
Objectives | 20
RagHistory | 7
Successes | 1
Outcomes | 1
Needs | 2
ProblemStatements | 1
ProblemStatementHist | 0
ProjectMissions | 0
ResourceFunding | 2
ResourceFundingHist | 7
ProjectContacts | 6
ProjectObjectives | 12
ProjectProducts | 2
StatusUpdates | 258
MonthlyUpdates | 0
MonthlyNarratives | 0
WeeklySuccess | 0
SROs | 24
ServiceOwners | 0
Directorates | 0
BudgetOwners | 0
PMOContacts | 0
Milestones | 4
MilestoneUpdates | 2
Risks | 1
Issues | 3
Actions | 2
Decisions | 1
Comments | 3
Dependencies | 1
RiskActions | 1
RiskRiskTypes | 3
IssueActions | 0
RiskDecisions | 0
IssueDecisions | 0
IssueRisks | 0
ActionDecisions | 0
MilestoneActions | 0
MilestoneRisks | 0
MilestoneIssues | 0